## Readme
Skill and Dependency Planner
Version history:
| 1 | 2017-03-01
What is this: This spreadsheet helps to probabilistically forecast how long it will take to complete features and stories based on range estimates.
How does it work? Given your estimates, this spreadsheet hypothetically completes all work 500 times. It calculates likelihood result as the number of simulated trials that finished on or before a given date.
Why is this better than burndowns and traditional Agile forecasting? Most forecasting techniques give a single date result and hide the likelihood of that date. Most often the date given as the result is 50% because work is divided by an average (or median). Thats the odds of a toin-coss. This method allows the reader to choose the amount of schedule risk they wish to sign-up for. 85% is a common middle ground used in the industry.
Is it reliable? It has no mathematical errors (that we know of!), and all we guarentee is its better than intuition alone and better than simple regression models. But, help us improve it by letting us know when it misses the actual results you are seeing.
How to: Fill in the orange boxes in the Forecast worksheet and read off the dates in the results table adjacent to the likelihood/certainty you think is appropriate. 85% is a common industry level of certainty used.
What is throughput? Where do I get that data? Throughput is the number of DONE stories completed by a team per week or per sprint (you choose in this spreadsheet, default is per week). We will be providing a viz that gathers this data for your team. Stay tuned.
What is this: This spreadsheet helps to plan delivery of features or projects that require multiple skills or multiple teams. It helps plan the start dates for work or team dependencies to identify where capacity is exceeded in any one day/week/sprint and helps find alternative start dates that reduce peak demand on any one skill or team.
Ideas, errors, requests? Email: troy.magennis@focusedobjective.com
Work licensed under a Creative Commons Attribution-NonCommercial-ShareAlike 4.0 International License.
Get more tools like this from: http://bit.ly/SimResources
About us: Focused Objective LLC offers tools, training and expert advice on metrics, risk and forecasting. We have more advanced tools to model Agile teams and projects that help analyze staffing options and risk, and a proven track record of positive results. We are always happy to discuss next steps and training opportunities should this tool prove useful. See our website: http://www.focusedobjective.com or email me at troy.magennis@focusedobjective.com.

## Skill and dependecy planner
Skillset and Dependency Planner - what is needed and when
[8 empty] | = exceeds limit for skill or team |  |  |  | = skill or team not used |  |  | = skill or team moderately used |  |  |  | = skill or team heavily used
 | time axis 2017-01-01 to 2018-12-02
|  |  |  | Team Legend | Skill or Team | Effort Limit or Capacity | time axis 2017-01-01 to 2018-12-02
|  |  |  | 6 | Team 1 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 7 | Team 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 9 | Team 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 10 | Team 4 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 11 | Team 5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 12 | Team 6 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 13 | Team 7 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 14 | Team 8 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 15 | Team 9 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Team 10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Color of team bars below |  | have you reserved capacity for un-planned work?
Tips: You can drag items or cut and past them, but limit selection and entry to columns A-G (orange cells). If you lose formatting, set the cell style to "Input"; it's just fill coloring so you know where to type! Hover over the column titles for instructions. |  |  |  |  | Important dates (events, releases, moments, vacations, etc) |  | 2017-04-02: Long weekend
 | time axis 2017-01-01 to 2018-12-02
Work Item Name | Skill or Team | Effort | Start Date | Shift Start by | Time Guess Low | Time Guess High | time axis 2017-01-01 to 2018-12-02
Team 1 | bar: 2017-01-01
What this does: This spreadsheet helps to plan what skills or teams need to deliver functionality, and to visualize when any one skill or team is overburdened during a week, sprint, etc.
How to use it:
1. Set the settings in the Settings worksheet.
2. Enter the team or skill names.
3. Populate the detals about the work items and estimate the number of resources (effort) needed for each period.
4. Read the capacity needed for each skill/team in the top table heatmap.
5. Set limits so that you can quickly determine when any one skill or team exceeds this limit.
6. Resolve by shifting start dates, or attempt less!
Note on F5: Troy Magennis: Enter the skills necessary to deliver or team names depending on how you wish to identify exceeding capacity.
Note on G5: Troy Magennis: Enter the maximum amount of summed effort for any one period. Periods exceeding this will be highlighted in the heatmp.
Note on A21: Troy Magennis: This is just text so you know what you are talking about :)
Note on B21: Troy Magennis: Choose the specific skill or team responsible for this piece of work. Enter the team or skill names above and then choose from the drop-down list. Be careful, if you alter the team and skill names above, they need to match EXACTLY in this selection.
Note on C21: Troy Magennis: Use whatever unit you prefer here. Effort is summed when shown in the heatmap. I've used # people, I've used how risky. If work is spread over the time (not full utilization), set it to less than 1, for example 0.5 means half effort by one person whilst they do 2 things at once.
Note on D21: Troy Magennis: Enter the anticipated start date. Effort will begin to be counted against this skill in the same period that contains this date.
Note on E21: Troy Magennis: To allow you to experiment with shifting the start date, enter the number of time periods to shift. > 0 moves forward, < 0 moves backwards. Experiment with different start dates to balance the load across teams or skills in the heatmap above.
Note on F21: Troy Magennis: This estimate is the number of time periods (as defined in days in the Settings worksheet) this piece or work will take at at a minimum. Thie effort entered for this item will be counted against the skill or team in the heatmap above at a minimum this amount of time.
Note on G21: Troy Magennis: This is the highest amount of time the effort entered will be applied against the skill or team in the heatmap above. Set the Risk percentage in the Settings tab to control how much of this time gets included. 100% means ALL of this time, 0% means none of this time. Default is 80%,

## Facillitation
Quarterly Portfolio Planning - one item at a time until you exceed capacity method
The scene: A group of product owners and stakeholders meet at regular intervals to plan an upcoming period of time. Everyone brings their laundry list of ideas to a full day meeting to plan what will get done. Normally, there are thousands of times more ideas than capacity, and even the MUST HAVES would take the next 12 months to complete.
The goal: To ensure that the most important items (highest cost of being delayed) make it into the next quarter. To make sure that no one team or skillset is burdened with more than it has achieved historically.
Suggested process:
1. Debrief last quarters plans. Identify carry over work. Identify how well the last plan played out with respect to keeping teams within their effort budget. No blame, just looking to learn how to set correct capacity limits and what type of work we plan poorly.
2. Identify key dates. Are any dates immovable, for example a consumer promotional cmpaign, sporting event, or conference. List these dates and decide when work will need to be "finished" to allow other activities to take place (for example, trining guides or website updates based on the new features or products.
3. Identify the total capacity limit for each team or skill. Decide what units make sense here. It can be people, it can be throughput, it can be story points. Just decide upfront and be consistent with this limit and the effort estimate for each line item.
4. Have the group identify THE ABSOLUTE ONE FEATURE that must deliver. It MUST be one single highest priority.
5. Brainstorm what teams or skills are needed to deliver this ONE feature. Enter this into this spreadsheet and break out one row per team or skill involved, have someone from each team perform a quick estimate of lowest and highest delivery time and effort estimates (these are broad 1 week or 2 week estimates, NOT detailed estimates. Allow the team the final say on these estimates, don't second guess them.
6. Once all of the dates and effort estimates are entered, look at the team and skill heatmap. Have any of the skills hit their limit yet?
No: Go back to step 4 and repeat for the net feature
Yes: Can you move the start date of this feature to reduce peak demand, for example can you move the start date later to avoid overwhelming the exceeded skill or team? If NOT then thats it. You have your plan.
6. Still have some teams lightly loaded? Can they help teams that are overwhelmed and get the next highest priority feature? Rule this out before loading them with "Nice to have work."
Tips and Ideas
- Use story mapping to organize priority of feature delivery - see http://jpattonassociates.com/user-story-mapping/
- If everything is number one priority, nothing is. Make sure everyone understands the reason a delay in a piece of work is improtant.
- Understand the cost of delivering late. Consider this cost of delay calculator: https://github.com/FocusedObjective/FocusedObjective.Resources/raw/master/Spreadsheets/Cost%20of%20Delay%20Prioritization%20Calculator.xlsx
- Understand the cost of over-utilization on delivery time. Review this Kingman's Formula that demonstrates > 80% utilization is risky because delays grow exponentially - https://github.com/FocusedObjective/FocusedObjective.Resources/raw/master/Spreadsheets/Kingmans%20Formula.xlsx
- Survey for how many people you have that can teach, do or are willing to learn different skills. Consider using this capability matrix - https://github.com/FocusedObjective/FocusedObjective.Resources/raw/master/Spreadsheets/Capability%20Matrix%20v2.xlsx

## Settings
Skill and Dependency Planner
Start date | 2017-01-01 | (date first interval starts)
Interval unit | 7 | (calendar days for each segment)
Forecast Percentile | 80% | (how much of the low to high time should be included?)

## Calculations
Indirect Item Name | Indirect Team Name | Indirect Effort | Indirect Start Date | Indirect Start Offset | Indirect Low Estimate | Indirect High Estimate | start int | start | end low | end risk | end high
| Team 1 | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2017-01-01 | FALSE | 1 | 1 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Formulas:
Indirect Start Date = IF(AND(TRIM(INDEX(StartDateRange,ROW([Indirect Effort])-1))<>"",INDEX(StartDateRange,ROW([Indirect Effort])-1)>0),INDEX(StartDateRange,ROW([Indirect Effort])-1),Settings!$B3)