## Sheet1
1. How much (sizing) Capabilities
1.1 Determine segmented groups of potential deliverable options.
Does the organization have an intentional way to define groupings of possible delivery options. How is this performed?
Product releases are regular calendar interval based | Yes | No | Interval:
Product releases are based on pre-planned feature completion | Yes | No | "Average feature count":
Product is released continuously when stable | Yes | No | Average releases per day/week/month:
If not all features are complete by a given planned date, what happens
Features are cut | Yes | No | Answer yes, for > 3 out of 4 times
The date is moved | Yes | No
Neither allowed (projects turned "Red" overtime, etc) | Yes | No
How are delivery options defined (the features targeting a future delivered to custmer product)
A list of features at the top of a backlog | Yes | No | How often is the backlog prioritized:
A list of features negotiated just prior to the planned next period period | Yes | No | How many periods per year?
A story map of the current planned release | Yes | No
A story map of the current + 1 future planning period | Yes | No | Horizon extends out how many releases?
1.2 Determine the size of these groups (in units that pace is measured or convertible to). Reference class forecasting is my preferred mechanism for relative size estimation against prior completed work. Keep he size of prior delivered features to compare proposed features against to quickly assess relative size.
1.3 Determine how much work size grows over time from defects, new ideas, lessons learned, etc. Analyzing historical data and sampling the sources of growth is my preferred mechanism. Pick five sample features and rigorously record what got added over time to deliver these five.
1.4 Determine how much work splits from this “size” to the size the team delivers and pace is measured. Splitting for the team to deliver should be encouraged, as it helps the team maintain flow and quality. Just measure it and remember to account for it when forecasting (1 to 3 times is common).
1.5 List what work might be needed (risks), but its too soon to tell (e.g. performance might be slow and need more optimization, the website might fail on certain browsers and need to be fixed).
How fast (pacing) Capabilities
The key capabilities in answering haw fast are -
List of equipment, capabilities and skills required to deliver an option. My preferred way to capture and analyse this is a simple spreadsheet: Capability Matrix.
Determine the constraint (point of minimal average flow rate) of the delivery system. My preferred method is to value stream map, or look at the capability matrix spreadsheet. If the team is delivering, look for where work sits idle, and the constraint is the process following that point.
Determine the amount of work delivered in a period of time through the constraint in the delivery system. System pace will be the pace through this constraint, making this pace the right value for forecasting. My preferred method is to look at throughput at multiple points in the delivery process and find the lowest. This is the constraint, and the flow at the constraint.
Determine periods of impaired or increased flow. Often events and seasonal vacation periods have a non-negligible impact on delivery rate. Have a way of collecting when these periods will occur and a way of estimating the impact on throughput during those periods.
How urgent (prioritization) Capabilities
The key capabilities in answering how urgent are -
Determine the impact if an option isn’t delivered. This is the ability to understand the near term impact of value from items not being delivered.
Determine when the impact of not delivering an option begins. Some options don’t incur impact until future dates. This is the ability to understand the longer term impact on future value.
Determine how the impact of not delivering an option impact other future options. This is the ability to understand dependencies between options.
Process Capabilities
These are a set of capabilities that help understand process and expectations. These differ from the forecasting capabilities, but they are necessary as inputs to enable those capabilities.
Determine what types of work is delivered. The ability to know what different types of work are flowing through a system and their specific stresses on the delivery system (skills, effort, etc.
The ability to know what work is in progress. Seems obvious, but a system must be able to show what work is waiting to be started, has started and has delivered.
Time in process. The ability to measure how long it takes from start to delivered for different types of work.
Delivery rate (or throughput). The ability to measure (and predict) how fast work is completed by type in a system
Arrival rate. The ability to measure (and predict) how fast new work arrives into the system.
Age of in-progress work. The ability to know the current time in process total for all in-progress work trended over time to see if it is growing or shrinking.

## Sheet2
Delivery Planning
Prioritization |  | how often is the number one item skipped last planning session, chosen the next planning session?
Grouping |  | is there a system for defining feature/item value
Assessing Progress |  | is there a system for defining feature/item cost of delayed release
how often is release planning performed? (shipped to customers)
Size Estimation |  | how often is iteration planning performed (not shipped to customers)
Features |  | how early is potential delivery delay detected
Items
Risk
Growth Rates and Size Adjustments
Pace Estimation
Delivery rate
Unplanned work assessment
Defect triage rate