## Instructions
Single Feature Forecaster or Throughput Forecaster
Want to learn how this works and how to use it? Read my "In-progress" book on Medium - Forecasting using Data
https://medium.com/forecasting-using-data
Version history:
| 1 | 2015-04-07 | Initial beta release for feedback.
| 1.01 | 2015-05-22 | Fixed validation usability errors.
| 1.1 | 2015-05-26 | Added risks and charts.
| 1.2 | 2015-06-01 | Updated instructions and charts.
| 1.3 | 2016-02-12 | Added split rate inputs.
| 1.4 | 2016-06-01 | Added actual plot.
| 1.5 | 2016-06-02 | Added story count forecast by period.
| 1.6 | 2017-06-09 | Added risk impact scores and increased risks to 10 entries
| 2 | 2018-01-17 | Refactored to support Excel 2007+ in all formulas
What is this: This spreadsheet helps to probabilistically forecast how long it will take to complete features and stories based on range estimates.
How does it work? Given your estimates, this spreadsheet hypothetically completes all work 500 times. It calculates likelihood result as the number of simulated trials that finished on or before a given date.
Why is this better than burndowns and traditional Agile forecasting? Most forecasting techniques give a single date result and hide the likelihood of that date. Most often the date given as the result is 50% because work is divided by an average (or median). Thats the odds of a toin-coss. This method allows the reader to choose the amount of schedule risk they wish to sign-up for. 85% is a common middle ground used in the industry.
Is it reliable? It has no mathematical errors (that we know of!), and all we guarentee is its better than intuition alone and better than simple regression models. But, help us improve it by letting us know when it misses the actual results you are seeing.
How to: Fill in the orange boxes in the Forecast worksheet and read off the dates in the results table adjacent to the likelihood/certainty you think is appropriate. 85% is a common industry level of certainty used.
What is throughput? Where do I get that data? Throughput is the number of DONE stories completed by a team per week or per sprint (you choose in this spreadsheet, default is per week). We will be providing a viz that gathers this data for your team. Stay tuned.
What is this: This spreadsheet helps to probabilistically forecast how long it will take to complete features based on story count range estimates and either estimated team throughput or historical team throughput samples.
How does it work? Given your estimates, this spreadsheet hypothetically completes all work 500 times. It calculates likelihood result as the number of simulated trials that finished on or before a given date. Given your desired scenario order, features are completed in order and the dates computed based on specified likelihood.
Why is this better than burndowns and traditional Agile forecasting? Most forecasting techniques give a single date result and hide the likelihood of that date. Most often the date given as the result is 50% because work is divided by an average (or median). That's the odds of a coin-toss. This method allows the reader to choose the amount of schedule risk they wish to sign-up for. 85% is a common middle ground used in the industry.
Is it reliable? It has no mathematical errors (that we know of!), and all we guarantee is its better than intuition alone and better than simple regression models. But, help us improve it by letting us know when it misses the actual results you are seeing.
How to: Fill in the orange boxes in the Forecast worksheet and read off the dates in the results table adjacent to the likelihood/certainty you think is appropriate. 85% is a common industry level of certainty used - a good balance of better than average but not susceptible to extreme outliers.
What is throughput? Where do I get that data? Throughput is the number of DONE stories completed by a team per week or per sprint (you choose in this spreadsheet, default is per week). Also see our Throughput and Cycle Time Calculator spreadsheet for converting story/item data to throughput values. Also see our tutorials on how to use Excel to calculate throughput rates.
Ideas, errors, requests? Email: troy.magennis@focusedobjective.com
Work licensed under a Creative Commons Attribution-NonCommercial-ShareAlike 4.0 International License.
Get more tools like this from: http://bit.ly/SimResources
About us: Focused Objective LLC offers tools, training and expert advice on metrics, risk and forecasting. We have more advanced tools to model Agile teams and projects that help analyze staffing options and risk, and a proven track record of positive results. We are always happy to discuss next steps and training opportunities should this tool prove useful. See our website: http://www.focusedobjective.com or email me at troy.magennis@focusedobjective.com.
About me….
I develop and teach how to use data in software development and operations teams for coaching or forecasting.
- Forecasting using Data workshop. Teach how to use these spreadsheets with practical hands-on examples based on your (and my) specific examples. Often run internally, sometimes publically.
- Data Driven Coaching workshop. Teach how to develop data driven approaches to improvement based on balancing multiple competing metrics. Often run internally, sometimes publically.
- Custom Dashboards or giving advice on your current dashboards. Take the next step in customizing our spreadsheets or deploying more advanced versions in Tableau or Power BI.
- Quantitative consulting or advice - give me a chance to answer something you need to know. I'll work with your teams in designing a prediction system or delivering a compelling visual demonstrting the issues.
Interested in chatting? Email me at troy.magennis@focusedobjective.com
Interested in stalking? Follow me on twitter @t_magennis
(best way to hear about new and improved spreadsheets like this)

## Forecast
Forecast Completion Date | [7 empty] | Results
Duration in
1. Start Date |  |  | 2017-06-09 |  |  |  |  | Likelihood | 1 week's | Date
[8 empty] | 100% | 34 | 2018-02-02
2. How many stories are remaining to be completed? | [7 empty] | 95% | 27 | 2017-12-15
(enter the range estimate of stories. Tip: start wide and narrow as certainty increases) | [7 empty] | 90% | 25 | 2017-12-01
| Low guess |  | 20 |  | Highest guess |  | 30 | 85% | 23 | 2017-11-17
[8 empty] | 80% | 22 | 2017-11-10
3. Stories are often split before and whilst being worked on. Estimate the split rate low and high bounds. | [7 empty] | 75% | 21 | 2017-11-03
(often the throughput in the backlog is pre-split, but captured throughput post-split. Adjust for this here) | [7 empty] | 70% | 20 | 2017-10-27
| Low guess |  | 1 |  | Highest guess |  | 3 | 65% | 19 | 2017-10-20
[8 empty] | 60% | 18 | 2017-10-13
4. Throughput. How many completed stories per week or sprint do you estimate low and high bounds? | [7 empty] | 55% | 18 | 2017-10-13
[8 empty] | 50% | 16 | 2017-09-29
Throughput/velocity data or estimate is for |  |  |  | 1 week | 7 | days |  | 45% | 16 | 2017-09-29
(choose a time interval that throughput of velocity is measured in weeks from the list in the orange cell above) | [7 empty] | 40% | 15 | 2017-09-22
Use historical throughput data OR enter a low and high estimate below. Use: | [6 empty] | Estimate | 35% | 14 | 2017-09-15
[8 empty] | 30% | 13 | 2017-09-08
[8 empty] | 25% | 12 | 2017-09-01
| Low guess |  | 1 |  | Highest guess |  | 5 | 20% | 12 | 2017-09-01
[8 empty] | 15% | 11 | 2017-08-25
[8 empty] | 10% | 10 | 2017-08-18
[8 empty] | 5% | 9 | 2017-08-11
[8 empty] | 0% | 6 | 2017-07-21
Forecast Story Count Completion by Time Period
5. How long? |  | 6 | 1 weeks |  | Result: Total Pre-split Stories in 6 1 weeks
(To forecast story counts, enter the how long. |  |  |  |  | (Pre-split means, splitting IS accounted for)
To change unit, change input 4. above.) |  |  |  |  | 95% | 7.3333
[5 empty] | 85% | 8.5 | <--- Tip: This is your forecasted # storiess for this period at 85% confidence
[5 empty] | 5% | 16.5
Almost certain
Somewhat certain
Less than coin-toss odds. But if you are game?
Can I use velocity rather than throughput?
Yes. If you do have estimates in story points, then you can sume all of the estimates and use that for input 2 and estimate or use historical team velocity for input 4. The benefit of using throughput (count of completed stories per week/sprint) is that the individual stories don't require estimation in story points.
Please Remember: This forecast is only as good as the estimates you enter into it. Always look for multiple ways to forecast your project and compare the outcomes, especially if making a financially critical decision. In the end - any decision to proceed with a project is YOURS.
How do I use this story count forecast?
This forecast aims to show how many stories might be completed given the team data or estimates entered above. Enter all data for inputs 3. and 4. above. This forecast simulates 500 times to determine what number of stories will be completed for the period you entered for input 5. It also creates a chart view of this forecast in the charts tab. This forecast ignores risk data, and un-necessary inputs 1 and 2 from above.
Note on I16: Author: This is the measure of how two random groups of your sample data would align when forecasting. Anything below 25% is good, but lower is better. It grows if there is too little data, and ALSO if the process changes over time and you use too much data.

## Risks
Likelihood | Impact Low | Impact High | Description | Combined Impact (higher is worse) | Est. impact in 1 week's | Impact Rank (fix lowest first)
Calculations -
Likelihood | Impact Low | Impact High | Description | average story count | 50
30% | 10 | 15 | Server performance issues | duration at 85th P | 23
15% | 5 | 10 | Layout issues when text localized | count per period | 2.1739
20% | 5 | 15 | Layout in Safari issues
Why would I use risks?
Risks allow you to put a probability on work being expanded because of something more than plan. For example, there might be a chance that more work is needed to improve performance characteristics. If you think there is a 20% chance, put 20 in the likelihood column. Have the team estimate the low and high story count to rectify and add these to the low and high impact columns.
Risk impact analysis
It can be hard to determine what risks are most impactful when they have different likelihoods and impacts. The risks are ranked here from most impactful (Rank = 1) to least impactful.
This is a simple ranking. It helps quickly see what is the most important to decrease likelihood or impact.

## Charts
[14 empty] | Week | Frequency
[14 empty] | 2017-07-21 | 3
[14 empty] | 2017-07-28 | 2
[14 empty] | 2017-08-04 | 13
[14 empty] | 2017-08-11 | 21
[14 empty] | 2017-08-18 | 30
[14 empty] | 2017-08-25 | 20
[14 empty] | 2017-09-01 | 40
[14 empty] | 2017-09-08 | 27
[14 empty] | 2017-09-15 | 32
[14 empty] | 2017-09-22 | 19
[14 empty] | 2017-09-29 | 44
[14 empty] | 2017-10-06 | 18
[14 empty] | 2017-10-13 | 33
[14 empty] | 2017-10-20 | 28
[14 empty] | 2017-10-27 | 36
[14 empty] | 2017-11-03 | 23
[14 empty] | 2017-11-10 | 20
[14 empty] | 2017-11-17 | 23
[14 empty] | 2017-11-24 | 14
[14 empty] | 2017-12-01 | 13
[14 empty] | 2017-12-08 | 10
[14 empty] | 2017-12-15 | 9
[14 empty] | 2017-12-22 | 11
[14 empty] | 2017-12-29 | 6
[14 empty] | 2018-01-05 | 4
[14 empty] | 2018-01-12 | 0
[14 empty] | 2018-01-19 | 1
[14 empty] | 2018-01-26 | 0
[14 empty] | 2018-02-02 | 1
0
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
Story count results in table form. For the probabilities entered, how many stories for each period?
| 4 1 weeks | 8 1 weeks | 12 1 weeks | 16 1 weeks | 20 1 weeks | 24 1 weeks | 28 1 weeks | 32 1 weeks | 36 1 weeks | 40 1 weeks | 44 1 weeks | 48 1 weeks | 52 1 weeks
95% | 4.3333 | 10.5 | 17.1667 | 23.6667 | 30.3333 | 37.3333 | 43.9917 | 51.6583 | 58.8333 | 65.8333 | 72.8333 | 79.6583 | 87
85% | 5.1417 | 12 | 18.6667 | 25.8333 | 33 | 40.1417 | 47.3083 | 54.8333 | 62.1667 | 69.3333 | 76.5 | 84.1667 | 91.5
5% | 12.0083 | 21.175 | 31 | 38.8667 | 48.0083 | 57.1667 | 66.0083 | 73.5167 | 82.5167 | 90.3417 | 97.8417 | 106.175 | 115.175
What is this chart?
This chart shows how many simulated trials completed on or before the x-axis date. The higher the bar, the more likely that outcome.
What is this chart?
This chart shows the simulated burn-down trends. It shows the first 50 trials and visually shows the general hotspots and outlier dates. Enter actual stories remaining in the Reamining Stories Actual worksheet to see progress.
What is this chart?
This chart shows the number of completed (pre-split) stories for a given period. Select the time period on the forecast worksheet. The forecast is shown at three confidence intervals specified on the forecast worksheet.

## Throughput Samples
Enter Samples Below | Group | Unique Rank
3 | 1 | 3
5 | 1 | 5
2 | 2 | 2
1 | 1 | 1
5 | 2 | 6
3 | 2 | 4
Stability Between Two Random Groups of the Samples
|  |  | Group | All | 1 | 2 | Diff
|  |  | count | 6 | 3 | 3 | 0
|  |  | min | 1 | 1 | 2
|  |  | max | 5 | 5 | 5
|  |  | avg | 3.1667 | 3 | 3.3333 | -0.33333
|  |  | median | 3 | 3 | 3 | 0
|  |  | avg error |  |  |  | 0.33333 | I also tried average of the mean and median error….but think average will do.
|  |  | error/range |  |  |  | 8.333% | Aim to keep this below 25%. By adding more sample data. You will see where to stop.
Transportable data formats
|  |  | Total Count |  | 6 |  |  |  |  | CSV | 3,5,2,1,5,3
|  |  | Data |  | 2 | 1 | 5 | 3 | 2 | SIP 2.0 | <sip name="dist" type="CSV" ver="1.0" count="6" average="3.16666666666667" median="3">3,5,2,1,5,3</sip>
|  |  | Estimate |  | 1 | 1 | 2 | 1 | 2 | Distribution | <distribution name="dist" shape="fromSamples">3,5,2,1,5,3</distribution>
|  |  | Samples Or Data |  | 1 | 4 | 1 | 4 | 3
Instructions.
If you have team historic throughput samples, you can use them when forecasting forward. If not, estimate the range in the forecast sheet. When actual data becomes available, add it here and your forecast will become more indicative.
Add seven (7) minimum, and twenty five (25) maximum recent throughput samples for your team. These samples will be used as throughput values picked at random. By using your teams data, the forecast will follow the patterns your teams throughput historically follows.
Remember to set the unit of throughput measure.
No blank rows within sample range, leave rows after the last sample blank.
Data beyond 24 weeks is most likely out of date. When adding, add most recent samples to the top and remove older samples from the bottom.
These are for testing the formulas that return random ssamples from data or between the estimates. They are included here for education and reference.
These formats are to help share throughput samples with others or teams should the need arise.
CSV = simple comma separated value list
SIP 2.0 = ProbabilityManagement.org's SIP standard for sharing data
Distribution = FocusedObjective.com's distribution format for sharing and creating random data from samples in their simulation software
What is throughput? Where do I get that data? Throughput is the number of DONE stories completed by a team per week or per sprint (you choose in this spreadsheet, default is per week). Also see our Throughput and Cycle Time Calculator spreadsheet for convertinf story/item data to throughput values. Also see our tutorials on how to use Excel to calculate throughput rates.
How many amples?
You could make this spreadsheet use more historical data, but its not statistically necessary. My advice: use the most recent 15 samples if you have them to avoid using "old" data that was cptured when the team was performing differently than it is now. You should use the most recent data where the error percentage is less than 10%

## Remaining Stories Actuals
Date (week ending) | Number of Incompleted (but in scope) stories | Notes
2017-06-09 | 27
2017-06-16 | 25
2017-06-23 | 20
2017-06-30 | 19
2017-07-07
2017-07-14
2017-07-21
2017-07-28
2017-08-04
2017-08-11
2017-08-18
2017-08-25
2017-09-01
2017-09-08
2017-09-15
2017-09-22
2017-09-29
2017-10-06
2017-10-13
2017-10-20
2017-10-27
2017-11-03
2017-11-10
2017-11-17
2017-11-24
2017-12-01
2017-12-08
2017-12-15
2017-12-22
2017-12-29
2018-01-05
2018-01-12
2018-01-19
2018-01-26
2018-02-02
2018-02-09
2018-02-16
2018-02-23
2018-03-02
2018-03-09
2018-03-16
2018-03-23
2018-03-30
2018-04-06
2018-04-13
2018-04-20
2018-04-27
2018-05-04
2018-05-11
2018-05-18
2018-05-25
Instructions.
Enter the actual number of IN-COMPLETE items in the backlog in column B for the dates shown in column A. This line will be charted on the burndown chart.

## Settings
Duration name | days
1 week | 7
2 weeks | 14
3 weeks | 21
4 weeks | 28
This table converts throughput duration name to number of days. Add more or edit these here. The days is used to increment forecasting periods. Resolution of forecast will also be in increments of this value.

## Monte Carlo
Trial | Weeks to Zero | End of Zero Week | TotalStories | End period 1 | End period 2 | End period 3 | End period 4 | End period 5 | End period 6 | End period 7 | End period 8 | End period 9 | End period 10 | End period 11 | End period 12 | End period 13 | End period 14 | End period 15 | End period 16 | End period 17 | End period 18 | End period 19 | End period 20 | End period 21 | End period 22 | End period 23 | End period 24 | End period 25 | End period 26 | End period 27 | End period 28 | End period 29 | End period 30 | End period 31 | End period 32 | End period 33 | End period 34 | End period 35 | End period 36 | End period 37 | End period 38 | End period 39 | End period 40 | End period 41 | End period 42 | End period 43 | End period 44 | End period 45 | End period 46 | End period 47 | End period 48 | End period 49 | End period 50 | End period 51 | End period 52 | End period 53 | End period 54 | End period 55 | End period 56 | End period 57 | End period 58 | End period 59 | End period 60 | End period 61 | End period 62 | End period 63 | End period 64 | End period 65 | End period 66 | End period 67 | End period 68 | End period 69 | End period 70 | End period 71 | End period 72 | End period 73 | End period 74 | End period 75 | End period 76 | End period 77 | End period 78 | End period 79 | End period 80 | End period 81 | End period 82 | End period 83 | End period 84 | End period 85 | End period 86 | End period 87 | End period 88 | End period 89 | End period 90 | End period 91 | End period 92 | End period 93 | End period 94 | End period 95 | End period 96 | End period 97 | End period 98 | End period 99 | End period 100 | End period 101 | End period 102 | End period 103 | End period 104 | End period 105 | End period 106 | End period 107 | End period 108 | End period 109 | End period 110 | End period 111
 | time axis 2017-06-09 to 2019-07-26
1 | 24 | 2017-11-24 | 66 | 64 | 59 | 56 | 54 | 49 | 46 | 45 | 43 | 42 | 38 | 35 | 31 | 28 | 27 | 25 | 21 | 19 | 14 | 13 | 10 | 9 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 26 | 2017-12-08 | 71 | 68 | 67 | 63 | 62 | 60 | 57 | 52 | 51 | 47 | 42 | 41 | 37 | 36 | 35 | 33 | 28 | 26 | 25 | 21 | 20 | 15 | 11 | 9 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 16 | 2017-09-29 | 55 | 54 | 49 | 44 | 39 | 38 | 37 | 32 | 29 | 28 | 25 | 20 | 15 | 10 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 24 | 2017-11-24 | 68 | 65 | 62 | 58 | 56 | 55 | 51 | 48 | 45 | 43 | 39 | 37 | 34 | 30 | 28 | 25 | 22 | 19 | 14 | 11 | 7 | 6 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 16 | 2017-09-29 | 49 | 48 | 44 | 41 | 36 | 31 | 26 | 22 | 19 | 17 | 14 | 10 | 9 | 7 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 24 | 2017-11-24 | 66 | 61 | 59 | 58 | 55 | 53 | 48 | 44 | 41 | 39 | 34 | 31 | 27 | 25 | 23 | 21 | 20 | 19 | 15 | 13 | 11 | 7 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 19 | 2017-10-20 | 53 | 51 | 50 | 49 | 45 | 41 | 39 | 36 | 34 | 33 | 29 | 26 | 25 | 20 | 18 | 13 | 8 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 14 | 2017-09-15 | 56 | 54 | 49 | 45 | 41 | 36 | 31 | 27 | 22 | 17 | 15 | 10 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 20 | 2017-10-27 | 57 | 56 | 51 | 47 | 46 | 43 | 39 | 38 | 37 | 32 | 29 | 27 | 24 | 19 | 17 | 16 | 13 | 9 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | 21 | 2017-11-03 | 59 | 58 | 57 | 55 | 53 | 52 | 47 | 42 | 41 | 39 | 35 | 30 | 26 | 21 | 19 | 18 | 16 | 15 | 11 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | 19 | 2017-10-20 | 61 | 58 | 56 | 51 | 48 | 46 | 43 | 38 | 35 | 30 | 27 | 25 | 21 | 16 | 12 | 11 | 9 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 18 | 2017-10-13 | 58 | 56 | 51 | 47 | 43 | 42 | 39 | 35 | 32 | 29 | 24 | 22 | 18 | 15 | 12 | 11 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | 15 | 2017-09-22 | 43 | 40 | 38 | 34 | 30 | 28 | 26 | 22 | 19 | 16 | 13 | 10 | 9 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 9 | 2017-08-11 | 29 | 26 | 21 | 19 | 18 | 15 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | 10 | 2017-08-18 | 28 | 25 | 22 | 18 | 14 | 9 | 7 | 6 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | 10 | 2017-08-18 | 33 | 28 | 27 | 23 | 18 | 16 | 11 | 7 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 18 | 2017-10-13 | 54 | 51 | 49 | 48 | 45 | 44 | 39 | 38 | 35 | 33 | 29 | 24 | 23 | 21 | 16 | 13 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 22 | 2017-11-10 | 71 | 67 | 66 | 63 | 58 | 53 | 48 | 46 | 43 | 42 | 38 | 35 | 31 | 26 | 21 | 18 | 15 | 11 | 7 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | 17 | 2017-10-06 | 56 | 52 | 47 | 42 | 38 | 35 | 30 | 28 | 26 | 21 | 20 | 16 | 15 | 11 | 10 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | 10 | 2017-08-18 | 35 | 31 | 27 | 22 | 20 | 19 | 18 | 13 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 6 | 2017-07-21 | 22 | 17 | 14 | 9 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | 14 | 2017-09-15 | 37 | 33 | 31 | 30 | 29 | 25 | 24 | 21 | 18 | 16 | 12 | 8 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | 9 | 2017-08-11 | 27 | 23 | 18 | 17 | 14 | 10 | 6 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 28 | 2017-12-22 | 80 | 76 | 75 | 70 | 65 | 64 | 61 | 59 | 57 | 55 | 51 | 49 | 47 | 43 | 39 | 35 | 34 | 31 | 30 | 25 | 24 | 19 | 18 | 16 | 13 | 10 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | 20 | 2017-10-27 | 59 | 57 | 53 | 48 | 43 | 42 | 39 | 37 | 36 | 34 | 30 | 27 | 24 | 21 | 17 | 14 | 11 | 9 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | 17 | 2017-10-06 | 45 | 41 | 36 | 34 | 33 | 28 | 25 | 24 | 23 | 22 | 20 | 19 | 14 | 12 | 7 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | 20 | 2017-10-27 | 58 | 57 | 55 | 51 | 47 | 45 | 44 | 42 | 37 | 33 | 31 | 28 | 23 | 21 | 20 | 16 | 11 | 8 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | 25 | 2017-12-01 | 68 | 64 | 61 | 56 | 55 | 52 | 47 | 45 | 44 | 41 | 36 | 32 | 29 | 25 | 21 | 20 | 19 | 17 | 14 | 13 | 12 | 9 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | 20 | 2017-10-27 | 55 | 53 | 52 | 50 | 45 | 43 | 40 | 39 | 38 | 35 | 34 | 32 | 27 | 25 | 23 | 18 | 14 | 10 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | 24 | 2017-11-24 | 66 | 65 | 64 | 63 | 58 | 54 | 49 | 45 | 43 | 41 | 36 | 35 | 30 | 28 | 24 | 20 | 19 | 15 | 14 | 11 | 8 | 7 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | 10 | 2017-08-18 | 36 | 33 | 29 | 25 | 22 | 19 | 14 | 11 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | 28 | 2017-12-22 | 77 | 73 | 71 | 67 | 62 | 60 | 56 | 51 | 50 | 48 | 44 | 41 | 40 | 38 | 34 | 33 | 31 | 30 | 29 | 27 | 23 | 21 | 18 | 17 | 14 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | 12 | 2017-09-01 | 47 | 43 | 39 | 36 | 33 | 28 | 27 | 22 | 17 | 12 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | 14 | 2017-09-15 | 46 | 43 | 42 | 38 | 34 | 30 | 27 | 24 | 19 | 17 | 12 | 8 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | 12 | 2017-09-01 | 35 | 33 | 29 | 25 | 21 | 20 | 15 | 14 | 12 | 9 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | 16 | 2017-09-29 | 54 | 49 | 46 | 43 | 40 | 36 | 31 | 27 | 22 | 21 | 17 | 16 | 11 | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | 20 | 2017-10-27 | 59 | 58 | 55 | 51 | 46 | 43 | 38 | 33 | 30 | 27 | 25 | 22 | 21 | 19 | 14 | 13 | 11 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | 15 | 2017-09-22 | 37 | 36 | 33 | 30 | 29 | 24 | 20 | 15 | 14 | 13 | 10 | 7 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | 26 | 2017-12-08 | 79 | 77 | 74 | 71 | 70 | 65 | 64 | 63 | 59 | 57 | 52 | 51 | 49 | 47 | 42 | 38 | 33 | 31 | 27 | 25 | 22 | 18 | 16 | 11 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | 10 | 2017-08-18 | 29 | 27 | 25 | 22 | 18 | 14 | 13 | 8 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | 20 | 2017-10-27 | 60 | 57 | 52 | 51 | 49 | 48 | 44 | 43 | 42 | 37 | 32 | 31 | 28 | 24 | 19 | 16 | 13 | 10 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | 21 | 2017-11-03 | 69 | 65 | 60 | 57 | 52 | 48 | 47 | 43 | 38 | 34 | 33 | 30 | 27 | 26 | 22 | 17 | 13 | 8 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | 16 | 2017-09-29 | 53 | 51 | 46 | 41 | 36 | 32 | 29 | 27 | 22 | 20 | 17 | 14 | 13 | 9 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | 20 | 2017-10-27 | 66 | 63 | 58 | 54 | 49 | 47 | 43 | 41 | 36 | 34 | 31 | 26 | 23 | 22 | 21 | 16 | 11 | 10 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | 9 | 2017-08-11 | 27 | 22 | 21 | 16 | 14 | 9 | 8 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | 12 | 2017-09-01 | 36 | 35 | 30 | 27 | 26 | 21 | 16 | 14 | 12 | 10 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | 18 | 2017-10-13 | 60 | 57 | 55 | 52 | 47 | 43 | 40 | 35 | 31 | 26 | 22 | 18 | 16 | 15 | 11 | 6 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 24 | 2017-11-24 | 78 | 74 | 73 | 69 | 65 | 63 | 58 | 57 | 56 | 51 | 47 | 46 | 41 | 37 | 33 | 28 | 24 | 23 | 18 | 16 | 15 | 11 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | 13 | 2017-09-08 | 31 | 27 | 24 | 21 | 20 | 19 | 18 | 15 | 14 | 11 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | 7 | 2017-07-28 | 24 | 21 | 19 | 16 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | 23 | 2017-11-17 | 69 | 68 | 67 | 64 | 63 | 60 | 59 | 54 | 50 | 49 | 44 | 42 | 40 | 35 | 32 | 27 | 22 | 19 | 14 | 10 | 8 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 | 20 | 2017-10-27 | 62 | 57 | 55 | 53 | 50 | 46 | 42 | 41 | 39 | 34 | 33 | 30 | 28 | 27 | 23 | 20 | 15 | 12 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | 12 | 2017-09-01 | 34 | 32 | 31 | 27 | 23 | 21 | 16 | 11 | 10 | 8 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | 15 | 2017-09-22 | 40 | 37 | 35 | 31 | 27 | 24 | 23 | 18 | 14 | 13 | 11 | 7 | 4 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 | 13 | 2017-09-08 | 37 | 35 | 30 | 26 | 23 | 18 | 16 | 15 | 12 | 9 | 6 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56 | 30 | 2018-01-05 | 80 | 76 | 75 | 71 | 69 | 65 | 63 | 60 | 55 | 53 | 49 | 46 | 45 | 44 | 43 | 40 | 37 | 35 | 33 | 32 | 29 | 27 | 25 | 24 | 23 | 19 | 18 | 13 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57 | 16 | 2017-09-29 | 52 | 47 | 43 | 38 | 33 | 30 | 26 | 22 | 20 | 16 | 14 | 11 | 9 | 8 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58 | 20 | 2017-10-27 | 63 | 59 | 55 | 54 | 49 | 48 | 43 | 39 | 38 | 35 | 33 | 29 | 28 | 23 | 19 | 15 | 12 | 8 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
59 | 22 | 2017-11-10 | 66 | 62 | 57 | 55 | 51 | 49 | 45 | 40 | 39 | 38 | 35 | 32 | 28 | 26 | 23 | 21 | 16 | 15 | 10 | 9 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 | 11 | 2017-08-25 | 27 | 26 | 21 | 18 | 17 | 16 | 15 | 11 | 9 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
61 | 14 | 2017-09-15 | 50 | 48 | 43 | 38 | 33 | 28 | 27 | 24 | 20 | 16 | 13 | 9 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
62 | 19 | 2017-10-20 | 55 | 51 | 49 | 48 | 45 | 41 | 40 | 37 | 32 | 28 | 27 | 24 | 20 | 18 | 13 | 12 | 9 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | 19 | 2017-10-20 | 58 | 56 | 51 | 49 | 46 | 44 | 41 | 37 | 34 | 29 | 28 | 27 | 24 | 21 | 16 | 13 | 10 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
64 | 14 | 2017-09-15 | 42 | 40 | 36 | 34 | 30 | 29 | 25 | 21 | 20 | 19 | 15 | 13 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
65 | 13 | 2017-09-08 | 39 | 34 | 31 | 30 | 27 | 25 | 21 | 17 | 14 | 13 | 10 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
66 | 6 | 2017-07-21 | 22 | 17 | 12 | 11 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
67 | 8 | 2017-08-04 | 25 | 22 | 18 | 15 | 12 | 10 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
68 | 22 | 2017-11-10 | 64 | 60 | 58 | 57 | 54 | 53 | 48 | 44 | 39 | 37 | 34 | 31 | 26 | 25 | 23 | 21 | 20 | 15 | 11 | 7 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
69 | 14 | 2017-09-15 | 44 | 40 | 39 | 34 | 31 | 28 | 24 | 20 | 18 | 13 | 12 | 11 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 | 22 | 2017-11-10 | 64 | 62 | 57 | 56 | 54 | 52 | 48 | 46 | 44 | 39 | 35 | 30 | 29 | 28 | 25 | 21 | 16 | 14 | 11 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
71 | 9 | 2017-08-11 | 22 | 21 | 19 | 17 | 16 | 12 | 10 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 24 | 2017-11-24 | 69 | 65 | 61 | 60 | 57 | 53 | 50 | 49 | 48 | 44 | 40 | 36 | 31 | 29 | 26 | 25 | 24 | 20 | 15 | 13 | 10 | 7 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
73 | 21 | 2017-11-03 | 62 | 59 | 54 | 49 | 44 | 40 | 39 | 38 | 36 | 33 | 31 | 28 | 26 | 23 | 22 | 17 | 13 | 10 | 9 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
74 | 12 | 2017-09-01 | 42 | 37 | 32 | 28 | 24 | 21 | 16 | 14 | 12 | 9 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
75 | 9 | 2017-08-11 | 28 | 27 | 23 | 19 | 17 | 13 | 8 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
76 | 21 | 2017-11-03 | 57 | 53 | 50 | 47 | 44 | 40 | 39 | 37 | 32 | 28 | 27 | 22 | 17 | 13 | 11 | 9 | 8 | 7 | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
77 | 19 | 2017-10-20 | 51 | 46 | 43 | 42 | 40 | 39 | 36 | 33 | 32 | 30 | 26 | 23 | 21 | 18 | 15 | 10 | 8 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
78 | 10 | 2017-08-18 | 29 | 25 | 24 | 22 | 20 | 15 | 11 | 8 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
79 | 12 | 2017-09-01 | 36 | 33 | 28 | 26 | 21 | 20 | 18 | 13 | 12 | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | 23 | 2017-11-17 | 72 | 68 | 66 | 65 | 64 | 59 | 57 | 52 | 50 | 45 | 42 | 37 | 34 | 31 | 30 | 29 | 24 | 21 | 17 | 12 | 10 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 | 14 | 2017-09-15 | 43 | 40 | 35 | 34 | 29 | 26 | 23 | 21 | 17 | 16 | 13 | 10 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
82 | 11 | 2017-08-25 | 29 | 28 | 24 | 21 | 19 | 18 | 16 | 11 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | 23 | 2017-11-17 | 68 | 66 | 63 | 60 | 57 | 54 | 53 | 51 | 47 | 42 | 41 | 40 | 38 | 37 | 34 | 29 | 25 | 21 | 18 | 13 | 8 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | 14 | 2017-09-15 | 43 | 42 | 38 | 37 | 33 | 30 | 29 | 25 | 20 | 18 | 13 | 8 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
85 | 16 | 2017-09-29 | 36 | 34 | 33 | 30 | 25 | 23 | 22 | 18 | 17 | 14 | 12 | 11 | 10 | 9 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 | 14 | 2017-09-15 | 40 | 38 | 35 | 31 | 28 | 26 | 25 | 22 | 18 | 14 | 11 | 7 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | 11 | 2017-08-25 | 32 | 29 | 27 | 24 | 19 | 17 | 14 | 11 | 7 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 | 30 | 2018-01-05 | 84 | 82 | 78 | 75 | 70 | 68 | 64 | 61 | 60 | 56 | 55 | 51 | 50 | 48 | 44 | 41 | 38 | 33 | 28 | 27 | 26 | 23 | 22 | 17 | 16 | 15 | 11 | 9 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
89 | 10 | 2017-08-18 | 35 | 30 | 26 | 23 | 22 | 19 | 14 | 10 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | 14 | 2017-09-15 | 41 | 37 | 34 | 30 | 28 | 23 | 20 | 18 | 16 | 12 | 7 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 | 18 | 2017-10-13 | 51 | 47 | 44 | 39 | 37 | 35 | 31 | 28 | 27 | 23 | 21 | 20 | 17 | 16 | 12 | 11 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 | 14 | 2017-09-15 | 42 | 41 | 38 | 33 | 32 | 28 | 27 | 22 | 17 | 13 | 11 | 8 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 | 22 | 2017-11-10 | 56 | 55 | 54 | 50 | 45 | 42 | 40 | 39 | 38 | 36 | 34 | 31 | 27 | 22 | 21 | 17 | 14 | 11 | 9 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 | 18 | 2017-10-13 | 52 | 48 | 44 | 40 | 38 | 37 | 36 | 35 | 34 | 31 | 27 | 25 | 22 | 17 | 16 | 13 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 | 12 | 2017-09-01 | 39 | 35 | 30 | 27 | 23 | 18 | 17 | 13 | 9 | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 | 12 | 2017-09-01 | 34 | 30 | 27 | 25 | 24 | 19 | 16 | 14 | 9 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
97 | 19 | 2017-10-20 | 68 | 63 | 60 | 57 | 53 | 49 | 48 | 45 | 41 | 37 | 32 | 28 | 24 | 19 | 16 | 13 | 10 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 | 8 | 2017-08-04 | 31 | 27 | 23 | 22 | 17 | 13 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | 19 | 2017-10-20 | 57 | 54 | 50 | 45 | 43 | 39 | 37 | 35 | 31 | 27 | 25 | 24 | 21 | 20 | 15 | 14 | 9 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100 | 16 | 2017-09-29 | 47 | 46 | 45 | 42 | 39 | 36 | 33 | 28 | 26 | 22 | 18 | 13 | 10 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
101 | 21 | 2017-11-03 | 64 | 61 | 56 | 51 | 50 | 47 | 42 | 37 | 36 | 33 | 30 | 25 | 24 | 19 | 14 | 9 | 8 | 6 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
102 | 24 | 2017-11-24 | 68 | 65 | 63 | 61 | 56 | 53 | 49 | 46 | 41 | 36 | 35 | 32 | 30 | 27 | 24 | 23 | 21 | 20 | 15 | 12 | 9 | 8 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
103 | 18 | 2017-10-13 | 62 | 58 | 54 | 53 | 49 | 48 | 43 | 39 | 36 | 33 | 30 | 25 | 21 | 18 | 13 | 9 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
104 | 21 | 2017-11-03 | 60 | 57 | 54 | 53 | 52 | 49 | 44 | 42 | 41 | 39 | 34 | 32 | 29 | 26 | 23 | 20 | 16 | 15 | 11 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
105 | 25 | 2017-12-01 | 75 | 71 | 68 | 67 | 64 | 61 | 56 | 52 | 50 | 48 | 45 | 40 | 37 | 36 | 31 | 30 | 28 | 24 | 20 | 15 | 11 | 7 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
106 | 12 | 2017-09-01 | 35 | 32 | 28 | 25 | 23 | 18 | 17 | 13 | 10 | 9 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
107 | 13 | 2017-09-08 | 33 | 29 | 26 | 25 | 22 | 20 | 16 | 14 | 13 | 8 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
108 | 27 | 2017-12-15 | 71 | 68 | 67 | 66 | 62 | 60 | 57 | 56 | 52 | 49 | 48 | 47 | 42 | 38 | 35 | 34 | 33 | 28 | 26 | 21 | 19 | 17 | 15 | 11 | 9 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
109 | 25 | 2017-12-01 | 71 | 67 | 62 | 59 | 58 | 53 | 52 | 47 | 43 | 41 | 36 | 35 | 30 | 28 | 27 | 26 | 23 | 20 | 16 | 15 | 13 | 8 | 6 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
110 | 14 | 2017-09-15 | 46 | 42 | 37 | 33 | 32 | 27 | 22 | 18 | 16 | 15 | 13 | 10 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
111 | 9 | 2017-08-11 | 31 | 26 | 24 | 22 | 17 | 15 | 11 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
112 | 28 | 2017-12-22 | 89 | 87 | 83 | 80 | 76 | 71 | 67 | 64 | 61 | 56 | 55 | 53 | 49 | 45 | 43 | 39 | 37 | 33 | 32 | 31 | 28 | 24 | 23 | 19 | 15 | 11 | 7 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
113 | 26 | 2017-12-08 | 78 | 74 | 73 | 70 | 68 | 63 | 62 | 61 | 60 | 58 | 55 | 51 | 49 | 44 | 43 | 39 | 35 | 30 | 25 | 22 | 19 | 17 | 12 | 9 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
114 | 26 | 2017-12-08 | 71 | 69 | 68 | 64 | 59 | 55 | 54 | 52 | 47 | 43 | 40 | 38 | 37 | 36 | 34 | 30 | 26 | 21 | 20 | 18 | 17 | 14 | 12 | 7 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
115 | 16 | 2017-09-29 | 55 | 52 | 48 | 43 | 38 | 33 | 31 | 30 | 28 | 25 | 20 | 17 | 12 | 11 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
116 | 34 | 2018-02-02 | 80 | 78 | 76 | 75 | 74 | 73 | 70 | 65 | 60 | 59 | 58 | 55 | 52 | 51 | 46 | 44 | 39 | 38 | 35 | 33 | 28 | 25 | 24 | 23 | 20 | 19 | 17 | 14 | 13 | 11 | 8 | 6 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
117 | 14 | 2017-09-15 | 40 | 38 | 34 | 30 | 29 | 24 | 23 | 20 | 17 | 13 | 9 | 8 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
118 | 15 | 2017-09-22 | 44 | 41 | 37 | 35 | 33 | 29 | 24 | 23 | 21 | 19 | 17 | 13 | 11 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
119 | 16 | 2017-09-29 | 51 | 48 | 44 | 40 | 36 | 32 | 31 | 29 | 27 | 22 | 18 | 16 | 15 | 10 | 7 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
120 | 26 | 2017-12-08 | 88 | 83 | 78 | 77 | 73 | 70 | 66 | 62 | 57 | 52 | 50 | 45 | 40 | 36 | 34 | 32 | 27 | 23 | 22 | 17 | 15 | 14 | 11 | 7 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
121 | 18 | 2017-10-13 | 45 | 44 | 42 | 39 | 37 | 36 | 32 | 29 | 28 | 25 | 21 | 20 | 19 | 18 | 16 | 13 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
122 | 20 | 2017-10-27 | 66 | 63 | 58 | 53 | 49 | 48 | 47 | 45 | 42 | 41 | 36 | 31 | 26 | 21 | 16 | 13 | 11 | 10 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
123 | 22 | 2017-11-10 | 67 | 63 | 61 | 56 | 55 | 53 | 50 | 46 | 43 | 41 | 39 | 35 | 34 | 30 | 28 | 27 | 22 | 17 | 12 | 7 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
124 | 19 | 2017-10-20 | 58 | 57 | 52 | 49 | 46 | 44 | 40 | 39 | 35 | 32 | 30 | 26 | 21 | 16 | 15 | 12 | 10 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
125 | 12 | 2017-09-01 | 35 | 32 | 29 | 25 | 22 | 20 | 19 | 16 | 13 | 9 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
126 | 13 | 2017-09-08 | 40 | 37 | 32 | 28 | 26 | 25 | 22 | 20 | 18 | 13 | 12 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
127 | 28 | 2017-12-22 | 79 | 78 | 76 | 75 | 73 | 71 | 67 | 62 | 61 | 58 | 54 | 53 | 48 | 44 | 43 | 39 | 35 | 32 | 30 | 29 | 28 | 26 | 21 | 17 | 13 | 10 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
128 | 10 | 2017-08-18 | 28 | 27 | 22 | 17 | 13 | 11 | 7 | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
129 | 17 | 2017-10-06 | 57 | 55 | 54 | 50 | 45 | 42 | 38 | 34 | 29 | 24 | 20 | 19 | 16 | 13 | 10 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
130 | 26 | 2017-12-08 | 72 | 70 | 67 | 65 | 64 | 60 | 58 | 53 | 51 | 50 | 45 | 40 | 35 | 32 | 28 | 27 | 24 | 21 | 19 | 17 | 16 | 14 | 12 | 11 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
131 | 27 | 2017-12-15 | 83 | 80 | 75 | 70 | 67 | 66 | 61 | 60 | 58 | 53 | 52 | 48 | 46 | 43 | 38 | 37 | 36 | 35 | 31 | 26 | 23 | 18 | 15 | 11 | 10 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
132 | 18 | 2017-10-13 | 59 | 56 | 51 | 50 | 45 | 41 | 38 | 34 | 29 | 26 | 23 | 20 | 18 | 17 | 16 | 11 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
133 | 16 | 2017-09-29 | 49 | 44 | 40 | 36 | 33 | 29 | 27 | 23 | 21 | 20 | 16 | 15 | 11 | 6 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
134 | 10 | 2017-08-18 | 35 | 31 | 27 | 22 | 17 | 14 | 13 | 8 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
135 | 13 | 2017-09-08 | 37 | 34 | 29 | 27 | 26 | 23 | 21 | 16 | 15 | 13 | 11 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
136 | 17 | 2017-10-06 | 44 | 41 | 40 | 38 | 34 | 33 | 29 | 27 | 25 | 22 | 18 | 16 | 15 | 13 | 9 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
137 | 24 | 2017-11-24 | 76 | 71 | 67 | 65 | 60 | 56 | 54 | 53 | 51 | 49 | 47 | 43 | 38 | 33 | 29 | 28 | 23 | 20 | 17 | 13 | 12 | 9 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
138 | 11 | 2017-08-25 | 31 | 27 | 25 | 22 | 19 | 18 | 17 | 16 | 13 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
139 | 8 | 2017-08-04 | 25 | 22 | 17 | 16 | 11 | 9 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
140 | 22 | 2017-11-10 | 66 | 63 | 61 | 60 | 56 | 55 | 50 | 48 | 46 | 41 | 38 | 33 | 29 | 25 | 22 | 21 | 17 | 16 | 15 | 10 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
141 | 12 | 2017-09-01 | 34 | 33 | 29 | 27 | 23 | 21 | 20 | 17 | 14 | 9 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
142 | 13 | 2017-09-08 | 33 | 31 | 30 | 29 | 27 | 23 | 19 | 18 | 15 | 13 | 9 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
143 | 20 | 2017-10-27 | 55 | 52 | 50 | 47 | 43 | 41 | 39 | 36 | 31 | 30 | 29 | 26 | 22 | 20 | 17 | 15 | 11 | 7 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
144 | 17 | 2017-10-06 | 48 | 43 | 41 | 40 | 39 | 35 | 34 | 30 | 28 | 24 | 20 | 19 | 17 | 13 | 10 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
145 | 14 | 2017-09-15 | 40 | 35 | 31 | 27 | 22 | 20 | 18 | 13 | 12 | 10 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
146 | 9 | 2017-08-11 | 28 | 26 | 22 | 21 | 18 | 14 | 9 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
147 | 13 | 2017-09-08 | 40 | 35 | 32 | 27 | 26 | 25 | 23 | 19 | 14 | 12 | 11 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
148 | 11 | 2017-08-25 | 32 | 27 | 26 | 24 | 22 | 21 | 19 | 14 | 10 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
149 | 11 | 2017-08-25 | 30 | 26 | 22 | 20 | 18 | 15 | 14 | 9 | 7 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
150 | 9 | 2017-08-11 | 32 | 29 | 26 | 22 | 18 | 15 | 11 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
151 | 14 | 2017-09-15 | 47 | 42 | 37 | 34 | 30 | 26 | 23 | 21 | 20 | 16 | 12 | 9 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
152 | 15 | 2017-09-22 | 41 | 38 | 37 | 33 | 31 | 26 | 24 | 23 | 22 | 18 | 15 | 13 | 9 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
153 | 28 | 2017-12-22 | 67 | 64 | 60 | 59 | 57 | 55 | 50 | 49 | 46 | 43 | 41 | 40 | 37 | 36 | 35 | 33 | 32 | 28 | 27 | 23 | 21 | 17 | 16 | 11 | 10 | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
154 | 28 | 2017-12-22 | 78 | 74 | 70 | 67 | 66 | 63 | 62 | 59 | 54 | 51 | 50 | 48 | 45 | 42 | 41 | 37 | 32 | 28 | 24 | 23 | 21 | 20 | 18 | 13 | 11 | 9 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
155 | 7 | 2017-07-28 | 23 | 18 | 14 | 11 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
156 | 25 | 2017-12-01 | 75 | 73 | 69 | 64 | 59 | 58 | 54 | 49 | 47 | 44 | 42 | 41 | 36 | 33 | 30 | 27 | 25 | 22 | 20 | 17 | 14 | 12 | 7 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
157 | 15 | 2017-09-22 | 49 | 45 | 40 | 38 | 34 | 33 | 28 | 27 | 22 | 21 | 18 | 13 | 11 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
158 | 21 | 2017-11-03 | 66 | 61 | 57 | 55 | 52 | 50 | 47 | 42 | 41 | 40 | 38 | 35 | 31 | 28 | 24 | 20 | 18 | 15 | 10 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
159 | 12 | 2017-09-01 | 46 | 42 | 39 | 35 | 30 | 25 | 23 | 18 | 13 | 8 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
160 | 21 | 2017-11-03 | 66 | 63 | 62 | 59 | 55 | 50 | 46 | 45 | 40 | 35 | 33 | 32 | 31 | 28 | 23 | 20 | 17 | 12 | 8 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
161 | 12 | 2017-09-01 | 37 | 32 | 28 | 26 | 25 | 24 | 21 | 19 | 14 | 9 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
162 | 16 | 2017-09-29 | 52 | 50 | 45 | 42 | 37 | 32 | 28 | 25 | 23 | 21 | 19 | 15 | 14 | 11 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
163 | 15 | 2017-09-22 | 43 | 39 | 35 | 32 | 31 | 30 | 26 | 24 | 23 | 18 | 17 | 12 | 8 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
164 | 12 | 2017-09-01 | 35 | 32 | 30 | 29 | 27 | 23 | 20 | 15 | 11 | 10 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
165 | 29 | 2017-12-29 | 64 | 60 | 58 | 56 | 54 | 53 | 52 | 49 | 48 | 44 | 42 | 41 | 38 | 36 | 34 | 33 | 29 | 26 | 23 | 21 | 20 | 19 | 16 | 13 | 10 | 9 | 6 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
166 | 16 | 2017-09-29 | 47 | 44 | 42 | 37 | 35 | 31 | 29 | 24 | 21 | 16 | 14 | 13 | 11 | 10 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
167 | 14 | 2017-09-15 | 52 | 47 | 43 | 38 | 36 | 33 | 29 | 27 | 22 | 17 | 14 | 10 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
168 | 13 | 2017-09-08 | 35 | 32 | 29 | 27 | 23 | 20 | 19 | 15 | 12 | 9 | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
169 | 11 | 2017-08-25 | 40 | 36 | 32 | 27 | 22 | 18 | 16 | 11 | 9 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
170 | 27 | 2017-12-15 | 76 | 72 | 68 | 67 | 65 | 62 | 58 | 56 | 55 | 54 | 51 | 49 | 48 | 43 | 40 | 36 | 31 | 30 | 27 | 25 | 22 | 18 | 16 | 12 | 8 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
171 | 23 | 2017-11-17 | 65 | 63 | 61 | 59 | 58 | 55 | 54 | 53 | 50 | 47 | 46 | 42 | 37 | 33 | 29 | 24 | 20 | 18 | 17 | 12 | 11 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
172 | 18 | 2017-10-13 | 65 | 62 | 57 | 54 | 52 | 48 | 43 | 40 | 35 | 33 | 31 | 26 | 24 | 20 | 18 | 13 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
173 | 10 | 2017-08-18 | 25 | 20 | 19 | 17 | 14 | 12 | 10 | 9 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
174 | 10 | 2017-08-18 | 34 | 30 | 25 | 24 | 22 | 20 | 17 | 12 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
175 | 16 | 2017-09-29 | 46 | 44 | 40 | 39 | 37 | 35 | 31 | 30 | 26 | 24 | 20 | 18 | 15 | 11 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
176 | 10 | 2017-08-18 | 36 | 34 | 31 | 27 | 22 | 17 | 14 | 10 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
177 | 16 | 2017-09-29 | 53 | 49 | 44 | 42 | 40 | 38 | 33 | 32 | 29 | 24 | 19 | 17 | 14 | 9 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
178 | 22 | 2017-11-10 | 57 | 53 | 49 | 48 | 46 | 45 | 42 | 40 | 37 | 36 | 31 | 30 | 27 | 24 | 21 | 19 | 15 | 14 | 11 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
179 | 12 | 2017-09-01 | 39 | 35 | 32 | 30 | 26 | 21 | 20 | 17 | 14 | 10 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
180 | 19 | 2017-10-20 | 56 | 55 | 54 | 50 | 47 | 44 | 39 | 35 | 33 | 31 | 27 | 23 | 22 | 17 | 14 | 9 | 7 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
181 | 14 | 2017-09-15 | 45 | 44 | 41 | 40 | 35 | 32 | 27 | 24 | 23 | 19 | 15 | 10 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
182 | 32 | 2018-01-19 | 87 | 84 | 83 | 80 | 75 | 70 | 68 | 66 | 62 | 59 | 56 | 54 | 51 | 50 | 48 | 44 | 43 | 39 | 38 | 36 | 33 | 28 | 27 | 22 | 20 | 19 | 14 | 13 | 10 | 7 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
183 | 12 | 2017-09-01 | 38 | 34 | 30 | 29 | 24 | 19 | 17 | 16 | 14 | 10 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
184 | 21 | 2017-11-03 | 59 | 58 | 53 | 49 | 48 | 47 | 46 | 42 | 41 | 38 | 37 | 34 | 30 | 27 | 24 | 23 | 18 | 13 | 8 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
185 | 29 | 2017-12-29 | 80 | 79 | 74 | 73 | 69 | 65 | 63 | 58 | 57 | 53 | 49 | 48 | 46 | 41 | 38 | 36 | 31 | 26 | 25 | 24 | 19 | 17 | 13 | 9 | 8 | 7 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
186 | 12 | 2017-09-01 | 28 | 24 | 21 | 18 | 15 | 14 | 10 | 7 | 6 | 5 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
187 | 16 | 2017-09-29 | 48 | 46 | 42 | 41 | 39 | 37 | 34 | 31 | 28 | 23 | 21 | 16 | 11 | 10 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
188 | 18 | 2017-10-13 | 58 | 54 | 52 | 48 | 43 | 42 | 37 | 36 | 33 | 29 | 26 | 22 | 19 | 18 | 15 | 14 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
189 | 16 | 2017-09-29 | 54 | 49 | 45 | 44 | 42 | 41 | 38 | 34 | 33 | 28 | 23 | 19 | 14 | 11 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
190 | 16 | 2017-09-29 | 43 | 38 | 37 | 33 | 28 | 27 | 26 | 24 | 22 | 20 | 18 | 14 | 9 | 7 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
191 | 20 | 2017-10-27 | 50 | 47 | 44 | 42 | 40 | 38 | 35 | 33 | 29 | 25 | 22 | 18 | 15 | 13 | 12 | 10 | 8 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
192 | 15 | 2017-09-22 | 43 | 39 | 36 | 34 | 29 | 26 | 24 | 20 | 17 | 16 | 13 | 12 | 8 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
193 | 28 | 2017-12-22 | 83 | 79 | 77 | 73 | 72 | 69 | 67 | 65 | 62 | 58 | 53 | 48 | 45 | 40 | 35 | 34 | 31 | 30 | 29 | 27 | 22 | 20 | 15 | 14 | 10 | 5 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
194 | 17 | 2017-10-06 | 51 | 48 | 44 | 43 | 39 | 36 | 33 | 32 | 29 | 28 | 23 | 22 | 17 | 15 | 11 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
195 | 8 | 2017-08-04 | 24 | 23 | 20 | 19 | 16 | 11 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
196 | 10 | 2017-08-18 | 34 | 30 | 26 | 22 | 19 | 15 | 13 | 11 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
197 | 24 | 2017-11-24 | 75 | 72 | 67 | 62 | 58 | 54 | 51 | 47 | 43 | 40 | 38 | 36 | 32 | 30 | 27 | 24 | 22 | 18 | 15 | 14 | 11 | 6 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
198 | 17 | 2017-10-06 | 53 | 52 | 47 | 42 | 38 | 35 | 31 | 27 | 24 | 21 | 16 | 13 | 12 | 11 | 8 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
199 | 9 | 2017-08-11 | 27 | 25 | 22 | 17 | 15 | 12 | 8 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
200 | 16 | 2017-09-29 | 48 | 43 | 40 | 37 | 36 | 33 | 28 | 25 | 22 | 19 | 16 | 12 | 9 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
201 | 10 | 2017-08-18 | 29 | 25 | 24 | 20 | 17 | 16 | 12 | 8 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
202 | 15 | 2017-09-22 | 45 | 42 | 38 | 33 | 31 | 30 | 28 | 27 | 24 | 21 | 16 | 12 | 7 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
203 | 12 | 2017-09-01 | 42 | 38 | 35 | 31 | 28 | 26 | 23 | 19 | 16 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
204 | 14 | 2017-09-15 | 44 | 43 | 41 | 40 | 38 | 35 | 31 | 29 | 24 | 20 | 16 | 11 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
205 | 30 | 2018-01-05 | 82 | 81 | 78 | 76 | 74 | 73 | 71 | 70 | 68 | 63 | 60 | 55 | 52 | 50 | 48 | 43 | 40 | 35 | 32 | 31 | 29 | 26 | 22 | 18 | 17 | 14 | 11 | 7 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
206 | 23 | 2017-11-17 | 64 | 60 | 58 | 53 | 48 | 45 | 40 | 39 | 35 | 30 | 29 | 26 | 25 | 23 | 21 | 16 | 14 | 11 | 9 | 7 | 6 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
207 | 10 | 2017-08-18 | 37 | 33 | 28 | 26 | 22 | 19 | 15 | 11 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
208 | 12 | 2017-09-01 | 33 | 31 | 27 | 24 | 23 | 19 | 15 | 12 | 11 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
209 | 14 | 2017-09-15 | 43 | 42 | 40 | 35 | 33 | 30 | 27 | 22 | 17 | 12 | 9 | 6 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
210 | 8 | 2017-08-04 | 29 | 28 | 24 | 19 | 18 | 13 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
211 | 23 | 2017-11-17 | 59 | 57 | 54 | 53 | 51 | 46 | 42 | 41 | 38 | 36 | 34 | 29 | 28 | 24 | 22 | 19 | 18 | 17 | 12 | 10 | 9 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
212 | 27 | 2017-12-15 | 79 | 75 | 70 | 69 | 66 | 62 | 57 | 54 | 53 | 52 | 50 | 46 | 44 | 40 | 38 | 37 | 32 | 27 | 25 | 23 | 19 | 14 | 12 | 10 | 9 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
213 | 16 | 2017-09-29 | 54 | 49 | 47 | 45 | 44 | 39 | 35 | 33 | 30 | 28 | 24 | 19 | 17 | 12 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
214 | 18 | 2017-10-13 | 50 | 48 | 46 | 43 | 42 | 39 | 34 | 31 | 30 | 27 | 23 | 18 | 14 | 13 | 11 | 8 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
215 | 28 | 2017-12-22 | 74 | 72 | 70 | 67 | 63 | 60 | 58 | 55 | 54 | 52 | 47 | 43 | 39 | 37 | 36 | 35 | 31 | 27 | 25 | 22 | 19 | 18 | 16 | 15 | 13 | 11 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
216 | 13 | 2017-09-08 | 37 | 34 | 31 | 26 | 21 | 16 | 13 | 12 | 11 | 10 | 7 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
217 | 21 | 2017-11-03 | 65 | 62 | 57 | 54 | 53 | 48 | 44 | 41 | 39 | 37 | 36 | 31 | 29 | 24 | 22 | 18 | 13 | 10 | 7 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
218 | 25 | 2017-12-01 | 64 | 59 | 57 | 54 | 53 | 48 | 45 | 44 | 42 | 41 | 36 | 33 | 32 | 31 | 26 | 25 | 24 | 20 | 16 | 14 | 11 | 9 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
219 | 28 | 2017-12-22 | 72 | 71 | 68 | 66 | 65 | 64 | 60 | 58 | 56 | 52 | 47 | 42 | 41 | 36 | 35 | 33 | 28 | 27 | 23 | 20 | 19 | 15 | 14 | 11 | 8 | 7 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
220 | 22 | 2017-11-10 | 65 | 62 | 61 | 60 | 57 | 53 | 51 | 50 | 49 | 46 | 42 | 39 | 35 | 30 | 26 | 24 | 21 | 17 | 12 | 9 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
221 | 14 | 2017-09-15 | 44 | 43 | 39 | 36 | 32 | 28 | 25 | 21 | 18 | 13 | 11 | 10 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
222 | 9 | 2017-08-11 | 31 | 28 | 24 | 22 | 18 | 15 | 14 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
223 | 11 | 2017-08-25 | 29 | 25 | 23 | 21 | 20 | 16 | 12 | 10 | 9 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
224 | 25 | 2017-12-01 | 73 | 69 | 65 | 61 | 60 | 56 | 54 | 50 | 49 | 48 | 46 | 42 | 40 | 38 | 33 | 30 | 25 | 23 | 22 | 18 | 15 | 13 | 9 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
225 | 14 | 2017-09-15 | 43 | 38 | 35 | 33 | 30 | 27 | 26 | 23 | 18 | 17 | 15 | 11 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
226 | 22 | 2017-11-10 | 59 | 54 | 53 | 52 | 50 | 46 | 41 | 37 | 36 | 32 | 31 | 29 | 25 | 23 | 20 | 18 | 16 | 11 | 10 | 8 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
227 | 25 | 2017-12-01 | 82 | 78 | 73 | 68 | 65 | 63 | 59 | 58 | 57 | 52 | 48 | 45 | 41 | 36 | 34 | 30 | 28 | 25 | 20 | 16 | 13 | 10 | 8 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
228 | 19 | 2017-10-20 | 55 | 53 | 52 | 48 | 44 | 39 | 36 | 34 | 31 | 28 | 24 | 21 | 20 | 17 | 13 | 11 | 10 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
229 | 20 | 2017-10-27 | 59 | 56 | 55 | 54 | 51 | 46 | 44 | 43 | 42 | 41 | 36 | 34 | 29 | 25 | 22 | 18 | 13 | 12 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
230 | 24 | 2017-11-24 | 64 | 60 | 57 | 54 | 52 | 48 | 47 | 43 | 41 | 37 | 36 | 31 | 26 | 25 | 24 | 21 | 18 | 17 | 13 | 11 | 6 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
231 | 16 | 2017-09-29 | 51 | 49 | 44 | 43 | 41 | 36 | 33 | 32 | 27 | 22 | 18 | 17 | 12 | 8 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
232 | 16 | 2017-09-29 | 55 | 53 | 48 | 44 | 39 | 35 | 31 | 30 | 29 | 24 | 23 | 21 | 17 | 12 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
233 | 18 | 2017-10-13 | 58 | 54 | 53 | 49 | 45 | 40 | 35 | 34 | 32 | 27 | 25 | 22 | 18 | 16 | 12 | 11 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
234 | 21 | 2017-11-03 | 63 | 61 | 59 | 56 | 53 | 50 | 48 | 44 | 40 | 38 | 36 | 33 | 32 | 30 | 25 | 20 | 18 | 13 | 11 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
235 | 19 | 2017-10-20 | 59 | 56 | 52 | 49 | 48 | 45 | 44 | 43 | 39 | 34 | 30 | 25 | 21 | 17 | 15 | 11 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
236 | 13 | 2017-09-08 | 42 | 38 | 33 | 29 | 27 | 24 | 19 | 17 | 12 | 7 | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
237 | 19 | 2017-10-20 | 62 | 58 | 57 | 54 | 52 | 51 | 46 | 41 | 36 | 33 | 29 | 26 | 21 | 16 | 11 | 10 | 9 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
238 | 17 | 2017-10-06 | 52 | 48 | 44 | 42 | 39 | 37 | 35 | 33 | 30 | 27 | 24 | 21 | 17 | 14 | 9 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
239 | 9 | 2017-08-11 | 25 | 24 | 21 | 20 | 16 | 13 | 9 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
240 | 12 | 2017-09-01 | 36 | 31 | 26 | 23 | 22 | 19 | 14 | 10 | 8 | 7 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
241 | 19 | 2017-10-20 | 63 | 61 | 56 | 51 | 47 | 44 | 42 | 39 | 34 | 29 | 25 | 21 | 20 | 17 | 15 | 14 | 9 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
242 | 20 | 2017-10-27 | 57 | 56 | 54 | 50 | 46 | 41 | 37 | 36 | 35 | 31 | 28 | 25 | 20 | 18 | 16 | 12 | 9 | 8 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
243 | 21 | 2017-11-03 | 65 | 62 | 57 | 54 | 53 | 50 | 48 | 44 | 41 | 37 | 36 | 32 | 27 | 26 | 24 | 19 | 17 | 15 | 10 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
244 | 13 | 2017-09-08 | 44 | 41 | 36 | 35 | 31 | 30 | 26 | 21 | 17 | 15 | 12 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
245 | 23 | 2017-11-17 | 72 | 69 | 65 | 60 | 59 | 54 | 51 | 49 | 44 | 41 | 36 | 35 | 30 | 27 | 26 | 25 | 21 | 19 | 15 | 11 | 9 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
246 | 25 | 2017-12-01 | 69 | 67 | 62 | 60 | 58 | 53 | 51 | 50 | 49 | 47 | 45 | 42 | 39 | 37 | 33 | 29 | 27 | 24 | 20 | 15 | 12 | 10 | 6 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
247 | 14 | 2017-09-15 | 44 | 41 | 38 | 35 | 33 | 32 | 28 | 24 | 22 | 20 | 15 | 10 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
248 | 12 | 2017-09-01 | 44 | 41 | 36 | 34 | 29 | 27 | 22 | 18 | 13 | 10 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
249 | 22 | 2017-11-10 | 66 | 64 | 61 | 57 | 53 | 48 | 45 | 41 | 40 | 39 | 37 | 34 | 29 | 24 | 19 | 14 | 13 | 9 | 8 | 7 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
250 | 18 | 2017-10-13 | 50 | 49 | 45 | 44 | 42 | 37 | 34 | 33 | 28 | 24 | 22 | 21 | 16 | 12 | 10 | 7 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
251 | 12 | 2017-09-01 | 31 | 28 | 23 | 22 | 21 | 19 | 16 | 12 | 10 | 7 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
252 | 18 | 2017-10-13 | 52 | 47 | 45 | 40 | 37 | 35 | 34 | 30 | 25 | 21 | 16 | 15 | 13 | 9 | 8 | 7 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
253 | 15 | 2017-09-22 | 46 | 44 | 42 | 39 | 36 | 32 | 28 | 24 | 21 | 18 | 14 | 9 | 6 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
254 | 18 | 2017-10-13 | 45 | 43 | 39 | 37 | 33 | 31 | 30 | 26 | 25 | 21 | 19 | 16 | 15 | 14 | 11 | 9 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
255 | 20 | 2017-10-27 | 62 | 59 | 54 | 52 | 51 | 50 | 48 | 44 | 41 | 37 | 32 | 27 | 23 | 21 | 19 | 17 | 13 | 10 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
256 | 23 | 2017-11-17 | 63 | 59 | 57 | 55 | 50 | 46 | 42 | 40 | 36 | 34 | 29 | 28 | 24 | 23 | 21 | 18 | 16 | 12 | 9 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
257 | 12 | 2017-09-01 | 36 | 33 | 29 | 25 | 24 | 21 | 17 | 14 | 10 | 8 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
258 | 27 | 2017-12-15 | 73 | 71 | 68 | 64 | 62 | 58 | 55 | 54 | 50 | 46 | 42 | 38 | 34 | 32 | 30 | 26 | 25 | 23 | 21 | 16 | 15 | 12 | 9 | 5 | 4 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
259 | 23 | 2017-11-17 | 65 | 64 | 59 | 55 | 52 | 50 | 48 | 45 | 40 | 38 | 35 | 33 | 30 | 25 | 23 | 19 | 15 | 14 | 13 | 8 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
260 | 13 | 2017-09-08 | 42 | 40 | 37 | 35 | 32 | 27 | 22 | 18 | 14 | 9 | 8 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
261 | 15 | 2017-09-22 | 38 | 36 | 34 | 29 | 28 | 25 | 24 | 20 | 19 | 16 | 11 | 10 | 6 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
262 | 23 | 2017-11-17 | 70 | 69 | 68 | 63 | 60 | 58 | 57 | 53 | 49 | 46 | 42 | 37 | 34 | 33 | 32 | 27 | 22 | 19 | 15 | 13 | 12 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
263 | 10 | 2017-08-18 | 33 | 28 | 23 | 22 | 19 | 17 | 12 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
264 | 17 | 2017-10-06 | 50 | 49 | 46 | 44 | 39 | 35 | 31 | 26 | 23 | 21 | 18 | 13 | 10 | 9 | 6 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
265 | 24 | 2017-11-24 | 66 | 65 | 60 | 56 | 54 | 49 | 45 | 41 | 39 | 35 | 33 | 31 | 29 | 26 | 25 | 24 | 21 | 19 | 17 | 12 | 11 | 10 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
266 | 11 | 2017-08-25 | 30 | 28 | 26 | 23 | 19 | 16 | 13 | 11 | 6 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
267 | 16 | 2017-09-29 | 54 | 52 | 49 | 48 | 47 | 42 | 39 | 34 | 30 | 25 | 24 | 19 | 15 | 10 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
268 | 27 | 2017-12-15 | 77 | 73 | 72 | 68 | 67 | 66 | 64 | 63 | 59 | 54 | 53 | 48 | 47 | 44 | 40 | 35 | 33 | 30 | 25 | 20 | 19 | 15 | 10 | 9 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
269 | 18 | 2017-10-13 | 48 | 43 | 41 | 38 | 34 | 32 | 27 | 22 | 21 | 19 | 18 | 14 | 11 | 10 | 9 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
270 | 19 | 2017-10-20 | 58 | 56 | 55 | 51 | 47 | 45 | 41 | 36 | 33 | 30 | 29 | 25 | 20 | 17 | 16 | 14 | 12 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
271 | 18 | 2017-10-13 | 46 | 43 | 42 | 40 | 38 | 34 | 32 | 31 | 27 | 22 | 18 | 16 | 14 | 11 | 7 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
272 | 10 | 2017-08-18 | 29 | 28 | 23 | 19 | 18 | 17 | 15 | 11 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
273 | 16 | 2017-09-29 | 41 | 40 | 36 | 34 | 33 | 30 | 29 | 24 | 23 | 19 | 16 | 13 | 12 | 9 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
274 | 18 | 2017-10-13 | 52 | 48 | 45 | 40 | 36 | 32 | 31 | 29 | 28 | 23 | 20 | 19 | 14 | 13 | 11 | 8 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
275 | 20 | 2017-10-27 | 56 | 55 | 52 | 51 | 50 | 49 | 44 | 39 | 34 | 30 | 28 | 25 | 24 | 19 | 14 | 13 | 9 | 8 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
276 | 6 | 2017-07-21 | 24 | 19 | 16 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
277 | 12 | 2017-09-01 | 33 | 32 | 30 | 27 | 25 | 20 | 18 | 14 | 12 | 9 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
278 | 12 | 2017-09-01 | 30 | 29 | 27 | 24 | 23 | 22 | 19 | 14 | 10 | 8 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
279 | 20 | 2017-10-27 | 67 | 63 | 59 | 54 | 49 | 44 | 40 | 38 | 34 | 32 | 31 | 30 | 25 | 23 | 19 | 14 | 10 | 9 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
280 | 16 | 2017-09-29 | 41 | 40 | 37 | 36 | 32 | 31 | 28 | 24 | 19 | 15 | 13 | 11 | 9 | 5 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
281 | 14 | 2017-09-15 | 40 | 36 | 31 | 28 | 26 | 24 | 20 | 15 | 14 | 13 | 12 | 10 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
282 | 16 | 2017-09-29 | 43 | 42 | 40 | 35 | 33 | 28 | 25 | 22 | 20 | 17 | 13 | 12 | 9 | 5 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
283 | 11 | 2017-08-25 | 42 | 38 | 34 | 30 | 29 | 26 | 21 | 18 | 13 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
284 | 21 | 2017-11-03 | 52 | 48 | 45 | 43 | 41 | 39 | 38 | 37 | 34 | 32 | 30 | 26 | 25 | 23 | 18 | 15 | 14 | 12 | 11 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
285 | 16 | 2017-09-29 | 47 | 44 | 40 | 35 | 32 | 29 | 27 | 26 | 24 | 23 | 19 | 16 | 11 | 9 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
286 | 12 | 2017-09-01 | 40 | 38 | 33 | 28 | 26 | 23 | 18 | 13 | 11 | 9 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
287 | 20 | 2017-10-27 | 54 | 53 | 48 | 45 | 41 | 40 | 36 | 32 | 28 | 27 | 26 | 21 | 17 | 13 | 11 | 10 | 7 | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
288 | 16 | 2017-09-29 | 49 | 48 | 44 | 39 | 34 | 30 | 29 | 26 | 23 | 20 | 17 | 13 | 10 | 7 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
289 | 15 | 2017-09-22 | 51 | 49 | 46 | 42 | 39 | 34 | 31 | 29 | 26 | 22 | 20 | 15 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
290 | 20 | 2017-10-27 | 55 | 52 | 47 | 45 | 40 | 37 | 36 | 35 | 34 | 32 | 27 | 25 | 20 | 19 | 16 | 14 | 10 | 7 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
291 | 8 | 2017-08-04 | 26 | 22 | 18 | 16 | 12 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
292 | 27 | 2017-12-15 | 71 | 67 | 66 | 62 | 61 | 58 | 55 | 54 | 52 | 51 | 48 | 44 | 40 | 37 | 36 | 35 | 34 | 32 | 31 | 26 | 21 | 17 | 15 | 11 | 8 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
293 | 10 | 2017-08-18 | 30 | 29 | 26 | 22 | 19 | 15 | 12 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
294 | 21 | 2017-11-03 | 56 | 52 | 51 | 50 | 45 | 42 | 39 | 38 | 37 | 36 | 31 | 28 | 27 | 26 | 21 | 19 | 17 | 15 | 12 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
295 | 12 | 2017-09-01 | 32 | 31 | 29 | 26 | 23 | 18 | 15 | 10 | 9 | 8 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
296 | 13 | 2017-09-08 | 31 | 29 | 27 | 26 | 25 | 24 | 23 | 18 | 15 | 11 | 8 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
297 | 12 | 2017-09-01 | 28 | 24 | 20 | 16 | 15 | 11 | 10 | 9 | 8 | 6 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
298 | 15 | 2017-09-22 | 44 | 43 | 41 | 38 | 34 | 32 | 29 | 25 | 20 | 15 | 11 | 8 | 7 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
299 | 12 | 2017-09-01 | 33 | 32 | 29 | 25 | 22 | 20 | 17 | 13 | 8 | 5 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
300 | 20 | 2017-10-27 | 59 | 56 | 54 | 50 | 49 | 45 | 41 | 40 | 35 | 31 | 29 | 26 | 25 | 20 | 19 | 15 | 11 | 10 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
301 | 19 | 2017-10-20 | 54 | 51 | 46 | 43 | 41 | 40 | 38 | 36 | 31 | 29 | 24 | 21 | 19 | 14 | 9 | 8 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
302 | 21 | 2017-11-03 | 68 | 64 | 61 | 59 | 54 | 52 | 51 | 49 | 45 | 44 | 42 | 38 | 36 | 31 | 26 | 22 | 20 | 16 | 12 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
303 | 18 | 2017-10-13 | 59 | 54 | 52 | 47 | 45 | 43 | 40 | 36 | 31 | 27 | 23 | 22 | 19 | 16 | 12 | 10 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
304 | 21 | 2017-11-03 | 65 | 63 | 59 | 58 | 54 | 52 | 50 | 45 | 43 | 38 | 35 | 34 | 31 | 30 | 26 | 22 | 18 | 16 | 11 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
305 | 12 | 2017-09-01 | 30 | 25 | 24 | 21 | 19 | 17 | 14 | 12 | 9 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
306 | 18 | 2017-10-13 | 55 | 50 | 47 | 44 | 43 | 38 | 34 | 29 | 26 | 24 | 19 | 15 | 14 | 13 | 11 | 9 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
307 | 12 | 2017-09-01 | 37 | 33 | 31 | 30 | 26 | 22 | 21 | 17 | 12 | 7 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
308 | 20 | 2017-10-27 | 48 | 46 | 44 | 42 | 37 | 34 | 31 | 30 | 27 | 26 | 21 | 20 | 15 | 14 | 10 | 9 | 7 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
309 | 15 | 2017-09-22 | 32 | 27 | 24 | 21 | 16 | 15 | 13 | 10 | 9 | 7 | 5 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
310 | 15 | 2017-09-22 | 41 | 40 | 37 | 36 | 33 | 31 | 29 | 25 | 23 | 18 | 14 | 12 | 9 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
311 | 9 | 2017-08-11 | 31 | 26 | 25 | 22 | 18 | 13 | 10 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
312 | 16 | 2017-09-29 | 50 | 48 | 44 | 41 | 36 | 32 | 29 | 27 | 23 | 19 | 16 | 11 | 10 | 7 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
313 | 20 | 2017-10-27 | 55 | 52 | 47 | 45 | 42 | 37 | 36 | 34 | 31 | 27 | 26 | 21 | 20 | 17 | 15 | 12 | 8 | 6 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
314 | 14 | 2017-09-15 | 42 | 39 | 36 | 32 | 27 | 26 | 25 | 23 | 19 | 17 | 13 | 11 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
315 | 8 | 2017-08-04 | 27 | 24 | 20 | 15 | 12 | 8 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
316 | 16 | 2017-09-29 | 40 | 37 | 36 | 35 | 34 | 29 | 24 | 21 | 18 | 16 | 13 | 11 | 9 | 8 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
317 | 20 | 2017-10-27 | 63 | 59 | 55 | 51 | 48 | 43 | 42 | 40 | 39 | 35 | 33 | 29 | 25 | 23 | 22 | 17 | 12 | 7 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
318 | 10 | 2017-08-18 | 29 | 26 | 21 | 20 | 18 | 14 | 13 | 8 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
319 | 21 | 2017-11-03 | 58 | 55 | 50 | 49 | 48 | 45 | 42 | 37 | 33 | 30 | 25 | 23 | 19 | 16 | 12 | 11 | 8 | 6 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
320 | 29 | 2017-12-29 | 84 | 81 | 79 | 74 | 72 | 70 | 69 | 66 | 62 | 60 | 57 | 53 | 51 | 47 | 42 | 39 | 34 | 33 | 29 | 25 | 23 | 21 | 20 | 19 | 15 | 10 | 8 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
321 | 23 | 2017-11-17 | 68 | 64 | 59 | 55 | 52 | 48 | 45 | 40 | 36 | 32 | 31 | 26 | 24 | 21 | 20 | 18 | 17 | 15 | 13 | 10 | 8 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
322 | 19 | 2017-10-20 | 50 | 49 | 48 | 45 | 44 | 41 | 37 | 34 | 32 | 30 | 26 | 24 | 21 | 17 | 15 | 13 | 8 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
323 | 8 | 2017-08-04 | 25 | 22 | 21 | 17 | 14 | 11 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
324 | 16 | 2017-09-29 | 39 | 38 | 37 | 32 | 31 | 26 | 25 | 22 | 20 | 17 | 15 | 11 | 7 | 6 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
325 | 21 | 2017-11-03 | 53 | 51 | 50 | 49 | 45 | 43 | 39 | 36 | 33 | 32 | 31 | 28 | 27 | 24 | 23 | 20 | 16 | 13 | 10 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
326 | 20 | 2017-10-27 | 60 | 56 | 52 | 51 | 47 | 42 | 40 | 38 | 35 | 32 | 28 | 24 | 21 | 17 | 12 | 10 | 6 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
327 | 20 | 2017-10-27 | 51 | 48 | 46 | 43 | 41 | 36 | 32 | 30 | 29 | 27 | 26 | 22 | 17 | 16 | 15 | 11 | 10 | 9 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
328 | 14 | 2017-09-15 | 33 | 30 | 29 | 25 | 24 | 21 | 20 | 17 | 16 | 12 | 11 | 7 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
329 | 22 | 2017-11-10 | 65 | 62 | 60 | 58 | 56 | 51 | 48 | 43 | 38 | 35 | 32 | 31 | 28 | 27 | 24 | 23 | 19 | 15 | 11 | 8 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
330 | 22 | 2017-11-10 | 65 | 61 | 58 | 53 | 50 | 45 | 43 | 38 | 37 | 33 | 32 | 29 | 28 | 24 | 19 | 16 | 12 | 10 | 6 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
331 | 18 | 2017-10-13 | 50 | 49 | 44 | 39 | 38 | 35 | 32 | 30 | 26 | 21 | 18 | 17 | 16 | 14 | 9 | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
332 | 18 | 2017-10-13 | 57 | 53 | 50 | 45 | 42 | 39 | 37 | 33 | 31 | 29 | 24 | 23 | 18 | 13 | 10 | 9 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
333 | 19 | 2017-10-20 | 56 | 55 | 53 | 48 | 45 | 43 | 41 | 36 | 32 | 27 | 22 | 20 | 17 | 16 | 13 | 9 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
334 | 23 | 2017-11-17 | 60 | 59 | 54 | 50 | 49 | 46 | 44 | 43 | 40 | 36 | 34 | 33 | 32 | 31 | 29 | 25 | 21 | 18 | 16 | 13 | 8 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
335 | 13 | 2017-09-08 | 37 | 32 | 30 | 27 | 24 | 23 | 18 | 17 | 12 | 11 | 8 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
336 | 16 | 2017-09-29 | 47 | 43 | 40 | 35 | 30 | 28 | 25 | 24 | 22 | 20 | 16 | 15 | 10 | 9 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
337 | 20 | 2017-10-27 | 64 | 60 | 56 | 51 | 49 | 46 | 43 | 38 | 35 | 32 | 31 | 27 | 22 | 19 | 17 | 15 | 12 | 9 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
338 | 16 | 2017-09-29 | 46 | 44 | 40 | 36 | 31 | 26 | 24 | 21 | 18 | 14 | 10 | 9 | 8 | 7 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
339 | 12 | 2017-09-01 | 35 | 30 | 28 | 27 | 25 | 22 | 17 | 15 | 14 | 9 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
340 | 13 | 2017-09-08 | 49 | 46 | 42 | 40 | 39 | 35 | 30 | 25 | 20 | 16 | 12 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
341 | 20 | 2017-10-27 | 54 | 52 | 51 | 48 | 43 | 40 | 38 | 34 | 31 | 27 | 22 | 19 | 16 | 12 | 10 | 8 | 7 | 5 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
342 | 23 | 2017-11-17 | 54 | 53 | 49 | 47 | 44 | 41 | 39 | 37 | 36 | 35 | 33 | 28 | 27 | 25 | 24 | 21 | 20 | 15 | 13 | 10 | 8 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
343 | 18 | 2017-10-13 | 62 | 60 | 56 | 51 | 47 | 43 | 38 | 35 | 30 | 25 | 22 | 20 | 15 | 14 | 13 | 8 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
344 | 15 | 2017-09-22 | 47 | 44 | 42 | 39 | 37 | 33 | 29 | 26 | 24 | 19 | 16 | 13 | 12 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
345 | 10 | 2017-08-18 | 34 | 32 | 27 | 22 | 17 | 13 | 11 | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
346 | 12 | 2017-09-01 | 35 | 32 | 31 | 30 | 28 | 26 | 22 | 18 | 14 | 9 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
347 | 12 | 2017-09-01 | 41 | 38 | 35 | 34 | 31 | 27 | 26 | 21 | 16 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
348 | 17 | 2017-10-06 | 47 | 46 | 44 | 40 | 38 | 36 | 33 | 32 | 31 | 27 | 22 | 21 | 17 | 14 | 10 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
349 | 16 | 2017-09-29 | 52 | 50 | 45 | 41 | 40 | 38 | 36 | 32 | 27 | 25 | 20 | 17 | 15 | 10 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
350 | 10 | 2017-08-18 | 34 | 32 | 30 | 26 | 24 | 20 | 16 | 11 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
351 | 22 | 2017-11-10 | 68 | 67 | 63 | 61 | 60 | 57 | 52 | 47 | 43 | 41 | 36 | 31 | 26 | 21 | 20 | 18 | 15 | 11 | 8 | 4 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
352 | 16 | 2017-09-29 | 54 | 53 | 52 | 49 | 44 | 39 | 34 | 30 | 29 | 26 | 22 | 18 | 16 | 12 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
353 | 10 | 2017-08-18 | 36 | 33 | 28 | 23 | 18 | 14 | 10 | 5 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
354 | 18 | 2017-10-13 | 55 | 50 | 45 | 40 | 38 | 33 | 30 | 28 | 23 | 22 | 21 | 20 | 17 | 16 | 11 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
355 | 19 | 2017-10-20 | 47 | 45 | 43 | 42 | 40 | 38 | 33 | 29 | 24 | 21 | 19 | 17 | 15 | 13 | 11 | 7 | 6 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
356 | 26 | 2017-12-08 | 67 | 66 | 64 | 63 | 60 | 59 | 54 | 51 | 48 | 46 | 43 | 41 | 36 | 33 | 31 | 29 | 28 | 26 | 23 | 21 | 16 | 13 | 8 | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
357 | 9 | 2017-08-11 | 29 | 25 | 23 | 19 | 16 | 12 | 7 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
358 | 9 | 2017-08-11 | 31 | 28 | 27 | 22 | 20 | 17 | 15 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
359 | 18 | 2017-10-13 | 64 | 62 | 57 | 56 | 53 | 48 | 47 | 42 | 40 | 36 | 31 | 26 | 21 | 16 | 14 | 11 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
360 | 15 | 2017-09-22 | 48 | 46 | 41 | 37 | 35 | 30 | 29 | 25 | 21 | 17 | 15 | 11 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
361 | 9 | 2017-08-11 | 22 | 18 | 16 | 13 | 9 | 8 | 7 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
362 | 29 | 2017-12-29 | 86 | 83 | 81 | 80 | 75 | 73 | 69 | 68 | 65 | 63 | 58 | 57 | 52 | 50 | 45 | 42 | 41 | 39 | 36 | 31 | 27 | 22 | 21 | 18 | 14 | 10 | 5 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
363 | 25 | 2017-12-01 | 74 | 70 | 66 | 62 | 58 | 55 | 52 | 47 | 43 | 41 | 38 | 36 | 35 | 31 | 26 | 25 | 23 | 21 | 20 | 16 | 15 | 12 | 10 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
364 | 9 | 2017-08-11 | 22 | 18 | 15 | 14 | 13 | 12 | 7 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
365 | 20 | 2017-10-27 | 55 | 54 | 49 | 47 | 45 | 43 | 42 | 38 | 37 | 32 | 29 | 28 | 26 | 24 | 22 | 18 | 14 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
366 | 24 | 2017-11-24 | 72 | 71 | 69 | 65 | 60 | 58 | 53 | 52 | 49 | 48 | 43 | 40 | 35 | 30 | 29 | 27 | 22 | 20 | 19 | 17 | 15 | 11 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
367 | 19 | 2017-10-20 | 56 | 52 | 48 | 46 | 41 | 37 | 35 | 34 | 31 | 29 | 24 | 21 | 17 | 16 | 14 | 10 | 9 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
368 | 13 | 2017-09-08 | 41 | 39 | 36 | 32 | 27 | 22 | 17 | 16 | 15 | 12 | 8 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
369 | 22 | 2017-11-10 | 60 | 57 | 54 | 50 | 48 | 47 | 42 | 37 | 33 | 32 | 27 | 25 | 23 | 21 | 20 | 18 | 17 | 14 | 10 | 8 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
370 | 20 | 2017-10-27 | 63 | 61 | 58 | 53 | 52 | 50 | 45 | 40 | 39 | 36 | 35 | 32 | 27 | 24 | 22 | 18 | 15 | 10 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
371 | 14 | 2017-09-15 | 35 | 34 | 29 | 26 | 24 | 22 | 20 | 17 | 15 | 13 | 11 | 8 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
372 | 13 | 2017-09-08 | 32 | 28 | 25 | 24 | 20 | 15 | 14 | 13 | 11 | 10 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
373 | 13 | 2017-09-08 | 43 | 38 | 34 | 31 | 27 | 24 | 22 | 17 | 16 | 12 | 7 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
374 | 12 | 2017-09-01 | 37 | 32 | 30 | 26 | 21 | 18 | 15 | 13 | 12 | 11 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
375 | 15 | 2017-09-22 | 37 | 35 | 30 | 28 | 26 | 25 | 23 | 22 | 18 | 17 | 15 | 12 | 7 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
376 | 23 | 2017-11-17 | 68 | 65 | 60 | 56 | 51 | 49 | 48 | 44 | 43 | 39 | 37 | 36 | 34 | 31 | 28 | 26 | 21 | 17 | 14 | 11 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
377 | 13 | 2017-09-08 | 43 | 40 | 35 | 30 | 27 | 22 | 20 | 16 | 15 | 13 | 10 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
378 | 25 | 2017-12-01 | 68 | 67 | 63 | 60 | 56 | 51 | 50 | 46 | 44 | 41 | 40 | 38 | 36 | 31 | 30 | 25 | 22 | 21 | 20 | 15 | 11 | 7 | 6 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
379 | 22 | 2017-11-10 | 63 | 60 | 59 | 54 | 50 | 49 | 47 | 43 | 38 | 37 | 35 | 33 | 28 | 25 | 21 | 19 | 17 | 12 | 11 | 8 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
380 | 23 | 2017-11-17 | 68 | 67 | 64 | 59 | 54 | 51 | 50 | 47 | 46 | 42 | 40 | 36 | 34 | 30 | 28 | 26 | 24 | 19 | 16 | 12 | 7 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
381 | 30 | 2018-01-05 | 77 | 74 | 73 | 72 | 67 | 63 | 62 | 58 | 56 | 53 | 48 | 44 | 40 | 38 | 36 | 32 | 30 | 27 | 25 | 21 | 17 | 15 | 12 | 11 | 10 | 9 | 6 | 5 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
382 | 25 | 2017-12-01 | 79 | 77 | 72 | 70 | 66 | 64 | 60 | 57 | 54 | 52 | 49 | 46 | 41 | 39 | 36 | 34 | 30 | 25 | 21 | 16 | 14 | 10 | 9 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
383 | 27 | 2017-12-15 | 82 | 81 | 77 | 73 | 70 | 68 | 66 | 65 | 63 | 58 | 54 | 53 | 48 | 44 | 40 | 37 | 35 | 32 | 28 | 25 | 23 | 19 | 14 | 12 | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
384 | 18 | 2017-10-13 | 50 | 47 | 43 | 40 | 38 | 35 | 31 | 26 | 23 | 22 | 18 | 14 | 13 | 11 | 8 | 7 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
385 | 16 | 2017-09-29 | 45 | 42 | 41 | 39 | 37 | 32 | 28 | 24 | 23 | 20 | 19 | 14 | 10 | 8 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
386 | 19 | 2017-10-20 | 54 | 51 | 50 | 48 | 47 | 42 | 38 | 36 | 34 | 31 | 28 | 27 | 22 | 21 | 18 | 13 | 8 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
387 | 9 | 2017-08-11 | 28 | 27 | 22 | 21 | 16 | 12 | 10 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
388 | 25 | 2017-12-01 | 71 | 67 | 62 | 61 | 59 | 57 | 52 | 47 | 46 | 43 | 39 | 38 | 37 | 36 | 32 | 27 | 25 | 24 | 21 | 20 | 19 | 15 | 11 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
389 | 11 | 2017-08-25 | 38 | 37 | 32 | 28 | 24 | 20 | 16 | 11 | 7 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
390 | 21 | 2017-11-03 | 52 | 48 | 43 | 41 | 38 | 37 | 35 | 34 | 32 | 31 | 30 | 28 | 23 | 22 | 20 | 19 | 14 | 12 | 10 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
391 | 20 | 2017-10-27 | 62 | 60 | 58 | 55 | 50 | 47 | 43 | 41 | 36 | 35 | 30 | 29 | 24 | 20 | 17 | 12 | 9 | 7 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
392 | 13 | 2017-09-08 | 39 | 34 | 29 | 28 | 27 | 24 | 21 | 16 | 15 | 13 | 9 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
393 | 13 | 2017-09-08 | 35 | 33 | 29 | 28 | 27 | 25 | 21 | 18 | 13 | 11 | 10 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
394 | 9 | 2017-08-11 | 32 | 28 | 23 | 18 | 15 | 10 | 7 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
395 | 24 | 2017-11-24 | 82 | 80 | 78 | 75 | 73 | 70 | 66 | 62 | 58 | 53 | 52 | 47 | 42 | 41 | 36 | 31 | 27 | 26 | 23 | 18 | 14 | 9 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
396 | 8 | 2017-08-04 | 24 | 19 | 18 | 13 | 11 | 10 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
397 | 9 | 2017-08-11 | 33 | 28 | 25 | 22 | 20 | 16 | 14 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
398 | 8 | 2017-08-04 | 28 | 25 | 21 | 18 | 13 | 11 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
399 | 11 | 2017-08-25 | 34 | 31 | 29 | 27 | 22 | 19 | 17 | 14 | 12 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
400 | 23 | 2017-11-17 | 64 | 61 | 60 | 58 | 56 | 52 | 51 | 46 | 43 | 42 | 39 | 36 | 31 | 28 | 26 | 24 | 19 | 15 | 13 | 10 | 7 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
401 | 16 | 2017-09-29 | 51 | 46 | 41 | 38 | 36 | 33 | 32 | 30 | 29 | 27 | 24 | 19 | 14 | 9 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
402 | 19 | 2017-10-20 | 63 | 58 | 54 | 53 | 50 | 47 | 42 | 37 | 35 | 30 | 26 | 23 | 21 | 18 | 16 | 12 | 7 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
403 | 23 | 2017-11-17 | 64 | 61 | 58 | 57 | 56 | 51 | 46 | 43 | 42 | 38 | 35 | 31 | 30 | 29 | 26 | 21 | 19 | 15 | 14 | 9 | 6 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
404 | 18 | 2017-10-13 | 57 | 56 | 51 | 47 | 45 | 44 | 39 | 34 | 33 | 29 | 25 | 20 | 19 | 15 | 12 | 7 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
405 | 16 | 2017-09-29 | 56 | 53 | 49 | 45 | 40 | 37 | 32 | 29 | 26 | 23 | 19 | 18 | 13 | 9 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
406 | 8 | 2017-08-04 | 23 | 20 | 17 | 15 | 12 | 8 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
407 | 16 | 2017-09-29 | 45 | 42 | 39 | 37 | 35 | 31 | 29 | 28 | 26 | 21 | 16 | 11 | 10 | 9 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
408 | 12 | 2017-09-01 | 39 | 36 | 32 | 27 | 25 | 22 | 17 | 15 | 14 | 9 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
409 | 26 | 2017-12-08 | 76 | 71 | 68 | 67 | 63 | 60 | 55 | 53 | 52 | 50 | 48 | 43 | 39 | 35 | 34 | 30 | 28 | 23 | 21 | 17 | 16 | 14 | 10 | 5 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
410 | 13 | 2017-09-08 | 39 | 36 | 35 | 34 | 29 | 28 | 24 | 22 | 19 | 15 | 10 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
411 | 13 | 2017-09-08 | 34 | 32 | 30 | 25 | 22 | 21 | 18 | 15 | 14 | 13 | 9 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
412 | 14 | 2017-09-15 | 34 | 29 | 27 | 26 | 25 | 23 | 19 | 18 | 16 | 14 | 10 | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
413 | 14 | 2017-09-15 | 39 | 37 | 34 | 31 | 30 | 25 | 20 | 18 | 15 | 14 | 9 | 7 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
414 | 17 | 2017-10-06 | 38 | 36 | 34 | 30 | 29 | 27 | 23 | 21 | 17 | 14 | 13 | 11 | 10 | 7 | 5 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
415 | 27 | 2017-12-15 | 80 | 77 | 72 | 69 | 68 | 66 | 62 | 57 | 52 | 49 | 46 | 42 | 41 | 39 | 38 | 34 | 32 | 30 | 25 | 20 | 17 | 16 | 13 | 11 | 9 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
416 | 13 | 2017-09-08 | 37 | 34 | 31 | 29 | 25 | 24 | 20 | 15 | 14 | 12 | 8 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
417 | 23 | 2017-11-17 | 67 | 66 | 63 | 60 | 58 | 56 | 55 | 53 | 48 | 47 | 45 | 40 | 36 | 32 | 27 | 24 | 20 | 18 | 14 | 9 | 8 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
418 | 20 | 2017-10-27 | 56 | 53 | 52 | 51 | 47 | 45 | 40 | 37 | 35 | 34 | 30 | 28 | 26 | 24 | 23 | 18 | 13 | 8 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
419 | 10 | 2017-08-18 | 26 | 23 | 22 | 17 | 16 | 14 | 11 | 7 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
420 | 18 | 2017-10-13 | 44 | 42 | 37 | 36 | 34 | 31 | 29 | 26 | 24 | 23 | 19 | 18 | 17 | 14 | 9 | 7 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
421 | 11 | 2017-08-25 | 28 | 23 | 22 | 18 | 16 | 12 | 9 | 8 | 7 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
422 | 20 | 2017-10-27 | 65 | 64 | 59 | 54 | 51 | 49 | 45 | 41 | 38 | 34 | 33 | 28 | 24 | 19 | 14 | 13 | 9 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
423 | 12 | 2017-09-01 | 39 | 34 | 32 | 28 | 24 | 23 | 20 | 16 | 13 | 9 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
424 | 14 | 2017-09-15 | 36 | 35 | 34 | 32 | 31 | 27 | 25 | 22 | 17 | 13 | 9 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
425 | 17 | 2017-10-06 | 55 | 52 | 49 | 45 | 42 | 37 | 34 | 29 | 26 | 21 | 16 | 14 | 9 | 6 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
426 | 14 | 2017-09-15 | 39 | 36 | 34 | 33 | 30 | 28 | 24 | 19 | 16 | 13 | 10 | 6 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
427 | 12 | 2017-09-01 | 35 | 34 | 32 | 30 | 26 | 22 | 20 | 16 | 12 | 10 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
428 | 19 | 2017-10-20 | 54 | 52 | 47 | 44 | 42 | 39 | 34 | 32 | 31 | 28 | 26 | 24 | 22 | 19 | 14 | 13 | 8 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
429 | 18 | 2017-10-13 | 56 | 55 | 54 | 50 | 47 | 45 | 44 | 39 | 34 | 33 | 29 | 27 | 24 | 19 | 16 | 11 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
430 | 25 | 2017-12-01 | 75 | 73 | 69 | 64 | 63 | 59 | 55 | 50 | 47 | 46 | 45 | 44 | 40 | 35 | 30 | 28 | 24 | 19 | 18 | 15 | 12 | 10 | 7 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
431 | 22 | 2017-11-10 | 70 | 67 | 65 | 62 | 58 | 55 | 52 | 50 | 45 | 40 | 36 | 31 | 28 | 24 | 20 | 19 | 15 | 11 | 10 | 9 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
432 | 29 | 2017-12-29 | 85 | 83 | 79 | 74 | 71 | 70 | 68 | 66 | 64 | 59 | 54 | 51 | 49 | 47 | 45 | 40 | 38 | 34 | 29 | 24 | 22 | 21 | 16 | 15 | 13 | 9 | 7 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
433 | 11 | 2017-08-25 | 30 | 29 | 24 | 22 | 21 | 19 | 17 | 13 | 11 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
434 | 29 | 2017-12-29 | 70 | 66 | 62 | 60 | 57 | 56 | 52 | 47 | 46 | 43 | 41 | 39 | 36 | 33 | 32 | 30 | 29 | 26 | 25 | 21 | 19 | 18 | 15 | 14 | 10 | 8 | 7 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
435 | 18 | 2017-10-13 | 58 | 53 | 51 | 47 | 45 | 42 | 38 | 33 | 29 | 24 | 22 | 19 | 16 | 15 | 12 | 9 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
436 | 8 | 2017-08-04 | 32 | 29 | 25 | 22 | 17 | 14 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
437 | 23 | 2017-11-17 | 71 | 68 | 65 | 63 | 58 | 53 | 51 | 48 | 43 | 41 | 37 | 35 | 34 | 31 | 27 | 22 | 21 | 19 | 17 | 12 | 11 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
438 | 10 | 2017-08-18 | 30 | 29 | 26 | 23 | 22 | 17 | 13 | 9 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
439 | 16 | 2017-09-29 | 45 | 41 | 38 | 36 | 35 | 31 | 30 | 26 | 22 | 19 | 15 | 11 | 10 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
440 | 12 | 2017-09-01 | 27 | 25 | 24 | 23 | 18 | 17 | 12 | 10 | 9 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
441 | 17 | 2017-10-06 | 54 | 53 | 49 | 44 | 40 | 35 | 34 | 31 | 28 | 27 | 26 | 21 | 17 | 13 | 10 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
442 | 9 | 2017-08-11 | 25 | 21 | 17 | 12 | 11 | 8 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
443 | 18 | 2017-10-13 | 64 | 59 | 54 | 50 | 46 | 45 | 40 | 36 | 33 | 29 | 24 | 21 | 18 | 15 | 14 | 11 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
444 | 19 | 2017-10-20 | 51 | 50 | 49 | 44 | 41 | 39 | 34 | 31 | 29 | 27 | 25 | 23 | 19 | 14 | 12 | 8 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
445 | 23 | 2017-11-17 | 68 | 64 | 61 | 57 | 56 | 53 | 49 | 46 | 41 | 40 | 36 | 32 | 27 | 22 | 18 | 15 | 13 | 11 | 10 | 6 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
446 | 17 | 2017-10-06 | 56 | 51 | 46 | 45 | 43 | 39 | 35 | 30 | 28 | 25 | 24 | 20 | 17 | 14 | 9 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
447 | 23 | 2017-11-17 | 77 | 73 | 70 | 66 | 61 | 57 | 54 | 51 | 49 | 44 | 40 | 36 | 34 | 33 | 32 | 27 | 25 | 24 | 19 | 16 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
448 | 12 | 2017-09-01 | 44 | 43 | 38 | 36 | 31 | 26 | 23 | 21 | 16 | 12 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
449 | 14 | 2017-09-15 | 35 | 31 | 29 | 27 | 25 | 20 | 15 | 11 | 8 | 7 | 5 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
450 | 16 | 2017-09-29 | 46 | 45 | 44 | 43 | 41 | 38 | 33 | 28 | 26 | 25 | 21 | 17 | 14 | 10 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
451 | 22 | 2017-11-10 | 66 | 61 | 56 | 53 | 49 | 47 | 46 | 43 | 39 | 38 | 34 | 30 | 25 | 22 | 17 | 16 | 12 | 11 | 9 | 7 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
452 | 13 | 2017-09-08 | 49 | 44 | 40 | 36 | 31 | 26 | 22 | 20 | 17 | 13 | 9 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
453 | 21 | 2017-11-03 | 58 | 56 | 51 | 49 | 48 | 44 | 43 | 38 | 35 | 33 | 29 | 27 | 25 | 21 | 20 | 16 | 13 | 9 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
454 | 17 | 2017-10-06 | 52 | 48 | 44 | 42 | 41 | 39 | 37 | 34 | 30 | 28 | 23 | 19 | 16 | 14 | 12 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
455 | 15 | 2017-09-22 | 40 | 38 | 35 | 31 | 29 | 26 | 22 | 21 | 16 | 12 | 8 | 6 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
456 | 24 | 2017-11-24 | 70 | 69 | 66 | 62 | 61 | 59 | 55 | 52 | 47 | 44 | 40 | 36 | 35 | 30 | 27 | 23 | 20 | 19 | 18 | 17 | 12 | 10 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
457 | 18 | 2017-10-13 | 52 | 47 | 46 | 44 | 40 | 35 | 32 | 30 | 27 | 24 | 22 | 20 | 18 | 16 | 12 | 7 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
458 | 16 | 2017-09-29 | 49 | 45 | 43 | 41 | 37 | 36 | 34 | 31 | 26 | 21 | 17 | 15 | 13 | 8 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
459 | 10 | 2017-08-18 | 30 | 25 | 20 | 16 | 15 | 13 | 12 | 11 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
460 | 11 | 2017-08-25 | 33 | 28 | 25 | 23 | 19 | 18 | 13 | 9 | 5 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
461 | 19 | 2017-10-20 | 47 | 46 | 42 | 38 | 36 | 35 | 33 | 31 | 28 | 27 | 23 | 21 | 18 | 17 | 12 | 11 | 7 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
462 | 10 | 2017-08-18 | 39 | 38 | 34 | 32 | 28 | 23 | 19 | 14 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
463 | 11 | 2017-08-25 | 36 | 34 | 30 | 29 | 24 | 20 | 17 | 16 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
464 | 20 | 2017-10-27 | 57 | 53 | 52 | 51 | 49 | 47 | 45 | 41 | 36 | 31 | 26 | 24 | 21 | 19 | 18 | 15 | 13 | 10 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
465 | 19 | 2017-10-20 | 54 | 49 | 46 | 43 | 42 | 38 | 35 | 33 | 28 | 24 | 22 | 21 | 20 | 16 | 13 | 12 | 8 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
466 | 17 | 2017-10-06 | 52 | 50 | 48 | 46 | 42 | 40 | 39 | 35 | 32 | 29 | 26 | 21 | 17 | 16 | 11 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
467 | 11 | 2017-08-25 | 38 | 36 | 31 | 27 | 25 | 22 | 18 | 15 | 10 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
468 | 10 | 2017-08-18 | 34 | 32 | 28 | 23 | 19 | 15 | 13 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
469 | 21 | 2017-11-03 | 67 | 65 | 64 | 61 | 58 | 57 | 54 | 51 | 47 | 46 | 41 | 36 | 32 | 29 | 24 | 19 | 15 | 12 | 9 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
470 | 20 | 2017-10-27 | 63 | 62 | 61 | 57 | 54 | 51 | 48 | 45 | 40 | 39 | 35 | 30 | 25 | 24 | 19 | 16 | 14 | 9 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
471 | 10 | 2017-08-18 | 29 | 27 | 23 | 22 | 17 | 12 | 10 | 9 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
472 | 19 | 2017-10-20 | 61 | 56 | 53 | 51 | 48 | 45 | 44 | 40 | 39 | 37 | 33 | 28 | 23 | 21 | 18 | 15 | 10 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
473 | 16 | 2017-09-29 | 39 | 38 | 36 | 31 | 30 | 26 | 24 | 22 | 21 | 17 | 14 | 11 | 9 | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
474 | 19 | 2017-10-20 | 47 | 45 | 43 | 42 | 41 | 39 | 35 | 32 | 30 | 26 | 24 | 20 | 16 | 11 | 10 | 9 | 8 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
475 | 16 | 2017-09-29 | 38 | 37 | 35 | 34 | 32 | 30 | 25 | 23 | 19 | 17 | 16 | 11 | 10 | 8 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
476 | 20 | 2017-10-27 | 60 | 58 | 57 | 52 | 50 | 46 | 43 | 39 | 36 | 34 | 31 | 30 | 26 | 22 | 19 | 17 | 13 | 8 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
477 | 22 | 2017-11-10 | 59 | 58 | 57 | 55 | 53 | 51 | 50 | 45 | 42 | 41 | 39 | 34 | 32 | 27 | 25 | 22 | 21 | 16 | 12 | 9 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
478 | 16 | 2017-09-29 | 35 | 31 | 30 | 28 | 27 | 22 | 21 | 19 | 18 | 15 | 13 | 9 | 7 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
479 | 23 | 2017-11-17 | 69 | 68 | 66 | 64 | 59 | 55 | 53 | 48 | 47 | 45 | 40 | 35 | 32 | 30 | 27 | 22 | 20 | 17 | 14 | 11 | 9 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
480 | 10 | 2017-08-18 | 36 | 32 | 29 | 26 | 22 | 21 | 17 | 14 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
481 | 11 | 2017-08-25 | 26 | 24 | 19 | 17 | 16 | 15 | 12 | 11 | 9 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
482 | 9 | 2017-08-11 | 24 | 20 | 15 | 14 | 11 | 9 | 7 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
483 | 21 | 2017-11-03 | 54 | 50 | 46 | 44 | 42 | 39 | 35 | 34 | 32 | 28 | 27 | 26 | 22 | 21 | 20 | 19 | 14 | 10 | 9 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
484 | 20 | 2017-10-27 | 55 | 51 | 49 | 48 | 45 | 44 | 42 | 41 | 37 | 32 | 28 | 27 | 24 | 23 | 19 | 17 | 13 | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
485 | 17 | 2017-10-06 | 65 | 60 | 55 | 54 | 52 | 49 | 44 | 39 | 34 | 29 | 24 | 19 | 16 | 11 | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
486 | 26 | 2017-12-08 | 80 | 76 | 73 | 70 | 69 | 66 | 63 | 62 | 60 | 55 | 53 | 49 | 47 | 45 | 41 | 39 | 37 | 32 | 28 | 25 | 22 | 19 | 14 | 11 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
487 | 26 | 2017-12-08 | 69 | 64 | 62 | 61 | 58 | 55 | 54 | 53 | 51 | 48 | 45 | 40 | 39 | 36 | 35 | 32 | 27 | 26 | 21 | 19 | 17 | 16 | 14 | 9 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
488 | 13 | 2017-09-08 | 38 | 35 | 34 | 30 | 25 | 22 | 19 | 18 | 15 | 13 | 8 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
489 | 17 | 2017-10-06 | 48 | 45 | 43 | 39 | 34 | 31 | 27 | 25 | 22 | 21 | 18 | 17 | 12 | 11 | 8 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
490 | 21 | 2017-11-03 | 74 | 73 | 68 | 66 | 62 | 58 | 55 | 50 | 45 | 43 | 39 | 34 | 31 | 29 | 24 | 20 | 15 | 11 | 6 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
491 | 14 | 2017-09-15 | 45 | 41 | 40 | 36 | 31 | 28 | 27 | 22 | 21 | 17 | 12 | 10 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
492 | 8 | 2017-08-04 | 32 | 29 | 24 | 19 | 14 | 11 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
493 | 18 | 2017-10-13 | 53 | 50 | 47 | 42 | 40 | 36 | 32 | 30 | 26 | 22 | 20 | 16 | 15 | 11 | 8 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
494 | 28 | 2017-12-22 | 80 | 77 | 76 | 71 | 69 | 65 | 64 | 61 | 56 | 51 | 50 | 46 | 42 | 41 | 36 | 31 | 29 | 28 | 24 | 20 | 15 | 14 | 11 | 10 | 8 | 7 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
495 | 28 | 2017-12-22 | 80 | 77 | 76 | 75 | 72 | 71 | 66 | 64 | 63 | 58 | 56 | 54 | 49 | 48 | 45 | 41 | 38 | 37 | 33 | 28 | 26 | 24 | 23 | 18 | 13 | 11 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
496 | 11 | 2017-08-25 | 31 | 28 | 27 | 23 | 21 | 20 | 15 | 14 | 11 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
497 | 19 | 2017-10-20 | 55 | 53 | 51 | 49 | 45 | 42 | 41 | 37 | 32 | 31 | 26 | 22 | 20 | 17 | 15 | 10 | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
498 | 10 | 2017-08-18 | 29 | 24 | 23 | 19 | 18 | 17 | 12 | 7 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
499 | 22 | 2017-11-10 | 55 | 52 | 51 | 46 | 45 | 43 | 41 | 36 | 31 | 27 | 26 | 22 | 19 | 16 | 15 | 11 | 10 | 9 | 5 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
500 | 23 | 2017-11-17 | 63 | 58 | 54 | 52 | 51 | 49 | 44 | 42 | 38 | 37 | 35 | 34 | 32 | 27 | 25 | 20 | 19 | 17 | 16 | 13 | 12 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
501 | 11 | 2017-08-25 | 32 | 30 | 29 | 26 | 23 | 18 | 14 | 10 | 9 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Formulas:
End of Zero Week = IF([Weeks to Zero]<>"",INDEX(D2:DK2,1,[Weeks to Zero]+1),"")

## Throughput Monte Carlo Weeks (hidden)
Trial # | Sumx | Sum4 | Sum8 | Sum12 | Sum16 | Sum20 | Sum24 | Sum28 | Sum32 | Sum36 | Sum40 | Sum44 | Sum48 | Sum52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
1 | 9.5 | 7.5 | 12.6667 | 21.6667 | 34.6667 | 42.1667 | 49.3333 | 58.3333 | 63 | 68.3333 | 73.8333 | 80.8333 | 87.3333 | 96 | 1 | 1 | 3 | 2.5 | 1 | 1 | 1.6667 | 1.5 | 3 | 4 | 1 | 1 | 1.6667 | 5 | 1.3333 | 5 | 1.5 | 1 | 1 | 4 | 1.5 | 1 | 3 | 1.6667 | 1 | 5 | 1 | 2 | 1 | 1 | 1 | 1.6667 | 1 | 1 | 2 | 1.3333 | 1 | 1.5 | 2 | 1 | 1 | 1 | 4 | 1 | 3 | 1 | 1.5 | 1 | 3 | 1.6667 | 2.5 | 1.5
2 | 8.5 | 6 | 10.8333 | 19.1667 | 28.1667 | 42.1667 | 49.6667 | 59 | 65 | 75 | 80 | 85 | 89 | 100.1667 | 3 | 1 | 1 | 1 | 1.5 | 1 | 1.3333 | 1 | 1.3333 | 5 | 1 | 1 | 5 | 1 | 1.3333 | 1.6667 | 4 | 4 | 5 | 1 | 1 | 2.5 | 1 | 3 | 1 | 1.3333 | 5 | 2 | 3 | 1 | 1 | 1 | 3 | 1.5 | 3 | 2.5 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1.6667 | 5 | 2.5
3 | 12.5 | 6 | 14.5 | 20 | 24.6667 | 31.1667 | 35.6667 | 45.6667 | 50.3333 | 62.1667 | 67.1667 | 71.8333 | 78.6667 | 87 | 1 | 1 | 3 | 1 | 2.5 | 4 | 1 | 1 | 1 | 2 | 1.5 | 1 | 1.6667 | 1 | 1 | 1 | 1 | 2 | 2 | 1.5 | 1 | 1 | 1.5 | 1 | 4 | 1 | 2.5 | 2.5 | 1 | 1 | 1 | 1.6667 | 4 | 1.5 | 1.3333 | 5 | 1 | 1.3333 | 1.6667 | 1 | 1.6667 | 1 | 1 | 1 | 1.3333 | 3 | 1.5 | 1 | 1.3333 | 1 | 5 | 1
4 | 16 | 10 | 19.3333 | 25.1667 | 37.1667 | 44.8333 | 54.5 | 59 | 63.3333 | 70.3333 | 76.5 | 83.5 | 90 | 96.1667 | 4 | 1 | 2 | 3 | 1 | 5 | 2 | 1.3333 | 2 | 1.5 | 1 | 1.3333 | 5 | 5 | 1 | 1 | 2.5 | 2.5 | 1.6667 | 1 | 2 | 1.6667 | 5 | 1 | 1 | 1 | 1 | 1.5 | 1 | 1.3333 | 1 | 1 | 1 | 1.3333 | 3 | 1.6667 | 1.5 | 2 | 1.6667 | 1 | 2.5 | 1.6667 | 1.5 | 1.3333 | 3 | 1.5 | 1 | 1 | 1.5 | 1 | 1.6667 | 2
5 | 11 | 6 | 14.5 | 19.8333 | 26.3333 | 34.3333 | 43.3333 | 51.8333 | 58.3333 | 63.3333 | 72.3333 | 80.3333 | 89.3333 | 93.3333 | 1 | 1 | 1.5 | 2.5 | 1 | 4 | 2.5 | 1 | 1 | 2 | 1.3333 | 1 | 1 | 3 | 1 | 1.5 | 1 | 1 | 1 | 5 | 4 | 2 | 2 | 1 | 1.5 | 1 | 1 | 5 | 1 | 2 | 2.5 | 1 | 1 | 1 | 1 | 2 | 2.5 | 4 | 1.5 | 1 | 1 | 5 | 1 | 1 | 1 | 4 | 3 | 1 | 1 | 1 | 1 | 1
6 | 10.3333 | 7.3333 | 13.6667 | 22.6667 | 30.3333 | 37.3333 | 47.8333 | 52.3333 | 57.6667 | 64 | 73.8333 | 79.1667 | 83.8333 | 93.8333 | 1.3333 | 2 | 3 | 1 | 2 | 1 | 2 | 1.3333 | 2 | 1 | 1 | 5 | 1 | 4 | 1.6667 | 1 | 3 | 2 | 1 | 1 | 2.5 | 2 | 1 | 5 | 1 | 1.5 | 1 | 1 | 1.3333 | 1 | 1 | 2 | 1 | 1 | 1.3333 | 3 | 2.5 | 1 | 1.3333 | 5 | 1 | 2 | 1.3333 | 1 | 1.3333 | 1 | 1 | 1.3333 | 4 | 1 | 1 | 4
7 | 12.6667 | 7.6667 | 19.6667 | 24.3333 | 31.8333 | 37.6667 | 46.6667 | 53 | 57.3333 | 70.3333 | 75.1667 | 81 | 90.8333 | 100 | 4 | 1 | 1.6667 | 1 | 2 | 3 | 2 | 5 | 1 | 1.6667 | 1 | 1 | 2.5 | 1.3333 | 2 | 1.6667 | 1 | 1 | 1.3333 | 2.5 | 4 | 2 | 2 | 1 | 2 | 1.3333 | 1 | 2 | 1 | 1 | 1.3333 | 1 | 3 | 1 | 5 | 4 | 1 | 1.3333 | 1.5 | 1 | 1 | 1.3333 | 2.5 | 1 | 1.3333 | 3 | 4 | 1.5 | 1.3333 | 1.3333 | 5 | 1.5
8 | 14 | 8 | 18.5 | 24 | 31 | 38.3333 | 46 | 57.6667 | 64.5 | 75.5 | 80 | 94 | 99.8333 | 107 | 4 | 1 | 2 | 1 | 5 | 1 | 2.5 | 2 | 1.6667 | 1.5 | 1 | 1.3333 | 2 | 1 | 1 | 3 | 2 | 3 | 1.3333 | 1 | 1.3333 | 2 | 3 | 1.3333 | 1.6667 | 4 | 5 | 1 | 1.6667 | 1.5 | 2 | 1.6667 | 1 | 4 | 2 | 4 | 1 | 1 | 1.5 | 1 | 4 | 1 | 5 | 4 | 1.5 | 1 | 2 | 1.3333 | 1 | 2.5 | 1.6667 | 2
9 | 12.6667 | 6.6667 | 15.6667 | 25 | 40.5 | 48 | 55 | 59 | 65.8333 | 73.8333 | 83.3333 | 95.3333 | 107 | 114.3333 | 1 | 1 | 1.6667 | 3 | 5 | 1 | 1.5 | 1.5 | 5 | 1.3333 | 1 | 2 | 5 | 2.5 | 5 | 3 | 1 | 4 | 1.5 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1.3333 | 2.5 | 1.6667 | 1.3333 | 2.5 | 2 | 1.5 | 2 | 5 | 1 | 1.5 | 2 | 5 | 1 | 5 | 1 | 5 | 3 | 1.6667 | 2 | 1.3333 | 1 | 2.5 | 2.5
10 | 8 | 4 | 10 | 16.6667 | 26.3333 | 30.3333 | 36.3333 | 41.3333 | 48.8333 | 56 | 65.3333 | 73.3333 | 82.6667 | 94.1667 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1.6667 | 2 | 2 | 1 | 1 | 1.6667 | 5 | 2 | 1 | 1 | 1 | 1 | 1.5 | 1.5 | 1 | 2 | 1 | 1.3333 | 1.6667 | 1 | 3 | 1 | 2.5 | 1 | 2.5 | 1.6667 | 2 | 1 | 3 | 1 | 1.3333 | 4 | 2 | 2 | 3 | 1 | 4 | 1.3333 | 2 | 2 | 1 | 2.5 | 4 | 4
11 | 13.5 | 8.5 | 16.5 | 25 | 29.3333 | 38.3333 | 43.3333 | 48.8333 | 57 | 61.8333 | 72.8333 | 79 | 83.8333 | 92 | 2.5 | 1 | 4 | 1 | 3 | 2 | 2 | 1 | 1.5 | 1 | 5 | 1 | 1 | 1 | 1 | 1.3333 | 2 | 1 | 4 | 2 | 1 | 2 | 1 | 1 | 1.5 | 1 | 2 | 1 | 1.6667 | 1.5 | 1 | 4 | 1 | 1.5 | 1 | 1.3333 | 1 | 1 | 4 | 5 | 2.5 | 1.6667 | 1 | 1 | 1 | 1.3333 | 1.5 | 1 | 1.5 | 1 | 1.6667 | 4
12 | 12.6667 | 6 | 15.3333 | 24.3333 | 35.8333 | 45.8333 | 50.5 | 57.8333 | 63 | 75 | 84.8333 | 92.5 | 98.5 | 104.5 | 1.5 | 1 | 1 | 2.5 | 1.6667 | 5 | 1.6667 | 1 | 1 | 2 | 1 | 5 | 2 | 5 | 2 | 2.5 | 1 | 1.5 | 2.5 | 5 | 1 | 1.6667 | 1 | 1 | 1 | 4 | 1 | 1.3333 | 1 | 1.5 | 1.3333 | 1.3333 | 5 | 1 | 5 | 1 | 1.3333 | 2 | 2.5 | 4 | 1 | 4 | 1 | 1.6667 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 3
13 | 8.6667 | 6 | 12.6667 | 18 | 24 | 36.3333 | 45.6667 | 52.6667 | 65.6667 | 75 | 84 | 92 | 100 | 107 | 1 | 1 | 1 | 3 | 1 | 1.6667 | 2.5 | 1.5 | 2 | 1 | 1 | 1.3333 | 2 | 1.6667 | 1.3333 | 1 | 5 | 1.3333 | 5 | 1 | 4 | 3 | 1.3333 | 1 | 1 | 1 | 3 | 2 | 5 | 2 | 5 | 1 | 1 | 2 | 5 | 1.3333 | 2 | 1 | 5 | 1 | 4 | 1 | 2 | 1 | 2 | 2 | 2 | 2 | 4 | 1 | 1 | 1
14 | 15.1667 | 12 | 17.6667 | 24.3333 | 34.6667 | 42.3333 | 47.6667 | 53 | 60 | 64 | 74.5 | 82.1667 | 86.8333 | 94.3333 | 3 | 1 | 4 | 4 | 1.6667 | 1.5 | 1 | 1.5 | 3 | 1 | 1 | 1.6667 | 2.5 | 1.3333 | 5 | 1.5 | 2.5 | 1.6667 | 1.5 | 2 | 1.6667 | 1 | 1.6667 | 1 | 1.6667 | 1 | 1.6667 | 1 | 2 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 2.5 | 2 | 4 | 2 | 1.6667 | 2 | 1 | 3 | 1.3333 | 1 | 1 | 1.3333 | 1 | 1.5 | 1 | 4
15 | 12.3333 | 8.8333 | 14.3333 | 20.6667 | 27.3333 | 36.3333 | 40.8333 | 48.8333 | 57.8333 | 62.8333 | 67.8333 | 73.8333 | 78.8333 | 85.8333 | 1.3333 | 4 | 1 | 2.5 | 2.5 | 1 | 1 | 1 | 1 | 1.3333 | 3 | 1 | 1 | 1.3333 | 3 | 1.3333 | 1 | 1.5 | 2.5 | 4 | 1 | 1 | 1.5 | 1 | 1 | 2 | 4 | 1 | 2 | 2.5 | 2.5 | 2 | 1.3333 | 1.3333 | 1.3333 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 1.3333 | 1.6667 | 2 | 3 | 1 | 1
16 | 8.5 | 5 | 11.1667 | 15.1667 | 20.1667 | 25.1667 | 33.1667 | 42.1667 | 48.3333 | 56 | 62.5 | 68.6667 | 76.6667 | 86 | 1 | 1 | 1.6667 | 1.3333 | 1 | 2.5 | 1.3333 | 1.3333 | 1 | 1 | 1 | 1 | 1.5 | 1 | 1.5 | 1 | 1.5 | 1.5 | 1 | 1 | 3 | 1 | 1 | 3 | 1 | 3 | 2 | 3 | 2.5 | 1 | 1 | 1.6667 | 1 | 3 | 1.6667 | 2 | 1 | 1.3333 | 1.6667 | 2.5 | 1.6667 | 2.5 | 1 | 1 | 2 | 1 | 1 | 4 | 2 | 1 | 1.3333 | 5
17 | 10 | 7 | 13.1667 | 19.6667 | 27.8333 | 35.1667 | 46.1667 | 50.1667 | 59.3333 | 63.6667 | 69.8333 | 76.3333 | 85.3333 | 92.3333 | 1 | 2.5 | 2.5 | 1 | 1 | 2 | 1.5 | 1.6667 | 1 | 1 | 2 | 2.5 | 1.5 | 2 | 1.6667 | 3 | 2 | 3 | 1.3333 | 1 | 2 | 3 | 1 | 5 | 1 | 1 | 1 | 1 | 1 | 1.6667 | 4 | 2.5 | 1 | 1 | 1.3333 | 1 | 2 | 1.5 | 1 | 1.6667 | 1 | 1 | 2.5 | 2 | 5 | 1 | 1 | 2 | 3 | 1 | 2 | 1
18 | 8.5 | 4 | 14.5 | 21.1667 | 28.5 | 36.5 | 46.5 | 56.5 | 62.5 | 68.3333 | 73.3333 | 82.3333 | 90 | 99.5 | 1 | 1 | 1 | 1 | 2.5 | 2 | 1 | 5 | 3 | 1 | 1 | 1.6667 | 1 | 1.3333 | 1 | 4 | 1 | 1 | 1 | 5 | 4 | 1 | 4 | 1 | 2 | 2.5 | 1.5 | 4 | 1 | 2 | 1 | 2 | 2.5 | 1 | 1.3333 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 2 | 4 | 3 | 2 | 1.6667 | 1 | 2.5 | 1 | 5 | 1
19 | 9.5 | 7.5 | 11.5 | 18.5 | 25 | 31.5 | 37.5 | 45.5 | 51 | 57 | 64 | 70.5 | 79.5 | 85.8333 | 4 | 1.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 1 | 1.5 | 1 | 1 | 3 | 1.5 | 2 | 2 | 1 | 1 | 1 | 1 | 3 | 3 | 2 | 1 | 2 | 1.3333 | 1.5 | 1 | 1.6667 | 1 | 3 | 1 | 1 | 2.5 | 1.5 | 2 | 1 | 1 | 2 | 1 | 2.5 | 1.3333 | 2 | 4 | 1.6667 | 1.3333 | 2 | 1 | 2
20 | 10.1667 | 7.5 | 15.1667 | 20 | 26.8333 | 37.3333 | 44.8333 | 52.3333 | 57.3333 | 65.3333 | 72.8333 | 81.5 | 90 | 96 | 2 | 1.5 | 2 | 2 | 1 | 1.6667 | 3 | 2 | 1 | 1.5 | 1.3333 | 1 | 3 | 1.3333 | 1.5 | 1 | 3 | 1 | 4 | 2.5 | 2 | 1 | 2.5 | 2 | 2.5 | 2.5 | 1.5 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 4 | 2 | 1.5 | 2 | 3 | 1 | 1.6667 | 2 | 2.5 | 2.5 | 2 | 2 | 2.5 | 2 | 2 | 1 | 1 | 2
21 | 8.5 | 6.5 | 10.8333 | 22.8333 | 29.6667 | 35 | 46 | 55.3333 | 64.3333 | 71 | 78 | 85.1667 | 93.8333 | 100.1667 | 1 | 2.5 | 1 | 2 | 1 | 1 | 1.3333 | 1 | 3 | 5 | 2 | 2 | 2.5 | 1.3333 | 1 | 2 | 1 | 1 | 1.6667 | 1.6667 | 2 | 5 | 2 | 2 | 1.3333 | 2 | 5 | 1 | 1 | 1 | 2 | 5 | 1 | 1.6667 | 1 | 3 | 2 | 3 | 1 | 1 | 1.5 | 3 | 1 | 1.6667 | 1 | 1.6667 | 1 | 5 | 1.3333 | 1 | 3 | 1
22 | 10.5 | 5.5 | 12.5 | 17.5 | 23.5 | 32.5 | 38.5 | 46 | 53.3333 | 64.3333 | 72.6667 | 82 | 88.5 | 95.1667 | 2 | 1 | 1 | 1.5 | 4 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1.3333 | 1.6667 | 1.3333 | 1.6667 | 2 | 4 | 2 | 1 | 1 | 1.3333 | 1.6667 | 2 | 1 | 2.5 | 1 | 3 | 4 | 1 | 1.3333 | 1 | 4 | 1 | 5 | 1 | 1.3333 | 5 | 1 | 1 | 3 | 1.6667 | 1.6667 | 3 | 1 | 1 | 1.5 | 3 | 2.5 | 1.5 | 1 | 1.6667
23 | 15.6667 | 12.1667 | 19.6667 | 25.6667 | 33.1667 | 41.1667 | 46.8333 | 56.3333 | 67.1667 | 72.5 | 77.1667 | 85.1667 | 92.3333 | 99.3333 | 4 | 1.6667 | 4 | 2.5 | 1 | 2.5 | 1 | 3 | 1 | 1 | 2 | 2 | 1.5 | 1 | 2 | 3 | 1 | 4 | 2 | 1 | 1.6667 | 1 | 1 | 2 | 1 | 1.5 | 5 | 2 | 5 | 1.5 | 1.3333 | 3 | 2 | 1 | 1 | 1.3333 | 1 | 1 | 1 | 1.6667 | 1 | 1 | 5 | 1 | 1 | 2 | 2.5 | 1.6667 | 1 | 1.5 | 1.5 | 3
24 | 12.5 | 9 | 16.5 | 22 | 29.1667 | 39.1667 | 47.8333 | 52.3333 | 59.8333 | 69.1667 | 74.5 | 79.1667 | 90.1667 | 96.6667 | 1 | 1 | 4 | 3 | 2.5 | 1 | 2 | 2 | 1.5 | 1 | 1.6667 | 1.3333 | 1.5 | 3 | 1.3333 | 1.3333 | 2 | 1 | 5 | 2 | 1.3333 | 1 | 1.3333 | 5 | 1.5 | 1 | 1 | 1 | 2.5 | 1 | 1.5 | 2.5 | 5 | 1 | 2 | 1.3333 | 1.5 | 1.5 | 1.3333 | 1 | 1 | 1.6667 | 1 | 1 | 4 | 2 | 2 | 3 | 2 | 2.5 | 1 | 1
25 | 11 | 7 | 13.3333 | 20 | 24.6667 | 30.8333 | 37.8333 | 42.5 | 48.5 | 55 | 67 | 78.5 | 87.5 | 99.5 | 1 | 2.5 | 1 | 2.5 | 2 | 2 | 1.3333 | 1 | 1 | 1.6667 | 1 | 3 | 1 | 1.6667 | 1 | 1 | 1.6667 | 1 | 1.5 | 2 | 1 | 1.5 | 3 | 1.5 | 1.6667 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 2 | 1 | 1.5 | 2 | 4 | 3 | 4 | 1 | 1.5 | 3 | 2 | 5 | 1 | 1 | 5 | 2 | 1 | 5 | 5 | 1
26 | 15.6667 | 9 | 19.3333 | 28.3333 | 37.3333 | 43.8333 | 55.5 | 65.5 | 69.5 | 78 | 85 | 96.6667 | 109.3333 | 115.8333 | 1 | 1.5 | 4 | 2.5 | 1.6667 | 5 | 1.6667 | 2 | 1 | 5 | 1 | 2 | 2 | 1 | 5 | 1 | 1 | 2 | 2 | 1.5 | 4 | 5 | 1.3333 | 1.3333 | 3 | 1 | 1 | 5 | 1 | 1 | 1 | 1 | 1 | 2.5 | 3 | 2 | 1 | 1 | 3 | 2 | 5 | 4 | 1 | 1.6667 | 4 | 1.6667 | 3 | 4 | 1 | 1 | 2 | 2.5
27 | 13 | 7 | 15.6667 | 26.6667 | 37 | 46 | 60 | 66.5 | 73.3333 | 81 | 90.5 | 96 | 107 | 114.1667 | 1 | 2.5 | 2.5 | 1 | 1 | 5 | 1.6667 | 1 | 1 | 1 | 5 | 4 | 5 | 1.3333 | 2 | 2 | 1.5 | 1 | 1.5 | 5 | 5 | 1 | 5 | 3 | 2 | 2.5 | 1 | 1 | 3 | 1.3333 | 1 | 1.5 | 1.6667 | 2 | 2 | 2 | 1 | 1 | 2.5 | 5 | 2.5 | 1 | 1 | 1 | 2.5 | 4 | 2.5 | 2 | 1.3333 | 2.5 | 2 | 1.3333
28 | 12.1667 | 6.1667 | 16.1667 | 21.1667 | 31.3333 | 38.3333 | 45 | 57 | 62 | 72.1667 | 78.5 | 87.6667 | 99.1667 | 111.5 | 2.5 | 1 | 1 | 1.6667 | 1 | 5 | 2 | 2 | 1 | 2 | 1 | 1 | 1.6667 | 3 | 4 | 1.5 | 1 | 1.5 | 2.5 | 2 | 1.6667 | 3 | 1 | 1 | 2 | 1 | 4 | 5 | 1 | 2 | 1 | 1 | 1 | 5 | 2.5 | 1.6667 | 3 | 1 | 1.3333 | 1 | 1 | 1.6667 | 4 | 2.5 | 3 | 2 | 2.5 | 4 | 1.6667 | 1.6667 | 5 | 4
29 | 9.8333 | 4.3333 | 14.1667 | 20.3333 | 27.3333 | 31.8333 | 38 | 46 | 54.3333 | 64.6667 | 73.5 | 83 | 88 | 93.5 | 1 | 1 | 1 | 1.3333 | 1.5 | 4 | 3 | 1.3333 | 1.6667 | 1.5 | 1.3333 | 1.6667 | 3 | 1 | 2 | 1 | 1 | 1 | 1.5 | 1 | 1 | 1 | 1.6667 | 2.5 | 2 | 4 | 1 | 1 | 1 | 1.3333 | 1 | 5 | 4 | 1 | 1.3333 | 4 | 5 | 1 | 1.5 | 1.3333 | 5 | 1.5 | 1 | 2 | 1 | 2 | 1 | 1 | 2.5 | 1 | 1 | 1
30 | 8.5 | 6.1667 | 12 | 17.5 | 24 | 29.5 | 39 | 48.3333 | 56 | 62.1667 | 66.1667 | 76.6667 | 89.6667 | 94.8333 | 1.5 | 1 | 2 | 1.6667 | 1.3333 | 1 | 2.5 | 1 | 2 | 1 | 1.5 | 1 | 2 | 2.5 | 1 | 1 | 1 | 1 | 2.5 | 1 | 1.3333 | 1.5 | 1.6667 | 5 | 1 | 1.3333 | 4 | 3 | 4 | 1 | 1.6667 | 1 | 1.5 | 1 | 2 | 1.6667 | 1 | 1 | 1 | 1 | 5 | 1 | 2 | 2.5 | 5 | 1 | 2 | 5 | 1.3333 | 1.5 | 1.3333 | 1
31 | 8.8333 | 5.8333 | 15.8333 | 21.3333 | 31.6667 | 37.3333 | 47.3333 | 52.1667 | 57.1667 | 65.1667 | 72.5 | 83 | 88.8333 | 95.3333 | 1 | 1.3333 | 2 | 1.5 | 2 | 1 | 4 | 3 | 1 | 1 | 2 | 1.5 | 1 | 3 | 5 | 1.3333 | 1 | 2 | 1 | 1.6667 | 4 | 1 | 1 | 4 | 1 | 1 | 1.3333 | 1.5 | 1.5 | 1.5 | 1 | 1 | 3 | 2 | 2 | 1 | 1 | 3 | 2 | 1.3333 | 2.5 | 2.5 | 4 | 1.5 | 1.3333 | 2.5 | 1 | 1 | 1 | 1 | 2.5 | 2
32 | 10.5 | 5.5 | 16.5 | 21.8333 | 30.8333 | 37.3333 | 42.8333 | 48.3333 | 53 | 58 | 63.1667 | 71.1667 | 76.5 | 86 | 1 | 2 | 1 | 1.5 | 1 | 4 | 5 | 1 | 1 | 1.5 | 1.3333 | 1.5 | 1 | 4 | 3 | 1 | 1.5 | 2.5 | 1 | 1.5 | 2 | 1 | 1.5 | 1 | 2 | 1 | 1 | 1.5 | 1 | 1 | 1 | 1.6667 | 1 | 1 | 1 | 2 | 1 | 1.5 | 1 | 1.6667 | 1 | 2 | 3 | 2 | 1.3333 | 1 | 1 | 2 | 1 | 1 | 5 | 2.5
33 | 11.5 | 8 | 15 | 20.3333 | 27.3333 | 37.3333 | 42.6667 | 51.6667 | 55.6667 | 63.1667 | 69.3333 | 82.3333 | 88.3333 | 92.6667 | 2 | 1 | 1 | 4 | 1 | 2.5 | 1 | 2.5 | 1 | 1 | 1.3333 | 2 | 1 | 1 | 2 | 3 | 2 | 5 | 1 | 2 | 1.3333 | 2 | 1 | 1 | 1 | 2 | 5 | 1 | 1 | 1 | 1 | 1 | 2.5 | 2 | 2 | 1 | 1 | 1.6667 | 2.5 | 1 | 4 | 1 | 3 | 5 | 1.5 | 1 | 2.5 | 1 | 1 | 1 | 1.3333 | 1
34 | 13 | 7 | 17.5 | 27 | 34 | 41 | 46.5 | 56.5 | 66.5 | 72.3333 | 80.3333 | 85.6667 | 92.6667 | 100 | 2 | 2 | 2 | 1 | 5 | 1 | 2.5 | 2 | 1.5 | 1 | 4 | 3 | 2 | 1 | 3 | 1 | 2 | 1.5 | 1.5 | 2 | 1 | 1.5 | 2 | 1 | 2.5 | 2 | 2.5 | 3 | 2.5 | 5 | 1.5 | 1 | 1 | 2.5 | 1.3333 | 1 | 1 | 2 | 1 | 4 | 1 | 1 | 1.3333 | 2 | 1.5 | 1.5 | 3 | 1 | 1.3333 | 4 | 1 | 1
35 | 9.5 | 6.5 | 11.5 | 23.3333 | 27.6667 | 32.3333 | 48 | 55 | 65.5 | 75.1667 | 80.1667 | 84.8333 | 90.1667 | 95.1667 | 2 | 1 | 1 | 2.5 | 1.6667 | 1.3333 | 1 | 1 | 2.5 | 1.3333 | 4 | 4 | 1 | 1.3333 | 1 | 1 | 1.6667 | 1 | 1 | 1 | 1.6667 | 5 | 5 | 4 | 1 | 1 | 4 | 1 | 1 | 3 | 1.5 | 5 | 3 | 4 | 1 | 1.6667 | 1 | 2 | 1 | 1 | 1 | 1.6667 | 1 | 1 | 1 | 1.3333 | 1 | 2 | 1 | 2 | 1 | 1
36 | 12.1667 | 8.1667 | 15.8333 | 21.3333 | 27.6667 | 32.6667 | 38.6667 | 45 | 51.6667 | 61.6667 | 68.1667 | 74.8333 | 83.8333 | 90.8333 | 3 | 1.6667 | 1.5 | 2 | 2 | 2 | 1.6667 | 2 | 2.5 | 1 | 1 | 1 | 1 | 1 | 3 | 1.3333 | 1 | 2 | 1 | 1 | 1.5 | 1 | 2.5 | 1 | 1.3333 | 2 | 2 | 1 | 2 | 2 | 1.6667 | 1 | 1.5 | 1.5 | 4 | 3 | 1.3333 | 1 | 2.5 | 1.6667 | 2 | 1.6667 | 2 | 1 | 2 | 3 | 3 | 1 | 3 | 2 | 1 | 1
37 | 9 | 5.8333 | 11.6667 | 21 | 26.3333 | 35.3333 | 40.8333 | 45.5 | 55.6667 | 66.5 | 71 | 76 | 88 | 93.8333 | 1 | 2.5 | 1.3333 | 1 | 1.6667 | 1.5 | 1.6667 | 1 | 1 | 1.6667 | 5 | 1.6667 | 1 | 2 | 1.3333 | 1 | 5 | 1 | 2 | 1 | 1 | 1.5 | 2 | 1 | 1 | 1 | 1.6667 | 1 | 2.5 | 2 | 4 | 1.6667 | 5 | 2.5 | 2 | 1.3333 | 1 | 1 | 1 | 1.5 | 2 | 1 | 1 | 1 | 1 | 4 | 2 | 5 | 1 | 2 | 1.5 | 1.3333
38 | 8.8333 | 5.8333 | 11.8333 | 21.8333 | 30.5 | 39.3333 | 52.3333 | 58.6667 | 65.6667 | 69.6667 | 75.6667 | 85.3333 | 89.8333 | 103.3333 | 1 | 1 | 2.5 | 1.3333 | 2 | 1 | 1 | 2 | 4 | 2 | 3 | 1 | 1 | 2 | 4 | 1.6667 | 5 | 1.5 | 1.3333 | 1 | 4 | 3 | 5 | 1 | 3 | 1.3333 | 1 | 1 | 1 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 5 | 2 | 1.6667 | 1 | 1.5 | 1 | 1 | 4 | 3 | 5 | 1.5
39 | 8.3333 | 4.8333 | 14.3333 | 26.3333 | 36.3333 | 42.8333 | 50.5 | 58.5 | 65.1667 | 72.5 | 78.3333 | 84.8333 | 93.8333 | 104.1667 | 1 | 1.3333 | 1.5 | 1 | 1.5 | 2 | 1 | 5 | 1 | 5 | 2 | 4 | 4 | 4 | 1 | 1 | 1 | 2.5 | 2 | 1 | 1 | 1 | 4 | 1.6667 | 4 | 1 | 2 | 1 | 3 | 1.6667 | 1 | 1 | 1.3333 | 1 | 1 | 4 | 1.3333 | 1 | 2.5 | 1 | 2.5 | 1 | 1.3333 | 1.6667 | 3 | 2 | 3 | 1 | 1.3333 | 3 | 1 | 5
40 | 11.3333 | 8.3333 | 14 | 24.5 | 30.6667 | 36.6667 | 43.6667 | 55.1667 | 64.5 | 70 | 78 | 83 | 91 | 103.3333 | 4 | 1.5 | 1.5 | 1.3333 | 1.5 | 1.5 | 1 | 1.6667 | 1.5 | 1 | 3 | 5 | 1.6667 | 2.5 | 1 | 1 | 2 | 1 | 1.3333 | 1.6667 | 2 | 2 | 1.6667 | 1.3333 | 4 | 1 | 2.5 | 4 | 3 | 4 | 1.3333 | 1 | 1 | 1 | 2.5 | 1 | 4 | 1.3333 | 1.6667 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 4 | 5 | 1 | 1.3333 | 5
41 | 7 | 4.6667 | 12.3333 | 19.8333 | 27.8333 | 37.3333 | 48.3333 | 53 | 58.5 | 67.5 | 73.1667 | 78.6667 | 85.6667 | 94.5 | 1.6667 | 1 | 1 | 1 | 1 | 1.3333 | 1.3333 | 4 | 1 | 1 | 2.5 | 3 | 4 | 2 | 1 | 1 | 3 | 4 | 1 | 1.5 | 5 | 1 | 3 | 2 | 1 | 1.6667 | 1 | 1 | 1 | 1.5 | 2 | 1 | 4 | 2 | 1 | 2 | 1 | 2 | 1 | 1.6667 | 2 | 1 | 1.5 | 1 | 4 | 1 | 1 | 1 | 2.5 | 1 | 4 | 1.3333
42 | 12 | 9 | 14 | 25.8333 | 37.5 | 42.5 | 47.5 | 61.5 | 68.1667 | 74.1667 | 81.6667 | 86.1667 | 90.6667 | 97.6667 | 2 | 4 | 1.6667 | 1.3333 | 2 | 1 | 1 | 1 | 1.3333 | 3 | 2.5 | 5 | 1 | 5 | 4 | 1.6667 | 1 | 1 | 1.5 | 1.5 | 1 | 1 | 2 | 1 | 3 | 1 | 5 | 5 | 3 | 1.6667 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 2.5 | 1 | 3 | 1.5 | 1 | 1 | 1 | 1 | 1.5 | 1 | 1 | 1 | 1 | 2 | 3
43 | 7 | 5 | 10.5 | 18 | 28 | 33.3333 | 38.3333 | 43.8333 | 57.3333 | 63.8333 | 72.5 | 78.5 | 88.6667 | 97.6667 | 1.6667 | 1 | 1.3333 | 1 | 1 | 1 | 1 | 2.5 | 1.5 | 2 | 3 | 1 | 1 | 1 | 4 | 4 | 2 | 1.3333 | 1 | 1 | 1 | 1 | 2 | 1 | 2.5 | 1 | 1 | 1 | 5 | 1 | 2.5 | 5 | 2.5 | 1 | 2 | 1 | 1.6667 | 1 | 4 | 2 | 1 | 3 | 1 | 1 | 4 | 1.6667 | 3 | 1.5 | 1 | 1 | 3 | 4
44 | 7.5 | 5.5 | 13.5 | 22.5 | 27.1667 | 35.6667 | 42.6667 | 47.8333 | 56.3333 | 60.8333 | 68.3333 | 77.6667 | 87.6667 | 93.1667 | 1 | 1 | 2.5 | 1 | 1 | 1 | 5 | 1 | 1.5 | 1.5 | 1 | 5 | 1 | 1 | 1 | 1.6667 | 1 | 2 | 1.5 | 4 | 1 | 2.5 | 1 | 2.5 | 1 | 1.5 | 1 | 1.6667 | 2.5 | 1 | 4 | 1 | 1 | 1 | 1 | 1.5 | 1 | 3 | 1 | 2.5 | 1.3333 | 3 | 4 | 1 | 3 | 4 | 1 | 2 | 2 | 1.5 | 1 | 1
45 | 11.1667 | 7.3333 | 13.8333 | 29.8333 | 40 | 52.8333 | 60.8333 | 71.3333 | 81.8333 | 91.8333 | 99.8333 | 108.1667 | 113.1667 | 118.5 | 2.5 | 1.3333 | 2.5 | 1 | 2.5 | 1.3333 | 1 | 1.6667 | 5 | 4 | 2 | 5 | 2.5 | 5 | 1.6667 | 1 | 4 | 2.5 | 1.3333 | 5 | 2 | 1 | 1 | 4 | 1.5 | 5 | 3 | 1 | 2 | 1 | 2.5 | 5 | 1 | 3 | 4 | 2 | 1 | 1 | 5 | 1 | 5 | 1 | 1 | 1.3333 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 1.3333
46 | 12.5 | 9.5 | 14.5 | 21.5 | 29.1667 | 37.1667 | 41.1667 | 48.1667 | 55.5 | 62.3333 | 68.3333 | 75.6667 | 82.6667 | 89.5 | 4 | 2.5 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 1 | 4 | 1.6667 | 1 | 1 | 1 | 2 | 4 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 1 | 3 | 1 | 1.3333 | 2 | 1.3333 | 3 | 1 | 1.5 | 1 | 2 | 1.5 | 1.5 | 1.3333 | 2 | 2.5 | 1.5 | 1.6667 | 3 | 1.3333 | 1 | 2.5 | 1.3333 | 2 | 1
47 | 8.5 | 6.5 | 11.5 | 18 | 27.5 | 33.8333 | 40.5 | 45.6667 | 53.1667 | 58.1667 | 66.1667 | 73 | 84.5 | 89.5 | 1 | 3 | 1 | 1.5 | 1 | 1 | 1 | 2 | 1 | 1.6667 | 2.5 | 1.3333 | 3 | 2.5 | 1.5 | 2.5 | 2 | 1.6667 | 1 | 1.6667 | 2 | 1 | 2 | 1.6667 | 1.6667 | 1 | 1.5 | 1 | 1 | 2 | 2.5 | 2 | 1 | 1 | 2 | 1 | 3 | 2 | 1.3333 | 1.6667 | 2 | 2.5 | 1 | 1.3333 | 1.5 | 4 | 5 | 1 | 2 | 1 | 1 | 1
48 | 11 | 8 | 16.3333 | 22.8333 | 30.8333 | 37.8333 | 42.5 | 50 | 57.6667 | 63 | 75 | 84.5 | 91.5 | 97.3333 | 4 | 1 | 1 | 2 | 2 | 1 | 4 | 1.3333 | 2.5 | 1 | 1.5 | 1.5 | 4 | 1 | 1 | 2 | 1 | 3 | 2 | 1 | 1.6667 | 1 | 1 | 1 | 2 | 2 | 1 | 2.5 | 1.6667 | 2.5 | 2.5 | 1 | 1.6667 | 1.6667 | 1 | 1 | 4 | 3 | 2 | 3 | 3 | 1.5 | 4 | 1 | 1 | 3 | 2 | 1 | 1 | 2.5 | 1 | 1.3333
49 | 10.6667 | 5.6667 | 14.6667 | 21.1667 | 33.1667 | 45.1667 | 56.1667 | 65.1667 | 75.6667 | 81.3333 | 86.8333 | 96.3333 | 104 | 109.6667 | 1.6667 | 1.5 | 1 | 1.5 | 2 | 3 | 1 | 3 | 1 | 2 | 1 | 2.5 | 5 | 1 | 1 | 5 | 1 | 1 | 5 | 5 | 1 | 3 | 5 | 2 | 4 | 2 | 1 | 2 | 2.5 | 2 | 5 | 1 | 1.6667 | 1 | 2 | 1 | 2.5 | 1 | 1 | 1 | 1 | 2.5 | 1 | 5 | 1 | 2 | 1.6667 | 3 | 1.3333 | 2 | 1.3333 | 1
50 | 9.3333 | 7.3333 | 11.6667 | 15.6667 | 26 | 32.3333 | 37.8333 | 44.8333 | 51.6667 | 58.1667 | 66.5 | 73.5 | 78.8333 | 83.3333 | 1.3333 | 1 | 1 | 4 | 1 | 1 | 1.3333 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1.3333 | 5 | 1.6667 | 1 | 2 | 1.6667 | 1 | 2.5 | 1 | 1 | 1.3333 | 3 | 1.6667 | 1 | 2.5 | 1.6667 | 1.6667 | 1 | 1.5 | 1 | 3 | 1 | 1 | 1 | 5 | 1.3333 | 1 | 2 | 1.5 | 2.5 | 1.6667 | 1 | 1.6667 | 1 | 1 | 1.5 | 1 | 1
51 | 11.3333 | 5.3333 | 15.3333 | 20.5 | 28.5 | 37.8333 | 48.8333 | 54.3333 | 62.3333 | 68.3333 | 73.3333 | 83 | 90 | 97 | 1.3333 | 2 | 1 | 1 | 3 | 3 | 1 | 3 | 1.3333 | 1.3333 | 1.5 | 1 | 4 | 1 | 1 | 2 | 1.6667 | 2 | 1.6667 | 4 | 2 | 3 | 5 | 1 | 1 | 1.5 | 1 | 2 | 5 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 2 | 1 | 2.5 | 2.5 | 3 | 1.6667 | 2 | 1 | 1 | 3 | 4 | 1 | 1 | 1
52 | 15.5 | 11.5 | 17.8333 | 22.3333 | 31.6667 | 37.1667 | 47.1667 | 59.1667 | 64.6667 | 76.6667 | 83.1667 | 89.6667 | 100.1667 | 107.5 | 2.5 | 2.5 | 1.5 | 5 | 3 | 1 | 1.3333 | 1 | 1.5 | 1 | 1 | 1 | 1.3333 | 1 | 4 | 3 | 1 | 1.5 | 1 | 2 | 2.5 | 4 | 2.5 | 1 | 1 | 5 | 5 | 1 | 1 | 1 | 2.5 | 1 | 1 | 2 | 5 | 4 | 1 | 2 | 2.5 | 1 | 1 | 2 | 1 | 2.5 | 1 | 2.5 | 2 | 5 | 2 | 1 | 1.3333 | 3
53 | 16 | 12 | 25 | 34 | 39.5 | 44.5 | 50.3333 | 59.8333 | 64.3333 | 74.8333 | 83.3333 | 92.1667 | 98.1667 | 108.1667 | 4 | 1 | 2 | 5 | 1 | 3 | 5 | 4 | 3 | 1 | 4 | 1 | 1 | 1 | 1 | 2.5 | 1 | 1 | 2 | 1 | 1 | 1.3333 | 1.5 | 2 | 1 | 4 | 2 | 2.5 | 1.5 | 1 | 1 | 1 | 1 | 3 | 1.5 | 5 | 1 | 5 | 1.5 | 1 | 1.3333 | 1 | 4 | 2.5 | 1 | 3 | 1 | 1 | 5 | 1 | 1 | 3
54 | 12 | 9.6667 | 14.6667 | 23.5 | 32.1667 | 41.8333 | 48.1667 | 52.1667 | 58 | 66 | 72.6667 | 81.8333 | 86.8333 | 97.8333 | 3 | 1.6667 | 1 | 4 | 1.3333 | 1 | 1.6667 | 1 | 5 | 1.3333 | 1 | 1.5 | 1.6667 | 1 | 4 | 2 | 5 | 1.6667 | 2 | 1 | 2 | 2 | 1.3333 | 1 | 1 | 1 | 1 | 1 | 2 | 1.3333 | 1 | 1.5 | 2.5 | 1 | 2 | 2.5 | 3 | 1.6667 | 1 | 1 | 2.5 | 1.6667 | 4 | 1 | 1 | 1 | 2 | 1 | 2 | 4 | 4 | 1
55 | 14.6667 | 12 | 24.6667 | 31.1667 | 38.6667 | 51.1667 | 57.1667 | 67.1667 | 72.5 | 82.3333 | 95.3333 | 107.3333 | 113.5 | 119.5 | 5 | 1 | 1 | 5 | 1 | 1.6667 | 5 | 5 | 1 | 1 | 2 | 2.5 | 2.5 | 2 | 1.3333 | 1.6667 | 1 | 5 | 5 | 1.5 | 1 | 1.6667 | 1.6667 | 1.6667 | 4 | 1 | 4 | 1 | 1.6667 | 1.6667 | 1 | 1 | 1 | 5 | 2.5 | 1.3333 | 5 | 4 | 1 | 3 | 3 | 4 | 4 | 1 | 1.6667 | 2.5 | 1 | 1 | 3 | 1 | 1 | 1
56 | 8.6667 | 6.1667 | 14.6667 | 22 | 32 | 39.5 | 45 | 53.8333 | 60.8333 | 67.6667 | 77.6667 | 85.6667 | 90.6667 | 97 | 1.6667 | 1 | 1.5 | 2 | 1 | 1.5 | 3 | 3 | 1 | 3 | 2 | 1.3333 | 1 | 1 | 3 | 5 | 1 | 2 | 2.5 | 2 | 1 | 1 | 2 | 1.5 | 2.5 | 2.5 | 1.3333 | 2.5 | 1.5 | 1 | 1.5 | 3 | 1.3333 | 2.5 | 2 | 1 | 2.5 | 4 | 1 | 2.5 | 1 | 3 | 1 | 3 | 2 | 1 | 1 | 1 | 2.5 | 1 | 1.3333 | 1.5
57 | 13.6667 | 7.6667 | 17.1667 | 32.1667 | 37.8333 | 45.6667 | 55.8333 | 66.1667 | 74.6667 | 79 | 89.5 | 95.8333 | 104.8333 | 109.8333 | 2.5 | 1.5 | 1.6667 | 2 | 5 | 1 | 1.5 | 2 | 5 | 5 | 2.5 | 2.5 | 1.3333 | 2 | 1 | 1.3333 | 4 | 1 | 1.5 | 1.3333 | 1.6667 | 1 | 2.5 | 5 | 3 | 1.3333 | 5 | 1 | 2 | 1 | 4 | 1.5 | 1 | 1 | 1 | 1.3333 | 3 | 3 | 3 | 1.5 | 1.3333 | 3 | 1 | 1 | 1 | 1.3333 | 5 | 1.6667 | 1 | 1.5 | 1 | 1.5
58 | 7.6667 | 5.6667 | 10 | 14.5 | 23 | 29 | 34.5 | 45 | 52 | 60.3333 | 66.8333 | 81.3333 | 85.6667 | 92.5 | 1.6667 | 1 | 2 | 1 | 1 | 1 | 1 | 1.3333 | 1 | 1.5 | 1 | 1 | 1 | 1.5 | 3 | 3 | 2 | 1 | 2 | 1 | 1 | 2.5 | 1 | 1 | 2.5 | 2 | 5 | 1 | 1 | 4 | 1 | 1 | 5 | 1 | 1 | 1.3333 | 1 | 2.5 | 2 | 1 | 5 | 5 | 1.5 | 3 | 1.3333 | 1 | 1 | 1 | 1 | 1.3333 | 2.5 | 2
59 | 15.8333 | 11.8333 | 19.1667 | 28.1667 | 37.5 | 46 | 59 | 65.5 | 73.8333 | 81.3333 | 86.3333 | 93.3333 | 99.3333 | 104.6667 | 5 | 4 | 1.3333 | 1.5 | 2 | 2 | 2 | 1.3333 | 1 | 1 | 5 | 2 | 2 | 4 | 1.3333 | 2 | 2.5 | 2 | 3 | 1 | 4 | 1 | 5 | 3 | 2 | 1 | 1.5 | 2 | 1 | 5 | 1 | 1.3333 | 1 | 2.5 | 1 | 3 | 2 | 1 | 1 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 1.3333
60 | 10 | 6 | 12 | 24.5 | 29.6667 | 42.1667 | 47.6667 | 60 | 68.5 | 77.5 | 89.1667 | 98.1667 | 102.6667 | 109.6667 | 1.6667 | 1.3333 | 2 | 1 | 3 | 1 | 1 | 1 | 4 | 3 | 4 | 1.5 | 1.6667 | 1.5 | 1 | 1 | 1.5 | 5 | 5 | 1 | 2.5 | 1 | 1 | 1 | 5 | 4 | 1.3333 | 2 | 1 | 1.5 | 1 | 5 | 1 | 2 | 5 | 1 | 4 | 5 | 1.6667 | 1 | 2 | 3 | 2.5 | 1.5 | 1 | 1 | 1.5 | 1 | 1 | 1 | 2.5 | 2.5
61 | 16.1667 | 11.6667 | 22.1667 | 28.1667 | 33.6667 | 41.1667 | 49.5 | 56.6667 | 62.5 | 71.1667 | 77.1667 | 85.6667 | 95.1667 | 102.1667 | 5 | 2 | 3 | 1.6667 | 2.5 | 2 | 1 | 5 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 2.5 | 1.5 | 1 | 3 | 2 | 2 | 4 | 1 | 1.3333 | 2 | 1.6667 | 1 | 2.5 | 1 | 1.3333 | 2.5 | 1 | 1 | 1.6667 | 1 | 5 | 2 | 2 | 1 | 1 | 1 | 4 | 1 | 2.5 | 4 | 1 | 2.5 | 2 | 1 | 2 | 3 | 1
62 | 14 | 11 | 20.3333 | 27.8333 | 39.8333 | 45.5 | 49.8333 | 57.3333 | 66.8333 | 75.8333 | 82.5 | 87.1667 | 92.1667 | 98.1667 | 1 | 4 | 2 | 4 | 1 | 2 | 1.3333 | 5 | 1 | 3 | 1.5 | 2 | 1 | 2 | 4 | 5 | 2 | 1.3333 | 1.3333 | 1 | 1 | 1.3333 | 1 | 1 | 1 | 1.5 | 2 | 3 | 1 | 2 | 4 | 2.5 | 1.6667 | 1.3333 | 5 | 1 | 1 | 3 | 1 | 1.6667 | 1 | 1 | 1 | 1.6667 | 1.5 | 1 | 1 | 1.5 | 1 | 1.5 | 1 | 2.5
63 | 12 | 9.5 | 15.5 | 22.8333 | 29.8333 | 37 | 44.6667 | 49.6667 | 62.6667 | 70.6667 | 78.1667 | 91.5 | 99.3333 | 106.1667 | 2 | 2 | 3 | 2.5 | 1 | 1.5 | 1.5 | 2 | 1.3333 | 1 | 1 | 4 | 2 | 2 | 2 | 1 | 2.5 | 2 | 1.6667 | 1 | 4 | 1.3333 | 1 | 1.3333 | 1.3333 | 1 | 1.6667 | 1 | 1.6667 | 1.3333 | 5 | 5 | 1 | 1 | 1 | 5 | 1 | 3 | 1 | 2.5 | 2 | 5 | 1.3333 | 5 | 3 | 1 | 1.3333 | 2.5 | 1.3333 | 2.5 | 1.3333 | 1.6667
64 | 7.5 | 4.8333 | 15.5 | 20.5 | 34.8333 | 40.5 | 49.1667 | 56.1667 | 61 | 66.3333 | 73 | 78.6667 | 87.5 | 96.3333 | 1.3333 | 1 | 1 | 1.5 | 1.3333 | 1.3333 | 4 | 4 | 1 | 1 | 1.3333 | 1.6667 | 3 | 5 | 5 | 1.3333 | 2 | 1.6667 | 1 | 1 | 1 | 1.6667 | 5 | 1 | 3 | 1 | 1 | 2 | 1.3333 | 1 | 1 | 1.5 | 2 | 1 | 1 | 1.3333 | 1.6667 | 2 | 1 | 2 | 1 | 2 | 1.6667 | 1 | 1.3333 | 1.5 | 2 | 4 | 1.6667 | 1.6667 | 3 | 2.5
65 | 7 | 4 | 12.5 | 19.5 | 25.5 | 33.1667 | 40.1667 | 48 | 53.6667 | 57.6667 | 62.3333 | 72.3333 | 82.3333 | 89.3333 | 1 | 1 | 1 | 1 | 1 | 2 | 2.5 | 3 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 3 | 1.6667 | 2 | 3 | 1 | 1 | 1.6667 | 3 | 1.3333 | 1.3333 | 2.5 | 3 | 1 | 1.6667 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1.3333 | 1.3333 | 1 | 1 | 1 | 1.5 | 2.5 | 5 | 2 | 5 | 2 | 1 | 1 | 1 | 4 | 1
66 | 12 | 6 | 21 | 29.5 | 35.1667 | 44.1667 | 52.3333 | 56.8333 | 61.5 | 67.1667 | 72.1667 | 79.5 | 84.5 | 89.3333 | 1.3333 | 1.6667 | 1.5 | 1.5 | 1 | 5 | 5 | 4 | 1.5 | 2 | 2.5 | 2.5 | 1 | 2 | 1.6667 | 1 | 1 | 2 | 1 | 5 | 1 | 1.5 | 4 | 1.6667 | 1 | 1 | 1 | 1.5 | 1.6667 | 1 | 1 | 1 | 1 | 1 | 1.6667 | 2 | 1 | 1 | 1 | 2 | 1 | 1.3333 | 1 | 4 | 1 | 2 | 1 | 1 | 1 | 1.5 | 1.3333 | 1
67 | 11 | 8 | 15 | 21.6667 | 31 | 38.5 | 51.5 | 60.3333 | 65.3333 | 71.8333 | 83.3333 | 90.3333 | 96 | 101.6667 | 1 | 2 | 1 | 4 | 1 | 2 | 3 | 1 | 1.6667 | 1 | 1 | 3 | 4 | 3 | 1.3333 | 1 | 3 | 2.5 | 1 | 1 | 5 | 1 | 4 | 3 | 1 | 2.5 | 4 | 1.3333 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 2.5 | 3 | 1 | 2.5 | 5 | 3 | 1 | 2 | 1 | 1 | 1 | 1.6667 | 2 | 1.6667 | 1.6667 | 1.3333 | 1
68 | 13.1667 | 8.5 | 15.1667 | 20.1667 | 34.3333 | 40.6667 | 48.6667 | 57.6667 | 64.1667 | 72.6667 | 81.1667 | 87.8333 | 97.3333 | 104.8333 | 1 | 2.5 | 1 | 4 | 3 | 1.6667 | 1 | 1 | 1 | 1.3333 | 1.6667 | 1 | 2.5 | 5 | 1.6667 | 5 | 2 | 1.6667 | 1.6667 | 1 | 1 | 2 | 1 | 4 | 1 | 3 | 4 | 1 | 1 | 2 | 2.5 | 1 | 1 | 2.5 | 3 | 2 | 1 | 1 | 4 | 2.5 | 1 | 1 | 1.6667 | 3 | 1 | 2 | 4 | 2.5 | 3 | 1 | 1 | 2.5
69 | 9.8333 | 6.3333 | 12.8333 | 23.8333 | 32.8333 | 38.8333 | 46.5 | 55.3333 | 61.3333 | 66.3333 | 77.6667 | 84.6667 | 90.1667 | 100.1667 | 1 | 1.3333 | 2 | 2 | 1 | 2.5 | 2 | 1 | 1 | 4 | 1 | 5 | 1.5 | 1 | 5 | 1.5 | 1 | 1 | 1 | 3 | 2 | 1 | 1.6667 | 3 | 4 | 1.3333 | 2.5 | 1 | 1 | 1 | 1.5 | 2.5 | 1 | 1 | 2 | 1 | 2.5 | 5 | 2.5 | 1.3333 | 1 | 1 | 4 | 1 | 1.5 | 1 | 2 | 1 | 4 | 2.5 | 1 | 2.5
70 | 13.6667 | 9.6667 | 17.6667 | 25.3333 | 29.8333 | 38.3333 | 44.3333 | 52.3333 | 59.1667 | 73.1667 | 78.6667 | 90.6667 | 104 | 108.5 | 1.6667 | 5 | 2 | 1 | 1 | 3 | 3 | 1 | 1 | 1.6667 | 1 | 4 | 1 | 1 | 1 | 1.5 | 4 | 1 | 2 | 1.5 | 1.6667 | 1 | 1.6667 | 1.6667 | 1 | 1 | 5 | 1 | 1 | 3 | 1.5 | 1.3333 | 1 | 5 | 5 | 3 | 1 | 2.5 | 1 | 1 | 5 | 5 | 1 | 1 | 2 | 5 | 5 | 1.3333 | 1 | 1.5 | 1 | 1
71 | 10.5 | 8 | 18 | 24.5 | 30.5 | 35.5 | 43.8333 | 48.8333 | 55.1667 | 62.8333 | 71.8333 | 79.8333 | 89.1667 | 96.6667 | 1 | 1 | 5 | 1 | 1 | 1.5 | 2.5 | 5 | 2 | 2.5 | 1 | 1 | 2 | 1 | 1 | 2 | 1.3333 | 1 | 1 | 1.6667 | 1 | 1.3333 | 5 | 1 | 1 | 1.3333 | 1.6667 | 1 | 1.3333 | 1 | 3 | 1 | 1.6667 | 4 | 1 | 1 | 2 | 1 | 1 | 5 | 2 | 4 | 1 | 1 | 1 | 2 | 1.3333 | 5 | 1 | 1.5 | 1 | 4
72 | 9.6667 | 7.1667 | 16.6667 | 22.6667 | 30.1667 | 38.3333 | 43 | 55 | 61.6667 | 65.6667 | 73.6667 | 78.5 | 83.8333 | 91.5 | 2 | 1.6667 | 1 | 2.5 | 1.5 | 1 | 3 | 4 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 2.5 | 4 | 1.6667 | 1.5 | 1 | 1.6667 | 1 | 1 | 1 | 5 | 3 | 2 | 2 | 1 | 3 | 1 | 1.6667 | 1 | 1 | 1 | 1 | 2.5 | 1 | 2 | 2.5 | 1 | 1.3333 | 1.5 | 1 | 1 | 1 | 1.3333 | 2 | 1.6667 | 4 | 1 | 1
73 | 6.8333 | 4.3333 | 13.3333 | 19.5 | 27.8333 | 36.8333 | 44.8333 | 51.3333 | 57.3333 | 64.3333 | 73.3333 | 81.8333 | 91.3333 | 97.8333 | 1 | 1 | 1 | 1.3333 | 1.5 | 1 | 5 | 1.5 | 2 | 1.3333 | 1.3333 | 1.5 | 2 | 1.3333 | 4 | 1 | 1 | 2 | 2 | 4 | 1 | 1 | 4 | 2 | 2 | 1 | 2.5 | 1 | 1 | 2 | 2 | 1 | 2 | 1.5 | 2.5 | 1 | 2 | 1 | 5 | 1 | 5 | 1 | 1.5 | 1 | 2 | 2.5 | 4 | 1 | 1.5 | 1 | 1 | 3
74 | 8 | 6 | 14 | 19.3333 | 26 | 35 | 39.8333 | 48.8333 | 57.8333 | 65.3333 | 70.8333 | 76.1667 | 84.6667 | 90.6667 | 2.5 | 1 | 1.5 | 1 | 1 | 1 | 4 | 2 | 1 | 1.6667 | 1.6667 | 1 | 3 | 1 | 1.6667 | 1 | 4 | 1 | 3 | 1 | 1.3333 | 1 | 1 | 1.5 | 5 | 1.6667 | 1 | 1.3333 | 1 | 2 | 4 | 2 | 1.6667 | 2.5 | 2 | 1.3333 | 1 | 1 | 1 | 2.5 | 1 | 1.5 | 1.5 | 1.3333 | 1.5 | 2 | 4 | 1 | 1 | 3 | 1 | 1
75 | 13.1667 | 9.1667 | 16.8333 | 26.8333 | 35 | 43.5 | 51 | 62.5 | 68 | 76 | 83.6667 | 91.1667 | 100.6667 | 109 | 1.6667 | 1 | 2.5 | 4 | 1 | 3 | 1.6667 | 2 | 2 | 1 | 4 | 3 | 3 | 2.5 | 1.6667 | 1 | 1 | 4 | 2.5 | 1 | 1 | 1.5 | 1 | 4 | 2 | 1.5 | 5 | 3 | 1 | 1 | 1.5 | 2 | 1.6667 | 2.5 | 2.5 | 1.3333 | 1.5 | 3 | 1.5 | 1.6667 | 4 | 1 | 1 | 1.5 | 1.5 | 2 | 5 | 1 | 1 | 3 | 3 | 1.3333
76 | 8.6667 | 6 | 11.6667 | 16.6667 | 28.1667 | 33.1667 | 39.5 | 45.8333 | 54.8333 | 65.3333 | 70.3333 | 76.3333 | 85.3333 | 91.8333 | 2 | 1 | 2 | 1 | 1 | 1.6667 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1.5 | 5 | 4 | 1 | 1 | 1 | 2 | 1 | 1.5 | 2.5 | 1.3333 | 1.6667 | 1 | 1.6667 | 2 | 1 | 1 | 2 | 5 | 3 | 1 | 4 | 2.5 | 1 | 2 | 1 | 1 | 1.5 | 2 | 1.5 | 1 | 5 | 1 | 1.6667 | 1.3333 | 1 | 2.5 | 1 | 2
77 | 6.8333 | 4.8333 | 10.3333 | 14.3333 | 24.5 | 33.1667 | 39.6667 | 48 | 55.1667 | 60.5 | 69 | 77.6667 | 86.6667 | 92 | 1 | 1.5 | 1 | 1.3333 | 1 | 1 | 2.5 | 1 | 1 | 1 | 1 | 1 | 2.5 | 2 | 4 | 1.6667 | 1 | 1.6667 | 5 | 1 | 1 | 3 | 1.5 | 1 | 1.3333 | 2.5 | 3 | 1.5 | 1.6667 | 2 | 1 | 2.5 | 1.3333 | 1.3333 | 1.6667 | 1 | 1.5 | 1 | 2 | 4 | 1.6667 | 4 | 1 | 2 | 4 | 1 | 2 | 2 | 1 | 1 | 2 | 1.3333
78 | 12.8333 | 10.5 | 20.8333 | 27.8333 | 32.1667 | 43.8333 | 53.1667 | 57.5 | 64.3333 | 69.3333 | 79.3333 | 91.3333 | 100.1667 | 108.1667 | 5 | 1 | 2.5 | 2 | 1 | 1.3333 | 3 | 5 | 1 | 1 | 1 | 4 | 1 | 1 | 1.3333 | 1 | 4 | 5 | 1 | 1.6667 | 1.6667 | 1.3333 | 5 | 1.3333 | 1 | 1.3333 | 1 | 1 | 1.6667 | 1.5 | 1.6667 | 2 | 1 | 2 | 1 | 1 | 1 | 5 | 3 | 1 | 1 | 4 | 3 | 4 | 2.5 | 4 | 1 | 1.3333 | 1 | 1 | 2 | 4
79 | 11.5 | 9.5 | 16 | 20.8333 | 25.8333 | 34.8333 | 48.3333 | 57.3333 | 69.3333 | 79 | 87 | 94.3333 | 101 | 109.6667 | 1 | 4 | 2 | 2.5 | 1 | 1 | 3 | 1.5 | 1.5 | 1 | 1.3333 | 1 | 1 | 1.3333 | 1.6667 | 1 | 1 | 3 | 4 | 1 | 5 | 2.5 | 1 | 5 | 1.3333 | 2 | 4 | 1.6667 | 2 | 3 | 2 | 5 | 2 | 5 | 1.6667 | 1 | 1 | 1 | 1 | 5 | 1 | 1 | 1.3333 | 4 | 1 | 3 | 1.6667 | 1 | 2 | 1.6667 | 1 | 4
80 | 14.8333 | 7.3333 | 19.8333 | 26.1667 | 32.6667 | 40.6667 | 49.1667 | 54.3333 | 58.3333 | 66.6667 | 73 | 82.6667 | 87.6667 | 97.5 | 1.3333 | 2.5 | 1.5 | 2 | 2.5 | 5 | 4 | 1 | 2.5 | 1 | 1.5 | 1.3333 | 1.5 | 1 | 1 | 3 | 2 | 1.5 | 1.5 | 3 | 1 | 2 | 1.5 | 4 | 1.5 | 1 | 1 | 1.6667 | 1 | 1 | 1 | 1 | 1.6667 | 1.6667 | 3 | 2 | 1.6667 | 1 | 2 | 1.6667 | 1 | 4 | 3 | 1.6667 | 1 | 1 | 1 | 2 | 5 | 2.5 | 1.3333 | 1
81 | 16 | 12 | 21.3333 | 29.3333 | 34.3333 | 40.3333 | 48.1667 | 52.1667 | 60.3333 | 69.1667 | 75.1667 | 79.1667 | 86.8333 | 95.1667 | 4 | 5 | 2 | 1 | 1 | 3 | 4 | 1.3333 | 1.6667 | 2 | 1.3333 | 3 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 1.3333 | 3 | 1.5 | 2 | 1 | 1 | 1 | 1 | 1.6667 | 3 | 1 | 2.5 | 1 | 5 | 1.5 | 1.3333 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2.5 | 2.5 | 1.6667 | 1 | 1 | 1.3333 | 4 | 2
82 | 11.1667 | 7.6667 | 13.6667 | 17.6667 | 26.6667 | 33.6667 | 41.6667 | 47.6667 | 58.8333 | 63.8333 | 70.1667 | 76.1667 | 82.5 | 90.1667 | 2 | 1.6667 | 3 | 1 | 2.5 | 1 | 1.5 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 5 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 5 | 1.5 | 2.5 | 1 | 1 | 2.5 | 5 | 1.6667 | 2 | 1.6667 | 1 | 1.3333 | 1 | 2 | 1 | 2 | 1.3333 | 1 | 1 | 2 | 2 | 3 | 1.3333 | 1 | 1 | 1.5 | 2 | 2.5 | 1.6667
83 | 6.3333 | 4.3333 | 13.3333 | 20 | 28.5 | 35.8333 | 41.8333 | 50.5 | 56.5 | 66.5 | 75 | 81.1667 | 92.3333 | 100.8333 | 1 | 1.3333 | 1 | 1 | 1 | 1 | 3 | 4 | 1 | 2 | 1.6667 | 2 | 2.5 | 1 | 4 | 1 | 2 | 1.5 | 1.3333 | 2.5 | 1 | 1.5 | 1 | 2.5 | 4 | 1.6667 | 1 | 2 | 1 | 1 | 1 | 3 | 1.5 | 2.5 | 1 | 5 | 2.5 | 4 | 1 | 1 | 1 | 1 | 2.5 | 1.6667 | 2 | 1.6667 | 5 | 2.5 | 3 | 2 | 2.5 | 1
84 | 8.3333 | 6 | 13.8333 | 22.5 | 28.6667 | 38 | 49 | 54 | 65 | 69.5 | 76 | 80.8333 | 88.5 | 96.1667 | 2 | 1.3333 | 1 | 1.6667 | 1 | 1.3333 | 3 | 2.5 | 1 | 5 | 1.6667 | 1 | 1 | 1.6667 | 2.5 | 1 | 1 | 1.3333 | 2 | 5 | 1 | 5 | 1 | 4 | 2 | 1 | 1 | 1 | 5 | 1 | 4 | 1 | 1 | 1.5 | 1 | 1 | 3 | 1 | 1.5 | 1 | 1 | 1.5 | 1 | 1.3333 | 3 | 1.6667 | 2 | 1 | 1.6667 | 2 | 2 | 2
85 | 15 | 11 | 21 | 27 | 33 | 42.6667 | 49.8333 | 63.8333 | 73.8333 | 83.5 | 88 | 93.5 | 105.5 | 115.1667 | 4 | 1 | 2 | 4 | 2 | 2 | 1 | 5 | 1.3333 | 2 | 1 | 1.6667 | 1 | 3 | 1 | 1 | 1 | 5 | 1.6667 | 2 | 1.3333 | 2 | 1.3333 | 2.5 | 1 | 3 | 5 | 5 | 5 | 1 | 2 | 2 | 1 | 5 | 1.6667 | 2 | 1 | 1 | 1.5 | 1 | 1 | 1 | 2.5 | 1 | 5 | 4 | 2 | 1 | 1.3333 | 2 | 1.3333 | 5
86 | 6.3333 | 4 | 11 | 17.3333 | 21.3333 | 26.8333 | 35.1667 | 44.1667 | 52.1667 | 59.1667 | 73.1667 | 83.1667 | 89.8333 | 96.6667 | 1 | 1 | 1 | 1 | 1 | 1.3333 | 3 | 1.6667 | 3 | 1 | 1.3333 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1.5 | 1 | 4 | 1.5 | 1.3333 | 1.5 | 2.5 | 4 | 1.5 | 1 | 1 | 5 | 1 | 1 | 1 | 1 | 1 | 4 | 4 | 5 | 4 | 1 | 1.5 | 1 | 5 | 2.5 | 1 | 1.6667 | 1 | 3 | 1.3333 | 2 | 2.5 | 1
87 | 11.3333 | 8 | 14.8333 | 23.8333 | 30.3333 | 39.6667 | 46.5 | 51 | 59 | 71.5 | 76.5 | 85 | 92.3333 | 99.6667 | 1 | 5 | 1 | 1 | 1.3333 | 2 | 1 | 2.5 | 2 | 1 | 5 | 1 | 1.5 | 1 | 1 | 3 | 1.3333 | 4 | 2 | 2 | 1.6667 | 1 | 1.6667 | 2.5 | 1.5 | 1 | 1 | 1 | 4 | 2 | 1 | 1 | 4 | 1 | 5 | 2.5 | 1 | 1 | 1 | 2 | 1 | 4 | 1 | 2.5 | 1 | 1.3333 | 4 | 1 | 3 | 1 | 1.3333 | 2
88 | 14 | 7.5 | 20.3333 | 33.3333 | 37.8333 | 42.8333 | 51.6667 | 58.3333 | 68.1667 | 77.6667 | 87.6667 | 95.3333 | 103 | 107.5 | 1 | 1.5 | 4 | 1 | 2.5 | 4 | 5 | 1.3333 | 4 | 1 | 5 | 3 | 1 | 1 | 1 | 1.5 | 1 | 1 | 1.3333 | 1.6667 | 5 | 1.5 | 1 | 1.3333 | 1.6667 | 3 | 1 | 1 | 1.5 | 1.3333 | 5 | 2 | 1 | 1.5 | 5 | 2 | 1 | 3 | 1 | 5 | 4 | 1.6667 | 1 | 1 | 4 | 1 | 1.3333 | 1.3333 | 1 | 1.5 | 1 | 1
89 | 15.1667 | 8.6667 | 19.1667 | 26.5 | 33.5 | 40.8333 | 48.5 | 55.1667 | 60 | 65.5 | 70 | 82.6667 | 89.6667 | 94 | 5 | 1 | 1.6667 | 1 | 4 | 2.5 | 2.5 | 1.5 | 1.3333 | 2.5 | 2.5 | 1 | 2.5 | 1.5 | 2 | 1 | 1.3333 | 1 | 2.5 | 2.5 | 1.6667 | 1 | 2 | 3 | 2 | 2 | 1 | 1.6667 | 1.5 | 1.3333 | 1 | 1 | 1 | 1 | 2.5 | 1 | 1 | 1 | 1.5 | 1 | 5 | 1 | 5 | 1.6667 | 1 | 1.5 | 2.5 | 2 | 1 | 1.3333 | 1 | 1
90 | 12 | 10 | 19 | 28 | 37.8333 | 43.8333 | 48.8333 | 54.3333 | 59.8333 | 72.8333 | 80.8333 | 86.3333 | 92 | 102.5 | 4 | 3 | 2 | 1 | 1 | 1 | 5 | 2 | 2 | 5 | 1 | 1 | 4 | 2 | 2.5 | 1.3333 | 1 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 1.5 | 1 | 1 | 1.5 | 2 | 1 | 5 | 5 | 1 | 2 | 1 | 1.6667 | 1.3333 | 4 | 2 | 1.5 | 1 | 1 | 1 | 2 | 1.6667 | 1 | 4 | 4 | 1.5 | 1
91 | 11 | 7 | 14 | 23.6667 | 29.1667 | 38.6667 | 46.1667 | 53.6667 | 59.8333 | 68.8333 | 76.3333 | 86.3333 | 94.6667 | 100.8333 | 3 | 1 | 2 | 1 | 2.5 | 1.5 | 1.3333 | 1.6667 | 1.6667 | 5 | 1 | 2 | 1 | 2.5 | 1 | 1 | 3 | 1 | 4 | 1.5 | 2.5 | 1 | 2 | 2 | 2.5 | 2 | 1 | 2 | 1.6667 | 2 | 1 | 1.5 | 4 | 1 | 2 | 2 | 2.5 | 1 | 1 | 3 | 3 | 1 | 1 | 5 | 1 | 5 | 1.3333 | 1 | 1.6667 | 1.5 | 1 | 2
92 | 16.5 | 13.5 | 20.1667 | 28.1667 | 34 | 38.3333 | 45.5 | 51.5 | 59 | 64 | 72 | 86.5 | 98.8333 | 108.1667 | 3 | 5 | 4 | 1.5 | 1 | 2 | 1.6667 | 2 | 1 | 4 | 1.6667 | 1.3333 | 1.3333 | 2.5 | 1 | 1 | 1 | 1.3333 | 1 | 1 | 2.5 | 2 | 1 | 1.6667 | 1 | 1 | 2.5 | 1.5 | 1.5 | 1 | 2.5 | 2.5 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 5 | 5 | 2.5 | 5 | 2 | 1 | 1.3333 | 5 | 5 | 5 | 1.3333 | 2 | 1
93 | 7.6667 | 4.6667 | 13.6667 | 21 | 30 | 36 | 40.6667 | 48.3333 | 59.6667 | 66.6667 | 72.6667 | 80.1667 | 86.1667 | 90.1667 | 1.3333 | 1 | 1.3333 | 1 | 2 | 1 | 1 | 5 | 1.3333 | 1 | 1 | 4 | 1.3333 | 1.6667 | 1 | 5 | 3 | 1 | 1 | 1 | 1 | 1.6667 | 1 | 1 | 1.6667 | 1 | 2 | 3 | 1 | 4 | 5 | 1.3333 | 2 | 1 | 2 | 2 | 2 | 1 | 2 | 1 | 3 | 2.5 | 1 | 1 | 2 | 1.3333 | 1 | 1.6667 | 1 | 1 | 1 | 1
94 | 13.5 | 10.5 | 17.5 | 30.5 | 36.8333 | 44.3333 | 53.1667 | 59.5 | 70.8333 | 76.8333 | 84.8333 | 89.6667 | 100.6667 | 106.1667 | 1.5 | 5 | 3 | 1 | 2 | 1 | 2 | 2 | 1 | 2 | 5 | 5 | 2 | 1 | 1.3333 | 2 | 2 | 2.5 | 2 | 1 | 2.5 | 1 | 1.3333 | 4 | 1.5 | 1.3333 | 2.5 | 1 | 1.3333 | 2.5 | 5 | 2.5 | 2 | 1 | 1 | 2 | 4 | 1.6667 | 1.3333 | 1 | 1.3333 | 1.5 | 1 | 1 | 2.5 | 2.5 | 1 | 5 | 2 | 1.5 | 1 | 1
95 | 7 | 5 | 9.3333 | 19.5 | 25.5 | 34.5 | 40 | 47.5 | 56.3333 | 64.8333 | 70.3333 | 76.8333 | 83.8333 | 93.8333 | 1 | 1 | 1.5 | 1.5 | 1 | 1 | 1.3333 | 1 | 2.5 | 4 | 1.6667 | 2 | 1 | 1 | 3 | 1 | 2 | 5 | 1 | 1 | 1 | 1 | 1.5 | 2 | 1 | 1 | 1.5 | 4 | 5 | 1.3333 | 1 | 1.5 | 2.5 | 1.5 | 2.5 | 2 | 2.5 | 1 | 1 | 1 | 2 | 1 | 2 | 1.5 | 1 | 1 | 4 | 1 | 4 | 1 | 1 | 4
96 | 11 | 6 | 16 | 27.3333 | 34.3333 | 40 | 46.8333 | 54.5 | 62.5 | 76.1667 | 85 | 91.3333 | 101.8333 | 110.6667 | 2.5 | 1 | 1.5 | 1 | 4 | 1 | 3 | 2 | 5 | 1.6667 | 1.6667 | 3 | 1 | 3 | 2 | 1 | 1 | 1.6667 | 1.6667 | 1.3333 | 1.3333 | 1 | 2 | 2.5 | 2.5 | 1.6667 | 2.5 | 1 | 1 | 1 | 5 | 1 | 1.6667 | 5 | 5 | 2 | 1.5 | 1 | 5 | 1.3333 | 1.3333 | 1 | 2 | 2 | 1.3333 | 5 | 2.5 | 1.6667 | 1 | 1.3333 | 1.5 | 5
97 | 17 | 11 | 22 | 30.6667 | 38.3333 | 44 | 53.6667 | 64.1667 | 69.3333 | 81.3333 | 87.8333 | 95.3333 | 104.8333 | 111 | 4 | 1.5 | 3 | 2.5 | 2 | 4 | 4 | 1 | 1 | 1 | 5 | 1.6667 | 1 | 4 | 1 | 1.6667 | 2 | 1 | 1.6667 | 1 | 2 | 1.6667 | 3 | 3 | 1 | 2 | 5 | 2.5 | 1 | 1 | 1.6667 | 1.5 | 5 | 4 | 2 | 1 | 2 | 1 | 2.5 | 1 | 1.6667 | 2 | 1.3333 | 2.5 | 2.5 | 1 | 4 | 2 | 2.5 | 1 | 1 | 1.6667
98 | 9 | 5 | 15 | 24.6667 | 33 | 39 | 43.8333 | 52.8333 | 59.8333 | 66.8333 | 71.1667 | 75.8333 | 81.8333 | 86.6667 | 1 | 1 | 1 | 2 | 1 | 3 | 5 | 1 | 1.5 | 2.5 | 4 | 1.6667 | 1.3333 | 5 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1.5 | 1 | 1.3333 | 1 | 2 | 4 | 2 | 4 | 1 | 1 | 1 | 2 | 1 | 1 | 3 | 1 | 1 | 1.3333 | 1 | 1.3333 | 1.3333 | 1 | 1 | 1 | 3 | 1 | 1 | 1.3333 | 1 | 1.5 | 1
99 | 10 | 6 | 13.5 | 19.5 | 29.5 | 36.5 | 41.3333 | 45.6667 | 54.6667 | 65.6667 | 72.1667 | 79.8333 | 89.3333 | 95.3333 | 1 | 1 | 3 | 1 | 1 | 3 | 1 | 2.5 | 1.5 | 1 | 1 | 2.5 | 2 | 1 | 5 | 2 | 4 | 1 | 1 | 1 | 1.3333 | 1 | 1.5 | 1 | 1 | 1.3333 | 1 | 1 | 5 | 2 | 1 | 1 | 1 | 1 | 5 | 4 | 2 | 2.5 | 1 | 1 | 1.6667 | 3 | 1.3333 | 1.6667 | 1 | 1 | 5 | 2.5 | 1 | 2 | 1.3333 | 1.6667
100 | 9 | 7 | 11.6667 | 20.6667 | 32.1667 | 41.3333 | 50 | 58.8333 | 64.5 | 72 | 81.3333 | 89 | 98.5 | 107.5 | 1 | 2 | 2.5 | 1.5 | 1 | 1 | 1 | 1.6667 | 5 | 2 | 1 | 1 | 5 | 3 | 2.5 | 1 | 1 | 5 | 1.6667 | 1.5 | 1.6667 | 1 | 5 | 1 | 1 | 1.3333 | 1.5 | 5 | 1.6667 | 2 | 1 | 1 | 1 | 4 | 1.5 | 1 | 2 | 5 | 1 | 1.3333 | 4 | 1 | 1 | 1.6667 | 1 | 1.5 | 5 | 2 | 2 | 5 | 1 | 1
101 | 18.5 | 12.5 | 27.5 | 36.1667 | 43.1667 | 51 | 59 | 66.6667 | 72.3333 | 81.3333 | 88.5 | 97 | 106 | 110 | 2 | 5 | 4 | 1.5 | 4 | 2 | 4 | 5 | 1 | 1 | 5 | 1.6667 | 1 | 4 | 1 | 1 | 1 | 1.5 | 1.3333 | 4 | 2 | 4 | 1 | 1 | 4 | 1 | 1.6667 | 1 | 1.6667 | 1.3333 | 1.6667 | 1 | 1 | 5 | 2 | 1 | 2 | 1.6667 | 2.5 | 1 | 2.5 | 3 | 1 | 2 | 1 | 1 | 5 | 2 | 1 | 1 | 1 | 1
102 | 10 | 7.3333 | 13 | 19.8333 | 27.8333 | 33.1667 | 39.1667 | 43.5 | 52.5 | 58.8333 | 67.8333 | 77.8333 | 82.8333 | 89.3333 | 1.3333 | 1 | 2 | 3 | 1.3333 | 1.3333 | 2 | 1 | 1.3333 | 1 | 2.5 | 2 | 1 | 2 | 1 | 4 | 1 | 1.6667 | 1 | 1.6667 | 1.3333 | 1.6667 | 2 | 1 | 1.3333 | 1 | 1 | 1 | 2 | 1 | 2 | 4 | 1.6667 | 1 | 1.6667 | 2 | 2 | 1 | 5 | 1 | 4 | 1 | 4 | 1 | 1 | 1 | 1.6667 | 1.3333 | 1.5 | 1 | 3 | 1
103 | 15 | 13 | 19 | 30.1667 | 35.8333 | 41.1667 | 46.1667 | 55.8333 | 62.3333 | 67.8333 | 76.3333 | 81.5 | 87.1667 | 94.5 | 3 | 2 | 5 | 3 | 1 | 1 | 3 | 1 | 4 | 2.5 | 1.6667 | 3 | 1 | 1.6667 | 1 | 2 | 1.6667 | 1 | 1 | 1.6667 | 2 | 1 | 1 | 1 | 1.6667 | 1 | 4 | 3 | 1.5 | 1 | 3 | 1 | 1 | 1 | 2 | 1.5 | 1.5 | 1 | 1 | 5 | 1.5 | 1 | 1 | 1.6667 | 1.3333 | 1 | 2 | 1.3333 | 1.3333 | 1 | 1 | 4
104 | 15 | 9 | 18.5 | 25.8333 | 39.8333 | 48.8333 | 58.6667 | 67.6667 | 78.6667 | 84.6667 | 90.3333 | 94.3333 | 99.8333 | 107.8333 | 3 | 1 | 3 | 2 | 5 | 1 | 1 | 2.5 | 4 | 1.3333 | 1 | 1 | 1 | 5 | 3 | 5 | 2 | 2 | 3 | 2 | 5 | 1.3333 | 1 | 2.5 | 1.3333 | 2 | 4 | 1.6667 | 1 | 1 | 5 | 4 | 2 | 1 | 1 | 2 | 1.6667 | 1.3333 | 1 | 1.6667 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2.5 | 3 | 1 | 1 | 3
105 | 11.5 | 5.5 | 14.5 | 22.5 | 27 | 34 | 39.1667 | 46.1667 | 53.1667 | 58.6667 | 67.3333 | 74.3333 | 78.8333 | 87.5 | 2.5 | 1 | 1 | 1 | 1 | 5 | 1 | 2 | 2 | 1 | 2.5 | 2.5 | 1.5 | 1 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 1.5 | 1.6667 | 1 | 4 | 1 | 1 | 1 | 2 | 1 | 1 | 3 | 1.5 | 1 | 2 | 1 | 1 | 1.6667 | 4 | 2 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1.5 | 1 | 1.6667 | 5 | 1
106 | 10.6667 | 8 | 13 | 18.6667 | 23.6667 | 34.5 | 41.5 | 49.5 | 58.1667 | 64.8333 | 76.5 | 83.8333 | 90.6667 | 102.6667 | 1 | 4 | 1 | 2 | 1 | 1.6667 | 1.3333 | 1 | 2 | 1.6667 | 1 | 1 | 1 | 2 | 1 | 1 | 1.3333 | 5 | 2 | 2.5 | 2.5 | 2.5 | 1 | 1 | 5 | 1 | 1 | 1 | 1.3333 | 5 | 1 | 1.3333 | 1 | 1.6667 | 2 | 2 | 3 | 5 | 1.6667 | 2 | 1.5 | 1.3333 | 2 | 2.5 | 1.5 | 1.3333 | 1 | 3 | 5 | 1 | 5 | 1
107 | 17.1667 | 10.1667 | 19.1667 | 24.1667 | 33.1667 | 43.3333 | 49.1667 | 54.1667 | 61.6667 | 70.6667 | 78.6667 | 89.1667 | 97.6667 | 104.6667 | 1 | 5 | 2.5 | 1.6667 | 5 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 1.5 | 1.5 | 5 | 1 | 1.5 | 3 | 1.6667 | 4 | 2 | 1.3333 | 1.5 | 1 | 1 | 1 | 1 | 2 | 1.5 | 2 | 3 | 1 | 3 | 2.5 | 2.5 | 1 | 2.5 | 1 | 2 | 2.5 | 3 | 1.5 | 5 | 1 | 1 | 2.5 | 2 | 3 | 1 | 2 | 3 | 1
108 | 8 | 5 | 11 | 19 | 30.6667 | 36.3333 | 43 | 48 | 57 | 65.6667 | 71.5 | 80.5 | 87 | 93 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 5 | 1 | 1 | 3 | 2 | 1.6667 | 5 | 1.6667 | 2 | 1 | 1 | 1 | 2 | 2 | 1.6667 | 1 | 2 | 1 | 1 | 1 | 2 | 3 | 3 | 1 | 5 | 1 | 1.6667 | 1 | 1 | 2.5 | 1.3333 | 2 | 5 | 1 | 1 | 1 | 1 | 1.5 | 3 | 2 | 1 | 1 | 2
109 | 7.3333 | 4.3333 | 10.8333 | 15.8333 | 22.8333 | 28.8333 | 36 | 40.6667 | 46.8333 | 53 | 60.8333 | 69.3333 | 74.6667 | 80.6667 | 1 | 1 | 1 | 1.3333 | 2 | 1 | 1.5 | 2 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 2 | 1 | 1.5 | 1.5 | 2 | 1 | 1.5 | 3 | 1.6667 | 1 | 1 | 1.6667 | 1 | 1 | 2 | 1.6667 | 1.5 | 1.3333 | 2.5 | 1.3333 | 1 | 3 | 1 | 1.3333 | 2.5 | 1 | 2.5 | 1 | 4 | 2 | 1 | 1 | 1.3333 | 2 | 2 | 1 | 1
110 | 9.5 | 4.5 | 17.5 | 25 | 31 | 39.5 | 46.8333 | 50.8333 | 60.8333 | 70.1667 | 78.5 | 83.1667 | 92.3333 | 99.8333 | 1 | 1.5 | 1 | 1 | 1 | 4 | 3 | 5 | 1 | 2.5 | 2 | 2 | 1 | 3 | 1 | 1 | 3 | 1.5 | 2 | 2 | 2 | 3 | 1 | 1.3333 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 5 | 5 | 1 | 1.3333 | 2 | 1 | 4 | 2 | 1.3333 | 1 | 1 | 1.6667 | 1 | 1 | 4 | 1.6667 | 2.5 | 2 | 2.5 | 1 | 2
111 | 8 | 5 | 11 | 17.1667 | 21.5 | 28 | 39 | 47 | 55.8333 | 60.1667 | 67.5 | 73.5 | 85.5 | 93.5 | 2 | 1 | 1 | 1 | 1.5 | 1.5 | 1 | 2 | 2 | 1.5 | 1 | 1.6667 | 1 | 1.3333 | 1 | 1 | 1 | 1.5 | 1 | 3 | 1 | 2.5 | 2.5 | 5 | 2.5 | 2.5 | 1 | 2 | 4 | 1 | 1.3333 | 2.5 | 1 | 1 | 1 | 1.3333 | 2 | 1.3333 | 1 | 3 | 1 | 3 | 1 | 1 | 2 | 3 | 4 | 3 | 3 | 1 | 3 | 1
112 | 15.5 | 9.5 | 21.8333 | 28.8333 | 34.5 | 40 | 45.5 | 53.5 | 64 | 75 | 81.5 | 87.3333 | 96.3333 | 102.8333 | 2 | 1.5 | 2 | 4 | 5 | 1 | 5 | 1.3333 | 1 | 1 | 1 | 4 | 1 | 1.6667 | 1 | 2 | 1.5 | 1 | 1 | 2 | 2.5 | 1 | 1 | 1 | 1.3333 | 1 | 4 | 1.6667 | 3 | 1.5 | 4 | 2 | 2 | 5 | 3 | 1 | 1 | 1 | 2 | 2.5 | 1.3333 | 1.5 | 1 | 2 | 1.5 | 2.5 | 1 | 4 | 1 | 2.5 | 2 | 1
113 | 14.6667 | 8 | 16.6667 | 25 | 31.6667 | 43.6667 | 49.1667 | 54.1667 | 60.1667 | 70.5 | 76.5 | 82.3333 | 90.3333 | 99 | 5 | 1 | 1 | 1 | 5 | 1.6667 | 1 | 1 | 1 | 1.3333 | 2 | 4 | 1.5 | 2.5 | 1.3333 | 1.3333 | 5 | 1 | 5 | 1 | 1 | 1.5 | 2 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 2 | 1.6667 | 4 | 3 | 1.6667 | 1 | 1.5 | 1 | 2.5 | 1.5 | 1.3333 | 1 | 2 | 1 | 2 | 3 | 2 | 5 | 1.3333 | 1 | 1.3333
114 | 10.6667 | 7.5 | 13.3333 | 19 | 25 | 33.5 | 47 | 55.3333 | 61.3333 | 68 | 77 | 81.5 | 87 | 97.5 | 3 | 1 | 1.5 | 2 | 1.6667 | 1.5 | 1.6667 | 1 | 1 | 1.6667 | 1.5 | 1.5 | 2 | 1 | 1 | 2 | 1 | 5 | 1 | 1.5 | 5 | 5 | 2.5 | 1 | 1.6667 | 4 | 1.3333 | 1.3333 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1.6667 | 4 | 1 | 1 | 3 | 1 | 1.5 | 1 | 1 | 2.5 | 1 | 1 | 1 | 1.5 | 4 | 4 | 1
115 | 11.3333 | 6 | 19.3333 | 24.1667 | 32.1667 | 40.1667 | 46.5 | 57.1667 | 67.8333 | 80.8333 | 90.5 | 94.8333 | 101.8333 | 107.8333 | 1 | 1 | 1 | 3 | 4 | 1.3333 | 4 | 4 | 1.3333 | 1 | 1 | 1.5 | 1.5 | 1 | 3 | 2.5 | 4 | 2 | 1 | 1 | 2 | 1 | 1.6667 | 1.6667 | 1.5 | 2.5 | 5 | 1.6667 | 5 | 1.6667 | 1 | 3 | 5 | 3 | 1 | 4 | 5 | 1 | 2 | 1.6667 | 1 | 1 | 1.3333 | 1 | 2.5 | 1 | 2 | 1.5 | 1 | 1.5 | 1.5 | 2
116 | 13.1667 | 9.6667 | 15.5 | 21 | 29.6667 | 42.3333 | 50 | 55 | 64 | 74 | 78 | 85.3333 | 93.6667 | 99.3333 | 1.6667 | 5 | 2 | 1 | 2.5 | 1 | 1.3333 | 1 | 1.5 | 1 | 2 | 1 | 4 | 2 | 1.6667 | 1 | 3 | 1.6667 | 4 | 4 | 1 | 1.6667 | 3 | 2 | 2 | 1 | 1 | 1 | 2 | 4 | 2 | 1 | 1.5 | 4 | 1.5 | 3 | 1 | 1 | 1 | 1 | 1 | 2.5 | 2.5 | 1.3333 | 1 | 5 | 1 | 1.3333 | 1.6667 | 1 | 1 | 2
117 | 12.1667 | 8 | 16.6667 | 23.1667 | 32.1667 | 40.1667 | 48.1667 | 54.3333 | 60.5 | 67.6667 | 74.1667 | 82.1667 | 90.1667 | 96 | 1 | 2 | 1 | 4 | 1.6667 | 2.5 | 2.5 | 2 | 1 | 2.5 | 1 | 2 | 4 | 3 | 1 | 1 | 1 | 5 | 1 | 1 | 2 | 4 | 1 | 1 | 1 | 1.6667 | 2.5 | 1 | 1 | 2.5 | 1.6667 | 1 | 1.6667 | 1.5 | 3 | 1 | 1 | 2 | 2 | 1.5 | 1 | 2 | 4 | 1 | 1 | 1 | 5 | 1 | 1.3333 | 1 | 1 | 2.5
118 | 13.8333 | 9.8333 | 18.8333 | 26.5 | 34.6667 | 47.1667 | 53.1667 | 57.5 | 64.8333 | 74.3333 | 80.1667 | 88.5 | 95.5 | 105.6667 | 2.5 | 1.3333 | 5 | 1 | 2 | 2 | 4 | 1 | 2.5 | 2.5 | 1.6667 | 1 | 2 | 1.6667 | 2 | 2.5 | 4 | 5 | 2 | 1.5 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1.3333 | 1.3333 | 1 | 1 | 4 | 2 | 4 | 1 | 2.5 | 1.3333 | 2 | 1.5 | 1 | 5 | 1 | 1.3333 | 1 | 1 | 1 | 3 | 2 | 5 | 2 | 1.5 | 1.6667
119 | 11.3333 | 4.8333 | 14 | 22.8333 | 28.5 | 34.8333 | 39.8333 | 48.3333 | 52.6667 | 58 | 68 | 74 | 82 | 87.5 | 1 | 1.3333 | 1 | 1.5 | 2.5 | 4 | 1 | 1.6667 | 2.5 | 1.3333 | 3 | 2 | 1 | 1 | 2 | 1.6667 | 3 | 1 | 1 | 1.3333 | 1 | 1 | 2 | 1 | 1 | 1.5 | 1 | 5 | 1 | 1 | 1 | 1.3333 | 1.6667 | 1 | 1 | 1.6667 | 1 | 3 | 5 | 1 | 3 | 1 | 1 | 1 | 1 | 4 | 2 | 1 | 1 | 1 | 2 | 1.5
120 | 12.1667 | 8.6667 | 18.1667 | 24.1667 | 33.1667 | 38.1667 | 49.1667 | 58.5 | 62.8333 | 67.5 | 75.3333 | 81.3333 | 90 | 96.5 | 1 | 5 | 1.6667 | 1 | 1 | 2.5 | 5 | 1 | 2 | 1 | 2 | 1 | 1 | 2 | 5 | 1 | 1.5 | 1.5 | 1 | 1 | 1 | 4 | 1 | 5 | 1.3333 | 1.5 | 1.5 | 5 | 1 | 1.3333 | 1 | 1 | 1 | 1 | 1.3333 | 1.3333 | 1.3333 | 3 | 2 | 1.5 | 3 | 1 | 1 | 1 | 1.6667 | 4 | 1 | 2 | 1 | 1 | 1.5 | 3
121 | 14 | 10.5 | 18.6667 | 23.6667 | 32 | 38.1667 | 44 | 51 | 59.3333 | 66 | 73 | 78 | 85 | 98.6667 | 2 | 2 | 2.5 | 4 | 1 | 2.5 | 3 | 1.6667 | 1.5 | 1 | 1 | 1.5 | 1 | 1 | 1.3333 | 5 | 1.3333 | 1.3333 | 2 | 1.5 | 1.3333 | 2 | 1.5 | 1 | 1 | 3 | 2 | 1 | 1 | 1 | 5 | 1.3333 | 2.5 | 1.5 | 1.6667 | 1 | 1 | 1 | 2 | 3 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 3 | 1.6667 | 3 | 4 | 5
122 | 15.6667 | 11 | 20.6667 | 29.3333 | 36.3333 | 42.3333 | 48.1667 | 53.6667 | 62.6667 | 70.1667 | 75.3333 | 80.3333 | 86 | 94 | 4 | 3 | 3 | 1 | 3 | 1.6667 | 1 | 4 | 1 | 1.6667 | 4 | 2 | 3 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 1.3333 | 1 | 2.5 | 1 | 1 | 2 | 1.5 | 1 | 5 | 1 | 2 | 1 | 2 | 1.3333 | 2.5 | 1.6667 | 1 | 1.5 | 1 | 1.6667 | 2 | 1 | 1 | 1 | 1.6667 | 1 | 2 | 1 | 1 | 5 | 1 | 1
123 | 10 | 6.5 | 15 | 24.8333 | 33.3333 | 43.3333 | 48.8333 | 57.5 | 69 | 78.1667 | 87.1667 | 91.1667 | 99.1667 | 104.6667 | 2.5 | 1 | 2 | 1 | 2.5 | 1 | 1 | 4 | 5 | 1.3333 | 2.5 | 1 | 3 | 1 | 1.5 | 3 | 5 | 1.5 | 2.5 | 1 | 1.5 | 1 | 1 | 2 | 1.6667 | 2 | 2 | 3 | 2.5 | 2.5 | 4 | 2.5 | 1.6667 | 4 | 2.5 | 1 | 2 | 3 | 1 | 3 | 1 | 1 | 1 | 1 | 2 | 1 | 2.5 | 2.5 | 2.5 | 1 | 1 | 1
124 | 15.5 | 11 | 20.1667 | 27.1667 | 35.8333 | 40.8333 | 46.3333 | 59 | 70 | 78 | 84 | 89.5 | 103.5 | 110.5 | 4 | 2 | 4 | 1 | 2 | 2.5 | 3 | 1.6667 | 1 | 3 | 1 | 2 | 4 | 1.6667 | 1.3333 | 1.6667 | 1.6667 | 1 | 1.3333 | 1 | 1 | 1 | 1 | 2.5 | 1.6667 | 4 | 5 | 2 | 4 | 4 | 1 | 2 | 5 | 1 | 1 | 1 | 1.6667 | 2 | 1 | 1.3333 | 2.5 | 1 | 1 | 1 | 4 | 2.5 | 2.5 | 5 | 1 | 1 | 4 | 1
125 | 10.5 | 6 | 12.8333 | 28.8333 | 36.5 | 44.8333 | 50.1667 | 58.1667 | 68 | 78.5 | 83.5 | 89.5 | 94.1667 | 100.1667 | 1.5 | 2.5 | 1 | 1 | 2.5 | 2 | 1 | 1.3333 | 5 | 5 | 3 | 3 | 3 | 2 | 1 | 1.6667 | 2 | 2.5 | 2.5 | 1.3333 | 1 | 1.3333 | 2 | 1 | 1 | 1 | 5 | 1 | 2.5 | 2 | 1.3333 | 4 | 2.5 | 3 | 1 | 4 | 1 | 1.5 | 1.5 | 1 | 1 | 1 | 2 | 2 | 1 | 1.6667 | 1 | 1 | 1 | 1.5 | 2 | 1.5
126 | 13.8333 | 7.8333 | 17.5 | 28.6667 | 36.1667 | 43.6667 | 57 | 64 | 71.3333 | 76 | 80.6667 | 86.3333 | 93.5 | 98.5 | 1 | 4 | 1.3333 | 1.5 | 1 | 5 | 2 | 1.6667 | 4 | 1.6667 | 1.5 | 4 | 4 | 1 | 1.5 | 1 | 3 | 2 | 1.5 | 1 | 5 | 5 | 2 | 1.3333 | 3 | 1 | 1 | 2 | 1 | 1.3333 | 4 | 1 | 1 | 1 | 1 | 1.6667 | 1 | 1.6667 | 1 | 1 | 1 | 1 | 1.6667 | 2 | 2 | 1.6667 | 2.5 | 1 | 1 | 2 | 1 | 1
127 | 8.3333 | 5 | 11 | 17.5 | 22.8333 | 31.8333 | 36.8333 | 44.3333 | 51.1667 | 59.1667 | 65.3333 | 71.5 | 77.1667 | 85.3333 | 1 | 1 | 1 | 2 | 1.3333 | 2 | 1.6667 | 1 | 1 | 2.5 | 2 | 1 | 1 | 1.6667 | 1.6667 | 1 | 1 | 1 | 2 | 5 | 1.5 | 1.5 | 1 | 1 | 1 | 3 | 2.5 | 1 | 2.5 | 2 | 1.3333 | 1 | 2 | 4 | 1 | 1 | 1 | 1.6667 | 2.5 | 1 | 1 | 1.3333 | 1.3333 | 2.5 | 1 | 1 | 1.6667 | 2 | 2 | 3 | 1.5 | 1.6667
128 | 9.6667 | 4.3333 | 12 | 18.6667 | 26.3333 | 34.5 | 43 | 49.5 | 57.5 | 67.5 | 74.8333 | 84.3333 | 93.3333 | 100.8333 | 1 | 1 | 1.3333 | 1 | 1.3333 | 4 | 1.3333 | 1 | 2 | 2 | 1 | 1.6667 | 1.6667 | 4 | 1 | 1 | 1.5 | 2.5 | 2.5 | 1.6667 | 1.5 | 1 | 4 | 2 | 1 | 1.6667 | 2.5 | 1.3333 | 1.6667 | 1 | 1.3333 | 4 | 2 | 5 | 1 | 2 | 1.3333 | 1 | 2.5 | 2.5 | 4 | 2 | 2.5 | 1 | 1.6667 | 5 | 1.3333 | 1 | 3 | 2 | 1.5 | 1
129 | 15.5 | 11.5 | 18.8333 | 25 | 30 | 44.3333 | 51.1667 | 60.1667 | 68.1667 | 81.1667 | 91.6667 | 97.6667 | 106.3333 | 113.8333 | 4 | 2.5 | 2 | 3 | 1 | 3 | 1.6667 | 1.6667 | 1 | 2.5 | 1 | 1.6667 | 1 | 2 | 1 | 1 | 5 | 4 | 1.3333 | 4 | 1.6667 | 1.6667 | 1 | 2.5 | 1 | 2 | 5 | 1 | 2 | 1 | 1 | 4 | 1 | 2 | 5 | 5 | 2.5 | 4 | 3 | 1 | 1.6667 | 1 | 1.6667 | 1.6667 | 1.6667 | 4 | 1 | 2 | 1 | 2 | 2 | 2.5
130 | 11 | 6.5 | 15.6667 | 23.6667 | 29.5 | 34.6667 | 42.5 | 50.1667 | 55.6667 | 62.8333 | 69.3333 | 80.3333 | 89 | 95.5 | 2 | 2.5 | 1 | 1 | 1.5 | 3 | 1.6667 | 3 | 1 | 1 | 3 | 3 | 2.5 | 1 | 1.3333 | 1 | 1.5 | 1 | 1.6667 | 1 | 1 | 1.3333 | 4 | 1.5 | 1.6667 | 2.5 | 1 | 2.5 | 1 | 1.3333 | 1.5 | 1.6667 | 1.6667 | 2.5 | 2 | 1 | 2.5 | 1 | 1 | 2 | 1 | 2.5 | 2.5 | 5 | 1 | 2 | 4 | 1.6667 | 1 | 1 | 2 | 2.5
131 | 10.8333 | 7 | 14.3333 | 23.8333 | 30.1667 | 39.6667 | 46.3333 | 50.6667 | 57.3333 | 69 | 77.1667 | 83.1667 | 89.1667 | 96.1667 | 1 | 3 | 1 | 2 | 1.3333 | 2.5 | 1 | 2.5 | 4 | 2 | 1.5 | 2 | 1.6667 | 1.6667 | 2 | 1 | 3 | 1 | 3 | 2.5 | 1.5 | 1.5 | 2 | 1.6667 | 1.3333 | 1 | 1 | 1 | 1 | 2.5 | 1.6667 | 1.5 | 1.3333 | 1.3333 | 4 | 5 | 4 | 1 | 1.5 | 1.6667 | 3 | 1 | 1 | 1 | 1.3333 | 2 | 1 | 1.6667 | 1 | 1 | 4 | 1
132 | 11.3333 | 7.1667 | 14.3333 | 18.8333 | 22.8333 | 31.8333 | 36.3333 | 46.3333 | 51.6667 | 64.6667 | 70 | 77 | 88.5 | 93.5 | 1.3333 | 2 | 1.3333 | 2.5 | 2.5 | 1.6667 | 1.5 | 1.5 | 1 | 1 | 1.5 | 1 | 1 | 1 | 1 | 1 | 2 | 4 | 2 | 1 | 1 | 1 | 1 | 1.5 | 5 | 1 | 2 | 2 | 1.6667 | 1 | 1.6667 | 1 | 5 | 2.5 | 1.5 | 4 | 1 | 2 | 1 | 1.3333 | 1 | 4 | 1 | 1 | 2.5 | 5 | 2 | 2 | 1 | 2 | 1 | 1
133 | 9 | 6.1667 | 12.5 | 21 | 27 | 32 | 41.5 | 49.5 | 59 | 68 | 78 | 83.6667 | 90.3333 | 100.8333 | 1 | 2.5 | 1.6667 | 1 | 1.5 | 1.3333 | 1 | 2.5 | 2 | 1 | 2.5 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 4 | 2.5 | 1.5 | 1 | 2.5 | 3 | 1 | 1 | 5 | 2.5 | 4 | 1 | 1 | 3 | 1 | 1 | 5 | 3 | 2 | 1 | 1.3333 | 1.3333 | 1 | 1 | 1.6667 | 3 | 5 | 1 | 3 | 1.5
134 | 12.5 | 10.5 | 15.5 | 23 | 27.3333 | 37 | 42.6667 | 51.6667 | 63.1667 | 69.3333 | 74.3333 | 80.1667 | 85.1667 | 94.5 | 2 | 1 | 2.5 | 5 | 1 | 1 | 2 | 1 | 1.5 | 1 | 1 | 4 | 1 | 1.3333 | 1 | 1 | 4 | 1 | 3 | 1.6667 | 1.6667 | 1.6667 | 1.3333 | 1 | 3 | 1 | 2.5 | 2.5 | 1.5 | 4 | 2 | 4 | 2.5 | 1 | 1.6667 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1.3333 | 2.5 | 1 | 1 | 2 | 1 | 1 | 1.3333 | 5 | 2
135 | 11.3333 | 5.3333 | 13.3333 | 21.3333 | 28.6667 | 35.3333 | 42.3333 | 49.3333 | 54.8333 | 60.8333 | 68.8333 | 78 | 84.1667 | 90.8333 | 2 | 1 | 1 | 1.3333 | 5 | 1 | 1 | 1 | 2 | 4 | 1 | 1 | 4 | 1 | 1 | 1.3333 | 2 | 1.6667 | 1 | 2 | 1 | 1 | 4 | 1 | 3 | 1 | 2 | 1 | 1 | 1 | 2.5 | 1 | 1 | 2.5 | 1.5 | 1 | 2 | 3 | 1 | 2 | 1.6667 | 1 | 2.5 | 4 | 1.6667 | 1 | 2.5 | 1 | 1.5 | 1 | 2.5 | 1.6667
136 | 10.8333 | 6.3333 | 14.5 | 25.8333 | 33.1667 | 39.1667 | 47.5 | 52.1667 | 57.1667 | 69.6667 | 80.1667 | 84.5 | 93.5 | 99.5 | 2.5 | 1 | 1.3333 | 1.5 | 2 | 2.5 | 2 | 1.6667 | 1.3333 | 4 | 3 | 3 | 1.3333 | 2.5 | 2.5 | 1 | 1.5 | 1 | 1 | 2.5 | 1 | 5 | 1.3333 | 1 | 1 | 1.6667 | 1 | 1 | 1.6667 | 1 | 1 | 1.3333 | 4 | 1 | 2.5 | 5 | 3 | 1 | 5 | 1.5 | 1.3333 | 1 | 1 | 1 | 1 | 2 | 5 | 1 | 1.6667 | 2 | 1 | 1.3333
137 | 15 | 9 | 18.5 | 26.5 | 32.5 | 41.8333 | 49.8333 | 54.6667 | 59.5 | 64.5 | 71.5 | 80.5 | 87.1667 | 92.1667 | 1 | 4 | 3 | 1 | 4 | 2 | 1 | 2.5 | 1.3333 | 4 | 1 | 1.6667 | 1 | 2 | 2 | 1 | 4 | 1 | 3 | 1.3333 | 1 | 1 | 1 | 5 | 1.3333 | 1 | 1 | 1.5 | 1 | 1.5 | 1.3333 | 1 | 1 | 2 | 1 | 1 | 3 | 2 | 1 | 1 | 1 | 5 | 2 | 1 | 2 | 2 | 1.6667 | 1 | 1 | 1 | 2 | 1
138 | 13 | 6 | 15 | 21.5 | 29.1667 | 38.6667 | 46.3333 | 54.5 | 58.5 | 63.5 | 68 | 76 | 82 | 91.5 | 1 | 1 | 3 | 1 | 4 | 3 | 1 | 1 | 1.3333 | 2.5 | 1 | 1.6667 | 1.6667 | 3 | 1 | 2 | 1 | 1 | 5 | 2.5 | 4 | 1 | 1.6667 | 1 | 1.6667 | 1.5 | 2.5 | 2.5 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1.5 | 1 | 1 | 1 | 1 | 1 | 1 | 5 | 2 | 2 | 1 | 1 | 5 | 1 | 2.5 | 1
139 | 12.6667 | 10.6667 | 16.6667 | 26.6667 | 33.8333 | 43.1667 | 53 | 64.3333 | 74.8333 | 84.5 | 91 | 103 | 114.5 | 120.1667 | 1.6667 | 4 | 3 | 2 | 1 | 1 | 3 | 1 | 5 | 2 | 2 | 1 | 1 | 2 | 2.5 | 1.6667 | 2 | 1.6667 | 4 | 1.6667 | 5 | 1.3333 | 2.5 | 1 | 1 | 1.3333 | 4 | 5 | 3 | 1 | 4 | 2.5 | 3 | 4 | 1 | 1.6667 | 2 | 1 | 1.5 | 2 | 3 | 4 | 1 | 4 | 1 | 5 | 1.5 | 4 | 1.6667 | 1.3333 | 1 | 1.6667
140 | 8.3333 | 5.3333 | 11.3333 | 17.6667 | 27.1667 | 35.1667 | 44.5 | 56.5 | 69.5 | 82.5 | 87.1667 | 97.1667 | 105.8333 | 114.1667 | 1.3333 | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1.6667 | 1.6667 | 2 | 1.5 | 1 | 3 | 4 | 1.3333 | 1.6667 | 2 | 3 | 3 | 1 | 4 | 1.3333 | 1 | 4 | 2 | 5 | 2 | 5 | 5 | 1 | 4 | 1 | 4 | 4 | 1.6667 | 1 | 1 | 1 | 5 | 1 | 1.5 | 2.5 | 5 | 1 | 1.6667 | 1 | 1 | 1.3333 | 1 | 5
141 | 15.5 | 10 | 21.8333 | 28.3333 | 38.3333 | 45 | 51.1667 | 55.8333 | 63.3333 | 75.3333 | 82.5 | 94.5 | 104.1667 | 113.3333 | 3 | 1.3333 | 1.6667 | 4 | 1.5 | 4 | 5 | 1.3333 | 1.5 | 3 | 1 | 1 | 2 | 2 | 1 | 5 | 3 | 1 | 1.3333 | 1.3333 | 1.6667 | 2 | 1 | 1.5 | 1 | 1 | 1.6667 | 1 | 1 | 2 | 2 | 2.5 | 4 | 1 | 2 | 5 | 1.3333 | 1.3333 | 2 | 2.5 | 5 | 1 | 1 | 5 | 1.3333 | 1.3333 | 4 | 3 | 1 | 4 | 2.5 | 1.6667
142 | 9 | 6.5 | 11.6667 | 18.6667 | 29.6667 | 34.8333 | 47 | 54.5 | 65 | 71.1667 | 76.3333 | 87.3333 | 93.3333 | 100.8333 | 1.3333 | 2.5 | 1 | 1.6667 | 1 | 1.5 | 1.6667 | 1 | 1 | 1 | 2 | 3 | 2 | 2.5 | 2.5 | 4 | 1.6667 | 1.5 | 1 | 1 | 2.5 | 1.6667 | 5 | 3 | 3 | 1 | 2 | 1.5 | 2.5 | 4 | 1 | 3 | 1.6667 | 1 | 2 | 1.5 | 1 | 1.6667 | 1.5 | 1 | 4 | 1 | 5 | 1 | 3 | 1 | 1 | 1 | 1 | 2.5 | 1 | 3
143 | 12.3333 | 10.3333 | 16.8333 | 22.5 | 28 | 33.3333 | 39.1667 | 43.8333 | 49 | 61 | 72 | 76 | 81.8333 | 86.8333 | 4 | 1.3333 | 4 | 1 | 1 | 1 | 2.5 | 2 | 2 | 1 | 1 | 1.6667 | 1 | 1.5 | 2 | 1 | 1.3333 | 1.6667 | 1.3333 | 1 | 2 | 1.5 | 1 | 1.3333 | 1 | 1.6667 | 1 | 1 | 1.6667 | 1 | 1 | 1.5 | 3 | 1 | 5 | 3 | 1 | 4 | 1 | 5 | 1 | 1 | 1 | 1 | 1.5 | 2 | 1.3333 | 1 | 1 | 1 | 2 | 1
144 | 12.1667 | 9 | 15.6667 | 21.1667 | 29.1667 | 34.5 | 46.5 | 54.1667 | 63.8333 | 71.1667 | 76.5 | 82 | 91.5 | 96.8333 | 1 | 3 | 4 | 1 | 1.5 | 1.6667 | 1 | 2.5 | 1 | 1 | 1.5 | 2 | 1 | 1 | 4 | 2 | 1.6667 | 1.3333 | 1 | 1.3333 | 2.5 | 2.5 | 5 | 2 | 1 | 1.6667 | 1 | 4 | 5 | 2 | 1.6667 | 1 | 1 | 1.6667 | 3 | 1.6667 | 1.6667 | 1 | 1 | 1.6667 | 1.5 | 1 | 1 | 2 | 5 | 1 | 1 | 2.5 | 1.6667 | 1.6667 | 1 | 1
145 | 11 | 9 | 14.3333 | 21.3333 | 30.3333 | 37.8333 | 41.8333 | 49.8333 | 58.6667 | 62.6667 | 70.6667 | 78.1667 | 85.6667 | 96 | 1 | 5 | 1 | 2 | 1 | 1 | 1.6667 | 1.6667 | 1 | 1 | 4 | 1 | 3 | 4 | 1 | 1 | 1.5 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 1.5 | 4 | 1 | 1.5 | 1.3333 | 5 | 1.5 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 4 | 1 | 1 | 1.5 | 2.5 | 3 | 1 | 1 | 4 | 1 | 1.3333 | 4
146 | 14 | 9 | 17.6667 | 23.3333 | 27.3333 | 38.8333 | 47.8333 | 53.8333 | 61.3333 | 67.8333 | 73.8333 | 80.6667 | 91.5 | 96.5 | 5 | 2 | 1 | 1 | 4 | 1 | 2 | 1.6667 | 1 | 1 | 2 | 1.6667 | 1 | 1 | 1 | 1 | 2 | 5 | 3 | 1.5 | 1 | 3 | 2 | 3 | 1 | 1 | 1.5 | 2.5 | 2.5 | 1.5 | 1.5 | 2 | 3 | 1 | 1 | 1.5 | 1 | 1 | 3 | 1 | 2.5 | 2 | 1 | 1.3333 | 1.6667 | 2.5 | 1.6667 | 5 | 1.6667 | 1 | 1.3333 | 1
147 | 13.3333 | 10.3333 | 15.3333 | 23.3333 | 33.3333 | 38.8333 | 47.8333 | 58.3333 | 65.6667 | 70.6667 | 75 | 85.3333 | 96.3333 | 103 | 2 | 4 | 1.3333 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 4 | 2 | 3 | 1 | 5 | 1 | 1 | 2.5 | 1 | 1 | 2.5 | 1.5 | 1 | 4 | 2 | 5 | 1 | 2.5 | 1.3333 | 1 | 1 | 4 | 1 | 2 | 1 | 1 | 1 | 1.3333 | 1 | 1 | 4 | 1.3333 | 3 | 2 | 4 | 4 | 1 | 2 | 1.6667 | 2.5 | 1 | 1.5
148 | 15 | 9 | 17 | 28.5 | 33.5 | 40.5 | 48.5 | 53.5 | 58.5 | 65.1667 | 73.1667 | 82.1667 | 91.5 | 98.1667 | 1 | 4 | 2.5 | 1.5 | 4 | 2 | 1 | 1 | 3 | 1 | 2.5 | 5 | 1 | 1 | 1 | 2 | 4 | 1 | 1 | 1 | 1 | 4 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 3 | 1.6667 | 2 | 1 | 3 | 2 | 1.5 | 4 | 1 | 2.5 | 3 | 4 | 1 | 1.3333 | 1 | 3 | 1 | 1.6667
149 | 7.5 | 4 | 10.5 | 20.5 | 29.6667 | 39.6667 | 49.6667 | 64.1667 | 68.5 | 74.5 | 80 | 85.5 | 95.5 | 102 | 1 | 1 | 1 | 1 | 2 | 1.5 | 2 | 1 | 4 | 1 | 4 | 1 | 2.5 | 1.6667 | 4 | 1 | 1 | 3 | 5 | 1 | 1 | 1 | 4 | 4 | 4 | 1.5 | 4 | 5 | 1.3333 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 2 | 1.5 | 1 | 1 | 1 | 1 | 2.5 | 3 | 2 | 1 | 4 | 1 | 1 | 2 | 2.5
150 | 10 | 8 | 13 | 23.5 | 35 | 40 | 45 | 56 | 62 | 67 | 71 | 76.5 | 84.8333 | 88.8333 | 4 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 3 | 4 | 1 | 2.5 | 3 | 3 | 4 | 1.5 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 5 | 1 | 1 | 4 | 2.5 | 1.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 2.5 | 1 | 1 | 1 | 1.6667 | 3 | 2 | 1.6667 | 1 | 1 | 1 | 1
151 | 14.8333 | 12.5 | 20.8333 | 26.8333 | 34.8333 | 40.1667 | 49.1667 | 55.6667 | 62.5 | 66.8333 | 72.3333 | 79.8333 | 86.5 | 92.8333 | 5 | 4 | 2.5 | 1 | 1 | 1.3333 | 1 | 5 | 2 | 1 | 2 | 1 | 1.5 | 2.5 | 1 | 3 | 1.3333 | 2 | 1 | 1 | 1 | 5 | 1.5 | 1.5 | 2 | 2 | 1 | 1.5 | 1.3333 | 1 | 3 | 1.5 | 1.3333 | 1 | 1 | 1 | 1.5 | 1 | 1 | 2 | 1 | 2 | 2 | 2.5 | 3 | 1 | 1.6667 | 1 | 1.6667 | 1.6667 | 2 | 1
152 | 14 | 11 | 19 | 24.6667 | 30.8333 | 38.1667 | 42.8333 | 52.6667 | 60.3333 | 72 | 78.5 | 86.5 | 92.3333 | 97.3333 | 1 | 1 | 4 | 5 | 1.5 | 1.5 | 2 | 3 | 2 | 1 | 1 | 1.6667 | 2.5 | 1 | 1 | 1.6667 | 2 | 2.5 | 1.5 | 1.3333 | 1.6667 | 1 | 1 | 1 | 1 | 1.3333 | 5 | 2.5 | 2 | 2 | 2 | 1.6667 | 1 | 1.6667 | 5 | 4 | 1.5 | 1 | 1 | 3 | 1.6667 | 1.3333 | 1 | 4 | 1.3333 | 1 | 1 | 2.5 | 1 | 2 | 1 | 1
153 | 12 | 9 | 14.5 | 18.5 | 23.5 | 34.5 | 43 | 50 | 62 | 68 | 77.3333 | 87.5 | 93.5 | 98.5 | 5 | 1 | 1 | 2 | 1 | 2 | 1 | 1.5 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 5 | 4 | 1 | 1 | 4 | 2 | 1.5 | 1 | 2 | 2 | 1 | 2 | 5 | 3 | 3 | 1 | 2 | 2 | 1 | 1 | 1.3333 | 2.5 | 3 | 2.5 | 1.6667 | 3 | 1.5 | 4 | 3 | 1 | 1 | 1 | 1.3333 | 1.6667 | 1 | 1
154 | 10.6667 | 5.3333 | 14.3333 | 18.3333 | 26.3333 | 34.6667 | 40.5 | 46 | 54.5 | 60.1667 | 71.1667 | 77.5 | 82.8333 | 90.3333 | 2 | 1 | 1 | 1.3333 | 4 | 1.3333 | 2 | 1.6667 | 1 | 1 | 1 | 1 | 1 | 2 | 4 | 1 | 1.3333 | 1 | 3 | 3 | 1 | 2.5 | 1 | 1.3333 | 1 | 1 | 2.5 | 1 | 1.6667 | 1.3333 | 3 | 2.5 | 1.3333 | 1 | 1.3333 | 2 | 5 | 4 | 1 | 1 | 1.3333 | 1.5 | 1 | 2.5 | 1 | 1.3333 | 2 | 1 | 3 | 1.5 | 2 | 1
155 | 17.6667 | 13.6667 | 20.6667 | 31 | 37.8333 | 51.8333 | 58 | 71 | 82 | 93.5 | 100.3333 | 106.8333 | 114.8333 | 123.5 | 1.6667 | 5 | 2 | 5 | 1 | 3 | 1.3333 | 1.6667 | 3 | 1 | 1.3333 | 5 | 3 | 1.5 | 1.3333 | 1 | 4 | 5 | 4 | 1 | 1 | 1.6667 | 2.5 | 1 | 5 | 2 | 4 | 2 | 1 | 3 | 4 | 3 | 2 | 2 | 5 | 2.5 | 2 | 2 | 1.3333 | 1.5 | 1.6667 | 2.5 | 1.3333 | 1 | 5 | 1 | 1 | 1 | 3 | 1.6667 | 2 | 2
156 | 9.3333 | 6.1667 | 16.8333 | 27.8333 | 38.5 | 44 | 49.1667 | 57.1667 | 67.6667 | 75.6667 | 81.1667 | 90.1667 | 95.5 | 108 | 1.3333 | 2 | 1.3333 | 1.5 | 1.5 | 1.6667 | 2.5 | 5 | 1 | 2.5 | 5 | 2.5 | 1.6667 | 3 | 5 | 1 | 1 | 2.5 | 1 | 1 | 1.5 | 1.3333 | 1 | 1.3333 | 1 | 1 | 2 | 4 | 5 | 1 | 3 | 1.5 | 1 | 1 | 5 | 1 | 1.5 | 2 | 1 | 1 | 1 | 2.5 | 4 | 1.5 | 1.3333 | 2 | 1 | 1 | 1 | 2.5 | 4 | 5
157 | 9.5 | 6.8333 | 11.5 | 21.5 | 29.8333 | 37 | 44.3333 | 51.3333 | 58.8333 | 64.8333 | 74.5 | 80 | 86.3333 | 97.3333 | 1 | 2.5 | 2 | 1.3333 | 1.6667 | 1 | 1 | 1 | 1 | 2 | 5 | 2 | 1.3333 | 1 | 2 | 4 | 1.6667 | 1.5 | 1.5 | 2.5 | 1 | 1.3333 | 1 | 4 | 1 | 4 | 1 | 1 | 2.5 | 1 | 1 | 3 | 1.5 | 2.5 | 1 | 1 | 4 | 1 | 3 | 1.6667 | 1 | 1.5 | 2 | 1 | 1.3333 | 2 | 2 | 1 | 1 | 3 | 2 | 5
158 | 10.5 | 8 | 13.5 | 19.5 | 27.1667 | 35.1667 | 44 | 54.1667 | 63.3333 | 68.3333 | 83.3333 | 93.1667 | 101.6667 | 110.6667 | 1 | 1 | 3 | 3 | 1.5 | 1 | 2 | 1 | 1.3333 | 1.6667 | 2 | 1 | 1 | 1.6667 | 4 | 1 | 1 | 1 | 2 | 4 | 2.5 | 1 | 1.3333 | 4 | 1 | 1.6667 | 2.5 | 5 | 1 | 2.5 | 1.6667 | 4 | 1 | 2 | 1 | 1 | 5 | 1 | 4 | 5 | 1.3333 | 4 | 1.5 | 3 | 1 | 1.5 | 5 | 1 | 5 | 1 | 1 | 2
159 | 12.6667 | 10 | 14.6667 | 21.6667 | 29 | 36.5 | 40.8333 | 50.5 | 56.8333 | 64.8333 | 71.5 | 75.8333 | 82.6667 | 89.1667 | 1 | 2 | 4 | 3 | 1 | 1.6667 | 1 | 1 | 1 | 1 | 1 | 4 | 1 | 1.3333 | 3 | 2 | 4 | 1 | 1.5 | 1 | 1 | 1 | 1 | 1.3333 | 1.6667 | 2.5 | 4 | 1.5 | 2 | 1.6667 | 1.6667 | 1 | 1 | 1 | 1 | 5 | 1 | 2 | 2 | 1.6667 | 1 | 1 | 1 | 1.3333 | 1 | 2.5 | 1.3333 | 2 | 2.5 | 1 | 1 | 2
160 | 16 | 12.5 | 20.1667 | 25.8333 | 34.5 | 40.8333 | 48.1667 | 53.1667 | 59.6667 | 69.8333 | 77.3333 | 87.8333 | 92.8333 | 103.1667 | 1.5 | 2 | 4 | 5 | 2.5 | 1 | 2.5 | 1.6667 | 1 | 1.6667 | 1 | 2 | 1.6667 | 1 | 4 | 2 | 1 | 3 | 1 | 1.3333 | 2 | 3 | 1.3333 | 1 | 1 | 1 | 1 | 2 | 1.5 | 1 | 3 | 1 | 1.5 | 5 | 2 | 1.6667 | 2.5 | 1 | 3 | 1 | 1 | 4 | 1.5 | 4 | 1 | 1 | 1 | 2 | 1 | 1.3333 | 4 | 4
161 | 10 | 7 | 13.3333 | 18 | 26 | 31.5 | 38.5 | 46.6667 | 53.1667 | 59.6667 | 64.8333 | 71.8333 | 78.5 | 82.8333 | 1.3333 | 1 | 3 | 1.6667 | 2 | 1 | 1.3333 | 2 | 1 | 1.6667 | 1 | 1 | 2 | 4 | 1 | 1 | 1.5 | 1 | 2 | 1 | 3 | 1 | 2 | 1 | 4 | 1 | 1.6667 | 1.5 | 1 | 2 | 1 | 2.5 | 1 | 1 | 2.5 | 2 | 1 | 1.5 | 1 | 1.6667 | 3 | 2 | 1 | 1 | 2 | 1 | 2 | 1.6667 | 1 | 1 | 1.3333 | 1
162 | 13.6667 | 9.6667 | 16.1667 | 28.5 | 32.5 | 37.5 | 45.8333 | 51.3333 | 58 | 64.5 | 73.5 | 77.5 | 86.8333 | 93.3333 | 2 | 1.6667 | 5 | 1 | 3 | 1 | 1 | 1.5 | 5 | 4 | 1.3333 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1.6667 | 1 | 1.6667 | 4 | 1 | 1 | 1.5 | 2 | 1.6667 | 1.5 | 1 | 2.5 | 1 | 2.5 | 1 | 2 | 1 | 4 | 1 | 3 | 1 | 1 | 1 | 1 | 2.5 | 4 | 1.3333 | 1.5 | 1 | 1.3333 | 1.6667 | 2.5
163 | 13.5 | 10 | 17.5 | 23.6667 | 29.8333 | 35.8333 | 50.8333 | 56.8333 | 63.5 | 67.5 | 76.1667 | 86.1667 | 90.1667 | 95.6667 | 4 | 3 | 2 | 1 | 2.5 | 1 | 1 | 3 | 1.3333 | 1.3333 | 1 | 2.5 | 2.5 | 1 | 1.6667 | 1 | 3 | 1 | 1 | 1 | 5 | 4 | 3 | 3 | 1 | 1 | 2 | 2 | 3 | 1 | 1.6667 | 1 | 1 | 1 | 1 | 1 | 1 | 5 | 1.6667 | 1 | 2 | 1 | 4 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1.5 | 2
164 | 13.3333 | 11 | 16.3333 | 22 | 30.1667 | 36.1667 | 44.1667 | 50.6667 | 55.6667 | 63.3333 | 69.8333 | 78.5 | 87 | 91 | 1 | 4 | 4 | 2 | 1.3333 | 1 | 1 | 2 | 1.5 | 1 | 1.6667 | 1.5 | 1.6667 | 3 | 1 | 2.5 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 5 | 1 | 1.5 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1.6667 | 2 | 3 | 2 | 1.5 | 1 | 2 | 1.6667 | 1.6667 | 4 | 1.3333 | 3 | 1.5 | 1.5 | 2.5 | 1 | 1 | 1 | 1
165 | 7 | 5 | 9 | 15.5 | 23.3333 | 33 | 41.1667 | 47.1667 | 52.1667 | 58.6667 | 63 | 68 | 76 | 83 | 1.6667 | 1 | 1 | 1.3333 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 2.5 | 4 | 1 | 1.3333 | 1.5 | 2 | 5 | 1 | 1.6667 | 3 | 1 | 1.6667 | 2.5 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1.5 | 3 | 1 | 1 | 1 | 1.3333 | 1.5 | 1.5 | 1 | 1 | 2 | 2 | 2 | 2 | 2.5 | 1.5 | 1 | 2
166 | 15.3333 | 11.3333 | 20.6667 | 27 | 34.6667 | 43.6667 | 51.6667 | 61.5 | 67.5 | 75.5 | 80 | 89 | 93.6667 | 103.3333 | 1.3333 | 4 | 2 | 4 | 2 | 2 | 1.3333 | 4 | 1.3333 | 1 | 1 | 3 | 1.6667 | 3 | 2 | 1 | 2 | 3 | 3 | 1 | 2 | 1 | 3 | 2 | 1.3333 | 1 | 2.5 | 5 | 1 | 3 | 1 | 1 | 1 | 5 | 1 | 1 | 1 | 1 | 1.5 | 1 | 3 | 1 | 1 | 4 | 1 | 1 | 1.6667 | 1 | 3 | 1.6667 | 4 | 1
167 | 9.6667 | 7 | 11.6667 | 19.6667 | 24.1667 | 29.8333 | 36.6667 | 46.1667 | 52.6667 | 58.6667 | 63.8333 | 73.8333 | 80 | 88.3333 | 1 | 2 | 1 | 3 | 1.6667 | 1 | 1 | 1 | 3 | 2.5 | 1.5 | 1 | 1 | 1 | 1.5 | 1 | 1 | 1.6667 | 2 | 1 | 1.5 | 2.5 | 1.5 | 1.3333 | 2.5 | 2 | 4 | 1 | 1 | 2.5 | 1 | 2 | 1 | 2.5 | 1 | 1.5 | 1.5 | 1.6667 | 1 | 1 | 5 | 1 | 3 | 1 | 1 | 2.5 | 1 | 1.6667 | 4 | 1.3333 | 1 | 2
168 | 10 | 5.6667 | 12 | 23.3333 | 32.1667 | 42.3333 | 46.3333 | 51.3333 | 57.8333 | 63.3333 | 71 | 75 | 86 | 95.5 | 1 | 1.6667 | 1 | 2 | 3 | 1.3333 | 1 | 1 | 1.3333 | 2 | 5 | 3 | 1.3333 | 3 | 3 | 1.5 | 1.6667 | 5 | 2.5 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2.5 | 1 | 2 | 2 | 1.5 | 1 | 1 | 1.6667 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 4 | 4 | 1 | 2.5 | 1 | 5
169 | 12.5 | 9.5 | 21.5 | 26.5 | 35 | 46 | 55.3333 | 68 | 75.5 | 85 | 89.6667 | 94.1667 | 103.6667 | 112 | 2.5 | 1 | 5 | 1 | 1 | 2 | 4 | 5 | 1 | 1 | 1 | 2 | 1 | 1 | 1.5 | 5 | 1.3333 | 5 | 1.6667 | 3 | 1 | 4 | 1.3333 | 3 | 1.6667 | 1 | 5 | 5 | 1 | 1 | 4 | 1.5 | 1.5 | 3 | 2.5 | 2.5 | 1 | 1.6667 | 1 | 1 | 1.5 | 1 | 1 | 1 | 4 | 1 | 1.5 | 3 | 4 | 2 | 1 | 1.3333
170 | 11.8333 | 9.1667 | 16.5 | 23.8333 | 30.8333 | 35.3333 | 45.1667 | 56.8333 | 68.3333 | 76 | 90.3333 | 96.3333 | 107.3333 | 114.3333 | 1.6667 | 3 | 2.5 | 2 | 1 | 1.6667 | 1.6667 | 3 | 1 | 3 | 2 | 1.3333 | 1 | 4 | 1 | 1 | 1 | 1.5 | 1 | 1 | 2.5 | 1.3333 | 1 | 5 | 5 | 4 | 1.6667 | 1 | 4 | 2 | 4 | 1.5 | 3 | 1.6667 | 1 | 2 | 5 | 4 | 4 | 1.3333 | 1 | 1 | 3 | 1 | 4 | 5 | 1 | 1 | 2 | 1 | 3 | 1
171 | 16 | 12 | 19.3333 | 27.3333 | 32.1667 | 37.5 | 46.8333 | 53.8333 | 61.1667 | 70.3333 | 80.3333 | 88.8333 | 94.8333 | 106.3333 | 5 | 1 | 2 | 4 | 3 | 1 | 1.3333 | 2 | 3 | 1 | 2 | 2 | 1 | 1.3333 | 1.5 | 1 | 1.3333 | 1 | 2 | 1 | 5 | 1.3333 | 1 | 2 | 2 | 2 | 1 | 2 | 2.5 | 2.5 | 1 | 1.3333 | 1.5 | 1.6667 | 1 | 5 | 4 | 2.5 | 1 | 2.5 | 2.5 | 1 | 2.5 | 2.5 | 2 | 1 | 1.6667 | 1.3333 | 3 | 2.5 | 5 | 1
172 | 12.3333 | 10 | 18.3333 | 24.5 | 31.1667 | 36.8333 | 44.8333 | 50.6667 | 57 | 65 | 70 | 75.8333 | 81.8333 | 90.8333 | 4 | 2.5 | 2.5 | 1 | 1.3333 | 1 | 5 | 1 | 1.6667 | 1 | 1 | 2.5 | 1.6667 | 1 | 1.5 | 2.5 | 1.6667 | 2 | 1 | 1 | 1 | 3 | 2 | 2 | 2.5 | 1 | 1 | 1.3333 | 1 | 2.5 | 1.5 | 1.3333 | 5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2.5 | 1.3333 | 1 | 1 | 2.5 | 1 | 1.5 | 4 | 1.6667 | 2 | 1.3333
173 | 12 | 6 | 16.1667 | 21.1667 | 29.6667 | 38.1667 | 48.5 | 55.3333 | 61.6667 | 70.1667 | 80.5 | 86 | 96.5 | 102 | 1 | 1 | 3 | 1 | 1 | 5 | 1.6667 | 2.5 | 1 | 1.3333 | 1 | 1.6667 | 1 | 4 | 2.5 | 1 | 1 | 5 | 1 | 1.5 | 1.3333 | 1 | 3 | 5 | 1.3333 | 3 | 1 | 1.5 | 1 | 2 | 2 | 1.3333 | 2 | 2.5 | 2 | 2 | 5 | 1.3333 | 3 | 1 | 1 | 2 | 1.5 | 1 | 2 | 1 | 5 | 2.5 | 2.5 | 1 | 1 | 1
174 | 8.5 | 6.5 | 13.5 | 25 | 30.6667 | 38.6667 | 43 | 49.3333 | 59.3333 | 65.3333 | 75 | 82 | 90.3333 | 99.3333 | 1.5 | 1 | 1 | 3 | 1 | 1 | 3 | 2 | 2.5 | 5 | 2 | 2 | 2 | 1 | 1.6667 | 1 | 4 | 1.5 | 1.5 | 1 | 1.3333 | 1 | 1 | 1 | 1.6667 | 1.6667 | 1.5 | 1.5 | 1 | 1 | 3 | 5 | 1 | 3 | 1 | 1 | 1.6667 | 4 | 3 | 1 | 1 | 2 | 3 | 1 | 1 | 5 | 1.3333 | 1 | 5 | 1 | 1.6667 | 1.3333
175 | 12 | 8 | 14 | 24 | 31.5 | 42.1667 | 46.1667 | 51.8333 | 61.8333 | 67.8333 | 73.5 | 77.5 | 85.1667 | 91.6667 | 1 | 5 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 4 | 4 | 3 | 1.5 | 2 | 1 | 1.6667 | 5 | 1 | 3 | 1 | 1 | 1 | 1 | 1.6667 | 1.3333 | 1.3333 | 1.3333 | 4 | 1 | 1 | 4 | 1 | 1 | 1 | 3 | 2 | 1.3333 | 1 | 1.3333 | 1 | 1 | 1 | 1 | 1 | 4 | 1.6667 | 1 | 1.5 | 1 | 3 | 1
176 | 12.3333 | 9.3333 | 15.6667 | 22.3333 | 29 | 37.6667 | 45.3333 | 53 | 63 | 68.6667 | 76.6667 | 82 | 93 | 97.5 | 4 | 3 | 1.3333 | 1 | 1 | 2 | 1.3333 | 2 | 1.5 | 2.5 | 1.6667 | 1 | 3 | 1.3333 | 1 | 1.3333 | 4 | 1.5 | 1.6667 | 1.5 | 1.6667 | 4 | 1 | 1 | 1.6667 | 4 | 1 | 1 | 2 | 4 | 2 | 2 | 1 | 1.6667 | 1.6667 | 1.3333 | 1.5 | 2.5 | 1 | 3 | 2 | 1.3333 | 1 | 1 | 4 | 5 | 1 | 1 | 1 | 1.5 | 1 | 1
177 | 13 | 10 | 16.5 | 26.8333 | 34.8333 | 44.3333 | 50.6667 | 59.5 | 66.1667 | 74.8333 | 82.8333 | 93.3333 | 101.3333 | 107 | 2 | 1 | 2 | 5 | 1.5 | 1.5 | 2.5 | 1 | 1 | 5 | 1.3333 | 3 | 1 | 2 | 4 | 1 | 5 | 1 | 1 | 2.5 | 3 | 1 | 1.3333 | 1 | 1.3333 | 1 | 2.5 | 4 | 1 | 1.6667 | 1 | 3 | 1 | 5 | 1 | 1.6667 | 1 | 1 | 1 | 5 | 5 | 2 | 1 | 2.5 | 1 | 2 | 2 | 3 | 1.6667 | 1 | 1 | 2
178 | 10.5 | 8 | 15.5 | 21 | 30.6667 | 39 | 46 | 56.3333 | 63.3333 | 68.6667 | 74.1667 | 82.1667 | 96.3333 | 101.3333 | 5 | 1 | 1 | 1 | 1.5 | 1 | 4 | 1 | 1 | 1 | 2.5 | 1 | 5 | 1 | 1.6667 | 2 | 2.5 | 2 | 2.5 | 1.3333 | 1 | 1 | 4 | 1 | 1.3333 | 2.5 | 1.5 | 5 | 3 | 2 | 1 | 1 | 1 | 1 | 2 | 1.3333 | 1.5 | 1.6667 | 1.3333 | 1 | 4 | 2 | 1 | 1 | 1.6667 | 5 | 2.5 | 5 | 2 | 1 | 1 | 1
179 | 14.6667 | 12.6667 | 18.8333 | 25 | 31.1667 | 36.5 | 43.5 | 51.6667 | 57 | 66 | 72.5 | 79.8333 | 84.6667 | 90.6667 | 1.6667 | 4 | 2 | 5 | 1 | 1 | 2.5 | 1.6667 | 1 | 2.5 | 1.6667 | 1 | 1 | 1.3333 | 1.3333 | 2.5 | 1.3333 | 1 | 2 | 1 | 1 | 1 | 1 | 4 | 4 | 1.6667 | 1.5 | 1 | 1 | 1 | 2 | 1.3333 | 1 | 2 | 4 | 2 | 2 | 2.5 | 1 | 1 | 1 | 1 | 1.3333 | 4 | 1.3333 | 1.5 | 1 | 1 | 1 | 1 | 1 | 3
180 | 12.6667 | 5.6667 | 18.6667 | 27.6667 | 35.6667 | 43.6667 | 49.1667 | 55.6667 | 68 | 73.6667 | 78.6667 | 89.6667 | 102.6667 | 107.1667 | 1 | 1.6667 | 2 | 1 | 5 | 2 | 5 | 1 | 2 | 1 | 1 | 5 | 1 | 2 | 1 | 4 | 1 | 2 | 4 | 1 | 1.5 | 1 | 1 | 2 | 1.3333 | 2.5 | 1.6667 | 1 | 5 | 5 | 1.3333 | 1 | 2 | 1 | 1 | 1.6667 | 1 | 1.5 | 1 | 1.5 | 3 | 1.5 | 4 | 2.5 | 5 | 3 | 4 | 1 | 1 | 1.5 | 1 | 1
181 | 9.5 | 6.3333 | 18.5 | 23.8333 | 29.1667 | 38.1667 | 42.6667 | 51.1667 | 61.1667 | 66 | 72.5 | 80.5 | 86.8333 | 98.3333 | 1.3333 | 1 | 3 | 1 | 1.5 | 1.6667 | 5 | 4 | 2 | 1 | 1.3333 | 1 | 1 | 1 | 2 | 1.3333 | 5 | 1 | 2 | 1 | 1 | 1.5 | 1 | 1 | 2.5 | 3 | 1 | 2 | 1 | 4 | 1 | 4 | 1 | 1.5 | 1.3333 | 1 | 1 | 2.5 | 1.6667 | 1.3333 | 1 | 4 | 2 | 1 | 1 | 2 | 2 | 1.3333 | 5 | 1 | 2.5 | 3
182 | 14.6667 | 8.6667 | 18.6667 | 25 | 34.5 | 42.5 | 54.5 | 62 | 68.8333 | 74.1667 | 84.5 | 91.1667 | 100.1667 | 109.8333 | 3 | 1.6667 | 1 | 3 | 5 | 1 | 3 | 1 | 2 | 2 | 1 | 1.3333 | 1 | 5 | 1 | 2.5 | 2.5 | 2 | 1 | 2.5 | 1 | 5 | 1 | 5 | 1 | 1.5 | 4 | 1 | 1 | 2.5 | 2 | 1.3333 | 1.3333 | 1 | 2 | 1 | 1 | 3 | 5 | 1.3333 | 1 | 1.6667 | 1 | 3 | 1 | 1 | 4 | 3 | 2 | 1.6667 | 5 | 1
183 | 6.8333 | 4.3333 | 9.5 | 15.5 | 25 | 29.6667 | 42.1667 | 53.1667 | 65 | 74 | 86.3333 | 94 | 100 | 108.5 | 1 | 1 | 1 | 1.3333 | 1.5 | 1 | 1.6667 | 1 | 3 | 1 | 1 | 1 | 2.5 | 5 | 1 | 1 | 1.6667 | 1 | 1 | 1 | 4 | 1 | 5 | 2.5 | 5 | 3 | 1 | 2 | 5 | 1.3333 | 4 | 1.5 | 3 | 3 | 1 | 2 | 1.3333 | 2 | 4 | 5 | 1 | 1.6667 | 4 | 1 | 1 | 1.6667 | 2 | 1.3333 | 2 | 2.5 | 3 | 1
184 | 13.5 | 10 | 18.5 | 31.5 | 37.5 | 48.5 | 54.6667 | 59.3333 | 64.6667 | 71 | 77.5 | 82 | 89.3333 | 94.8333 | 2 | 2 | 1 | 5 | 2.5 | 1 | 3 | 2 | 3 | 5 | 4 | 1 | 1.6667 | 2 | 1 | 1.3333 | 5 | 1 | 1 | 4 | 1 | 1.5 | 1.6667 | 2 | 1 | 1 | 1 | 1.6667 | 1.3333 | 1 | 2 | 1 | 1 | 1.3333 | 1 | 3 | 2.5 | 1 | 2 | 1 | 1 | 1 | 1 | 1.5 | 1.3333 | 3 | 2 | 1 | 1 | 1 | 2.5 | 1
185 | 16.6667 | 13.6667 | 20.1667 | 28.5 | 35.1667 | 41.1667 | 48 | 53.5 | 62.5 | 69.5 | 77 | 82.8333 | 88 | 93.6667 | 1.6667 | 3 | 4 | 5 | 2 | 1 | 1 | 2.5 | 2 | 1.3333 | 2 | 3 | 2 | 1 | 2 | 1.6667 | 2 | 1 | 2 | 1 | 2 | 1 | 1.3333 | 2.5 | 1 | 2 | 1 | 1.5 | 1 | 4 | 1 | 3 | 1 | 1 | 2 | 3 | 1 | 1 | 4 | 1.5 | 2.5 | 1.3333 | 1 | 1 | 1 | 1.6667 | 1.5 | 1 | 1 | 2 | 1 | 1.6667
186 | 8.3333 | 6 | 14.3333 | 21.3333 | 29.3333 | 37.3333 | 42.3333 | 47.1667 | 52.6667 | 59.5 | 68 | 77.5 | 86.5 | 93 | 1 | 2 | 1 | 2 | 1 | 1.3333 | 4 | 2 | 1 | 1 | 2.5 | 2.5 | 1 | 5 | 1 | 1 | 4 | 1.3333 | 1 | 1.6667 | 2 | 1 | 1 | 1 | 1.5 | 1 | 1 | 1.3333 | 1.5 | 1 | 2 | 1 | 1.3333 | 1 | 3 | 1.5 | 1 | 4 | 2.5 | 1 | 5 | 2 | 1 | 1.5 | 2 | 1.5 | 2.5 | 3 | 1 | 1.5 | 2 | 2
187 | 8.6667 | 5.6667 | 11.3333 | 20 | 26.5 | 33.5 | 44.5 | 50 | 58 | 72.5 | 78 | 88.5 | 95.3333 | 99.8333 | 1 | 2 | 1 | 1.6667 | 1 | 2 | 1.6667 | 1 | 1.6667 | 1.5 | 1.5 | 4 | 2.5 | 1 | 2 | 1 | 1 | 3 | 1 | 2 | 4 | 2 | 2 | 3 | 1 | 2 | 1.5 | 1 | 2 | 1 | 2 | 3 | 3 | 4 | 5 | 2.5 | 1 | 1.5 | 2 | 1 | 2 | 4 | 1.5 | 3 | 1.6667 | 1 | 1.6667 | 2.5 | 1.5 | 1 | 1 | 1
188 | 12.5 | 10.5 | 19.5 | 26.5 | 33.5 | 43 | 49.5 | 57.8333 | 63.8333 | 68.8333 | 75.3333 | 88.3333 | 92.3333 | 101.8333 | 1 | 4 | 4 | 1.5 | 1 | 1 | 2 | 5 | 2 | 1.6667 | 1.3333 | 2 | 2 | 1 | 2.5 | 1.5 | 1 | 5 | 1 | 2.5 | 1 | 2 | 1.5 | 2 | 1 | 1.3333 | 1 | 5 | 1.5 | 2.5 | 1 | 1 | 1 | 1.3333 | 1 | 1.6667 | 1 | 2 | 1 | 2.5 | 5 | 1 | 2 | 5 | 1 | 1 | 1 | 1 | 1.5 | 4 | 2 | 2
189 | 15 | 8 | 19.6667 | 26.1667 | 35.5 | 42 | 48.1667 | 52.6667 | 57.6667 | 62.1667 | 70.1667 | 81.5 | 90 | 99 | 1 | 2 | 1 | 4 | 5 | 2 | 1.6667 | 3 | 1 | 2.5 | 2 | 1 | 1.3333 | 1.6667 | 1.3333 | 5 | 2.5 | 1 | 1 | 2 | 1.6667 | 1 | 2 | 1.5 | 1 | 1 | 1.5 | 1 | 1.5 | 1 | 1.5 | 1 | 1 | 1.5 | 1 | 1 | 5 | 1 | 1 | 1 | 5 | 4 | 1.3333 | 1 | 2.5 | 4 | 1 | 1 | 1 | 2 | 4 | 2
190 | 7.3333 | 4 | 9.3333 | 20.3333 | 25.3333 | 30.3333 | 37.8333 | 47.3333 | 59.6667 | 68.6667 | 80.6667 | 93 | 105 | 111.6667 | 1 | 1 | 1 | 1 | 2 | 1.3333 | 1 | 1 | 1 | 5 | 2.5 | 2.5 | 1.3333 | 1.6667 | 1 | 1 | 2 | 1 | 1 | 1 | 2.5 | 2 | 2 | 1 | 2 | 3 | 2.5 | 2 | 4 | 2 | 1.3333 | 5 | 5 | 1.5 | 1.5 | 1 | 4 | 1 | 3 | 4 | 4 | 1.3333 | 3 | 4 | 5 | 2.5 | 2.5 | 2 | 3 | 1 | 1.6667 | 1
191 | 10.6667 | 8 | 16.6667 | 25.5 | 38.1667 | 48.8333 | 52.8333 | 57.6667 | 66.5 | 73 | 81.3333 | 88.3333 | 96.3333 | 106.3333 | 3 | 2 | 2 | 1 | 1 | 1.6667 | 1 | 5 | 1.5 | 1 | 5 | 1.3333 | 1 | 1.6667 | 5 | 5 | 5 | 1.6667 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1.5 | 1.3333 | 1 | 2.5 | 1.3333 | 4 | 1 | 3 | 1.5 | 1 | 5 | 1 | 1.3333 | 1 | 1 | 1 | 1 | 4 | 1 | 1 | 1 | 5 | 1.5 | 1 | 2.5 | 5
192 | 9 | 6.3333 | 11.8333 | 17.5 | 29.1667 | 37.6667 | 44.3333 | 49.3333 | 55.5 | 62.5 | 68.1667 | 77.6667 | 88.1667 | 94.6667 | 1 | 1 | 1.3333 | 3 | 1.6667 | 1 | 1.3333 | 1.5 | 1 | 2 | 1.6667 | 1 | 1.6667 | 2 | 4 | 4 | 4 | 1 | 2.5 | 1 | 1.6667 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 1.6667 | 1 | 2.5 | 2 | 3 | 1 | 1 | 1 | 2 | 1.6667 | 1 | 1 | 2 | 4 | 2.5 | 1 | 5 | 2.5 | 2 | 2.5 | 2 | 1 | 1
193 | 10.1667 | 6 | 12.1667 | 17.5 | 26.8333 | 35.6667 | 45.6667 | 50.6667 | 64.6667 | 70 | 79 | 92.5 | 103 | 109.5 | 1 | 1 | 3 | 1 | 2.5 | 1.6667 | 1 | 1 | 2 | 1 | 1.3333 | 1 | 4 | 2 | 1.3333 | 2 | 1.3333 | 5 | 1.5 | 1 | 3 | 1.3333 | 1.6667 | 4 | 2 | 1 | 1 | 1 | 5 | 1 | 5 | 3 | 2 | 1.3333 | 1 | 1 | 5 | 2 | 1 | 1 | 4 | 2 | 5 | 2.5 | 2.5 | 2 | 1 | 5 | 2.5 | 1 | 1 | 2
194 | 9 | 7 | 15.6667 | 20.3333 | 30.8333 | 38.1667 | 43.1667 | 52.1667 | 60.1667 | 67.6667 | 75.1667 | 79.5 | 84.8333 | 98.3333 | 1 | 2.5 | 2.5 | 1 | 1 | 1 | 5 | 1.6667 | 1.6667 | 1 | 1 | 1 | 4 | 4 | 1 | 1.5 | 1.6667 | 2 | 2 | 1.6667 | 2 | 1 | 1 | 1 | 3 | 4 | 1 | 1 | 1 | 1 | 5 | 1 | 2.5 | 1 | 3 | 1 | 4 | 1.5 | 1 | 1 | 1 | 1 | 1 | 1.3333 | 1 | 1 | 1.6667 | 1.6667 | 5 | 1 | 2.5 | 5
195 | 8.1667 | 6.1667 | 11.8333 | 18.1667 | 25.8333 | 32.8333 | 44.3333 | 55.8333 | 68.8333 | 75.8333 | 85 | 95.1667 | 103.1667 | 111.3333 | 1.6667 | 1 | 1 | 2.5 | 1 | 1 | 2 | 1.6667 | 1 | 1.3333 | 1 | 3 | 2 | 1.6667 | 1 | 3 | 1 | 1 | 1 | 4 | 1 | 1.5 | 5 | 4 | 2.5 | 3 | 5 | 1 | 5 | 3 | 1 | 4 | 1 | 1 | 1 | 4 | 5 | 1.6667 | 1 | 1.5 | 3 | 4 | 1.5 | 1.6667 | 2 | 2.5 | 2 | 1.5 | 1 | 3 | 2.5 | 1.6667
196 | 7 | 4 | 10 | 17 | 22.5 | 26.5 | 37.5 | 46.5 | 54.1667 | 60.1667 | 65.1667 | 74 | 83.5 | 92.5 | 1 | 1 | 1 | 1 | 1.6667 | 1.3333 | 1 | 2 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 2.5 | 1 | 1 | 1 | 1 | 1 | 4 | 2 | 4 | 3 | 1 | 4 | 1 | 1 | 3 | 2 | 1.6667 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 2 | 2 | 2.5 | 1.3333 | 3 | 1.5 | 4 | 3 | 1 | 2 | 1 | 1 | 5
197 | 8.6667 | 5 | 12.8333 | 19 | 27.5 | 32.1667 | 40.8333 | 49.3333 | 59.8333 | 67.8333 | 72.5 | 79.1667 | 88.1667 | 93.5 | 1 | 1 | 1 | 2 | 2 | 1.6667 | 1.6667 | 2.5 | 1.5 | 1.6667 | 1.6667 | 1.3333 | 2 | 1.5 | 2.5 | 2.5 | 1 | 1.6667 | 1 | 1 | 1 | 1.6667 | 5 | 1 | 2 | 1 | 2.5 | 3 | 2.5 | 1 | 2 | 5 | 1 | 1 | 1 | 5 | 1 | 1 | 1 | 1.6667 | 1 | 3 | 1.6667 | 1 | 2.5 | 2.5 | 2.5 | 1.5 | 2 | 1.3333 | 1 | 1
198 | 12.6667 | 9 | 14.6667 | 22.6667 | 31.6667 | 37.1667 | 45.5 | 54.5 | 60.1667 | 66.3333 | 73.3333 | 77.8333 | 84.1667 | 94.6667 | 1.3333 | 1.6667 | 4 | 2 | 2 | 1.6667 | 1 | 1 | 2.5 | 2.5 | 1.6667 | 1.3333 | 1 | 5 | 2 | 1 | 1.5 | 1 | 2 | 1 | 1 | 1.3333 | 2 | 4 | 3 | 1 | 1 | 4 | 1 | 2 | 1.6667 | 1 | 1.6667 | 2.5 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 1.5 | 2 | 1.3333 | 2 | 1 | 2 | 4 | 2 | 2.5
199 | 10 | 8 | 13 | 20.1667 | 30.6667 | 40.6667 | 50 | 55.3333 | 62.3333 | 69.8333 | 75.8333 | 82.3333 | 87.3333 | 95.6667 | 2 | 2 | 1 | 3 | 1 | 1 | 1 | 2 | 2 | 2.5 | 1 | 1.6667 | 3 | 5 | 1.5 | 1 | 3 | 5 | 1 | 1 | 5 | 2 | 1.3333 | 1 | 2 | 1 | 1.3333 | 1 | 1 | 1 | 1 | 4 | 2 | 2.5 | 2 | 1 | 1 | 1.6667 | 2 | 1.3333 | 1.5 | 2 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 5 | 1 | 1.3333
200 | 8.5 | 4.5 | 14.5 | 23.8333 | 27.8333 | 33.5 | 42.6667 | 54.6667 | 59 | 66.8333 | 77.3333 | 82 | 90.8333 | 97 | 1 | 1.5 | 1 | 1 | 1 | 3 | 5 | 1 | 1.3333 | 4 | 1 | 3 | 1 | 1 | 1 | 1 | 1.6667 | 1 | 2 | 1 | 1 | 2.5 | 1.6667 | 4 | 1 | 5 | 1 | 5 | 1 | 1.3333 | 1 | 1 | 4 | 1.3333 | 1.5 | 1 | 5 | 3 | 1 | 1.5 | 1 | 1.3333 | 1 | 1.3333 | 1 | 1.3333 | 5 | 1.5 | 1 | 1.6667 | 1.5 | 2
201 | 9.6667 | 5.5 | 12.6667 | 20 | 25 | 34.6667 | 43.6667 | 49.6667 | 56.6667 | 62 | 66 | 72.8333 | 79 | 88.5 | 1.5 | 1 | 1 | 2 | 1.6667 | 2.5 | 2 | 1 | 1 | 4 | 1 | 1.3333 | 1 | 1 | 1 | 2 | 1.6667 | 2 | 5 | 1 | 3 | 1.5 | 2 | 2.5 | 3 | 1 | 1 | 1 | 2 | 2 | 1 | 2 | 1 | 1.3333 | 2 | 1 | 1 | 1 | 1 | 1 | 1.3333 | 1 | 2 | 2.5 | 2 | 1.6667 | 1 | 1.5 | 4 | 2.5 | 1 | 2
202 | 14.1667 | 7.5 | 16.1667 | 22.8333 | 29.8333 | 38.3333 | 43.8333 | 51.3333 | 61.3333 | 67.8333 | 74.3333 | 83.8333 | 90.3333 | 102.3333 | 2 | 2.5 | 1.3333 | 1.6667 | 1.6667 | 5 | 1 | 1 | 1.6667 | 2.5 | 1.5 | 1 | 3 | 1.5 | 1.5 | 1 | 1 | 2.5 | 1 | 4 | 1 | 2 | 1 | 1.5 | 3 | 1 | 1 | 2.5 | 3 | 2 | 4 | 1 | 1 | 1 | 2 | 2.5 | 2 | 2.5 | 1 | 1 | 2.5 | 3 | 3 | 1 | 2.5 | 1 | 2 | 1 | 4 | 2 | 4 | 2
203 | 12 | 9 | 16 | 22 | 27 | 35.3333 | 42 | 51.5 | 58.3333 | 63.5 | 72.1667 | 86.6667 | 92 | 97.1667 | 1.5 | 5 | 1.5 | 1 | 2 | 1 | 2 | 2 | 1.6667 | 1 | 1.6667 | 1.6667 | 1 | 1 | 1 | 2 | 1.3333 | 1 | 5 | 1 | 1 | 3 | 1.6667 | 1 | 2 | 1.5 | 1 | 5 | 1.3333 | 1 | 1.5 | 3 | 1.6667 | 1 | 1.5 | 1 | 5 | 1 | 1 | 1.6667 | 2.5 | 5 | 5 | 2 | 1 | 1.3333 | 1.6667 | 1.3333 | 1 | 1 | 1.5 | 1.6667
204 | 8.5 | 5.5 | 13 | 22.6667 | 30.5 | 43.6667 | 50 | 54.5 | 59.8333 | 68.3333 | 73.5 | 77.5 | 83.5 | 91.1667 | 1 | 1.5 | 2 | 1 | 1 | 2 | 2 | 2.5 | 1.6667 | 4 | 1 | 3 | 1.3333 | 1 | 2.5 | 3 | 1.6667 | 1.5 | 5 | 5 | 2 | 1 | 2 | 1.3333 | 1.5 | 1 | 1 | 1 | 1 | 1.3333 | 2 | 1 | 1 | 5 | 1.5 | 1 | 1.5 | 1.3333 | 1 | 1.3333 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1.5 | 3 | 1.6667 | 1.5
205 | 9.5 | 7.5 | 16 | 22 | 32.1667 | 37.6667 | 43.6667 | 55.6667 | 62.8333 | 72.8333 | 78.8333 | 88.8333 | 99.3333 | 103.3333 | 2 | 2 | 1 | 2.5 | 1 | 1 | 5 | 1.5 | 2.5 | 1.5 | 1 | 1 | 2.5 | 2 | 1.6667 | 4 | 1 | 1.5 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 5 | 1 | 5 | 1.5 | 1.6667 | 1 | 3 | 1 | 4 | 4 | 1 | 2 | 1.3333 | 1.3333 | 1.3333 | 1 | 5 | 3 | 1 | 2.5 | 5 | 2 | 1 | 1 | 1 | 1 | 1
206 | 15.3333 | 8.8333 | 18.8333 | 26.8333 | 33.1667 | 40.1667 | 46.6667 | 52.6667 | 56.6667 | 63.1667 | 69.5 | 74.5 | 81.5 | 88.5 | 2.5 | 1 | 4 | 1.3333 | 2.5 | 4 | 1 | 2.5 | 2 | 3 | 2 | 1 | 1 | 2 | 1.6667 | 1.6667 | 3 | 2 | 1 | 1 | 2 | 1.5 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 2.5 | 1 | 1.3333 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 3 | 1 | 1 | 4 | 1 | 1
207 | 14 | 5 | 20 | 28.5 | 38.5 | 47.8333 | 60.8333 | 73.8333 | 78.8333 | 85.3333 | 90.8333 | 98.8333 | 103.5 | 111.5 | 2 | 1 | 1 | 1 | 5 | 4 | 5 | 1 | 1.5 | 2 | 3 | 2 | 1.5 | 2.5 | 5 | 1 | 2 | 5 | 1.3333 | 1 | 3 | 1 | 5 | 4 | 1 | 5 | 5 | 2 | 1 | 2 | 1 | 1 | 1.5 | 2 | 2 | 1 | 1 | 1 | 2 | 1.5 | 1 | 1 | 5 | 1 | 1.6667 | 1 | 1 | 1 | 1 | 5 | 1 | 1
208 | 7.5 | 5.5 | 12.1667 | 18 | 23.3333 | 29 | 37 | 43.5 | 52 | 61.5 | 67.5 | 74.6667 | 81 | 90 | 1.5 | 1.6667 | 1 | 1.3333 | 1 | 1 | 1.6667 | 3 | 1.3333 | 1 | 1 | 2.5 | 1.3333 | 1 | 2 | 1 | 1.3333 | 1.3333 | 1 | 2 | 4 | 2 | 1 | 1 | 3 | 1 | 1.5 | 1 | 2 | 2 | 3 | 1.5 | 2 | 4 | 2 | 1.5 | 2 | 1.3333 | 1.6667 | 1 | 2 | 1.6667 | 2.5 | 1 | 2 | 1 | 1.3333 | 2 | 4 | 2 | 1 | 2
209 | 8.3333 | 5.3333 | 14.3333 | 21.6667 | 29.8333 | 38.8333 | 47.8333 | 55.3333 | 66.3333 | 76 | 83.5 | 87.5 | 91.5 | 100.6667 | 1.3333 | 1 | 2 | 1 | 1.6667 | 1.3333 | 4 | 2 | 1 | 3 | 2 | 1.3333 | 4 | 1.5 | 1.6667 | 1 | 1 | 1.5 | 5 | 1.5 | 4 | 1.5 | 1.5 | 2 | 1 | 2 | 2 | 2.5 | 5 | 4 | 1 | 1 | 5 | 1.6667 | 1 | 2 | 2 | 3 | 1 | 1.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 1 | 1.6667 | 2.5
210 | 8.3333 | 5.6667 | 13.3333 | 20.3333 | 29.8333 | 33.8333 | 43.3333 | 48.3333 | 58.8333 | 66.8333 | 74.1667 | 82.6667 | 87.3333 | 96.3333 | 1 | 1.6667 | 2 | 1 | 1.6667 | 1 | 2 | 3 | 2 | 1 | 2 | 2 | 5 | 1 | 1 | 2.5 | 1 | 1 | 1 | 1 | 1.5 | 3 | 3 | 2 | 1 | 1 | 2 | 1 | 2 | 2.5 | 5 | 1 | 2 | 1 | 1 | 4 | 1.5 | 1.3333 | 2 | 2.5 | 4 | 1 | 2.5 | 1 | 1 | 1.6667 | 1 | 1 | 4 | 1 | 1 | 3
211 | 13 | 9.5 | 18.5 | 24.6667 | 29.6667 | 33.6667 | 38.3333 | 43.8333 | 56.3333 | 67.3333 | 75.5 | 87.8333 | 95.3333 | 105.3333 | 4 | 2 | 2.5 | 1 | 2 | 1.5 | 1.5 | 4 | 1 | 1 | 1.6667 | 2.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1.6667 | 1 | 1 | 1 | 2.5 | 1 | 1 | 1 | 4 | 2.5 | 1 | 5 | 1 | 1 | 4 | 5 | 1.5 | 1.6667 | 3 | 2 | 3 | 1.3333 | 5 | 3 | 1 | 2.5 | 1 | 3 | 3 | 1 | 5 | 1
212 | 10.1667 | 7.5 | 13.1667 | 23.1667 | 28.6667 | 37.3333 | 50 | 55.5 | 62.5 | 70.5 | 76.1667 | 84.1667 | 92.1667 | 97.5 | 2 | 2.5 | 2 | 1 | 1 | 1.6667 | 1.5 | 1.5 | 4 | 1 | 4 | 1 | 1.5 | 2 | 1 | 1 | 4 | 1.6667 | 1 | 2 | 2 | 4 | 5 | 1.6667 | 1 | 1 | 2.5 | 1 | 1 | 1 | 4 | 1 | 5 | 1 | 1 | 1 | 1 | 1.6667 | 2 | 1 | 1 | 2.5 | 2.5 | 2 | 2 | 1 | 1 | 4 | 2 | 1 | 1.3333 | 1
213 | 9.8333 | 5.8333 | 14.8333 | 19.8333 | 27.3333 | 32.8333 | 42.8333 | 51.8333 | 58.8333 | 71.8333 | 80.8333 | 86.5 | 93.5 | 103.8333 | 1.5 | 1.3333 | 1.5 | 1.5 | 3 | 1 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 2 | 1.5 | 3 | 1.5 | 1 | 2 | 1 | 2 | 4 | 2 | 2 | 1 | 5 | 1 | 2 | 4 | 1 | 1 | 1 | 5 | 5 | 1 | 2 | 1 | 1.3333 | 5 | 1.6667 | 1.6667 | 1.6667 | 1.3333 | 1 | 1 | 1 | 2 | 3 | 1.3333 | 5 | 3 | 1
214 | 10 | 8 | 14.6667 | 24.3333 | 38 | 49 | 55.3333 | 60.5 | 67.5 | 75 | 84.3333 | 94.8333 | 104.3333 | 114.5 | 1 | 5 | 1 | 1 | 1 | 1 | 1.6667 | 3 | 1 | 1.6667 | 2 | 5 | 4 | 3 | 1.6667 | 5 | 3 | 1 | 4 | 3 | 1 | 1.5 | 1.3333 | 2.5 | 1.5 | 1.3333 | 1.3333 | 1 | 1 | 2 | 2 | 2 | 1 | 3 | 1 | 2.5 | 1 | 1.3333 | 5 | 2 | 1 | 3 | 1.5 | 5 | 1.5 | 1 | 2 | 5 | 2 | 4 | 2.5 | 1.6667
215 | 8.8333 | 6.1667 | 11.5 | 21.1667 | 30.1667 | 39.6667 | 50.1667 | 59.1667 | 67.1667 | 76.1667 | 90.6667 | 99.1667 | 106.6667 | 115.8333 | 1 | 2 | 1.6667 | 1.5 | 1 | 1.6667 | 1.6667 | 1 | 2 | 5 | 1.3333 | 1.3333 | 1 | 1.3333 | 1.6667 | 5 | 1.5 | 2.5 | 1.5 | 4 | 2.5 | 5 | 2 | 1 | 1 | 2 | 1 | 5 | 1 | 5 | 1 | 1 | 1 | 1 | 2 | 5 | 5 | 5 | 2 | 2.5 | 5 | 1.5 | 1 | 1 | 1 | 1 | 4 | 1.5 | 1.6667 | 5 | 1.5 | 1
216 | 11.1667 | 7 | 14.1667 | 22.1667 | 30.1667 | 38.1667 | 44.6667 | 51.1667 | 58.1667 | 73.1667 | 80.3333 | 89 | 95.5 | 103.5 | 2.5 | 2.5 | 1 | 1 | 2.5 | 1.6667 | 1 | 2 | 1 | 4 | 2 | 1 | 1 | 1 | 5 | 1 | 1 | 1 | 4 | 2 | 1 | 1 | 2 | 2.5 | 2.5 | 1 | 1 | 2 | 2 | 3 | 1 | 1 | 4 | 5 | 1 | 5 | 2 | 1 | 1.6667 | 2.5 | 3 | 1 | 1.6667 | 3 | 1 | 1 | 2.5 | 2 | 1 | 5 | 1 | 1
217 | 9 | 7 | 11 | 21.1667 | 25.8333 | 32.1667 | 39.8333 | 48.1667 | 53.1667 | 57.8333 | 62.8333 | 68.3333 | 77.3333 | 86.3333 | 3 | 1 | 1.5 | 1.5 | 1 | 1 | 1 | 1 | 5 | 1.5 | 2 | 1.6667 | 1 | 1 | 1 | 1.6667 | 1 | 2 | 2 | 1.3333 | 1.3333 | 3 | 2 | 1.3333 | 1.3333 | 5 | 1 | 1 | 1 | 1.6667 | 1 | 1.3333 | 1 | 1 | 1 | 1.6667 | 1 | 1.3333 | 1.6667 | 1 | 1 | 2 | 1 | 1.5 | 3 | 4 | 1 | 1 | 1 | 5 | 2 | 1
218 | 13.3333 | 7.3333 | 17.3333 | 28.3333 | 40.5 | 49.5 | 62.6667 | 71.1667 | 81.5 | 88.5 | 94.8333 | 103.5 | 109.3333 | 120.1667 | 1.6667 | 1 | 1.6667 | 3 | 1 | 5 | 3 | 1 | 2 | 1 | 5 | 3 | 4 | 5 | 1.6667 | 1.5 | 1.5 | 1 | 1.5 | 5 | 1.6667 | 5 | 1.5 | 5 | 1 | 1 | 1.5 | 5 | 2 | 1.6667 | 5 | 1.6667 | 1 | 1 | 2 | 3 | 2.5 | 1 | 1.3333 | 1.5 | 4 | 2 | 1.6667 | 1 | 1.3333 | 1.5 | 1.6667 | 1.3333 | 5 | 1.3333 | 3 | 1.5
219 | 8.6667 | 6 | 10.6667 | 24.1667 | 29.1667 | 35 | 41.5 | 51 | 56.5 | 65 | 75.5 | 83 | 90 | 101 | 1 | 1 | 1 | 3 | 1 | 1.6667 | 1 | 1 | 2.5 | 5 | 5 | 1 | 1 | 2 | 1 | 1 | 1 | 2.5 | 1.3333 | 1 | 2 | 1.5 | 1 | 2 | 5 | 2.5 | 1 | 1 | 1 | 1.3333 | 1.6667 | 1.5 | 2.5 | 4 | 1 | 1 | 1 | 3 | 2.5 | 4 | 4 | 1.5 | 1 | 1 | 1 | 1 | 4 | 1 | 5 | 3 | 1 | 2
220 | 11 | 8.6667 | 15 | 21.1667 | 25.1667 | 30.8333 | 39.3333 | 48 | 58.6667 | 69.6667 | 74 | 81.5 | 90.5 | 95.5 | 2 | 1 | 1.6667 | 4 | 1 | 1.3333 | 1 | 3 | 1 | 2.5 | 1 | 1.6667 | 1 | 1 | 1 | 1 | 1 | 1.3333 | 1.3333 | 2 | 3 | 2 | 1.5 | 2 | 2 | 1 | 1.6667 | 4 | 1 | 1.6667 | 4 | 4 | 4 | 1 | 5 | 1 | 1.3333 | 1 | 1 | 1 | 1.5 | 2 | 3 | 1 | 1 | 1 | 4 | 3 | 1 | 1 | 2 | 1
221 | 10.1667 | 7.8333 | 13.6667 | 19.5 | 24.6667 | 33 | 39.5 | 47 | 55 | 66 | 73.1667 | 81.6667 | 93 | 97.5 | 2 | 1.3333 | 2.5 | 2 | 1.3333 | 1 | 2.5 | 1 | 1 | 1.3333 | 1.5 | 2 | 1.3333 | 1.5 | 1.3333 | 1 | 1 | 1 | 1.3333 | 5 | 1 | 2.5 | 2 | 1 | 3 | 2.5 | 1 | 1 | 1 | 5 | 1 | 1 | 1 | 5 | 1 | 4 | 2 | 1.6667 | 2.5 | 1 | 4 | 2.5 | 1 | 1 | 2 | 5 | 3 | 1.3333 | 1 | 1 | 1 | 1.5
222 | 15.6667 | 9.3333 | 19.1667 | 25.6667 | 31 | 40 | 44.6667 | 50.6667 | 57.6667 | 64.1667 | 72.1667 | 79 | 85 | 89 | 1.3333 | 4 | 2 | 2 | 5 | 1.3333 | 2.5 | 1 | 1 | 1.3333 | 2.5 | 1.6667 | 1.3333 | 1.3333 | 1 | 1.6667 | 5 | 1 | 1.3333 | 1.6667 | 1.6667 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 4 | 1 | 1 | 2 | 1.5 | 2 | 4 | 1 | 1 | 2 | 2 | 1.3333 | 1 | 2.5 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1
223 | 9.1667 | 5.8333 | 13.1667 | 22.1667 | 28.8333 | 34 | 39.1667 | 45.6667 | 55.1667 | 62.3333 | 66.3333 | 74.3333 | 79.3333 | 84.3333 | 1 | 2 | 1.5 | 1.3333 | 1.6667 | 1.6667 | 2 | 2 | 5 | 2 | 1 | 1 | 2 | 1.6667 | 2 | 1 | 1.6667 | 1 | 1.5 | 1 | 1.3333 | 1.5 | 1.3333 | 1 | 3 | 1 | 1 | 1.5 | 1 | 5 | 2 | 1.5 | 3 | 1.5 | 1.6667 | 1 | 1 | 1 | 1 | 1 | 2.5 | 3 | 1 | 1.5 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2
224 | 21.5 | 15.5 | 24.5 | 36.5 | 48.5 | 53.5 | 60.8333 | 67.8333 | 73.3333 | 85.3333 | 90 | 97.1667 | 101.8333 | 108 | 5 | 4 | 2.5 | 4 | 3 | 3 | 2 | 1 | 5 | 2 | 4 | 1 | 3 | 3 | 5 | 1 | 1 | 1 | 2 | 1 | 1.6667 | 1 | 3 | 1.6667 | 2.5 | 2.5 | 1 | 1 | 1.6667 | 1.3333 | 1.5 | 1 | 1 | 1 | 5 | 5 | 1 | 1.3333 | 1.3333 | 1 | 2.5 | 1.6667 | 2 | 1 | 1.6667 | 1 | 1 | 1 | 1.6667 | 1.5 | 1 | 2
225 | 11 | 8 | 13.6667 | 19.6667 | 29.1667 | 37.1667 | 42.8333 | 55.8333 | 62.1667 | 66.8333 | 76.3333 | 89 | 96.1667 | 101.6667 | 1 | 5 | 1 | 1 | 1.6667 | 1.3333 | 1 | 1.6667 | 1 | 1 | 3 | 1 | 2.5 | 1 | 2 | 4 | 1 | 2 | 2 | 3 | 1 | 1.6667 | 2 | 1 | 5 | 1 | 5 | 2 | 2 | 1.3333 | 1 | 2 | 1 | 1 | 1 | 1.6667 | 5 | 1 | 2.5 | 1 | 1.6667 | 2 | 4 | 5 | 2.5 | 1.6667 | 2 | 1 | 1 | 1 | 2.5 | 1
226 | 11.6667 | 8.6667 | 16.1667 | 20.5 | 25 | 31.1667 | 37.1667 | 42.6667 | 53.3333 | 57.3333 | 65 | 70.5 | 75.5 | 84 | 1.3333 | 1 | 1.3333 | 5 | 1 | 2 | 2 | 2.5 | 1 | 1.3333 | 1 | 1 | 1 | 1 | 1 | 1.5 | 1 | 2.5 | 1.3333 | 1.3333 | 1.3333 | 1 | 2 | 1.6667 | 1.3333 | 1.6667 | 1 | 1.5 | 3 | 1.6667 | 1 | 5 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 1.6667 | 1 | 1.5 | 1 | 2 | 1 | 2 | 1 | 1 | 2.5 | 1.5 | 2.5 | 2
227 | 12.5 | 8 | 19.5 | 26.5 | 33.5 | 45.1667 | 51.1667 | 58.5 | 63.5 | 69.3333 | 78.1667 | 84.6667 | 94.1667 | 100.3333 | 4 | 2 | 1 | 1 | 2 | 2.5 | 4 | 3 | 2 | 1.5 | 2.5 | 1 | 3 | 1 | 1.6667 | 1.3333 | 3 | 1.6667 | 3 | 4 | 1 | 2 | 2 | 1 | 1 | 1 | 1.3333 | 4 | 1 | 1 | 1 | 2 | 1 | 1 | 2.5 | 1.3333 | 2.5 | 1.3333 | 1 | 4 | 2 | 2 | 1 | 1.5 | 1 | 5 | 1 | 2.5 | 1 | 2.5 | 1.6667 | 1
228 | 9 | 6 | 11 | 20 | 35 | 42.3333 | 52.3333 | 59.6667 | 65.5 | 70.5 | 76.1667 | 83 | 90 | 99 | 1 | 1 | 1.5 | 2.5 | 2 | 1 | 1 | 1 | 1 | 5 | 1 | 2 | 2 | 3 | 5 | 5 | 2 | 3 | 1 | 1.3333 | 1.6667 | 4 | 1.3333 | 3 | 1.3333 | 4 | 1 | 1 | 1.3333 | 1.5 | 2 | 1 | 1 | 2 | 1 | 1 | 2 | 1.6667 | 1 | 1 | 1.5 | 2 | 1.3333 | 2 | 1 | 2 | 2 | 2 | 5 | 1 | 1 | 2
229 | 16.5 | 10.5 | 21 | 32 | 44.5 | 52.5 | 58.6667 | 67.1667 | 76.1667 | 88.5 | 95.5 | 100.8333 | 106.1667 | 112.6667 | 1 | 4 | 4 | 1.5 | 5 | 1 | 2.5 | 2 | 5 | 1 | 4 | 1 | 5 | 1 | 2.5 | 4 | 1.5 | 1 | 3 | 2.5 | 1 | 1.6667 | 2.5 | 1 | 5 | 1 | 1.5 | 1 | 2 | 1 | 1 | 5 | 4 | 1.3333 | 2 | 5 | 2.5 | 1.5 | 1 | 2 | 1 | 1.6667 | 1.6667 | 1 | 1 | 2 | 1.3333 | 1 | 1 | 1.3333 | 1.6667 | 2.5
230 | 11 | 7.6667 | 13.3333 | 17.3333 | 26.6667 | 34.6667 | 46.6667 | 52.8333 | 62.8333 | 70.8333 | 80.3333 | 87.3333 | 97 | 108.6667 | 1 | 3 | 2 | 1.6667 | 1.3333 | 2 | 1.3333 | 1 | 1 | 1 | 1 | 1 | 5 | 1 | 1.6667 | 1.6667 | 2 | 1 | 4 | 1 | 5 | 1 | 5 | 1 | 1.6667 | 2 | 1.5 | 1 | 1.6667 | 3 | 4 | 1.3333 | 1 | 5 | 1 | 1 | 5 | 1 | 1.5 | 2 | 2 | 1.6667 | 1.3333 | 2 | 1.6667 | 2 | 4 | 2 | 5 | 1.6667 | 3 | 2
231 | 9.6667 | 6.1667 | 13.8333 | 20.5 | 25 | 33 | 43.5 | 49.5 | 57 | 68 | 78.3333 | 83 | 89.8333 | 97.3333 | 2 | 1 | 1.6667 | 1.5 | 1 | 2.5 | 2.5 | 1.6667 | 3 | 1.6667 | 1 | 1 | 1 | 1 | 1 | 1.5 | 2 | 2.5 | 1 | 2.5 | 4 | 4 | 1 | 1.5 | 1 | 2 | 1 | 2 | 1 | 2 | 3 | 1.5 | 1 | 4 | 1 | 5 | 3 | 1.3333 | 5 | 1 | 1 | 1.6667 | 1 | 1 | 1 | 2.5 | 1.3333 | 2 | 2 | 1.5 | 1 | 3
232 | 7.3333 | 4 | 9.3333 | 18.1667 | 23.5 | 29.1667 | 37.1667 | 43.6667 | 55.1667 | 59.5 | 70.5 | 74.5 | 79.5 | 84.3333 | 1 | 1 | 1 | 1 | 1.3333 | 2 | 1 | 1 | 4 | 2.5 | 1 | 1.3333 | 1 | 1 | 1.3333 | 2 | 2 | 1 | 1.6667 | 1 | 4 | 1 | 2 | 1 | 1.5 | 2 | 2 | 1 | 2.5 | 1 | 4 | 4 | 1 | 1.3333 | 1 | 1 | 4 | 1 | 5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1.3333 | 1.5 | 1 | 1
233 | 14.8333 | 9.8333 | 18.8333 | 23.3333 | 30.6667 | 41.6667 | 47.8333 | 53.1667 | 60.1667 | 66.1667 | 72.5 | 78.5 | 84.5 | 94.5 | 2.5 | 1.3333 | 1 | 5 | 1 | 4 | 2 | 2 | 1 | 1 | 1.5 | 1 | 2.5 | 1.3333 | 1.5 | 2 | 2 | 2 | 5 | 2 | 1.6667 | 1 | 2.5 | 1 | 1 | 2 | 1 | 1.3333 | 4 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1.3333 | 3 | 1 | 2 | 1 | 1 | 2 | 1 | 2 | 1.6667 | 1.3333 | 5 | 3 | 1 | 1
234 | 12.1667 | 8.5 | 15.1667 | 24.1667 | 31 | 42.5 | 51.5 | 58.5 | 66.5 | 74.5 | 83.5 | 90 | 95 | 101 | 5 | 1 | 1.5 | 1 | 1.6667 | 2 | 2 | 1 | 5 | 1.3333 | 1.6667 | 1 | 1 | 1.5 | 3 | 1.3333 | 3 | 1 | 2.5 | 5 | 1.3333 | 1.6667 | 2 | 4 | 1 | 1 | 1 | 4 | 1 | 4 | 1 | 2 | 1 | 1 | 4 | 2 | 1.5 | 1.5 | 4 | 2 | 1 | 1 | 2 | 2.5 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 2
235 | 16.6667 | 11.6667 | 19 | 23 | 31.8333 | 40.1667 | 47.3333 | 51.8333 | 60.5 | 66 | 71.5 | 81.5 | 87.5 | 92.1667 | 4 | 4 | 2 | 1.6667 | 4 | 1 | 1 | 1.3333 | 1 | 1 | 1 | 1 | 1.6667 | 1.5 | 4 | 1.6667 | 1.6667 | 1 | 1.6667 | 4 | 1.6667 | 2 | 2.5 | 1 | 1 | 1.5 | 1 | 1 | 1 | 1.6667 | 3 | 3 | 2 | 1 | 1 | 1.5 | 2.5 | 1 | 1 | 1 | 4 | 2 | 2.5 | 1.5 | 3 | 1 | 1 | 1 | 1.6667 | 1 | 1 | 1
236 | 18.5 | 12.5 | 21 | 26 | 35.5 | 41 | 47 | 54.1667 | 64.6667 | 71.1667 | 77.6667 | 88.6667 | 101.1667 | 109.1667 | 1.5 | 1 | 5 | 5 | 5 | 1 | 1.5 | 1 | 1 | 2 | 1 | 1 | 1.5 | 2 | 5 | 1 | 2.5 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 2 | 1 | 2.5 | 1.6667 | 5 | 1 | 2 | 2.5 | 1 | 1 | 2.5 | 2 | 3 | 1 | 1.5 | 1 | 1 | 2 | 3 | 5 | 2 | 5 | 4 | 1.5 | 1 | 5 | 1 | 1
237 | 8.3333 | 5.6667 | 14.8333 | 24.8333 | 33.1667 | 38.1667 | 48.1667 | 53.1667 | 63.1667 | 67.6667 | 74.6667 | 80.1667 | 86.5 | 97 | 1 | 1 | 1.6667 | 2 | 1.3333 | 1.3333 | 2.5 | 4 | 2 | 2 | 1 | 5 | 3 | 2 | 1.3333 | 2 | 1 | 1.5 | 1 | 1.5 | 4 | 4 | 1 | 1 | 1 | 1 | 1.6667 | 1.3333 | 1 | 1 | 4 | 4 | 1 | 1.5 | 1 | 1 | 3 | 1 | 2 | 1 | 2.5 | 1 | 1 | 1 | 1 | 3 | 1 | 1.3333 | 2 | 1 | 5 | 2.5
238 | 16.3333 | 8.8333 | 20.3333 | 32.6667 | 41 | 46 | 56.6667 | 67.5 | 72 | 76.5 | 86.8333 | 97.8333 | 106.3333 | 116.6667 | 1 | 1.3333 | 2.5 | 4 | 5 | 2.5 | 1 | 3 | 5 | 5 | 1.3333 | 1 | 1.3333 | 2 | 1 | 4 | 1.5 | 1.5 | 1 | 1 | 3 | 5 | 1.3333 | 1.3333 | 5 | 2.5 | 2 | 1.3333 | 1 | 1.5 | 1 | 1 | 1.5 | 1 | 1 | 1 | 4 | 3 | 2 | 1.3333 | 1 | 2.5 | 5 | 2.5 | 2 | 1.5 | 4 | 1 | 5 | 1.3333 | 3 | 1
239 | 14.3333 | 11.3333 | 18.3333 | 24.6667 | 34.1667 | 42.6667 | 49.6667 | 56.6667 | 65 | 74.5 | 84 | 95.6667 | 102.5 | 106.8333 | 1 | 4 | 5 | 1.3333 | 1.3333 | 1.6667 | 3 | 1 | 3 | 1 | 1 | 1.3333 | 5 | 1.5 | 1 | 2 | 5 | 1.5 | 1 | 1 | 3 | 1.3333 | 1 | 1.6667 | 1.5 | 1 | 2.5 | 2 | 1 | 1 | 5 | 1.3333 | 1.5 | 1.3333 | 5 | 1.6667 | 2 | 3 | 3 | 1.5 | 1.6667 | 2 | 4 | 4 | 1 | 1.3333 | 2.5 | 2 | 1.3333 | 1 | 1 | 1
240 | 11.6667 | 8.3333 | 15.1667 | 31.6667 | 40.6667 | 45.1667 | 50 | 59 | 64.5 | 75 | 83.5 | 89 | 95.8333 | 100.3333 | 1 | 1.3333 | 5 | 1 | 1.6667 | 1.6667 | 2.5 | 1 | 4 | 2.5 | 5 | 5 | 5 | 1 | 1 | 2 | 1 | 1 | 1 | 1.5 | 1.5 | 1 | 1.3333 | 1 | 2 | 3 | 1 | 3 | 1 | 1 | 1 | 2.5 | 3 | 5 | 1.5 | 1 | 4 | 1 | 1 | 2.5 | 1 | 2.5 | 1 | 1 | 1.3333 | 1.5 | 2 | 2 | 1 | 1 | 1 | 1.5
241 | 12.5 | 6.1667 | 16 | 22.6667 | 29.6667 | 37.6667 | 43.6667 | 52.6667 | 67.1667 | 73.6667 | 78.3333 | 83.5 | 92.5 | 100.5 | 1 | 2.5 | 1.6667 | 1 | 5 | 1.3333 | 1 | 2.5 | 1 | 1.6667 | 3 | 1 | 1 | 3 | 1.5 | 1.5 | 1 | 1.5 | 4 | 1.5 | 2.5 | 1 | 1 | 1.5 | 2 | 5 | 1 | 1 | 3 | 4 | 5 | 2.5 | 1 | 1.5 | 1 | 3 | 1 | 1 | 1 | 1.6667 | 1 | 1.3333 | 1.3333 | 1.5 | 3 | 2.5 | 2.5 | 1 | 4 | 2 | 1 | 1
242 | 6.8333 | 4.5 | 11.1667 | 16.6667 | 23.6667 | 33.8333 | 44.3333 | 49.8333 | 54.8333 | 62.1667 | 70.5 | 81 | 91 | 103 | 1 | 1.5 | 1 | 1 | 1 | 1.3333 | 3 | 1.3333 | 1 | 1.5 | 2 | 1 | 2 | 1 | 3 | 1 | 5 | 1.6667 | 2.5 | 1 | 3 | 4 | 1 | 2.5 | 1.6667 | 1.3333 | 1.5 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1.3333 | 4 | 1 | 3 | 1.3333 | 3 | 2.5 | 1 | 5 | 2 | 1 | 2.5 | 5 | 1.5 | 5 | 1 | 1 | 5
243 | 16.6667 | 8.6667 | 22.6667 | 27.6667 | 37.3333 | 45.3333 | 53.6667 | 59.8333 | 65.8333 | 77.3333 | 85.3333 | 94.3333 | 102.8333 | 107.8333 | 2 | 1 | 4 | 1.6667 | 3 | 5 | 5 | 1 | 2 | 1 | 1 | 1 | 1.6667 | 5 | 1.3333 | 1.6667 | 1 | 2 | 1 | 4 | 4 | 1.3333 | 2 | 1 | 2 | 1.5 | 1 | 1.6667 | 1 | 1.6667 | 1.3333 | 2 | 5 | 2.5 | 3 | 1 | 4 | 1 | 1 | 2 | 1.5 | 2.5 | 1 | 4 | 4 | 1 | 2 | 1.5 | 1 | 1 | 2 | 1
244 | 10 | 8 | 13 | 21 | 25 | 34 | 39.8333 | 52.8333 | 63.8333 | 73.8333 | 88.8333 | 95.8333 | 102.3333 | 107.6667 | 1 | 1 | 1 | 5 | 1 | 1 | 2 | 1 | 1 | 2 | 4 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 5 | 1 | 1.3333 | 1.5 | 1 | 2 | 3 | 5 | 4 | 1 | 2 | 4 | 2 | 3 | 1.3333 | 2 | 1.6667 | 5 | 3 | 5 | 4 | 3 | 2 | 2 | 2 | 1 | 1 | 2.5 | 1 | 2 | 1.3333 | 2 | 1 | 1
245 | 14.3333 | 11 | 16.3333 | 25.3333 | 32.8333 | 39.1667 | 47.1667 | 52.3333 | 56.3333 | 66.8333 | 71.1667 | 80.6667 | 87.6667 | 92 | 4 | 5 | 1 | 1 | 2 | 1.3333 | 1 | 1 | 2 | 3 | 2 | 2 | 3 | 1 | 1.5 | 2 | 1 | 1.3333 | 1 | 3 | 1 | 1 | 2 | 4 | 1 | 1.5 | 1.6667 | 1 | 1 | 1 | 1 | 1 | 1 | 5 | 2.5 | 2 | 1.3333 | 1 | 1 | 1 | 1 | 3 | 4 | 1.5 | 2 | 1 | 1 | 3 | 1 | 1 | 1.3333 | 1
246 | 10 | 5.6667 | 14.1667 | 24.1667 | 35.1667 | 40.5 | 44.8333 | 56.1667 | 62.1667 | 70.1667 | 77.6667 | 88.6667 | 98.6667 | 102.6667 | 1.3333 | 2 | 1.3333 | 1 | 3 | 1.3333 | 1.6667 | 2.5 | 4 | 1.5 | 3 | 1.5 | 1 | 5 | 3 | 2 | 1 | 1 | 1.3333 | 2 | 1 | 1 | 1.3333 | 1 | 1 | 4 | 1.3333 | 5 | 1.5 | 2.5 | 1 | 1 | 4 | 2 | 1 | 1 | 1.5 | 2 | 1 | 3 | 1 | 3 | 4 | 3 | 2 | 2 | 1 | 5 | 1 | 1 | 1 | 1
247 | 13.5 | 8.5 | 17.6667 | 26.3333 | 32.3333 | 39.8333 | 46.8333 | 60.8333 | 67.8333 | 76.8333 | 82.6667 | 92.6667 | 101.3333 | 114.8333 | 5 | 1.5 | 1 | 1 | 1 | 4 | 1.6667 | 2.5 | 1 | 1.6667 | 5 | 1 | 2 | 2 | 1 | 1 | 2 | 2 | 1 | 2.5 | 2 | 2.5 | 1.5 | 1 | 5 | 3 | 2 | 4 | 1.3333 | 1.6667 | 1 | 3 | 1 | 2 | 4 | 2 | 2.5 | 1 | 1 | 1.3333 | 2 | 3 | 4 | 1 | 3 | 3 | 1 | 1.6667 | 4 | 3 | 5 | 1.5
248 | 10.5 | 5.5 | 13 | 19.3333 | 23.6667 | 29.6667 | 37.6667 | 43.6667 | 52.6667 | 59 | 64.5 | 76 | 85.6667 | 92.1667 | 1 | 1.5 | 1 | 2 | 3 | 2 | 1.5 | 1 | 1.3333 | 2 | 1 | 2 | 1.3333 | 1 | 1 | 1 | 1 | 1 | 2.5 | 1.5 | 1 | 4 | 2 | 1 | 2 | 2 | 1 | 1 | 2 | 2 | 4 | 1 | 2 | 1 | 1.6667 | 1.6667 | 1.5 | 2 | 1 | 1 | 5 | 1 | 2.5 | 3 | 3 | 4 | 1 | 1.6667 | 1.6667 | 1 | 1.3333 | 2.5
249 | 14 | 8.3333 | 19 | 26.5 | 31.8333 | 37.8333 | 43 | 52.6667 | 59.5 | 63.5 | 72.1667 | 80.5 | 84.8333 | 90.8333 | 1.3333 | 1 | 5 | 1 | 1.6667 | 4 | 1 | 4 | 1 | 2.5 | 3 | 1 | 1.3333 | 2 | 1 | 1 | 3 | 1 | 1 | 1 | 1.6667 | 1 | 1.5 | 1 | 1.6667 | 2 | 1 | 5 | 1.6667 | 2.5 | 1.6667 | 1 | 1 | 1 | 1 | 1 | 4 | 2 | 1 | 1.6667 | 1 | 1 | 5 | 1.3333 | 1.3333 | 1 | 1 | 1 | 1 | 1 | 3 | 1
250 | 15 | 10 | 20 | 26 | 34 | 41 | 53.6667 | 69.6667 | 79.1667 | 84.3333 | 93.8333 | 99.3333 | 107.3333 | 116.3333 | 3 | 5 | 1 | 1 | 3 | 2 | 1 | 4 | 1.6667 | 1 | 2 | 1.3333 | 1.3333 | 1.6667 | 3 | 2 | 2 | 2 | 1 | 2 | 4 | 3 | 1.6667 | 4 | 1 | 5 | 5 | 5 | 1 | 5 | 1 | 2.5 | 1.5 | 1 | 1 | 1.6667 | 2.5 | 2 | 1 | 4 | 1.5 | 1 | 2 | 1 | 1 | 5 | 1 | 1 | 2 | 1 | 5 | 1
251 | 13.5 | 10.8333 | 18.5 | 28.5 | 33.5 | 39.8333 | 44.6667 | 52.6667 | 57.6667 | 65.6667 | 74.3333 | 80.3333 | 85.6667 | 92.3333 | 5 | 2 | 2.5 | 1.3333 | 1 | 1.6667 | 1 | 4 | 4 | 2.5 | 2.5 | 1 | 1 | 2 | 1 | 1 | 1 | 1.6667 | 2 | 1.6667 | 1.3333 | 1 | 1 | 1.5 | 1 | 4 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 5 | 1 | 1 | 5 | 1 | 1 | 1.6667 | 1 | 1 | 1 | 3 | 1 | 1.3333 | 1 | 2 | 1.6667 | 1 | 1 | 3
252 | 14.3333 | 9.3333 | 19 | 26 | 31 | 40.5 | 45.1667 | 50.1667 | 59.5 | 66 | 72.6667 | 79.3333 | 88.3333 | 97.3333 | 2 | 4 | 1.6667 | 1.6667 | 2 | 3 | 1.6667 | 3 | 3 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 2.5 | 5 | 1 | 1 | 1 | 1.6667 | 1 | 2 | 1 | 1 | 4 | 2.5 | 1.3333 | 1.5 | 2.5 | 1 | 2 | 1 | 3 | 1.6667 | 1 | 1 | 3 | 1 | 1 | 1.6667 | 1 | 4 | 2 | 2 | 5 | 1 | 1 | 2
253 | 10 | 6 | 15 | 21.1667 | 29.1667 | 36.5 | 44 | 49 | 55 | 62.1667 | 71.1667 | 79.1667 | 87.1667 | 94.1667 | 1 | 1 | 3 | 1 | 1 | 3 | 2 | 3 | 1 | 2.5 | 1 | 1.6667 | 4 | 2 | 1 | 1 | 1 | 4 | 1.3333 | 1 | 1 | 2 | 2.5 | 2 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1.6667 | 1 | 3 | 1.5 | 5 | 2 | 1 | 1 | 3 | 2 | 2 | 1 | 2 | 2.5 | 2.5 | 1 | 2 | 2 | 2 | 1
254 | 9.3333 | 5.3333 | 14.3333 | 23.3333 | 30.3333 | 35.6667 | 43.6667 | 56.3333 | 60.6667 | 65.6667 | 74 | 84 | 94.5 | 101.5 | 1.3333 | 1 | 2 | 1 | 3 | 1 | 4 | 1 | 4 | 3 | 1 | 1 | 1.6667 | 1.3333 | 2.5 | 1.5 | 1 | 1 | 1.6667 | 1.6667 | 1 | 1 | 5 | 1 | 1 | 5 | 1.6667 | 5 | 1.3333 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1.3333 | 2 | 1 | 4 | 2.5 | 2.5 | 2 | 3 | 1.5 | 4 | 3 | 2 | 1 | 4 | 1 | 1
255 | 16.8333 | 10.3333 | 22.8333 | 31.3333 | 40.6667 | 48.6667 | 60 | 67.5 | 75.5 | 82.3333 | 88.3333 | 97.3333 | 106 | 113.5 | 1.3333 | 3 | 1 | 5 | 2.5 | 4 | 4 | 2 | 1.5 | 1 | 5 | 1 | 4 | 2 | 1.3333 | 2 | 1.5 | 1 | 1.5 | 4 | 1.3333 | 1 | 4 | 5 | 2 | 1 | 1.5 | 3 | 4 | 1.3333 | 1 | 1.6667 | 2 | 1.6667 | 1.6667 | 1.5 | 1 | 3 | 1 | 1 | 4 | 1.5 | 1 | 2.5 | 2 | 1.6667 | 4 | 1 | 1 | 1 | 3 | 2.5
256 | 12.3333 | 7.3333 | 17.3333 | 26.8333 | 34.1667 | 40.3333 | 46.8333 | 54.1667 | 62.1667 | 73.1667 | 80.1667 | 90.6667 | 96.3333 | 106.8333 | 1 | 1.3333 | 2 | 3 | 2.5 | 2.5 | 1 | 4 | 1 | 2.5 | 1 | 5 | 3 | 1 | 1.3333 | 2 | 1.6667 | 1 | 1.5 | 2 | 1.6667 | 2.5 | 1.3333 | 1 | 1 | 4 | 1 | 1.3333 | 1 | 1 | 1 | 5 | 5 | 1 | 2 | 3 | 1 | 1 | 2.5 | 2.5 | 2.5 | 1.5 | 2.5 | 4 | 1 | 1.6667 | 1 | 2 | 5 | 2 | 1 | 2.5
257 | 12.3333 | 10 | 18 | 27.3333 | 34.3333 | 41.6667 | 52.3333 | 58.3333 | 65.6667 | 72.6667 | 78.1667 | 85.8333 | 93.1667 | 99.5 | 3 | 5 | 1 | 1 | 1 | 1.3333 | 1.6667 | 4 | 4 | 1.3333 | 2.5 | 1.5 | 2 | 2 | 1 | 2 | 4 | 1 | 1.3333 | 1 | 4 | 1.3333 | 4 | 1.3333 | 1 | 1.5 | 1.5 | 2 | 1 | 2 | 3 | 1.3333 | 2 | 1 | 1 | 3 | 2 | 1 | 1 | 1.5 | 1.5 | 2.5 | 2 | 1.6667 | 1.6667 | 3 | 1 | 1.6667 | 1 | 3 | 1 | 1.3333
258 | 12.5 | 9 | 15.5 | 22 | 31.1667 | 41.1667 | 48.6667 | 57.6667 | 62.6667 | 67.8333 | 80.1667 | 91.1667 | 95.1667 | 107.3333 | 5 | 2 | 1 | 1 | 2.5 | 1 | 2 | 1 | 1 | 2.5 | 1 | 2 | 1.5 | 5 | 1.6667 | 1 | 1.6667 | 1.3333 | 4 | 3 | 1 | 1.5 | 1 | 4 | 1.6667 | 5 | 1.3333 | 1 | 2 | 1 | 1 | 1 | 1.3333 | 1 | 1.3333 | 1.5 | 2 | 4 | 5 | 1.3333 | 4 | 1 | 1 | 5 | 1 | 1 | 1 | 1 | 3 | 1.6667 | 2.5 | 5
259 | 14.3333 | 11.6667 | 19.8333 | 29.3333 | 39.6667 | 48.1667 | 56.5 | 66.1667 | 72 | 80 | 88.8333 | 101.5 | 110.5 | 116 | 1.6667 | 5 | 4 | 1 | 1 | 1.6667 | 2.5 | 3 | 1 | 1 | 5 | 2.5 | 5 | 3 | 1 | 1.3333 | 2.5 | 1 | 2 | 3 | 5 | 1 | 1 | 1.3333 | 1.6667 | 4 | 2 | 2 | 2 | 1 | 1.3333 | 1.5 | 1 | 2 | 1 | 4 | 1 | 4 | 2.5 | 1.3333 | 5 | 5 | 1 | 1.6667 | 2 | 1 | 5 | 1 | 1 | 1 | 2.5 | 1
260 | 22 | 14 | 25.3333 | 40.3333 | 47.6667 | 53 | 64.3333 | 68.6667 | 76.5 | 90.1667 | 98.1667 | 107.1667 | 116.5 | 127 | 3 | 2 | 4 | 5 | 4 | 4 | 1.3333 | 2 | 5 | 1 | 5 | 4 | 1 | 1.3333 | 4 | 1 | 1.3333 | 1 | 2 | 1 | 5 | 1.3333 | 3 | 2 | 1 | 1 | 1.3333 | 1 | 3 | 2.5 | 1 | 1.3333 | 5 | 1.6667 | 5 | 2 | 1 | 4 | 2 | 1 | 1 | 3 | 1 | 4 | 2 | 1.6667 | 1.6667 | 4 | 1.5 | 5 | 3 | 1
261 | 7.6667 | 5.3333 | 9.6667 | 15 | 20.6667 | 32.6667 | 37.3333 | 44.3333 | 51.6667 | 59.1667 | 63.1667 | 72.1667 | 78.5 | 84 | 1.6667 | 1.6667 | 1 | 1 | 1 | 1.3333 | 1 | 1 | 2 | 1.3333 | 1 | 1 | 1 | 2 | 1 | 1.6667 | 5 | 2.5 | 2.5 | 2 | 1 | 1.6667 | 1 | 1 | 2 | 1 | 2 | 2 | 4 | 1.3333 | 1 | 1 | 2 | 1 | 2.5 | 2 | 1 | 1 | 1 | 1 | 1 | 2.5 | 3 | 2.5 | 2 | 1.3333 | 2 | 1 | 1.5 | 1 | 1 | 2
262 | 14.3333 | 8.3333 | 19.3333 | 29 | 36.1667 | 45.6667 | 50.6667 | 58.1667 | 67.1667 | 74.6667 | 81.5 | 91.1667 | 99.1667 | 107.1667 | 3 | 1 | 3 | 1.3333 | 2 | 4 | 4 | 1 | 4 | 3 | 1.6667 | 1 | 1.6667 | 1 | 1.5 | 3 | 1.6667 | 1.3333 | 1.5 | 5 | 2 | 1 | 1 | 1 | 1.5 | 1 | 2 | 3 | 1 | 3 | 4 | 1 | 4 | 1 | 1 | 1.5 | 3 | 1 | 1.3333 | 1.5 | 1 | 4 | 1.6667 | 3 | 1 | 1 | 5 | 1 | 4 | 1 | 2 | 1
263 | 12 | 9.3333 | 15 | 26.1667 | 35.1667 | 42.1667 | 49.8333 | 54.3333 | 68 | 78.5 | 84 | 89 | 97.5 | 102.5 | 3 | 4 | 1 | 1.3333 | 1.6667 | 1 | 2 | 1 | 5 | 2.5 | 2 | 1.6667 | 5 | 2 | 1 | 1 | 1 | 1 | 1 | 4 | 4 | 1.6667 | 1 | 1 | 1 | 1 | 1 | 1.5 | 5 | 1.6667 | 2 | 5 | 3 | 2.5 | 2 | 3 | 1 | 1 | 1 | 2.5 | 1 | 2 | 1 | 1 | 1 | 2.5 | 4 | 1 | 1 | 1 | 2 | 1
264 | 10.1667 | 8.1667 | 14.1667 | 19 | 29 | 36 | 45.5 | 50.8333 | 57.6667 | 64 | 68 | 76.3333 | 85.3333 | 96.6667 | 1.6667 | 1.5 | 1 | 4 | 1 | 1 | 2.5 | 1.5 | 1 | 1.5 | 1.3333 | 1 | 3 | 1 | 5 | 1 | 1 | 2 | 3 | 1 | 2 | 5 | 1.5 | 1 | 1.3333 | 1 | 1.5 | 1.5 | 1.3333 | 2 | 1.5 | 2 | 3 | 1 | 1.3333 | 1 | 1 | 1 | 1 | 1 | 4 | 1 | 2 | 1.3333 | 1 | 1 | 3 | 4 | 4 | 5 | 1.3333 | 1
265 | 14.5 | 11.5 | 17.5 | 27.5 | 34 | 43.3333 | 51.3333 | 55.3333 | 61 | 67 | 76.5 | 80.5 | 85.8333 | 91.8333 | 3 | 5 | 1 | 2.5 | 2 | 1 | 2 | 1 | 1 | 1 | 4 | 4 | 2 | 1 | 2 | 1.5 | 4 | 1.3333 | 1 | 3 | 2 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 2 | 1.6667 | 1 | 1 | 1 | 1.5 | 1.5 | 2 | 2 | 1 | 2.5 | 4 | 1 | 1 | 1 | 1 | 1 | 1.3333 | 2 | 1 | 1 | 1 | 3 | 1
266 | 16 | 9 | 18.5 | 27.5 | 36.5 | 43 | 49.6667 | 58.6667 | 67.6667 | 76.3333 | 81 | 90 | 94.5 | 104.6667 | 4 | 1 | 2 | 2 | 3 | 4 | 1.5 | 1 | 5 | 1.6667 | 1.3333 | 1 | 1.5 | 4 | 1 | 2.5 | 2.5 | 1 | 2 | 1 | 1.6667 | 1 | 2 | 2 | 1 | 3 | 1 | 4 | 1 | 4 | 2 | 2 | 1 | 1.6667 | 5 | 1 | 1 | 1.6667 | 1 | 1 | 1 | 1 | 5 | 2 | 1 | 1.5 | 1 | 1 | 1.6667 | 3 | 2.5 | 3
267 | 8 | 6 | 10 | 19.8333 | 25.8333 | 31.8333 | 38 | 49.1667 | 61.1667 | 70 | 80 | 89.3333 | 93.3333 | 103 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 5 | 2 | 1.3333 | 1.5 | 1 | 3 | 1 | 1 | 1.5 | 2.5 | 1 | 1 | 1.6667 | 1 | 2.5 | 1 | 1.5 | 4 | 4 | 1.6667 | 1 | 5 | 4 | 2 | 1.3333 | 1 | 1.5 | 5 | 2.5 | 2 | 3 | 2.5 | 2.5 | 1.3333 | 4 | 1.5 | 1 | 1 | 1 | 1 | 1.6667 | 4 | 3 | 1
268 | 11.5 | 5.5 | 14.5 | 21 | 26.8333 | 33.8333 | 40.8333 | 51.8333 | 61.8333 | 65.8333 | 71 | 78 | 89 | 94 | 2 | 1 | 1 | 1.5 | 1 | 5 | 2 | 1 | 2.5 | 1 | 1 | 2 | 1.5 | 1.3333 | 2 | 1 | 2 | 1 | 2 | 2 | 1 | 4 | 1 | 1 | 2 | 3 | 5 | 1 | 2 | 1 | 5 | 2 | 1 | 1 | 1 | 1 | 1.5 | 1 | 1 | 1.6667 | 1 | 2 | 3 | 1 | 2 | 2 | 4 | 3 | 1 | 2 | 1 | 1
269 | 9.3333 | 6.3333 | 16.3333 | 23.8333 | 30.5 | 37.5 | 43.1667 | 49.5 | 55.8333 | 64.8333 | 72.8333 | 83.6667 | 92.1667 | 102.3333 | 2 | 2 | 1.3333 | 1 | 2 | 1 | 2 | 5 | 2 | 2.5 | 1 | 2 | 2 | 1.6667 | 1 | 2 | 1 | 1 | 3 | 2 | 1 | 1 | 1.6667 | 2 | 2 | 2 | 1.3333 | 1 | 1 | 3 | 1.3333 | 1 | 1 | 1 | 2 | 5 | 1 | 1 | 1 | 5 | 1.3333 | 3 | 5 | 1.5 | 5 | 1.5 | 1 | 1 | 1.6667 | 3 | 3 | 2.5
270 | 15 | 9.6667 | 18.5 | 29.8333 | 34.1667 | 41.1667 | 53.1667 | 65.1667 | 69.5 | 75.5 | 85.5 | 91.8333 | 96.5 | 105.5 | 1.6667 | 2 | 5 | 1 | 4 | 1.3333 | 1.5 | 2 | 4 | 5 | 1 | 1.3333 | 1 | 1 | 1.3333 | 1 | 2 | 2 | 2 | 1 | 3 | 1 | 5 | 3 | 5 | 2 | 2 | 3 | 1 | 1 | 1.3333 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 4 | 3 | 1.6667 | 2 | 1.6667 | 1 | 1 | 1.6667 | 1 | 1 | 4 | 1 | 2 | 2
271 | 9.5 | 6 | 12.5 | 20.5 | 29.5 | 41.5 | 53 | 59.5 | 70.1667 | 80.6667 | 88.6667 | 94.5 | 103.5 | 115.5 | 1 | 1 | 2 | 2 | 2.5 | 1 | 1 | 2 | 4 | 2 | 1 | 1 | 2 | 1 | 4 | 2 | 5 | 2 | 1 | 4 | 3 | 1.5 | 4 | 3 | 1 | 2.5 | 1 | 2 | 5 | 2 | 2 | 1.6667 | 1 | 4 | 4 | 1.5 | 2 | 3 | 2 | 1 | 1.3333 | 2.5 | 1 | 1 | 2 | 1 | 1 | 5 | 2 | 4 | 5 | 1
272 | 10.3333 | 6.3333 | 14 | 25 | 35.6667 | 41.6667 | 50.6667 | 57.6667 | 64.1667 | 70.1667 | 78.6667 | 87.6667 | 93.6667 | 102.1667 | 1.3333 | 3 | 1 | 1 | 3 | 1 | 2 | 1.6667 | 1 | 1 | 5 | 4 | 1.6667 | 2 | 5 | 2 | 1.5 | 1 | 2.5 | 1 | 1.3333 | 1.6667 | 3 | 3 | 2 | 2 | 1.6667 | 1.3333 | 2 | 1 | 2 | 1.5 | 1 | 1 | 1 | 3 | 1 | 1.5 | 1 | 5 | 1.6667 | 2 | 1.3333 | 4 | 1 | 3 | 1 | 1 | 2.5 | 2 | 3 | 1
273 | 10.1667 | 6.6667 | 13.6667 | 18.3333 | 25 | 30.8333 | 40.5 | 45.8333 | 55.8333 | 62.3333 | 70 | 76.5 | 85 | 96.5 | 1.6667 | 1 | 1 | 3 | 1 | 2.5 | 1 | 2.5 | 1.3333 | 1.3333 | 1 | 1 | 1 | 1.6667 | 3 | 1 | 1.3333 | 2.5 | 1 | 1 | 2 | 4 | 2 | 1.6667 | 1.5 | 1 | 1.3333 | 1.5 | 2.5 | 2 | 2.5 | 3 | 1 | 2.5 | 2 | 1 | 1 | 4 | 1.6667 | 1 | 2.5 | 1.6667 | 1.3333 | 1 | 1.5 | 1 | 5 | 1 | 1 | 5 | 2.5 | 3
274 | 11.1667 | 8 | 14.6667 | 24.6667 | 35.1667 | 50.6667 | 60.6667 | 69.1667 | 80.6667 | 87.1667 | 96.5 | 103.5 | 114 | 120 | 2.5 | 2 | 2.5 | 1 | 1.6667 | 1.5 | 1 | 2.5 | 4 | 2.5 | 2.5 | 1 | 2 | 2.5 | 4 | 2 | 1.5 | 5 | 4 | 5 | 3 | 2.5 | 2.5 | 2 | 2.5 | 4 | 1 | 1 | 5 | 2 | 2.5 | 2 | 2 | 1 | 2.5 | 1 | 1 | 5 | 2 | 1.3333 | 1 | 1 | 4 | 1 | 1 | 1.5 | 5 | 3 | 1.5 | 1 | 1 | 2.5
275 | 11.3333 | 8.6667 | 14.3333 | 19.3333 | 24.8333 | 33.6667 | 41.6667 | 49.6667 | 58 | 66.6667 | 73.6667 | 80.1667 | 89.8333 | 98.8333 | 2 | 1.3333 | 1.3333 | 4 | 1.6667 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 1.6667 | 1.5 | 1.3333 | 1 | 1.3333 | 2.5 | 1 | 4 | 1 | 5 | 1 | 1 | 2 | 3 | 2 | 1 | 4 | 2 | 1 | 1.3333 | 1 | 4 | 1.6667 | 2 | 2 | 1 | 1 | 3 | 2 | 2.5 | 1 | 1 | 5 | 2 | 1.6667 | 1 | 1 | 1 | 4 | 3
276 | 12.3333 | 9.3333 | 14.6667 | 18.6667 | 27.1667 | 32.8333 | 38.6667 | 44.5 | 52.5 | 62.5 | 68.1667 | 78.1667 | 87.6667 | 97.3333 | 3 | 1.3333 | 2 | 3 | 1 | 2 | 1.3333 | 1 | 1 | 1 | 1 | 1 | 1.5 | 3 | 2 | 2 | 1.6667 | 1.3333 | 1.6667 | 1 | 2.5 | 1 | 1.3333 | 1 | 2.5 | 1.3333 | 1 | 1 | 1 | 4 | 1 | 2 | 2 | 3 | 1 | 4 | 1.6667 | 1 | 1.3333 | 1.6667 | 1 | 1 | 5 | 3 | 1 | 5 | 1 | 2.5 | 5 | 1.5 | 1.5 | 1.6667
277 | 7.3333 | 5.3333 | 14 | 18.8333 | 29.8333 | 38.3333 | 46 | 52 | 57.1667 | 63.6667 | 68.1667 | 73.3333 | 82.3333 | 86.8333 | 1.3333 | 2 | 1 | 1 | 1 | 1 | 5 | 1.6667 | 1.5 | 1 | 1.3333 | 1 | 1 | 3 | 4 | 3 | 2.5 | 1 | 2 | 3 | 1.6667 | 3 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1.5 | 1.6667 | 1 | 1 | 2 | 2.5 | 1 | 1 | 1.5 | 1 | 1 | 1.5 | 1 | 1.6667 | 1 | 1 | 3 | 4 | 1.5 | 1 | 1 | 1
278 | 15 | 13 | 22 | 29.6667 | 38.1667 | 42.1667 | 51.1667 | 60.1667 | 64.8333 | 76.8333 | 80.8333 | 86.6667 | 92 | 99 | 5 | 2 | 2 | 4 | 1 | 1 | 4 | 3 | 1 | 1 | 1.6667 | 4 | 1 | 1 | 1.5 | 5 | 1 | 1 | 1 | 1 | 5 | 1 | 2 | 1 | 2 | 2 | 1 | 4 | 1.3333 | 1 | 1.3333 | 1 | 3 | 5 | 2 | 2 | 1 | 1 | 1 | 1 | 1.5 | 2 | 1 | 1.3333 | 1.3333 | 1 | 1 | 2 | 2 | 1 | 3 | 1
279 | 11 | 9 | 14 | 25 | 29 | 35 | 43 | 52.8333 | 57.8333 | 68.3333 | 75.3333 | 82.1667 | 90.6667 | 96.1667 | 1 | 1.3333 | 1.6667 | 5 | 1 | 1 | 2 | 1 | 1 | 1 | 4 | 5 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 5 | 1 | 1 | 1 | 1.3333 | 5 | 1.5 | 2 | 1 | 1 | 1 | 2 | 2.5 | 1 | 4 | 3 | 4 | 1 | 1 | 1 | 1.3333 | 2 | 2.5 | 1 | 2.5 | 3 | 2 | 1 | 1 | 1 | 2 | 1.5
280 | 10.6667 | 8.3333 | 19.6667 | 29.3333 | 35.8333 | 40.3333 | 50.5 | 57.5 | 66.1667 | 76.5 | 82.6667 | 90.6667 | 96.1667 | 103.6667 | 1.3333 | 4 | 2 | 1 | 1 | 1.3333 | 4 | 5 | 1.6667 | 1 | 2 | 5 | 2.5 | 1 | 2 | 1 | 1 | 1 | 1.5 | 1 | 2.5 | 3 | 1.6667 | 3 | 4 | 1 | 1 | 1 | 5 | 1.3333 | 1 | 1.3333 | 1.3333 | 5 | 2.5 | 1.5 | 1 | 1.6667 | 1 | 2.5 | 5 | 1 | 1 | 1 | 1 | 2 | 1.5 | 1 | 2 | 2 | 1 | 2.5
281 | 20.5 | 14 | 26.5 | 37.8333 | 48.5 | 54.5 | 62 | 67.5 | 76.1667 | 85.5 | 92.5 | 105.5 | 110.5 | 117.5 | 5 | 4 | 2 | 3 | 4 | 2.5 | 1 | 5 | 2.5 | 5 | 2.5 | 1.3333 | 5 | 1.6667 | 2 | 2 | 1 | 1 | 3 | 1 | 2.5 | 1 | 1 | 3 | 1 | 1 | 2.5 | 1 | 1 | 1.6667 | 1 | 5 | 1 | 1.3333 | 4 | 3 | 1 | 2 | 2.5 | 1.5 | 5 | 5 | 2 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 3 | 1
282 | 10.3333 | 7.3333 | 12.3333 | 22 | 29 | 37.5 | 45.3333 | 50.8333 | 57.5 | 65 | 72.5 | 78 | 84.6667 | 93.6667 | 1.3333 | 2 | 1 | 3 | 1.3333 | 1.6667 | 1 | 1 | 3 | 1 | 4 | 1.6667 | 1 | 4 | 1 | 1 | 1 | 1 | 5 | 1.5 | 1.5 | 1.3333 | 3 | 2 | 1 | 1 | 2.5 | 1 | 1.6667 | 2 | 1 | 2 | 1.5 | 2.5 | 1 | 2.5 | 1 | 1 | 1.5 | 4 | 2.5 | 1 | 1 | 1 | 2 | 1.6667 | 1.3333 | 1.6667 | 1 | 1.6667 | 5 | 1.3333
283 | 10.8333 | 7.5 | 18.8333 | 30.1667 | 36.6667 | 45.8333 | 54.1667 | 58.1667 | 64.1667 | 71.8333 | 78.8333 | 84.8333 | 90.3333 | 99.3333 | 1.5 | 1 | 3 | 2 | 1.3333 | 2 | 4 | 4 | 5 | 4 | 1.3333 | 1 | 1 | 3 | 1 | 1.5 | 2.5 | 2.5 | 1.6667 | 2.5 | 4 | 1.3333 | 1.5 | 1.5 | 1 | 1 | 1 | 1 | 2 | 1.6667 | 1.3333 | 1 | 2 | 1 | 1.6667 | 3 | 1.5 | 2 | 1 | 2.5 | 1.6667 | 2 | 1.3333 | 1 | 2.5 | 1 | 1 | 1 | 2 | 1 | 1 | 5
284 | 14.8333 | 8.8333 | 20.8333 | 24.8333 | 35.3333 | 41.6667 | 47.6667 | 51.6667 | 57.6667 | 68.1667 | 73.5 | 80.8333 | 90.8333 | 102.8333 | 1.5 | 1.3333 | 3 | 3 | 5 | 1 | 4 | 2 | 1 | 1 | 1 | 1 | 3 | 1.5 | 1 | 5 | 3 | 1 | 1 | 1.3333 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 4 | 1 | 2.5 | 3 | 1.3333 | 1 | 1.3333 | 1.6667 | 3 | 1.3333 | 2 | 1 | 3 | 1 | 5 | 1 | 5 | 2 | 3 | 2
285 | 6.3333 | 4.3333 | 15.3333 | 19.8333 | 32.5 | 37.5 | 51.5 | 56.8333 | 65.5 | 71.8333 | 77.3333 | 84.8333 | 94.8333 | 98.8333 | 1.3333 | 1 | 1 | 1 | 1 | 1 | 5 | 4 | 1 | 1.5 | 1 | 1 | 1.6667 | 1 | 5 | 5 | 1.3333 | 1.3333 | 1.3333 | 1 | 2 | 5 | 3 | 4 | 1 | 2 | 1 | 1.3333 | 1 | 1.3333 | 5 | 1.3333 | 2 | 1 | 2 | 1.3333 | 2.5 | 1 | 1 | 1 | 1 | 1.5 | 3 | 2 | 4 | 1 | 2.5 | 2.5 | 1 | 1 | 1 | 1
286 | 9.6667 | 7 | 14 | 26.6667 | 32.6667 | 41.6667 | 48.6667 | 56 | 65.1667 | 73.1667 | 79.5 | 86.5 | 93.5 | 100.1667 | 1 | 3 | 1 | 2 | 1.6667 | 1 | 3 | 1.3333 | 1.6667 | 5 | 2 | 4 | 1 | 3 | 1 | 1 | 1 | 5 | 1 | 2 | 3 | 2 | 1 | 1 | 2 | 3 | 1 | 1.3333 | 2.5 | 3 | 1.6667 | 2 | 2 | 1 | 1 | 4 | 2 | 1.6667 | 1 | 1.6667 | 2 | 2.5 | 1.5 | 1 | 4 | 1 | 1 | 1 | 1.6667 | 3 | 1 | 1
287 | 13.1667 | 9 | 19.5 | 29.1667 | 41.1667 | 47.1667 | 54.1667 | 63.1667 | 73.1667 | 85.8333 | 90.1667 | 94.8333 | 104.3333 | 116.3333 | 2 | 5 | 1 | 1 | 2.5 | 1.6667 | 1.3333 | 5 | 5 | 1.6667 | 2 | 1 | 2.5 | 2.5 | 5 | 2 | 1 | 1 | 2 | 2 | 1.6667 | 1.3333 | 1 | 3 | 2 | 1 | 4 | 2 | 3 | 1 | 5 | 1 | 5 | 3 | 3 | 1.6667 | 1 | 1 | 1.3333 | 1 | 1 | 1 | 1.6667 | 1 | 5 | 2.5 | 1 | 1 | 5 | 2 | 1 | 4
288 | 10.8333 | 8.5 | 14.3333 | 25.8333 | 31.3333 | 39.3333 | 49.6667 | 53.6667 | 63.6667 | 71.6667 | 82.6667 | 89.5 | 97.1667 | 103.1667 | 1.5 | 1 | 5 | 1 | 1.3333 | 1 | 2.5 | 1 | 4 | 3 | 3 | 1.5 | 1.6667 | 1 | 1.3333 | 1.5 | 4 | 1 | 1.6667 | 1.3333 | 4 | 1.3333 | 3 | 2 | 1 | 1 | 1 | 1 | 2 | 1.6667 | 5 | 1.3333 | 1 | 1 | 2 | 4 | 1 | 5 | 4 | 1 | 1.6667 | 2 | 1.5 | 1.6667 | 1.6667 | 4 | 1 | 1 | 1.6667 | 1.3333 | 1 | 2
289 | 9.3333 | 6.5 | 11.3333 | 21.3333 | 29.8333 | 35.8333 | 41.3333 | 52.3333 | 58.3333 | 68.3333 | 77.8333 | 84 | 91.6667 | 97.1667 | 2 | 1 | 1 | 2.5 | 1.5 | 1.3333 | 1 | 1 | 1.3333 | 5 | 1.6667 | 2 | 1 | 1 | 2.5 | 4 | 1 | 2.5 | 1.5 | 1 | 1 | 1 | 2 | 1.5 | 3 | 1 | 4 | 3 | 1 | 3 | 1 | 1 | 2 | 2 | 5 | 1 | 1.5 | 2 | 5 | 1 | 1.6667 | 1 | 1 | 2.5 | 1.6667 | 3 | 2 | 1 | 1 | 1 | 2.5 | 1
290 | 11.6667 | 9 | 16.6667 | 28.6667 | 36.6667 | 45 | 49 | 59.5 | 66 | 71.1667 | 78.6667 | 87.6667 | 94.6667 | 106.6667 | 3 | 1.5 | 1.5 | 3 | 1 | 1.6667 | 4 | 1 | 2 | 1 | 4 | 5 | 1 | 5 | 1 | 1 | 1.3333 | 1 | 1 | 5 | 1 | 1 | 1 | 1 | 5 | 1 | 1.5 | 3 | 1 | 2 | 2.5 | 1 | 1 | 1 | 1.5 | 1.6667 | 1 | 1 | 4 | 1.5 | 1 | 1 | 2 | 5 | 2 | 2 | 2 | 1 | 3 | 2 | 5 | 2
291 | 12.6667 | 10 | 17.1667 | 22.1667 | 27.5 | 39 | 47.3333 | 54.6667 | 60.5 | 70.1667 | 79.1667 | 84.3333 | 90.3333 | 95.5 | 5 | 1.3333 | 1.6667 | 2 | 1.6667 | 1 | 2.5 | 2 | 1 | 1 | 1 | 2 | 1.3333 | 2 | 1 | 1 | 4 | 4 | 1.5 | 2 | 1.3333 | 5 | 1 | 1 | 1.3333 | 1.5 | 2 | 2.5 | 1 | 2.5 | 1 | 1.3333 | 5 | 1.3333 | 1.3333 | 2 | 1 | 1 | 5 | 2 | 1.6667 | 1.5 | 1 | 1 | 2 | 1 | 1.5 | 1.5 | 1.5 | 1 | 1 | 1.6667
292 | 19 | 13 | 21.5 | 29 | 33 | 37.5 | 45.5 | 51 | 55.6667 | 61.6667 | 69.6667 | 79.8333 | 91.8333 | 100.1667 | 2.5 | 4 | 4 | 2.5 | 1 | 5 | 1.5 | 1 | 2 | 2 | 2.5 | 1 | 1 | 1 | 1 | 1 | 1.5 | 1 | 1 | 1 | 2.5 | 1.5 | 3 | 1 | 2.5 | 1 | 1 | 1 | 1.3333 | 1.3333 | 1 | 1 | 1 | 2 | 2 | 1 | 3 | 1 | 3 | 1 | 1.6667 | 1 | 2.5 | 5 | 2 | 1 | 5 | 4 | 1 | 1 | 1.3333 | 5
293 | 9.6667 | 7.3333 | 11.6667 | 15.6667 | 25.5 | 32.8333 | 41.1667 | 50.1667 | 56 | 63 | 71.5 | 77.3333 | 82.3333 | 90.1667 | 1 | 3 | 2 | 1.3333 | 1 | 1.3333 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 5 | 2.5 | 1.3333 | 1.6667 | 1.6667 | 3 | 1 | 1.3333 | 5 | 1 | 1 | 1 | 2 | 5 | 1 | 1 | 2.5 | 1 | 1.3333 | 1 | 4 | 1 | 1 | 3 | 2.5 | 2 | 1 | 1 | 1 | 1.3333 | 2.5 | 1 | 1 | 1.6667 | 1.3333 | 3 | 1.3333 | 1 | 2.5
294 | 12 | 10 | 14 | 19 | 23.5 | 28 | 36.1667 | 40.1667 | 51.8333 | 65.3333 | 71.3333 | 84.3333 | 91.1667 | 97.5 | 1.5 | 1.5 | 2 | 5 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1.5 | 1 | 1 | 1 | 1 | 1.5 | 1 | 1 | 4 | 1 | 1.5 | 1.6667 | 1 | 1 | 1 | 1 | 1 | 4 | 1.6667 | 5 | 5 | 1 | 5 | 2.5 | 1 | 1 | 3 | 1 | 5 | 1.5 | 2.5 | 4 | 1 | 2.5 | 1.3333 | 2 | 1.3333 | 2 | 2 | 1
295 | 9 | 5 | 11.3333 | 17.8333 | 29.8333 | 38.8333 | 45.1667 | 53.8333 | 61.1667 | 67.1667 | 76.6667 | 83.1667 | 92.1667 | 100 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 1.3333 | 2 | 1 | 1 | 2.5 | 5 | 1 | 5 | 1 | 1 | 4 | 3 | 1 | 1 | 2 | 1.6667 | 1.6667 | 2 | 2.5 | 2.5 | 1.6667 | 1 | 4 | 1.3333 | 1 | 1.5 | 2.5 | 1 | 1 | 1 | 1 | 5 | 2.5 | 3 | 1 | 1 | 1.5 | 2 | 3 | 2 | 2 | 4 | 1.3333 | 1 | 1.5
296 | 14.8333 | 12.5 | 18.3333 | 28.8333 | 37 | 46.6667 | 51.3333 | 57.3333 | 64 | 73.3333 | 83.3333 | 88.3333 | 94.3333 | 100.5 | 4 | 2.5 | 2 | 4 | 1.3333 | 1 | 1.5 | 2 | 1.5 | 4 | 1 | 4 | 1.5 | 1 | 4 | 1.6667 | 2 | 1.6667 | 5 | 1 | 1 | 1 | 1 | 1.6667 | 3 | 1 | 1 | 1 | 3 | 1 | 1.6667 | 1 | 2 | 2 | 1.3333 | 4 | 1 | 2 | 3 | 4 | 1.6667 | 1 | 1.3333 | 1 | 2 | 1 | 1 | 2 | 2 | 1 | 1.5 | 1.6667
297 | 13.3333 | 11 | 17.3333 | 24 | 30.5 | 39 | 43.8333 | 49.6667 | 59.6667 | 68.5 | 79.6667 | 85.6667 | 91.6667 | 99.3333 | 1 | 4 | 1 | 5 | 1 | 1.3333 | 2 | 2 | 1 | 1.6667 | 1.5 | 2.5 | 2.5 | 1 | 2 | 1 | 1 | 5 | 1.5 | 1 | 1 | 1.3333 | 1 | 1.5 | 1.3333 | 1 | 2 | 1.5 | 2 | 1 | 3 | 4 | 1.3333 | 1 | 4 | 2.5 | 1.5 | 5 | 3 | 1.6667 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 1 | 1.5 | 1.5 | 1.6667 | 3
298 | 9 | 4.6667 | 12 | 21 | 26.5 | 36 | 42.1667 | 51.6667 | 57.6667 | 63.3333 | 72.8333 | 78.8333 | 89.8333 | 96.1667 | 1 | 1.6667 | 1 | 1 | 3 | 1.3333 | 2 | 1 | 2 | 2 | 1 | 4 | 2 | 1 | 1 | 1.5 | 5 | 1 | 1 | 2.5 | 1 | 2 | 1.5 | 1.6667 | 1.5 | 1 | 5 | 2 | 1 | 1 | 2 | 2 | 1 | 1 | 2 | 1.6667 | 1 | 1 | 5 | 2.5 | 2 | 1.3333 | 1 | 1.6667 | 3 | 3 | 4 | 1 | 1 | 3 | 1.3333 | 1
299 | 13 | 8 | 16.3333 | 21.8333 | 25.8333 | 36.6667 | 45.3333 | 54.8333 | 63 | 69.5 | 76 | 84 | 88.5 | 95.5 | 2 | 2.5 | 1 | 2.5 | 1 | 4 | 2 | 1.3333 | 1 | 1 | 2.5 | 1 | 1 | 1 | 1 | 1 | 5 | 1.5 | 1.3333 | 3 | 1 | 2 | 4 | 1.6667 | 3 | 1 | 2.5 | 3 | 1.6667 | 4 | 1 | 1.5 | 2 | 1 | 1 | 2.5 | 1.5 | 1 | 3 | 1 | 1 | 1 | 3 | 3 | 1 | 1.5 | 1 | 1 | 1 | 2 | 1.5 | 2.5
300 | 10 | 5 | 12.5 | 16.8333 | 25.3333 | 29.3333 | 34.8333 | 40.3333 | 45.3333 | 50.3333 | 62.3333 | 66.3333 | 72.6667 | 83.6667 | 2 | 1 | 1 | 1 | 4 | 1 | 1.5 | 1 | 1 | 1 | 1 | 1.3333 | 2.5 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1.5 | 1 | 1 | 1.5 | 2 | 1 | 1.3333 | 1.6667 | 1 | 1 | 1 | 2 | 1 | 4 | 1 | 2 | 5 | 1 | 1 | 1 | 1 | 1 | 1.3333 | 1 | 3 | 1 | 1 | 5 | 4
301 | 6.6667 | 4.6667 | 9.6667 | 13.6667 | 22.8333 | 30.3333 | 41.1667 | 51.6667 | 59.6667 | 66.6667 | 75.5 | 86.5 | 91.6667 | 99 | 1 | 1 | 1 | 1.6667 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2.5 | 2 | 3 | 1.6667 | 1 | 2.5 | 2 | 2 | 5 | 1.5 | 1.3333 | 3 | 2.5 | 2 | 2 | 4 | 4 | 1.5 | 1 | 1.5 | 1 | 1 | 2 | 3 | 1.5 | 1.3333 | 1 | 5 | 1.5 | 2 | 2.5 | 5 | 1 | 1.5 | 1.6667 | 1 | 1.3333 | 1 | 1 | 4
302 | 12.8333 | 10.5 | 15.1667 | 20.6667 | 25.6667 | 39.5 | 47 | 51.3333 | 56.3333 | 61.6667 | 69.3333 | 79.1667 | 84.8333 | 99.8333 | 4 | 1 | 3 | 2.5 | 1.3333 | 1 | 1 | 1.3333 | 1 | 1 | 1.5 | 2 | 2 | 1 | 1 | 1 | 1.3333 | 5 | 5 | 2.5 | 2 | 2.5 | 1 | 2 | 1 | 1.3333 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 1.3333 | 1.6667 | 4 | 1 | 1 | 2 | 4 | 2.5 | 1.3333 | 2 | 1 | 1.6667 | 1 | 5 | 5 | 1 | 4
303 | 12.3333 | 8.6667 | 15.3333 | 22.3333 | 26.6667 | 34.1667 | 41.1667 | 46.6667 | 53 | 64.5 | 71.1667 | 77.1667 | 82.6667 | 88.1667 | 5 | 1.6667 | 1 | 1 | 2 | 1.6667 | 1 | 2 | 2 | 1 | 1 | 3 | 1 | 1 | 1.3333 | 1 | 2 | 2.5 | 1 | 2 | 1 | 1 | 3 | 2 | 2.5 | 1 | 1 | 1 | 1 | 2 | 2 | 1.3333 | 5 | 2 | 2.5 | 2 | 1 | 2 | 2 | 1.6667 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 1.5 | 1 | 2.5 | 1 | 1
304 | 9 | 4 | 11 | 17 | 28.6667 | 38 | 42.6667 | 52 | 57.1667 | 64.1667 | 72.5 | 77.5 | 88.1667 | 95.8333 | 1 | 1 | 1 | 1 | 1 | 4 | 1 | 1 | 2.5 | 1.5 | 1 | 1 | 1.6667 | 4 | 4 | 2 | 3 | 4 | 1.3333 | 1 | 1 | 1 | 1 | 1.6667 | 4 | 1 | 1.3333 | 3 | 1 | 1 | 1.5 | 1.6667 | 1 | 3 | 2 | 1 | 1.3333 | 1 | 2 | 4 | 1 | 2 | 1 | 1 | 1 | 1.6667 | 5 | 3 | 2.5 | 2.5 | 1 | 1.6667
305 | 7.8333 | 5 | 9.8333 | 19.1667 | 25.1667 | 32.3333 | 37.5 | 44 | 52.6667 | 60 | 72 | 84.3333 | 89.3333 | 98 | 1.5 | 1 | 1 | 1.5 | 1.5 | 1.3333 | 1 | 1 | 1.3333 | 3 | 4 | 1 | 2.5 | 1 | 1.5 | 1 | 2.5 | 2 | 1.6667 | 1 | 1 | 1 | 1.5 | 1.6667 | 1 | 1 | 2.5 | 2 | 1.6667 | 1 | 3 | 3 | 1.3333 | 1 | 1 | 4 | 2.5 | 2.5 | 4 | 3 | 5 | 1.3333 | 5 | 1 | 1 | 1 | 2 | 1 | 1 | 1.6667 | 5 | 1
306 | 11.5 | 6 | 15.6667 | 22.1667 | 27 | 35.1667 | 42.8333 | 49.1667 | 57.1667 | 64.5 | 70.3333 | 78.6667 | 85 | 92.1667 | 1.3333 | 1.6667 | 2 | 1 | 1.5 | 4 | 1.6667 | 2.5 | 2 | 1 | 2.5 | 1 | 1 | 1.3333 | 1.5 | 1 | 1.6667 | 2 | 2.5 | 2 | 4 | 1 | 1 | 1.6667 | 1.6667 | 1 | 1.6667 | 2 | 2.5 | 1 | 2.5 | 2 | 2 | 1 | 3 | 1.3333 | 1 | 1 | 1.3333 | 2.5 | 1.3333 | 1 | 1 | 5 | 1.6667 | 1 | 2 | 1.6667 | 1.5 | 1 | 1.6667 | 3
307 | 8.1667 | 4 | 14.1667 | 25.8333 | 33.6667 | 41.3333 | 52.3333 | 59.8333 | 65.5 | 74.3333 | 79.3333 | 85.3333 | 93.6667 | 98.1667 | 1 | 1 | 1 | 1 | 2.5 | 1.6667 | 1 | 5 | 1.6667 | 1 | 4 | 5 | 4 | 1 | 1.3333 | 1.5 | 2 | 3 | 1.6667 | 1 | 5 | 2 | 3 | 1 | 1 | 2 | 1.5 | 3 | 1.6667 | 1 | 2 | 1 | 4 | 1.3333 | 2.5 | 1 | 1 | 1 | 1.3333 | 1.6667 | 2 | 1.5 | 1 | 1.5 | 1 | 5 | 1.3333 | 1 | 1 | 1 | 1 | 1.5
308 | 13 | 7 | 19 | 23.3333 | 27.8333 | 33.3333 | 46.3333 | 53.6667 | 60.8333 | 66.8333 | 77.8333 | 83.8333 | 94.8333 | 105.1667 | 1.5 | 2 | 2.5 | 1 | 5 | 1 | 1 | 5 | 1.3333 | 1 | 1 | 1 | 1.5 | 1 | 1 | 1 | 1 | 1 | 2 | 1.5 | 2 | 3 | 4 | 4 | 1.3333 | 3 | 2 | 1 | 1 | 1.6667 | 1.5 | 3 | 2.5 | 1 | 1 | 1.5 | 1 | 3 | 2 | 5 | 2 | 2 | 1 | 1 | 3 | 4 | 2 | 2 | 1.6667 | 5 | 2 | 1.6667
309 | 10.6667 | 4.6667 | 16.6667 | 26.6667 | 32 | 42.8333 | 51.3333 | 56.6667 | 62.6667 | 67.6667 | 75.8333 | 84.3333 | 96.3333 | 101.6667 | 1 | 1 | 1 | 1.6667 | 5 | 1 | 4 | 2 | 1 | 4 | 3 | 2 | 1 | 2 | 1.3333 | 1 | 1.5 | 4 | 4 | 1.3333 | 2 | 1.5 | 4 | 1 | 1.6667 | 1 | 1 | 1.6667 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 2 | 4 | 1 | 1.6667 | 1.5 | 2 | 3 | 2.5 | 1 | 2.5 | 2 | 5 | 2.5 | 1 | 1 | 1.3333 | 2
310 | 13 | 11 | 15 | 21.1667 | 31.1667 | 35.5 | 47 | 53.5 | 60.5 | 66.5 | 73.1667 | 79 | 87.1667 | 96 | 1 | 5 | 3 | 2 | 1 | 1 | 1 | 1 | 1.6667 | 2.5 | 1 | 1 | 1.5 | 4 | 3 | 1.5 | 1 | 1 | 1 | 1.3333 | 2 | 4 | 2.5 | 3 | 1.5 | 2 | 1 | 2 | 1 | 1 | 1 | 4 | 3 | 1 | 1 | 1 | 1 | 1.6667 | 1.5 | 2.5 | 1 | 1.3333 | 2.5 | 1 | 3 | 2.5 | 1 | 1.6667 | 1 | 4 | 1.3333 | 2.5
311 | 8.6667 | 6.3333 | 12.6667 | 17.1667 | 29.6667 | 34.5 | 40.8333 | 47.8333 | 52.1667 | 59.1667 | 69 | 79 | 86.5 | 99 | 1 | 2 | 1.6667 | 1.6667 | 1 | 1.3333 | 1 | 3 | 1 | 1 | 1.5 | 1 | 1.5 | 5 | 1 | 5 | 1 | 1.3333 | 1.5 | 1 | 1.5 | 1.5 | 2 | 1.3333 | 2.5 | 2 | 1.5 | 1 | 1 | 1 | 1 | 1.3333 | 3 | 1 | 2 | 1 | 5 | 1 | 2.5 | 1.3333 | 1 | 2 | 5 | 2 | 2 | 1.5 | 3 | 1 | 2.5 | 4 | 5 | 1
312 | 12 | 8 | 16.5 | 25.5 | 30 | 35 | 42.5 | 47 | 53.5 | 62.1667 | 68.1667 | 75.6667 | 83.1667 | 88.6667 | 5 | 1 | 1 | 1 | 3 | 1 | 2 | 2.5 | 1.5 | 1 | 4 | 2.5 | 1 | 1.5 | 1 | 1 | 1 | 1.6667 | 1 | 1.3333 | 1 | 1 | 1.5 | 4 | 1.5 | 1 | 1 | 1 | 1 | 2.5 | 1.6667 | 1.3333 | 1.6667 | 1 | 1 | 5 | 3 | 1 | 1 | 1 | 1 | 2.5 | 1.5 | 2.5 | 1 | 1 | 4 | 1.5 | 2.5 | 1 | 1 | 1
313 | 9.3333 | 6 | 14.3333 | 19.5 | 26.5 | 31.6667 | 39.6667 | 47.6667 | 54.6667 | 62.6667 | 73.6667 | 79 | 85.3333 | 89.6667 | 1 | 1 | 1 | 3 | 2 | 1.3333 | 3 | 2 | 1.6667 | 1.5 | 1 | 1 | 1.3333 | 2 | 1.6667 | 2 | 1 | 1.5 | 1 | 1.6667 | 1 | 1 | 5 | 1 | 1 | 1 | 5 | 1 | 1 | 4 | 1 | 1 | 3 | 1 | 2 | 2 | 3 | 4 | 2 | 2 | 1 | 1.3333 | 1 | 2 | 1 | 1.3333 | 1 | 3 | 1 | 1 | 1.3333 | 1
314 | 6.8333 | 4.3333 | 13.8333 | 18.8333 | 25.8333 | 30.5 | 35.1667 | 43.5 | 49.5 | 55.5 | 65.8333 | 70.5 | 79.6667 | 85.5 | 1 | 1 | 1 | 1.3333 | 1 | 1.5 | 3 | 4 | 1 | 2 | 1 | 1 | 1 | 1 | 2.5 | 2.5 | 1 | 1 | 1.6667 | 1 | 1 | 1 | 1.6667 | 1 | 1.6667 | 1 | 1.6667 | 4 | 2 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 5 | 1.6667 | 1.6667 | 1.3333 | 1 | 1 | 1.3333 | 3 | 2 | 1.6667 | 2.5 | 1 | 1.5 | 2 | 1.3333
315 | 10 | 8 | 13 | 21 | 26.5 | 37 | 44 | 49.6667 | 63.1667 | 74.6667 | 85.1667 | 92.6667 | 99.6667 | 106.5 | 1 | 4 | 1.5 | 1.5 | 1 | 1 | 1 | 2 | 1 | 4 | 1 | 2 | 1 | 1 | 2.5 | 1 | 2.5 | 2 | 1 | 5 | 4 | 1 | 1 | 1 | 1.6667 | 1 | 2 | 1 | 5 | 1 | 2.5 | 5 | 2.5 | 5 | 1 | 3 | 5 | 1 | 2 | 2.5 | 2 | 2.5 | 1 | 2 | 1 | 1 | 4 | 1 | 1.5 | 1.3333 | 3 | 1
316 | 13.5 | 8 | 20 | 26.5 | 33.6667 | 40.6667 | 48.1667 | 53.1667 | 62.6667 | 70.1667 | 76.1667 | 82.1667 | 92.1667 | 99.1667 | 1 | 1 | 1 | 5 | 1.5 | 4 | 5 | 1.5 | 1 | 1.5 | 3 | 1 | 2 | 1 | 2.5 | 1.6667 | 4 | 1 | 1 | 1 | 1.5 | 4 | 1 | 1 | 1 | 1.3333 | 1.6667 | 1 | 2.5 | 1 | 5 | 1 | 2 | 1 | 2.5 | 2 | 1.6667 | 1.6667 | 1.6667 | 1 | 1.6667 | 1.5 | 1.5 | 1.3333 | 1 | 3 | 3 | 3 | 1 | 1.5 | 2.5 | 2
317 | 14.6667 | 8 | 20.1667 | 31.5 | 40 | 49 | 54 | 59.8333 | 68.6667 | 74 | 81.3333 | 90.3333 | 99 | 106 | 1 | 4 | 2 | 1 | 5 | 1.6667 | 4 | 1.5 | 1.3333 | 4 | 5 | 1 | 1 | 1.5 | 1 | 5 | 2 | 1 | 5 | 1 | 2 | 1 | 1 | 1 | 1.5 | 2 | 1.3333 | 1 | 1.3333 | 1.5 | 1 | 5 | 1.3333 | 1 | 1.6667 | 1.3333 | 2 | 1 | 3 | 1.3333 | 1 | 4 | 2 | 2 | 4 | 2 | 1.6667 | 1 | 4 | 1 | 1 | 1
318 | 16 | 8 | 18.8333 | 24.8333 | 34.1667 | 42.3333 | 48 | 54.6667 | 59.8333 | 70.3333 | 77.6667 | 90.6667 | 95.1667 | 105 | 1 | 1 | 3 | 3 | 3 | 5 | 1.3333 | 1.5 | 1 | 2 | 1 | 2 | 1 | 1.3333 | 3 | 4 | 3 | 1.5 | 1.6667 | 2 | 1.5 | 1 | 1.5 | 1.6667 | 2 | 1 | 2 | 1.6667 | 1.5 | 1 | 1 | 1.6667 | 3 | 4 | 1.5 | 2 | 2 | 2 | 2 | 1.3333 | 5 | 3 | 4 | 1 | 1.5 | 1 | 1 | 1 | 2.5 | 5 | 1 | 1.3333
319 | 11.3333 | 9 | 17.3333 | 22.8333 | 30.8333 | 40.5 | 47 | 53.1667 | 61.5 | 69.5 | 77.1667 | 83 | 92 | 97 | 1 | 5 | 2 | 1 | 1.3333 | 1 | 1 | 5 | 2 | 1.5 | 1 | 1 | 1 | 1 | 1 | 5 | 2 | 5 | 1.6667 | 1 | 1.5 | 1 | 2.5 | 1.5 | 1 | 1.5 | 2 | 1.6667 | 1 | 1 | 5 | 1.3333 | 1 | 1 | 1 | 5 | 1.6667 | 1 | 4 | 1 | 1 | 2 | 1.5 | 1.3333 | 1 | 5 | 1.6667 | 1.3333 | 1 | 2 | 1 | 1
320 | 18.3333 | 13 | 25.3333 | 31 | 35.3333 | 41.8333 | 49.3333 | 61.3333 | 66.1667 | 77.8333 | 86.5 | 98.5 | 104.8333 | 112.1667 | 2 | 5 | 1 | 5 | 4 | 1.3333 | 5 | 2 | 2 | 1.3333 | 1.3333 | 1 | 1.3333 | 1 | 1 | 1 | 1 | 1 | 3 | 1.5 | 1.5 | 2.5 | 2.5 | 1 | 5 | 3 | 1 | 3 | 1.3333 | 1 | 1.5 | 1 | 1.6667 | 1 | 5 | 4 | 3 | 3 | 1.6667 | 1 | 5 | 5 | 1 | 1 | 1 | 1.3333 | 1 | 3 | 1.6667 | 1.6667 | 1 | 3
321 | 12 | 6 | 14 | 18.3333 | 28.3333 | 32.8333 | 38.8333 | 46.3333 | 54 | 62 | 67 | 75 | 84.3333 | 91.3333 | 1 | 2 | 1 | 2 | 2 | 4 | 1 | 1 | 1 | 1 | 1 | 1.3333 | 2.5 | 1 | 1.5 | 5 | 1 | 1.5 | 1 | 1 | 1.5 | 1 | 2.5 | 1 | 3 | 2.5 | 1 | 1 | 1.3333 | 1 | 1.3333 | 4 | 2 | 3 | 2 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 4 | 1 | 2 | 5 | 1.3333 | 1 | 1 | 2.5 | 1 | 2.5
322 | 12.5 | 6.5 | 16.5 | 22.1667 | 29.3333 | 34.6667 | 40.6667 | 46.6667 | 51.6667 | 58.1667 | 72.1667 | 80.6667 | 88.6667 | 100.6667 | 2 | 2.5 | 1 | 1 | 5 | 1 | 1.5 | 2.5 | 1 | 2 | 1.6667 | 1 | 3 | 1.5 | 1.6667 | 1 | 1.6667 | 1.6667 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 1 | 1.3333 | 1 | 1 | 1.6667 | 1 | 2 | 2.5 | 1 | 5 | 1 | 4 | 4 | 5 | 1 | 1.5 | 1 | 1 | 1 | 5 | 1 | 5 | 2 | 4 | 1
323 | 9 | 7 | 12.5 | 18.1667 | 25.3333 | 36.3333 | 46.6667 | 60.3333 | 69 | 84 | 91 | 97 | 105 | 117 | 1 | 3 | 2 | 1 | 1 | 1 | 2.5 | 1 | 2 | 1.3333 | 1.3333 | 1 | 2.5 | 1 | 2 | 1.6667 | 1 | 4 | 3 | 3 | 3 | 1.3333 | 1 | 5 | 3 | 4 | 5 | 1.6667 | 1 | 1.6667 | 4 | 2 | 5 | 2 | 5 | 3 | 1 | 2.5 | 2.5 | 1 | 1.5 | 1 | 2.5 | 1 | 1 | 1 | 5 | 1 | 5 | 1.5 | 4 | 1.5
324 | 8.3333 | 5.3333 | 13.3333 | 19.3333 | 25 | 30.6667 | 38.3333 | 48.3333 | 57.6667 | 69.1667 | 75.1667 | 80.3333 | 90.3333 | 95 | 1 | 1.3333 | 2 | 1 | 2 | 1 | 3 | 2 | 2.5 | 1 | 1.5 | 1 | 1 | 1 | 2 | 1.6667 | 1.6667 | 1.3333 | 1.6667 | 1 | 3 | 1 | 1.6667 | 2 | 1 | 5 | 1 | 3 | 1.3333 | 5 | 1 | 2 | 4 | 1 | 2.5 | 4 | 2 | 2 | 1 | 1 | 1 | 1.5 | 1 | 1.6667 | 1 | 3 | 1 | 5 | 1 | 1.3333 | 1.3333 | 1
325 | 12.3333 | 10 | 14.3333 | 24.6667 | 30.1667 | 36.1667 | 44.6667 | 53.6667 | 63.6667 | 76.3333 | 85.8333 | 92.8333 | 99.3333 | 106.3333 | 3 | 1 | 5 | 1 | 1 | 1.3333 | 1 | 1 | 2 | 5 | 2 | 1.3333 | 1.5 | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1.5 | 1 | 5 | 2 | 2 | 2 | 3 | 1.5 | 5 | 2.5 | 1 | 5 | 3 | 1.6667 | 3 | 2 | 4 | 2 | 1.5 | 1 | 1 | 1 | 4 | 2.5 | 2 | 1 | 1 | 1 | 1.5 | 2 | 2.5
326 | 10.5 | 6 | 13.5 | 21.8333 | 30.8333 | 40.5 | 46.5 | 51.8333 | 58.3333 | 63.8333 | 69.5 | 79.5 | 91.5 | 103.5 | 2 | 2 | 1 | 1 | 3 | 1.5 | 1 | 2 | 1.3333 | 2 | 4 | 1 | 1 | 2 | 5 | 1 | 4 | 1.6667 | 3 | 1 | 2 | 1 | 1 | 2 | 1.3333 | 2 | 1 | 1 | 2.5 | 1.5 | 1.5 | 1 | 1.5 | 1 | 1 | 2 | 1.6667 | 1.5 | 1 | 1.5 | 1 | 1 | 3 | 5 | 2 | 2 | 3 | 5 | 2 | 5 | 4 | 1
327 | 9.6667 | 7 | 12.1667 | 20.3333 | 32.6667 | 39 | 49 | 55.5 | 63.6667 | 71.6667 | 79.8333 | 85.8333 | 95.8333 | 101.3333 | 2 | 1 | 3 | 1 | 1.6667 | 1 | 1.5 | 1 | 1 | 1.6667 | 1.5 | 4 | 2 | 4 | 5 | 1.3333 | 2 | 1.3333 | 2 | 1 | 2.5 | 1 | 5 | 1.5 | 1.5 | 1 | 2 | 2 | 1 | 1.6667 | 3 | 2.5 | 1.6667 | 1.3333 | 4 | 1 | 1.6667 | 1 | 4 | 1.5 | 3 | 1 | 1 | 1 | 1 | 5 | 2 | 2 | 1.5 | 1 | 2 | 1
328 | 9.8333 | 6.8333 | 13.5 | 22 | 30 | 37.6667 | 47.6667 | 53.5 | 63 | 72.1667 | 80.5 | 91 | 99.8333 | 107.3333 | 2 | 1.3333 | 1 | 2.5 | 1 | 2 | 1.6667 | 2 | 1 | 1 | 1.5 | 5 | 2 | 1 | 4 | 1 | 1.6667 | 2.5 | 1 | 2.5 | 3 | 5 | 1 | 1 | 1.3333 | 1 | 2.5 | 1 | 3 | 1 | 4 | 1.5 | 1.6667 | 1 | 1.5 | 5 | 2 | 2 | 1.3333 | 3 | 3 | 2 | 3 | 2.5 | 2 | 1.3333 | 1.5 | 4 | 1 | 2.5 | 1 | 3
329 | 12 | 8.8333 | 16 | 27 | 38.3333 | 45.3333 | 52.6667 | 61.6667 | 74 | 84 | 92 | 99 | 111 | 125.5 | 1.3333 | 1 | 1.5 | 5 | 1.6667 | 1.5 | 1 | 3 | 1 | 2 | 4 | 4 | 3 | 1.3333 | 2 | 5 | 1 | 2.5 | 2.5 | 1 | 1 | 4 | 1.3333 | 1 | 1 | 5 | 1 | 2 | 1 | 5 | 5 | 1.3333 | 1 | 4 | 4 | 1 | 3 | 1 | 2 | 2 | 3 | 1 | 1 | 2 | 1 | 1 | 5 | 5 | 1.5 | 3 | 5 | 5
330 | 8.6667 | 4.8333 | 13.6667 | 23.1667 | 28.5 | 37.5 | 50 | 54.5 | 62.5 | 69 | 76 | 85 | 90.8333 | 102.8333 | 1 | 1.3333 | 1.5 | 1 | 1.3333 | 2.5 | 3 | 2 | 1 | 5 | 2.5 | 1 | 1.3333 | 2 | 1 | 1 | 1 | 4 | 1 | 3 | 4 | 5 | 2.5 | 1 | 1 | 1.5 | 1 | 1 | 2 | 3 | 1.3333 | 1.6667 | 1 | 2 | 2.5 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 5 | 2 | 1 | 2.5 | 1.3333 | 1 | 1.6667 | 1.3333 | 5 | 4
331 | 10 | 8 | 12 | 21 | 26 | 35 | 41.8333 | 51.5 | 64.5 | 68.5 | 75.5 | 82.8333 | 88.5 | 99 | 1 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 5 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 4 | 1 | 1 | 3 | 1.3333 | 1 | 3 | 1.5 | 5 | 1 | 1.6667 | 2 | 5 | 2 | 3 | 3 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 4 | 1 | 1.3333 | 1 | 2 | 1.6667 | 1 | 3 | 1.5 | 1 | 5
332 | 14.3333 | 10.8333 | 16.3333 | 24.6667 | 28.6667 | 37.6667 | 43.8333 | 54.5 | 59.5 | 74.5 | 80.5 | 94.1667 | 102.5 | 106.5 | 1.3333 | 4 | 1.5 | 4 | 1 | 2.5 | 1 | 1 | 1.3333 | 2 | 1 | 4 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 4 | 1 | 1.6667 | 1 | 2.5 | 1.6667 | 3 | 2 | 4 | 2 | 1 | 1 | 1 | 4 | 2 | 5 | 4 | 3 | 1 | 1 | 1 | 5 | 1.6667 | 3 | 4 | 1 | 4 | 2 | 1.3333 | 1 | 1 | 1 | 1
333 | 8 | 5 | 11.5 | 20.8333 | 25.5 | 34.1667 | 38.5 | 44.6667 | 57.1667 | 67.8333 | 74.8333 | 81.8333 | 88.8333 | 96.1667 | 1.3333 | 1.6667 | 1 | 1 | 1 | 2 | 1 | 2.5 | 1.3333 | 5 | 2 | 1 | 1 | 1 | 1 | 1.6667 | 1 | 5 | 1 | 1.6667 | 1.3333 | 1 | 1 | 1 | 1 | 1.6667 | 2.5 | 1 | 3 | 2 | 5 | 2.5 | 1 | 1.6667 | 3 | 5 | 1 | 1 | 4 | 1 | 1 | 2 | 2 | 2 | 2.5 | 1.5 | 2 | 1 | 1.6667 | 3 | 1.6667 | 1
334 | 7.6667 | 5.6667 | 9.6667 | 19 | 27.3333 | 32.8333 | 37.8333 | 44.5 | 51.5 | 59.8333 | 68.3333 | 72.8333 | 79.1667 | 87.6667 | 1.6667 | 1.5 | 1 | 1.5 | 1 | 1 | 1 | 1 | 5 | 2 | 1 | 1.3333 | 1.3333 | 5 | 1 | 1 | 2.5 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1.6667 | 1 | 3 | 1 | 2 | 2 | 1 | 2 | 4 | 2 | 1.3333 | 1 | 4 | 1 | 2.5 | 1 | 1 | 1 | 1 | 1.5 | 1 | 1.3333 | 1 | 3 | 1 | 5 | 1 | 1.5
335 | 14.5 | 12 | 19.5 | 23.5 | 29.5 | 33.8333 | 42 | 47 | 58.3333 | 66.8333 | 80.5 | 90 | 94.5 | 101 | 4 | 4 | 1 | 3 | 1 | 1.5 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1.3333 | 1 | 3 | 1.6667 | 1 | 2.5 | 1 | 1 | 2 | 1 | 1.3333 | 4 | 5 | 1 | 2 | 1 | 3 | 2.5 | 5 | 1.6667 | 3 | 4 | 1 | 5 | 2.5 | 1 | 1.5 | 1 | 1 | 1 | 1.6667 | 1.5 | 1.3333 | 2
336 | 10 | 8 | 14 | 25 | 29.5 | 38 | 49 | 55.5 | 60.5 | 69.5 | 77 | 85 | 90.3333 | 97.3333 | 1 | 2 | 2.5 | 2.5 | 1 | 1 | 1 | 3 | 1 | 1 | 4 | 5 | 1 | 1 | 1 | 1.5 | 5 | 1 | 1 | 1.5 | 5 | 1 | 1 | 4 | 3 | 1.5 | 1 | 1 | 2 | 1 | 1 | 1 | 4 | 1 | 2.5 | 1.5 | 1 | 2.5 | 3 | 1 | 1 | 1 | 1 | 5 | 1.3333 | 1 | 2 | 1 | 1 | 1 | 4 | 1
337 | 10.6667 | 6 | 14 | 23 | 31.6667 | 36 | 46.3333 | 52.3333 | 60.3333 | 66.8333 | 76.3333 | 81.3333 | 91.6667 | 97.1667 | 1.5 | 2.5 | 1 | 1 | 1.6667 | 3 | 1.6667 | 1.6667 | 2 | 2 | 1 | 4 | 1.6667 | 1 | 4 | 2 | 1.3333 | 1 | 1 | 1 | 1.3333 | 5 | 3 | 1 | 2 | 2 | 1 | 1 | 1.6667 | 2.5 | 2.5 | 1.3333 | 1 | 2.5 | 1.5 | 1.5 | 2.5 | 4 | 1 | 2 | 1 | 1 | 1 | 2 | 3 | 4 | 2 | 1.3333 | 1.5 | 1 | 1 | 2
338 | 11.5 | 6.5 | 14 | 24 | 28.3333 | 37.8333 | 47.8333 | 53.5 | 61.5 | 65.8333 | 71.3333 | 76 | 85 | 97 | 3 | 1 | 1.5 | 1 | 2 | 3 | 1.5 | 1 | 1 | 4 | 4 | 1 | 1 | 1 | 1.3333 | 1 | 4 | 1 | 2 | 2.5 | 1 | 1.5 | 2.5 | 5 | 1.3333 | 2 | 1 | 1.3333 | 1 | 4 | 2 | 1 | 1 | 1 | 1 | 1.3333 | 1 | 1 | 2 | 1.5 | 1.6667 | 1 | 1 | 1 | 2 | 1 | 1 | 5 | 1 | 5 | 5 | 1
339 | 14 | 10 | 20 | 28 | 36.5 | 42.3333 | 48 | 56.5 | 63.1667 | 75.1667 | 80.1667 | 87.1667 | 95.6667 | 101.1667 | 5 | 1 | 2 | 2 | 2 | 2 | 1 | 5 | 3 | 1 | 3 | 1 | 2.5 | 2.5 | 2.5 | 1 | 1 | 2.5 | 1.3333 | 1 | 1 | 2 | 1 | 1.6667 | 5 | 1 | 1.5 | 1 | 1 | 3 | 1 | 1.6667 | 1 | 4 | 5 | 2 | 1 | 1 | 1 | 2 | 3 | 1 | 2 | 1 | 1.5 | 3 | 3 | 1 | 1 | 1 | 2 | 1.5
340 | 14 | 12 | 16.5 | 26 | 31.6667 | 36.6667 | 47.1667 | 57.3333 | 67.8333 | 75.5 | 82 | 86 | 95 | 102 | 4 | 2 | 1 | 5 | 1 | 1 | 1.5 | 1 | 1 | 1.5 | 4 | 3 | 1.6667 | 2 | 1 | 1 | 1 | 1 | 1.3333 | 1.6667 | 2.5 | 2 | 1 | 5 | 5 | 1 | 1.6667 | 2.5 | 1.5 | 3 | 5 | 1 | 2 | 2 | 1.6667 | 2 | 1 | 2 | 1.5 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 2 | 2 | 1 | 2.5 | 1.5
341 | 8.8333 | 5.8333 | 10.8333 | 21.8333 | 25.8333 | 36.3333 | 44.3333 | 55.3333 | 60.8333 | 67.8333 | 76.1667 | 84.1667 | 92.6667 | 102.8333 | 1.6667 | 1.5 | 1 | 1.6667 | 2 | 1 | 1 | 1 | 4 | 5 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2.5 | 5 | 1 | 1 | 1 | 2 | 4 | 1 | 5 | 2.5 | 2.5 | 1 | 1 | 2.5 | 1 | 3 | 1.6667 | 1 | 1.3333 | 1.3333 | 1 | 4 | 2 | 1 | 1.6667 | 1.3333 | 4 | 1.5 | 4 | 1.5 | 1.5 | 1.6667 | 2 | 4 | 2.5
342 | 13.5 | 9.5 | 17.1667 | 23.1667 | 32.1667 | 39.5 | 43.8333 | 53.1667 | 58.6667 | 65.6667 | 71.1667 | 80.1667 | 87.6667 | 97.1667 | 2 | 4 | 1.5 | 2 | 2 | 2 | 2 | 1.6667 | 2 | 1 | 1 | 2 | 4 | 3 | 1 | 1 | 2 | 1.3333 | 1 | 3 | 1 | 1 | 1.3333 | 1 | 5 | 1 | 1.6667 | 1.6667 | 1.6667 | 1.3333 | 1 | 1.5 | 1 | 4 | 1 | 1 | 1 | 2 | 1.5 | 1 | 1 | 3 | 1 | 4 | 2.5 | 3 | 1 | 1 | 2.5 | 5 | 1 | 1
343 | 13.8333 | 10.1667 | 16.5 | 23.3333 | 33.3333 | 41.6667 | 45.6667 | 50.1667 | 63.6667 | 69.6667 | 80.5 | 93 | 104.5 | 113.5 | 5 | 1.6667 | 1 | 2.5 | 2 | 1.6667 | 1 | 1.6667 | 2.5 | 2 | 1.3333 | 1 | 1 | 4 | 1 | 4 | 3 | 2 | 1.6667 | 1.6667 | 1 | 1 | 1 | 1 | 1.5 | 1 | 1 | 1 | 2.5 | 5 | 5 | 1 | 1.5 | 1 | 2.5 | 1 | 1.5 | 4 | 1.3333 | 4 | 1.5 | 5 | 4 | 2 | 1 | 2.5 | 4 | 4 | 1 | 1 | 5 | 2
344 | 11.5 | 7.5 | 13.5 | 18.1667 | 23.8333 | 32.3333 | 41.3333 | 51 | 60.3333 | 73 | 79.5 | 84.5 | 96.1667 | 106.1667 | 1.5 | 3 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1.6667 | 1 | 2 | 1.6667 | 1 | 1 | 1 | 3 | 2.5 | 2 | 2 | 1 | 2 | 4 | 1.6667 | 1 | 4 | 3 | 5 | 1 | 2 | 1.3333 | 1 | 5 | 1.6667 | 5 | 2.5 | 1.6667 | 1 | 1.3333 | 1.5 | 1.5 | 1 | 1 | 5 | 2 | 3 | 1.6667 | 1.5 | 5 | 2.5 | 1
345 | 9 | 6 | 13.5 | 18.5 | 25.3333 | 30.8333 | 43.1667 | 52.8333 | 59.8333 | 65.8333 | 71.8333 | 78 | 84.5 | 89.5 | 1 | 1 | 2 | 2 | 2 | 1 | 2 | 2.5 | 1 | 1 | 2 | 1 | 2.5 | 1 | 2 | 1.3333 | 1 | 1.5 | 2 | 1 | 5 | 1.3333 | 2 | 4 | 3 | 1.6667 | 1 | 4 | 2 | 3 | 1 | 1 | 2 | 1.3333 | 1 | 1.6667 | 1 | 1 | 1 | 3 | 2.5 | 1.3333 | 1.3333 | 1 | 1 | 1 | 2 | 2.5 | 2 | 1 | 1 | 1
346 | 13.1667 | 8.6667 | 16.1667 | 31.6667 | 35.6667 | 43.6667 | 51.6667 | 57.8333 | 64.3333 | 74 | 87.5 | 93.5 | 102 | 106.8333 | 5 | 1.3333 | 1.3333 | 1 | 2 | 2.5 | 2 | 1 | 4 | 2.5 | 5 | 4 | 1 | 1 | 1 | 1 | 4 | 1 | 1 | 2 | 3 | 2 | 2 | 1 | 1.6667 | 2.5 | 1 | 1 | 1 | 2.5 | 2 | 1 | 1.3333 | 3 | 4 | 1.3333 | 1 | 2.5 | 5 | 5 | 1 | 2 | 2 | 1 | 2.5 | 1 | 1 | 4 | 1 | 1.5 | 1 | 1.3333
347 | 10 | 6.5 | 12.5 | 22.1667 | 30.1667 | 39.1667 | 47.6667 | 56.6667 | 62.3333 | 69.6667 | 75.3333 | 80.1667 | 88.6667 | 95.6667 | 1 | 1 | 2 | 2.5 | 1 | 2.5 | 1 | 1.5 | 1.6667 | 4 | 1 | 3 | 2 | 3 | 2 | 1 | 1 | 1 | 5 | 2 | 1.5 | 5 | 1 | 1 | 3 | 2.5 | 1 | 2.5 | 1.3333 | 2 | 1 | 1.3333 | 1 | 2.5 | 1.3333 | 2.5 | 1 | 2 | 1.6667 | 1 | 1 | 1 | 1.5 | 1.3333 | 2.5 | 2.5 | 1 | 2.5 | 1 | 1 | 1 | 4
348 | 8.5 | 4 | 10.5 | 21.3333 | 25.3333 | 30.3333 | 36.1667 | 43.6667 | 50.3333 | 63.3333 | 69.5 | 73.8333 | 84.1667 | 88.8333 | 1 | 1 | 1 | 1 | 1.5 | 3 | 1 | 1 | 4 | 2.5 | 3 | 1.3333 | 1 | 1 | 1 | 1 | 1.5 | 1 | 1.5 | 1 | 1 | 2.5 | 1 | 1.3333 | 1.5 | 1 | 1 | 4 | 2 | 1.3333 | 1.3333 | 2 | 2 | 2 | 5 | 4 | 1 | 1.6667 | 1 | 2.5 | 1.3333 | 1 | 1 | 1 | 2 | 1.3333 | 3 | 4 | 1 | 1 | 1 | 1.6667
349 | 8.8333 | 6.5 | 14.3333 | 20.3333 | 25.1667 | 30.6667 | 36.8333 | 43.3333 | 51.3333 | 59 | 66.5 | 71.5 | 76.5 | 82.5 | 1.5 | 3 | 1 | 1 | 1.3333 | 1 | 4 | 1.5 | 1.6667 | 1.6667 | 1 | 1.6667 | 1 | 1.3333 | 1 | 1.5 | 2 | 1 | 1 | 1.5 | 2 | 1 | 1.5 | 1.6667 | 2 | 1.5 | 2 | 1 | 2 | 2.5 | 1 | 2.5 | 4 | 1 | 1 | 1.6667 | 1 | 1 | 3 | 2.5 | 1 | 1 | 1.5 | 1.5 | 1 | 1 | 1.5 | 1.5 | 1 | 1 | 2 | 2
350 | 9.8333 | 7.5 | 15.8333 | 24.1667 | 32.1667 | 39.1667 | 48.1667 | 55.1667 | 60.3333 | 66 | 75.6667 | 81.1667 | 89.8333 | 99.8333 | 1.5 | 4 | 1 | 1 | 1 | 1.3333 | 1 | 5 | 5 | 1 | 1 | 1.3333 | 1 | 5 | 1 | 1 | 1 | 1 | 1 | 4 | 2 | 3 | 2 | 2 | 1 | 1 | 1 | 4 | 1.6667 | 1.5 | 1 | 1 | 2 | 1 | 1 | 1.6667 | 1.6667 | 1 | 4 | 3 | 1 | 1.5 | 1 | 2 | 1 | 1.6667 | 2 | 4 | 5 | 1.6667 | 2 | 1.3333
351 | 7.6667 | 5.6667 | 9.6667 | 14 | 22.3333 | 32.3333 | 38.8333 | 47.5 | 55 | 68 | 76 | 84 | 89.6667 | 94 | 1.6667 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1.3333 | 1 | 5 | 1.3333 | 1 | 1 | 2 | 2 | 2 | 4 | 1 | 2 | 2 | 1.5 | 1 | 1.6667 | 4 | 2 | 2 | 1.5 | 1 | 3 | 5 | 5 | 1 | 2 | 2 | 1 | 3 | 2 | 1 | 3 | 3 | 1 | 1.3333 | 1 | 1.3333 | 2 | 1.3333 | 1 | 1 | 1
352 | 12 | 8 | 14.3333 | 18.3333 | 30.8333 | 39.8333 | 47.8333 | 55.3333 | 65.1667 | 72.1667 | 83.6667 | 88.6667 | 96.6667 | 101.1667 | 1 | 1 | 3 | 3 | 1.5 | 2.5 | 1 | 1.3333 | 1 | 1 | 1 | 1 | 2.5 | 2 | 3 | 5 | 1.5 | 3 | 1.5 | 3 | 1 | 1.5 | 3 | 2.5 | 2 | 1.6667 | 1.3333 | 2.5 | 1.6667 | 2.5 | 1.6667 | 4 | 2 | 1.3333 | 2 | 1.6667 | 1.5 | 2.5 | 5 | 2.5 | 1 | 1 | 2 | 1 | 2 | 1 | 4 | 1 | 1 | 1 | 1.5 | 1
353 | 16.5 | 10.5 | 22.1667 | 26.6667 | 35 | 39 | 44.8333 | 53.8333 | 62.3333 | 71 | 77 | 85.3333 | 91.3333 | 100.8333 | 5 | 2 | 1 | 2.5 | 1 | 5 | 4 | 1.6667 | 1 | 1 | 1.5 | 1 | 1.3333 | 4 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1.3333 | 1.5 | 2 | 1 | 2 | 1 | 5 | 4 | 2 | 1 | 1.5 | 1 | 5 | 1.6667 | 1 | 2 | 1 | 1 | 2 | 1 | 4 | 2 | 1.3333 | 1 | 3 | 1 | 1 | 2.5 | 1 | 5 | 1
354 | 9.3333 | 5.6667 | 12.8333 | 18.1667 | 24.6667 | 29 | 40 | 49 | 55 | 63.6667 | 70.6667 | 77.6667 | 83.5 | 93.6667 | 1.5 | 1 | 1.6667 | 1.5 | 2 | 1.6667 | 1 | 2.5 | 1 | 1 | 1.3333 | 2 | 1 | 3 | 1 | 1.5 | 1 | 1 | 1.3333 | 1 | 1 | 2.5 | 2.5 | 5 | 2.5 | 1 | 2.5 | 3 | 2.5 | 1 | 1 | 1.5 | 2 | 1 | 1.6667 | 4 | 1.6667 | 2 | 1.3333 | 2 | 1 | 1 | 4 | 1 | 1.3333 | 2.5 | 1 | 1 | 2.5 | 1.6667 | 5 | 1
355 | 15.5 | 9 | 18.5 | 26.8333 | 32.5 | 44.5 | 58.5 | 64 | 69 | 73.6667 | 83.6667 | 88.3333 | 97.6667 | 107.8333 | 1 | 5 | 1 | 2 | 2.5 | 4 | 1 | 2 | 2 | 1 | 1.3333 | 4 | 1 | 1.3333 | 2 | 1.3333 | 4 | 4 | 2.5 | 1.5 | 4 | 5 | 4 | 1 | 1.5 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1.6667 | 3 | 1 | 1 | 5 | 1.6667 | 1 | 1 | 1 | 1.3333 | 1.3333 | 5 | 1.6667 | 1 | 2.5 | 5 | 1.6667
356 | 7.6667 | 5 | 13.6667 | 19.1667 | 23.5 | 30 | 37.5 | 45.1667 | 51.1667 | 60.6667 | 67.6667 | 76.6667 | 82.6667 | 87.3333 | 1.3333 | 1.6667 | 1 | 1 | 1 | 1.6667 | 5 | 1 | 2.5 | 1 | 1 | 1 | 1 | 1 | 1.3333 | 1 | 1.5 | 1 | 1 | 3 | 1 | 2.5 | 2.5 | 1.5 | 3 | 2 | 1.6667 | 1 | 2 | 1.5 | 1.5 | 1 | 1 | 4 | 2 | 2.5 | 4 | 1 | 1 | 1 | 4 | 1.5 | 2 | 1.5 | 1.6667 | 1.3333 | 2 | 1 | 1 | 1 | 1 | 1.6667
357 | 8.1667 | 6.1667 | 10.8333 | 19.8333 | 28.1667 | 37.1667 | 43.5 | 54.8333 | 60.6667 | 65 | 73 | 81.5 | 91 | 99.5 | 2.5 | 1 | 1 | 1.6667 | 1 | 1 | 1 | 1.6667 | 4 | 3 | 1 | 1 | 3 | 1.3333 | 1 | 3 | 1.6667 | 1.3333 | 1 | 5 | 1.3333 | 1 | 1 | 3 | 2 | 1.3333 | 5 | 3 | 2.5 | 1 | 1 | 1.3333 | 1.3333 | 1 | 1 | 1 | 2 | 2.5 | 1.5 | 2 | 1 | 4 | 1 | 2.5 | 5 | 2 | 1 | 1.5 | 2 | 3 | 1 | 2.5
358 | 14.6667 | 12.6667 | 17.1667 | 23.1667 | 27.5 | 36.8333 | 45.5 | 59 | 66 | 77 | 81.6667 | 86.5 | 95 | 100.8333 | 1 | 5 | 1.6667 | 5 | 1 | 1 | 1 | 1.5 | 1 | 1 | 1 | 3 | 1 | 1 | 1.3333 | 1 | 2 | 2 | 4 | 1.3333 | 2.5 | 2 | 2.5 | 1.6667 | 5 | 2.5 | 4 | 2 | 2 | 1.5 | 2 | 1.5 | 5 | 1 | 4 | 1 | 1 | 1 | 1 | 1.6667 | 1.5 | 1 | 1 | 1.3333 | 2.5 | 1 | 1 | 4 | 1.3333 | 1 | 2 | 1.5
359 | 12.3333 | 4.3333 | 15 | 25 | 31.5 | 35.8333 | 40.8333 | 45.8333 | 58.8333 | 62.8333 | 66.8333 | 71.3333 | 79.6667 | 87.8333 | 1 | 1 | 1 | 1.3333 | 3 | 5 | 1.6667 | 1 | 1.6667 | 4 | 3 | 1.3333 | 2.5 | 1 | 1.5 | 1.5 | 1 | 1 | 1.3333 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 4 | 3 | 2 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1.5 | 5 | 1 | 1.3333 | 1 | 1.5 | 2.5 | 2.5 | 1.6667
360 | 14 | 7.5 | 16 | 26.5 | 35.6667 | 43.6667 | 52.3333 | 60.3333 | 66.8333 | 73.5 | 81.5 | 89.8333 | 96.3333 | 104.8333 | 2.5 | 3 | 1 | 1 | 1.5 | 5 | 1 | 1 | 2.5 | 3 | 1 | 4 | 1.6667 | 2.5 | 2 | 3 | 1 | 5 | 1 | 1 | 1 | 3 | 1.6667 | 3 | 2 | 1 | 1 | 4 | 2.5 | 1 | 2 | 1 | 1 | 1.6667 | 2 | 2 | 5 | 1 | 1 | 1 | 1.3333 | 5 | 1 | 1 | 2 | 2 | 1.5 | 1 | 2 | 3 | 1 | 2.5
361 | 12.5 | 10 | 18.5 | 25.5 | 34.3333 | 42.3333 | 46.6667 | 56.6667 | 62.1667 | 68 | 76 | 83.1667 | 92.3333 | 97.3333 | 3 | 1.6667 | 1.3333 | 4 | 1.5 | 1 | 1 | 5 | 1 | 1 | 3 | 2 | 1.3333 | 1.5 | 1 | 5 | 4 | 1 | 2 | 1 | 1 | 1 | 1 | 1.3333 | 4 | 1 | 4 | 1 | 1 | 1 | 1 | 2.5 | 1.3333 | 2 | 1 | 1.5 | 1.6667 | 1.3333 | 2.5 | 2.5 | 2 | 2.5 | 1.6667 | 1 | 1.6667 | 4 | 2.5 | 1 | 2 | 1 | 1 | 1
362 | 15.6667 | 9.6667 | 17.6667 | 25.5 | 40.5 | 51.5 | 65.8333 | 74 | 80 | 90.3333 | 96.3333 | 105.5 | 114.8333 | 120.5 | 2 | 2 | 4 | 1.6667 | 4 | 2 | 1 | 1 | 2.5 | 1.3333 | 3 | 1 | 5 | 1 | 4 | 5 | 5 | 2 | 1 | 3 | 5 | 3 | 5 | 1.3333 | 4 | 1 | 1.5 | 1.6667 | 1 | 3 | 1 | 1 | 1 | 1.3333 | 3 | 5 | 2 | 1.3333 | 1.6667 | 1 | 1 | 1.6667 | 5 | 1.5 | 1.3333 | 1 | 3 | 4 | 1 | 2 | 1 | 1.6667
363 | 10 | 5 | 16 | 24.8333 | 30.3333 | 39.5 | 45 | 53.6667 | 60.6667 | 66 | 74 | 83.3333 | 89.3333 | 98.8333 | 1 | 1.6667 | 1.3333 | 1 | 4 | 1 | 5 | 1 | 2 | 4 | 1.3333 | 1.5 | 1.6667 | 1 | 1.5 | 1.3333 | 2 | 1.5 | 4 | 1.6667 | 1 | 2.5 | 1 | 1 | 2 | 1 | 4 | 1.6667 | 4 | 1 | 1 | 1 | 1 | 1 | 1.3333 | 2 | 3 | 1 | 3 | 1 | 1.3333 | 1 | 2 | 5 | 2 | 2 | 1 | 1 | 1.3333 | 2.5 | 1.6667 | 4
364 | 9.3333 | 7.3333 | 12.3333 | 20.8333 | 28.5 | 32.8333 | 37.3333 | 42.6667 | 52 | 57 | 62.5 | 71.3333 | 81.3333 | 93.3333 | 1.3333 | 1 | 2.5 | 2.5 | 1 | 1 | 1 | 2 | 1 | 5 | 1 | 1.5 | 4 | 1.6667 | 1 | 1 | 1 | 1 | 1.3333 | 1 | 1 | 1 | 1.5 | 1 | 2 | 1 | 1.3333 | 1 | 2 | 2 | 4 | 1.3333 | 1.3333 | 1 | 1.6667 | 1 | 2.5 | 1 | 1 | 1 | 1.3333 | 1 | 1.5 | 5 | 4 | 2.5 | 1 | 2.5 | 4 | 2 | 2 | 4
365 | 16.1667 | 12.1667 | 22.1667 | 26.1667 | 36.5 | 46.1667 | 55.3333 | 65.3333 | 73 | 80.1667 | 87.1667 | 95.8333 | 100.8333 | 107.8333 | 5 | 1.5 | 4 | 1.6667 | 2 | 2 | 5 | 1 | 1 | 1 | 1 | 1 | 1.3333 | 4 | 1 | 4 | 1 | 1.6667 | 5 | 2 | 1.6667 | 1.5 | 5 | 1 | 3 | 1 | 4 | 2 | 1 | 1.6667 | 1 | 4 | 1.3333 | 1.5 | 3 | 1.3333 | 2 | 1 | 3 | 1 | 1.6667 | 1 | 1 | 5 | 1 | 1 | 1 | 2 | 4 | 1 | 1 | 1
366 | 10 | 4 | 14.1667 | 23.6667 | 32.1667 | 42.1667 | 49.1667 | 62.1667 | 70.1667 | 77.1667 | 83.1667 | 91.1667 | 98.5 | 107.5 | 1 | 1 | 1 | 1 | 5 | 1 | 2.5 | 1.6667 | 1 | 1.5 | 2 | 5 | 5 | 1 | 1 | 1.5 | 1 | 4 | 2 | 3 | 3 | 2 | 1 | 1 | 1 | 5 | 4 | 3 | 3 | 2 | 2 | 1 | 2 | 2.5 | 1.5 | 1 | 1 | 1 | 1 | 3 | 1 | 2 | 2 | 3 | 1.3333 | 2.5 | 2 | 1.5 | 1 | 5 | 2 | 1
367 | 7.5 | 5.5 | 13.5 | 23 | 31 | 40 | 52 | 58 | 67 | 74.5 | 82.1667 | 92.1667 | 98.5 | 106 | 1 | 2 | 1 | 1.5 | 1 | 1 | 5 | 1 | 1 | 5 | 1 | 2.5 | 1 | 2.5 | 2.5 | 2 | 1 | 2.5 | 3 | 2.5 | 4 | 2 | 3 | 3 | 2.5 | 1 | 1.5 | 1 | 2.5 | 2 | 2 | 2.5 | 1 | 2 | 3 | 1.5 | 1 | 4 | 1.6667 | 1 | 4 | 1 | 1 | 4 | 1 | 3 | 1.3333 | 1 | 2.5 | 3 | 1 | 1
368 | 9.6667 | 5.6667 | 14.1667 | 19.6667 | 27.5 | 37.5 | 46.8333 | 52.3333 | 58 | 65.5 | 75.3333 | 86.3333 | 97.5 | 103 | 1.3333 | 2 | 1.3333 | 1 | 3 | 1 | 2 | 2.5 | 1 | 2.5 | 1 | 1 | 4 | 1.3333 | 1 | 1.5 | 3 | 5 | 1 | 1 | 4 | 2 | 1.3333 | 2 | 1 | 1 | 1.5 | 2 | 1 | 2 | 1 | 1.6667 | 1 | 2 | 2.5 | 2 | 1.5 | 4 | 1.3333 | 3 | 2.5 | 2.5 | 2 | 4 | 2.5 | 3 | 4 | 1.6667 | 1.5 | 1 | 2 | 1
369 | 10.5 | 6.5 | 13.8333 | 24.3333 | 31.3333 | 41.3333 | 47.5 | 54.5 | 62.5 | 68.1667 | 76 | 83.3333 | 91.3333 | 95.8333 | 1.5 | 3 | 1 | 1 | 2 | 2 | 1.3333 | 2 | 2.5 | 2 | 2 | 4 | 2 | 2 | 2 | 1 | 1 | 5 | 1 | 3 | 1 | 1.6667 | 2 | 1.5 | 1 | 2 | 2 | 2 | 1 | 2 | 2 | 3 | 1 | 1.3333 | 1.6667 | 1.6667 | 3 | 1.3333 | 2 | 1.5 | 1.5 | 3 | 1.5 | 1.3333 | 5 | 1 | 1 | 1 | 1 | 1 | 1.5 | 1
370 | 12 | 10 | 15.5 | 22.6667 | 28.3333 | 34.1667 | 38.8333 | 44.6667 | 51.3333 | 60.3333 | 69 | 77.5 | 82.8333 | 89.1667 | 1 | 1 | 4 | 4 | 1 | 1 | 2 | 1.5 | 1 | 1.6667 | 3 | 1.5 | 1 | 2 | 1 | 1.6667 | 1.3333 | 1.5 | 1 | 2 | 1 | 1.6667 | 1 | 1 | 1 | 1.3333 | 1.5 | 2 | 3 | 1.6667 | 1 | 1 | 4 | 2 | 2 | 1 | 1.6667 | 5 | 1 | 1 | 3 | 1 | 2 | 2.5 | 1 | 1.3333 | 1 | 2 | 1.3333 | 2 | 1 | 2
371 | 6.5 | 4 | 11.5 | 18.1667 | 25.8333 | 34.8333 | 42.3333 | 50.3333 | 56.5 | 65.8333 | 76.3333 | 82.5 | 93.5 | 100.3333 | 1 | 1 | 1 | 1 | 1.5 | 1 | 2 | 3 | 1 | 1 | 1.6667 | 3 | 1 | 1.6667 | 4 | 1 | 1 | 1 | 2 | 5 | 2 | 1 | 2.5 | 2 | 2 | 1 | 1 | 4 | 1.6667 | 1.5 | 2 | 1 | 1 | 1.3333 | 3 | 4 | 2.5 | 2 | 5 | 1 | 1 | 2.5 | 1.6667 | 1 | 5 | 1 | 1 | 4 | 1.6667 | 2.5 | 1.6667 | 1
372 | 12.5 | 9 | 17 | 23 | 28 | 40 | 44.5 | 58.1667 | 64.1667 | 72.6667 | 77 | 82.3333 | 93.3333 | 102.8333 | 2 | 1 | 5 | 1 | 2.5 | 1 | 2.5 | 2 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 2 | 4 | 5 | 1.6667 | 1.3333 | 1.5 | 1 | 1 | 1 | 2 | 5 | 1.6667 | 5 | 2 | 2 | 1 | 1 | 2 | 3 | 1 | 2.5 | 1.3333 | 1 | 1 | 1 | 1 | 1.3333 | 1 | 2 | 5 | 1 | 2 | 3 | 3 | 1 | 4 | 1.5
373 | 10.3333 | 8 | 14.3333 | 20.5 | 26.1667 | 33.5 | 38.5 | 45.1667 | 50.1667 | 60.1667 | 66 | 71.8333 | 81 | 87.5 | 1 | 5 | 1 | 1 | 1.3333 | 1 | 1 | 3 | 1.5 | 1.6667 | 2 | 1 | 1 | 1 | 1.6667 | 2 | 4 | 1 | 1.3333 | 1 | 2 | 1 | 1 | 1 | 1 | 3 | 1 | 1.6667 | 1 | 1 | 1.6667 | 1.3333 | 4 | 1 | 1 | 4 | 1.5 | 1.6667 | 1.6667 | 1 | 1.6667 | 1.6667 | 1.5 | 1 | 1.5 | 5 | 1 | 1.6667 | 1.5 | 3 | 1 | 1
374 | 11.8333 | 5.8333 | 14.8333 | 20.1667 | 24.6667 | 31.6667 | 40 | 45.5 | 52.5 | 62 | 67.3333 | 74 | 81.3333 | 88.3333 | 1 | 1.3333 | 2.5 | 1 | 5 | 1 | 2 | 1 | 1.3333 | 1.3333 | 1 | 1.6667 | 1.5 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 1.3333 | 5 | 1.5 | 1 | 1 | 2 | 1 | 1.6667 | 3 | 1.3333 | 2 | 2 | 3 | 2.5 | 1 | 1 | 1.3333 | 2 | 1.3333 | 1 | 1.3333 | 3 | 2 | 2 | 2 | 1.3333 | 1 | 1.3333 | 3 | 1.6667
375 | 9.3333 | 5.6667 | 12.3333 | 18.8333 | 25.5 | 31.5 | 43.5 | 53.3333 | 60.3333 | 68 | 73 | 78.5 | 83.5 | 92.5 | 1 | 2 | 1 | 1.6667 | 2 | 1.6667 | 1 | 2 | 2 | 2.5 | 1 | 1 | 1.6667 | 2 | 2 | 1 | 2 | 1 | 1 | 2 | 5 | 1 | 5 | 1 | 5 | 1 | 1.3333 | 2.5 | 1 | 1 | 1 | 4 | 2.5 | 2.5 | 1 | 1.6667 | 1 | 1 | 1 | 2 | 1.5 | 1 | 1 | 2 | 1.5 | 1 | 1 | 1.5 | 5 | 2 | 1 | 1
376 | 9.1667 | 5.6667 | 11.5 | 19.3333 | 24.8333 | 35 | 42.3333 | 46.3333 | 53.6667 | 65.1667 | 73.5 | 78.1667 | 88.1667 | 98.3333 | 1.3333 | 2 | 1 | 1.3333 | 1 | 2.5 | 1 | 1.3333 | 1.3333 | 1.5 | 1 | 4 | 2 | 1 | 1 | 1.5 | 3 | 1.6667 | 2.5 | 3 | 1 | 1.3333 | 4 | 1 | 1 | 1 | 1 | 1 | 3 | 1.3333 | 2 | 1 | 5 | 4 | 1 | 1.5 | 1.3333 | 1 | 1 | 5 | 1 | 1 | 1 | 1.6667 | 1 | 3 | 3 | 3 | 1.6667 | 1.5 | 5 | 2
377 | 15.1667 | 10.5 | 21.1667 | 29.1667 | 37.1667 | 43.5 | 49.6667 | 54.5 | 60.1667 | 64.8333 | 69.5 | 78 | 88.6667 | 94 | 1.6667 | 2.5 | 5 | 1.3333 | 1.6667 | 3 | 5 | 1 | 1 | 1 | 1 | 5 | 1 | 5 | 1 | 1 | 1.3333 | 1 | 1 | 3 | 1 | 1.6667 | 2.5 | 1 | 1 | 1.3333 | 1.5 | 1 | 1.6667 | 2 | 1 | 1 | 1 | 1 | 1.6667 | 1 | 1 | 1 | 1.6667 | 1 | 3 | 1 | 2 | 2.5 | 1.6667 | 5 | 1 | 3 | 1.3333 | 1.6667 | 1.3333 | 1
378 | 8.5 | 4 | 12.3333 | 18.1667 | 24.1667 | 36.8333 | 45.6667 | 50.1667 | 62.3333 | 69.3333 | 78.3333 | 85.3333 | 92.3333 | 105 | 1 | 1 | 1 | 1 | 1.5 | 3 | 1.3333 | 2.5 | 1 | 1.5 | 1.6667 | 1.6667 | 1.5 | 1 | 1.5 | 2 | 1.6667 | 3 | 3 | 5 | 1.3333 | 1.5 | 5 | 1 | 1.5 | 1 | 1 | 1 | 5 | 1.6667 | 4 | 1.5 | 1 | 3 | 2 | 1 | 1.5 | 4 | 2.5 | 1 | 1 | 2 | 1 | 3 | 1.5 | 3 | 1 | 1.5 | 1.6667 | 5 | 1 | 5
379 | 12.5 | 8.5 | 19 | 26.8333 | 31.8333 | 42 | 48 | 57 | 65.5 | 70.1667 | 80.6667 | 85.1667 | 90.6667 | 102.3333 | 2 | 3 | 2.5 | 1 | 1 | 3 | 4 | 2.5 | 1.3333 | 3 | 2 | 1.5 | 1 | 1.3333 | 1.6667 | 1 | 2.5 | 5 | 1.3333 | 1.3333 | 3 | 1 | 1 | 1 | 5 | 1 | 1 | 2 | 2.5 | 2 | 2 | 2 | 1 | 1.6667 | 1 | 1 | 1 | 3 | 4 | 2.5 | 1.5 | 1 | 1 | 1 | 1.5 | 1 | 2 | 1 | 1 | 5 | 1.6667 | 4
380 | 14.5 | 10 | 21 | 26 | 32.8333 | 39.1667 | 44.6667 | 49.3333 | 53.3333 | 60.8333 | 65.6667 | 76.3333 | 89.8333 | 100.8333 | 1 | 4 | 1 | 4 | 1.5 | 3 | 1.5 | 5 | 2 | 1 | 1 | 1 | 1.5 | 1.3333 | 1 | 3 | 1.6667 | 1.6667 | 1.5 | 1.5 | 1 | 1 | 1 | 2.5 | 1 | 1 | 1.6667 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 2.5 | 1 | 1 | 1.5 | 1 | 1.3333 | 2 | 4 | 1.6667 | 3 | 2.5 | 1 | 5 | 5 | 1.5 | 3 | 1.5 | 5
381 | 16.6667 | 7.6667 | 21.1667 | 28.8333 | 32.8333 | 41.1667 | 47.1667 | 56 | 65 | 71.5 | 80 | 85.3333 | 94.8333 | 103.5 | 3 | 1 | 2 | 1.6667 | 4 | 5 | 2.5 | 2 | 1.6667 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 5 | 1.3333 | 1 | 1 | 1 | 2 | 2 | 2 | 1.3333 | 3 | 2.5 | 2 | 1 | 5 | 1 | 1 | 2.5 | 2 | 1 | 1 | 4 | 2.5 | 1 | 1.5 | 1.5 | 1.3333 | 1 | 5 | 1 | 2.5 | 1 | 1 | 1 | 1.6667 | 5
382 | 13.1667 | 6.1667 | 18.1667 | 25.1667 | 32.6667 | 40.6667 | 45 | 54.5 | 63.5 | 71.5 | 76.1667 | 84.1667 | 97.6667 | 107.1667 | 1.5 | 2 | 1.6667 | 1 | 2 | 5 | 2 | 3 | 1 | 1 | 4 | 1 | 1 | 2 | 3 | 1.5 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 1.3333 | 2.5 | 4 | 2 | 1 | 1 | 2 | 4 | 2 | 3 | 1 | 1 | 3 | 1.6667 | 1 | 1 | 1 | 1 | 1 | 5 | 1 | 4 | 4 | 2.5 | 3 | 1.5 | 1 | 3 | 4
383 | 10 | 7 | 16 | 22 | 28.3333 | 37.8333 | 45.1667 | 51.1667 | 58 | 63.5 | 72.6667 | 83.6667 | 96 | 105 | 1 | 1 | 3 | 2 | 1.5 | 1.5 | 1 | 5 | 1 | 1 | 3 | 1 | 1 | 1.3333 | 3 | 1 | 2.5 | 1 | 1 | 5 | 1 | 3 | 2 | 1.3333 | 1 | 1 | 3 | 1 | 2 | 1.3333 | 1.5 | 2 | 1 | 1 | 1.5 | 2 | 1 | 2.5 | 1.6667 | 4 | 4 | 1 | 3 | 3 | 1 | 1.3333 | 5 | 5 | 3 | 1 | 1 | 4
384 | 14.3333 | 8 | 16.3333 | 22.8333 | 29.3333 | 37.6667 | 43.8333 | 48.8333 | 54.8333 | 61.3333 | 73.3333 | 81 | 85.3333 | 90.3333 | 2 | 1 | 3 | 2 | 5 | 1.3333 | 1 | 1 | 2 | 1 | 2.5 | 1 | 1.5 | 3 | 1 | 1 | 1.6667 | 4 | 1 | 1.6667 | 1.3333 | 1.3333 | 1.5 | 2 | 1 | 2 | 1 | 1 | 2.5 | 1 | 1 | 1.5 | 2 | 1 | 2.5 | 1 | 5 | 2 | 2 | 3 | 3 | 1 | 1.6667 | 2 | 1 | 1 | 1 | 1.3333 | 1 | 2 | 1 | 1
385 | 10.1667 | 7.5 | 12.5 | 19 | 27.5 | 33.8333 | 41.3333 | 50.3333 | 56.8333 | 62.1667 | 68.6667 | 75.6667 | 86.3333 | 97.8333 | 1 | 1 | 3 | 2.5 | 1 | 1.6667 | 1 | 1.3333 | 2.5 | 1 | 2 | 1 | 1 | 2.5 | 1 | 4 | 1 | 2 | 1.6667 | 1.6667 | 1 | 1 | 2.5 | 3 | 1.5 | 5 | 1 | 1.5 | 2.5 | 2 | 1 | 1 | 1.5 | 1.3333 | 1.5 | 1 | 1 | 1 | 2 | 2.5 | 4 | 1 | 1 | 1 | 1.6667 | 4 | 1 | 4 | 2.5 | 3 | 5 | 1
386 | 9.6667 | 5.6667 | 12.6667 | 20.1667 | 27.1667 | 34.1667 | 47.8333 | 59.8333 | 68.3333 | 72.3333 | 80.6667 | 88.6667 | 98.5 | 103.3333 | 2 | 1.6667 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 2.5 | 3 | 1 | 1 | 4 | 1 | 1 | 2.5 | 1 | 1 | 2.5 | 5 | 5 | 1.6667 | 2 | 1.3333 | 5 | 4 | 1.6667 | 2.5 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 4 | 1.6667 | 1 | 1.6667 | 4 | 2 | 1 | 1 | 1 | 5 | 1.3333 | 2.5 | 1.3333 | 1 | 1.5 | 1
387 | 12.8333 | 7.8333 | 14.8333 | 19.3333 | 31.3333 | 43.8333 | 51.8333 | 57.8333 | 69.3333 | 78.1667 | 85.6667 | 96.1667 | 102.8333 | 109.3333 | 2.5 | 3 | 1 | 1.3333 | 4 | 1 | 1 | 1 | 1 | 1.5 | 1 | 1 | 4 | 2 | 3 | 3 | 2 | 5 | 4 | 1.5 | 1 | 1 | 1 | 5 | 1 | 3 | 1 | 1 | 2.5 | 5 | 2.5 | 1.5 | 2 | 2.5 | 1.3333 | 3 | 2 | 1 | 2 | 2.5 | 5 | 2 | 1 | 2.5 | 1.5 | 2.5 | 1 | 1.6667 | 1.5 | 1 | 1.5 | 2.5
388 | 15 | 9 | 17 | 28.5 | 34.5 | 42.5 | 55.5 | 65 | 73 | 82 | 91 | 99.8333 | 107.6667 | 115.1667 | 4 | 2 | 1 | 2 | 5 | 1 | 1 | 1 | 1 | 5 | 4 | 1.5 | 1 | 1 | 1 | 3 | 1 | 1 | 4 | 2 | 1 | 4 | 3 | 5 | 5 | 1 | 1 | 2.5 | 4 | 1 | 1 | 2 | 1 | 1 | 5 | 2 | 2 | 1 | 5 | 1 | 1.5 | 1.3333 | 1 | 5 | 1 | 1.3333 | 2.5 | 3 | 2 | 1.3333 | 2.5 | 1.6667
389 | 14 | 7 | 17 | 21 | 27.6667 | 36.1667 | 48.1667 | 54.6667 | 62.5 | 78 | 88 | 94.3333 | 103.3333 | 110 | 1.6667 | 1.5 | 2.5 | 1.3333 | 3 | 4 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1.6667 | 1 | 1.5 | 3 | 3 | 4 | 2 | 1 | 5 | 3 | 1 | 1 | 1.5 | 1.6667 | 1.5 | 3 | 1.6667 | 2.5 | 4 | 5 | 4 | 3 | 1 | 5 | 1 | 1 | 1 | 1.3333 | 3 | 2 | 1 | 5 | 1 | 1.6667 | 1 | 3 | 1
390 | 9.3333 | 7 | 13.3333 | 19.5 | 32.5 | 38 | 43.8333 | 50.8333 | 57.8333 | 65.6667 | 72.6667 | 77.6667 | 88.1667 | 96 | 2 | 1 | 1 | 3 | 1 | 1.3333 | 3 | 1 | 1 | 1 | 1.6667 | 2.5 | 2 | 1 | 5 | 5 | 2 | 1 | 1 | 1.5 | 1 | 1 | 1.3333 | 2.5 | 1 | 1 | 2.5 | 2.5 | 1 | 1 | 4 | 1 | 1.3333 | 1.5 | 1 | 4 | 4 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1.5 | 1 | 5 | 3 | 1 | 1.3333 | 2.5 | 3
391 | 12.3333 | 9 | 17.3333 | 22.6667 | 29.6667 | 37 | 47 | 56.6667 | 63.3333 | 72.1667 | 82.6667 | 90 | 102.5 | 112.5 | 1 | 1 | 5 | 2 | 1.6667 | 1.6667 | 4 | 1 | 1 | 1.3333 | 1 | 2 | 1.6667 | 1 | 1.3333 | 3 | 1.6667 | 1.6667 | 1 | 3 | 1 | 2 | 3 | 4 | 1.5 | 1.6667 | 2.5 | 4 | 1 | 1.6667 | 1 | 3 | 3 | 1.3333 | 1.5 | 3 | 2.5 | 3 | 1 | 4 | 2 | 1.3333 | 2.5 | 1.5 | 4 | 4 | 1.5 | 3 | 4 | 2.5 | 1.5 | 2
392 | 12.6667 | 6.6667 | 14.6667 | 18.6667 | 28.6667 | 37 | 42.6667 | 48.3333 | 58.3333 | 66 | 71.5 | 79 | 85 | 91.5 | 1 | 1 | 3 | 1.6667 | 4 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 2.5 | 2 | 2.5 | 3 | 4 | 1.3333 | 1 | 2 | 2 | 1 | 1.6667 | 1 | 1 | 1.6667 | 2 | 1 | 5 | 1 | 3 | 1 | 1 | 2 | 3 | 1.6667 | 2.5 | 1 | 1 | 1 | 1 | 3 | 1 | 2.5 | 1 | 1 | 3 | 1 | 3 | 1 | 1.5 | 1
393 | 11.3333 | 7 | 17.8333 | 24.8333 | 29.5 | 40.5 | 46 | 50 | 57.6667 | 63.6667 | 68.6667 | 75 | 88 | 98.1667 | 4 | 1 | 1 | 1 | 1.3333 | 3 | 5 | 1.5 | 1 | 1 | 2 | 3 | 1 | 1 | 1.6667 | 1 | 5 | 1.5 | 1.5 | 3 | 2 | 1 | 1 | 1.5 | 1 | 1 | 1 | 1 | 1.6667 | 3 | 2 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1.3333 | 1 | 3 | 4 | 5 | 3 | 1 | 1 | 5 | 2.5 | 1.6667
394 | 7.6667 | 5 | 10.1667 | 21.1667 | 25.8333 | 30.1667 | 39.1667 | 49.1667 | 59.8333 | 65.1667 | 76.6667 | 84.3333 | 90.1667 | 95.6667 | 1 | 2 | 1 | 1 | 1.3333 | 1.3333 | 1 | 1.5 | 1 | 5 | 1 | 4 | 1 | 1 | 1.6667 | 1 | 1 | 1 | 1 | 1.3333 | 1 | 1 | 2 | 5 | 5 | 1 | 1 | 3 | 5 | 3 | 1 | 1.6667 | 1.6667 | 1.6667 | 1 | 1 | 4 | 2 | 4 | 1.5 | 1.6667 | 3 | 1.6667 | 1.3333 | 1 | 1.3333 | 1 | 2.5 | 1 | 1 | 2.5 | 1
395 | 12.5 | 10.5 | 14.5 | 24 | 34.5 | 39.5 | 45.5 | 50.3333 | 55.3333 | 63.1667 | 67.5 | 76.5 | 81.5 | 89.5 | 1.5 | 2 | 4 | 3 | 1 | 1 | 1 | 1 | 2 | 4 | 1 | 2.5 | 3 | 1 | 5 | 1.5 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 2 | 1.3333 | 1 | 1 | 1.5 | 2 | 1 | 1 | 1 | 2 | 1.3333 | 3 | 1.5 | 1 | 1 | 1.3333 | 1 | 1 | 1 | 4 | 3 | 1 | 1 | 2 | 1 | 1 | 1 | 5 | 1
396 | 14 | 7 | 18 | 27.3333 | 38 | 46.5 | 57.1667 | 64.6667 | 69.3333 | 81.8333 | 89.8333 | 94.8333 | 104.8333 | 110.8333 | 1.3333 | 1 | 3 | 1.6667 | 3 | 4 | 2 | 2 | 2 | 1 | 5 | 1.3333 | 2 | 1.6667 | 4 | 3 | 2.5 | 2 | 3 | 1 | 3 | 1.6667 | 4 | 2 | 1.5 | 1 | 4 | 1 | 1 | 1 | 1.6667 | 1 | 1.5 | 4 | 4 | 3 | 1 | 5 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 4 | 1 | 4 | 2 | 1 | 1 | 2
397 | 12.5 | 6.5 | 17.5 | 23.3333 | 28.3333 | 33.6667 | 39.3333 | 45.3333 | 50.3333 | 58.8333 | 68 | 74.1667 | 81.1667 | 91.1667 | 2 | 1 | 1 | 2.5 | 1 | 5 | 3 | 2 | 1 | 1 | 1.3333 | 2.5 | 1 | 2 | 1 | 1 | 1 | 1.5 | 1.5 | 1.3333 | 1 | 1 | 1.6667 | 2 | 1.6667 | 1.3333 | 2 | 1 | 2 | 1 | 1 | 1 | 1.5 | 4 | 1.6667 | 1.3333 | 3 | 2.5 | 2 | 1.6667 | 1 | 1.6667 | 1 | 2.5 | 1 | 4 | 1 | 1 | 4 | 2 | 1 | 3
398 | 7.8333 | 5.5 | 12.8333 | 19.8333 | 27.8333 | 37 | 43 | 50.5 | 57.3333 | 63.3333 | 71 | 80 | 89.5 | 93.5 | 2.5 | 1 | 1 | 1 | 1 | 1.3333 | 3 | 2 | 1 | 1 | 1 | 4 | 1 | 1 | 1 | 5 | 5 | 1 | 1.5 | 1.6667 | 1.3333 | 2 | 1 | 1.6667 | 1.5 | 3 | 1 | 2 | 1.3333 | 2.5 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 2 | 3 | 1.6667 | 1.5 | 5 | 1 | 1.5 | 4 | 2.5 | 2 | 1 | 1 | 1 | 1 | 1
399 | 12.5 | 9 | 16.5 | 28 | 34.6667 | 40.8333 | 50.3333 | 61.6667 | 72.1667 | 80.1667 | 89.5 | 93.5 | 100.5 | 108.1667 | 1 | 3 | 1 | 4 | 1.5 | 2 | 1 | 3 | 4 | 1.5 | 1 | 5 | 1.5 | 2.5 | 1.6667 | 1 | 1.6667 | 1 | 2.5 | 1 | 5 | 2.5 | 1 | 1 | 4 | 5 | 1 | 1.3333 | 5 | 2 | 2.5 | 1 | 1 | 5 | 1 | 1 | 4 | 1.3333 | 3 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1.3333 | 1.6667 | 1.6667 | 1 | 1 | 4
400 | 14.8333 | 8.3333 | 16.8333 | 20.8333 | 31.8333 | 38.1667 | 45.8333 | 52 | 60.3333 | 70.8333 | 77.8333 | 90.3333 | 96.3333 | 102.5 | 4 | 1.3333 | 1 | 2 | 1.5 | 5 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 1 | 2 | 4 | 2 | 1.3333 | 1 | 2 | 2 | 2 | 1.6667 | 2 | 1.6667 | 2.5 | 1 | 1 | 3 | 3 | 1.3333 | 1 | 2 | 3 | 1.5 | 4 | 4 | 1 | 1 | 1 | 4 | 2.5 | 1 | 5 | 1 | 3 | 1 | 1 | 1.6667 | 2 | 1.5 | 1
401 | 11 | 9 | 13 | 22.5 | 28 | 36.8333 | 43 | 54 | 63.6667 | 73.6667 | 79.5 | 86.1667 | 91.3333 | 104 | 1 | 1 | 2 | 5 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 2.5 | 2.5 | 1 | 1 | 1 | 1.5 | 1.6667 | 1.6667 | 4 | 1 | 1.6667 | 2.5 | 1 | 1 | 5 | 1 | 4 | 1 | 5 | 1.6667 | 2 | 1 | 2 | 5 | 2 | 1.5 | 1 | 1.3333 | 2 | 1 | 1 | 3 | 1.6667 | 1 | 1 | 1.5 | 1.6667 | 4 | 1.6667 | 2 | 5
402 | 17 | 11 | 21 | 26.5 | 35 | 42.8333 | 54.8333 | 60.5 | 66.5 | 73 | 81.5 | 87.1667 | 96.1667 | 102.8333 | 1.5 | 2 | 2.5 | 5 | 1 | 5 | 3 | 1 | 2.5 | 1 | 1 | 1 | 1 | 4 | 1.5 | 2 | 1.3333 | 2.5 | 1 | 3 | 1 | 3 | 3 | 5 | 2 | 1 | 1.6667 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 2.5 | 4 | 2 | 1.5 | 1 | 1.3333 | 1.3333 | 1 | 2 | 1 | 5 | 1 | 2 | 3 | 1 | 1 | 1.6667
403 | 7.6667 | 5.6667 | 12.1667 | 22.6667 | 27.6667 | 36.8333 | 45.8333 | 53.5 | 57.5 | 63.8333 | 77.8333 | 85.3333 | 89.6667 | 99.1667 | 1 | 2 | 1.6667 | 1 | 1 | 1 | 2.5 | 2 | 3 | 1.5 | 2 | 4 | 1 | 1 | 1 | 2 | 1.6667 | 4 | 2.5 | 1 | 5 | 2 | 1 | 1 | 1.6667 | 2 | 2.5 | 1.5 | 1 | 1 | 1 | 1 | 1.3333 | 1.5 | 2.5 | 1 | 4 | 2 | 3 | 5 | 1 | 1.5 | 4 | 1 | 1 | 1.3333 | 1 | 1 | 5 | 2.5 | 1 | 1
404 | 13.6667 | 10.6667 | 16.6667 | 24.8333 | 31.1667 | 38 | 43.8333 | 48.5 | 56.1667 | 64.1667 | 75.6667 | 84.1667 | 90.1667 | 95.5 | 3 | 1.6667 | 4 | 2 | 1 | 2 | 1 | 2 | 1.5 | 4 | 1.6667 | 1 | 2 | 1 | 2 | 1.3333 | 2.5 | 1.6667 | 1.6667 | 1 | 1 | 1.3333 | 1 | 2.5 | 1 | 1.6667 | 1 | 1 | 1 | 2 | 1.6667 | 3 | 2.5 | 3 | 1 | 1.5 | 5 | 1 | 3 | 2.5 | 5 | 1 | 1.5 | 1 | 3 | 1 | 1 | 1 | 1.3333 | 2 | 1 | 1
405 | 18.5 | 11 | 20.8333 | 31.3333 | 38.8333 | 49.8333 | 61.3333 | 67.3333 | 75.8333 | 82.8333 | 88.3333 | 94.6667 | 101.6667 | 109.6667 | 5 | 3 | 1.5 | 1.5 | 5 | 2.5 | 1 | 1.3333 | 1 | 2 | 5 | 2.5 | 2 | 2 | 1.5 | 2 | 3 | 5 | 1 | 2 | 4 | 1 | 2.5 | 4 | 1 | 3 | 1 | 1 | 4 | 1 | 2 | 1.5 | 4 | 1 | 1 | 1 | 2 | 1 | 1.5 | 1 | 2.5 | 1 | 1.5 | 1.3333 | 3 | 1 | 1.6667 | 1.3333 | 1 | 1 | 2 | 4
406 | 8.3333 | 5 | 11.3333 | 17.1667 | 23 | 32.5 | 43 | 51 | 64 | 69.5 | 80.5 | 86.5 | 92.3333 | 99 | 2 | 1 | 1 | 1 | 1.3333 | 2 | 2 | 1 | 1 | 1 | 1.3333 | 2.5 | 1.3333 | 2 | 1 | 1.5 | 1 | 2.5 | 3 | 3 | 5 | 2.5 | 2 | 1 | 1 | 1 | 5 | 1 | 5 | 5 | 1 | 2 | 1.5 | 1 | 1 | 2 | 4 | 3 | 3 | 1 | 1 | 3 | 1 | 1 | 2.5 | 1.3333 | 1 | 1 | 1.5 | 2.5 | 1.3333 | 1.3333
407 | 19.3333 | 12.3333 | 21.3333 | 36.8333 | 43.8333 | 51.8333 | 57.5 | 64.8333 | 69.1667 | 76.5 | 83.1667 | 90.6667 | 96.1667 | 107.1667 | 5 | 1 | 1.3333 | 5 | 5 | 2 | 1 | 1 | 2.5 | 5 | 4 | 4 | 1 | 1 | 1 | 4 | 2 | 3 | 1.3333 | 1.6667 | 2 | 1.3333 | 1 | 1.3333 | 1 | 1 | 1.3333 | 4 | 1 | 1 | 1.3333 | 1 | 4 | 1 | 1 | 1.3333 | 1 | 1.5 | 1.6667 | 2.5 | 3 | 1 | 1 | 2.5 | 1.5 | 2 | 1 | 1 | 1 | 5 | 4 | 1
408 | 7.5 | 4.5 | 9.5 | 22.5 | 29.1667 | 35.1667 | 46.6667 | 57.1667 | 65 | 72 | 83.5 | 93.5 | 109.5 | 115.5 | 1 | 1 | 1.5 | 1 | 1 | 2 | 1 | 1 | 2 | 3 | 4 | 4 | 2 | 1.6667 | 1.5 | 1.5 | 1 | 3 | 1 | 1 | 2.5 | 3 | 5 | 1 | 3 | 1.5 | 2 | 4 | 3 | 2.5 | 1.3333 | 1 | 4 | 1 | 1 | 1 | 4 | 4 | 2.5 | 1 | 1.6667 | 5 | 2 | 1.3333 | 2 | 4 | 5 | 5 | 1 | 2 | 2 | 1
409 | 8.5 | 6.5 | 12.6667 | 18.1667 | 26.8333 | 34.8333 | 49 | 59.8333 | 66.8333 | 75.6667 | 80 | 91.5 | 95.5 | 101.1667 | 2 | 1 | 2.5 | 1 | 1 | 1 | 1.6667 | 2.5 | 1.5 | 1 | 2 | 1 | 1.6667 | 5 | 1 | 1 | 1 | 1 | 1 | 5 | 2.5 | 5 | 1.6667 | 5 | 4 | 3 | 1.3333 | 2.5 | 1 | 3 | 2 | 1 | 1 | 4 | 2.5 | 1.3333 | 1 | 1 | 1.3333 | 1 | 4 | 4 | 2.5 | 1 | 1 | 1 | 1 | 1 | 1.6667 | 1 | 1.3333 | 1.6667
410 | 11.5 | 8 | 15.5 | 20 | 27.1667 | 33.6667 | 40.1667 | 48.8333 | 56.8333 | 63.3333 | 71.3333 | 77.3333 | 83 | 91.5 | 4 | 1.5 | 1.5 | 1 | 1 | 2.5 | 3 | 1 | 1 | 1.5 | 1 | 1 | 1.6667 | 2 | 1 | 2.5 | 1.3333 | 2.5 | 1 | 1.6667 | 1 | 2.5 | 2 | 1 | 1.6667 | 2 | 1 | 4 | 1 | 1 | 2 | 4 | 1.3333 | 1 | 1.6667 | 2.5 | 5 | 1 | 1 | 1 | 2.5 | 1.5 | 1 | 1 | 1.3333 | 2 | 1 | 1.3333 | 2 | 1 | 2.5 | 3
411 | 14.5 | 12.5 | 16.5 | 26.5 | 33 | 38.6667 | 48.6667 | 56.6667 | 66.5 | 71.5 | 79.8333 | 89.3333 | 96.6667 | 105.3333 | 3 | 2 | 2.5 | 5 | 1 | 1 | 1 | 1 | 2 | 2.5 | 1.5 | 4 | 2.5 | 1 | 2 | 1 | 1.6667 | 2 | 1 | 1 | 1 | 2 | 2 | 5 | 1 | 2 | 1 | 4 | 1.3333 | 1.5 | 3 | 4 | 1 | 1 | 2 | 1 | 2 | 1 | 1.3333 | 4 | 2.5 | 2 | 4 | 1 | 1.3333 | 2 | 2 | 2 | 1.6667 | 2 | 2.5 | 2.5
412 | 10.6667 | 4.6667 | 17 | 26.5 | 34.6667 | 39 | 46.5 | 53.5 | 58.1667 | 62.1667 | 68.6667 | 78.6667 | 83.6667 | 92 | 1 | 1 | 1 | 1.6667 | 5 | 1 | 5 | 1.3333 | 2 | 2 | 4 | 1.5 | 2.5 | 1 | 3 | 1.6667 | 1 | 1.3333 | 1 | 1 | 2 | 2.5 | 1 | 2 | 3 | 1 | 1 | 2 | 1 | 1 | 1 | 1.6667 | 1 | 1 | 1 | 1 | 1.5 | 1 | 1 | 3 | 5 | 2.5 | 1 | 1.5 | 1 | 1 | 2 | 1 | 4 | 1.3333 | 1 | 2
413 | 9.1667 | 6.6667 | 12.5 | 18.5 | 25.8333 | 35.8333 | 42 | 50.6667 | 59.1667 | 73.8333 | 77.8333 | 86.3333 | 96.3333 | 102.6667 | 1 | 2 | 1.6667 | 2 | 1.5 | 1 | 1.6667 | 1.6667 | 1.5 | 2.5 | 1 | 1 | 1 | 4 | 1 | 1.3333 | 5 | 1 | 2.5 | 1.5 | 1 | 2.5 | 1.3333 | 1.3333 | 1.6667 | 1.5 | 1.5 | 4 | 1.5 | 3 | 1 | 3 | 1.6667 | 5 | 5 | 3 | 1 | 1 | 1 | 1 | 2.5 | 1 | 4 | 1 | 4 | 3 | 2 | 1 | 2 | 1 | 1.3333 | 2
414 | 16 | 8 | 21 | 31.5 | 40.1667 | 48 | 60 | 66 | 73.5 | 81.5 | 86.6667 | 96.1667 | 103.1667 | 112.5 | 1.5 | 2.5 | 3 | 1 | 5 | 3 | 1 | 4 | 3 | 2 | 1.5 | 4 | 2 | 2.5 | 2.5 | 1.6667 | 2.5 | 2.5 | 1.3333 | 1.5 | 3 | 5 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1.5 | 4 | 1 | 1 | 1 | 1 | 5 | 1.5 | 1.6667 | 1 | 1 | 3 | 3 | 1.5 | 2 | 1 | 1 | 2 | 3 | 1.3333 | 4 | 3 | 1
415 | 13.5 | 7.5 | 19.1667 | 29.1667 | 35.5 | 41 | 49 | 57 | 66.6667 | 75.8333 | 83.3333 | 93.3333 | 103.3333 | 110.8333 | 1 | 1.5 | 4 | 1 | 4 | 2 | 4 | 1.6667 | 3 | 1 | 2 | 4 | 1.3333 | 3 | 1 | 1 | 2.5 | 1 | 1 | 1 | 1 | 5 | 1 | 1 | 1 | 2 | 1 | 4 | 2.5 | 1.5 | 1.6667 | 4 | 1.6667 | 4 | 2.5 | 1 | 2.5 | 1 | 1 | 3 | 3 | 1 | 1 | 5 | 4 | 2 | 2 | 2 | 1 | 2.5 | 3 | 1
416 | 8 | 5 | 10.5 | 16.1667 | 23.6667 | 30.1667 | 37.1667 | 48 | 58.5 | 63.6667 | 71.6667 | 77.1667 | 82.6667 | 91 | 1 | 1.6667 | 1 | 1.3333 | 2 | 1 | 1.5 | 1 | 1.6667 | 1 | 1.5 | 1.5 | 1 | 2.5 | 2.5 | 1.5 | 1 | 3 | 1.5 | 1 | 2 | 1 | 1 | 3 | 2.5 | 5 | 1.6667 | 1.6667 | 3 | 2.5 | 4 | 1 | 1 | 1 | 1.6667 | 1.5 | 1 | 1 | 2 | 4 | 1 | 1 | 2.5 | 1 | 1 | 1.3333 | 1.6667 | 1.5 | 1 | 1.3333 | 1 | 5
417 | 6.8333 | 4.8333 | 11.8333 | 18.3333 | 25 | 32 | 42 | 48 | 59.5 | 66.8333 | 75.8333 | 82.8333 | 89.3333 | 96 | 1 | 1.5 | 1 | 1.3333 | 1 | 1 | 1 | 4 | 2 | 2.5 | 1 | 1 | 1 | 1.6667 | 1 | 3 | 2 | 2 | 1 | 2 | 5 | 1 | 3 | 1 | 2 | 1 | 1 | 2 | 1 | 5 | 2.5 | 3 | 1.3333 | 4 | 1 | 1 | 5 | 1.3333 | 1 | 1.6667 | 1 | 1 | 1 | 4 | 1 | 2 | 1 | 2.5 | 2 | 1.5 | 1.5 | 1.6667
418 | 8 | 5 | 10.6667 | 19.8333 | 28.1667 | 32.8333 | 42.8333 | 50.5 | 58.5 | 68.8333 | 78.5 | 91 | 100.1667 | 104.8333 | 1 | 1 | 2 | 1 | 1 | 2 | 1.3333 | 1.3333 | 2.5 | 4 | 1 | 1.6667 | 1.3333 | 1 | 2 | 4 | 1 | 1 | 1.6667 | 1 | 4 | 4 | 1 | 1 | 1.6667 | 4 | 1 | 1 | 3 | 2 | 2 | 1 | 5 | 1.3333 | 1.5 | 2.5 | 5 | 2 | 1 | 1.6667 | 2.5 | 5 | 2 | 3 | 4 | 2 | 1.6667 | 1.5 | 1.6667 | 1 | 1 | 1
419 | 15.5 | 10 | 22.5 | 33.5 | 41.8333 | 51.3333 | 58.3333 | 63.6667 | 75.6667 | 84.3333 | 91 | 96.6667 | 105.1667 | 111.1667 | 1 | 2 | 2 | 5 | 4 | 1.5 | 3 | 4 | 4 | 1 | 5 | 1 | 1.6667 | 2 | 1.6667 | 3 | 1.5 | 2 | 5 | 1 | 3 | 1 | 2 | 1 | 1.3333 | 1 | 2 | 1 | 5 | 2 | 1 | 4 | 4 | 1.6667 | 2 | 1 | 2 | 1 | 1.6667 | 2 | 2 | 1.3333 | 1 | 1.3333 | 2.5 | 4 | 1 | 1 | 2.5 | 1.5 | 1 | 1
420 | 10.8333 | 6.8333 | 13.8333 | 21 | 31 | 42.6667 | 53.3333 | 60.3333 | 68.1667 | 78.6667 | 82.6667 | 88.8333 | 96 | 104.1667 | 1.3333 | 2.5 | 1 | 2 | 3 | 1 | 2 | 1 | 1 | 2 | 2.5 | 1.6667 | 4 | 1 | 2 | 3 | 3 | 5 | 2 | 1.6667 | 5 | 1.6667 | 2 | 2 | 3 | 1 | 1 | 2 | 1 | 3 | 2.5 | 1.3333 | 5 | 1.5 | 1.5 | 2.5 | 1 | 1 | 1 | 1 | 2.5 | 1 | 1 | 1.6667 | 3 | 1.6667 | 1.5 | 1 | 1.6667 | 2.5 | 2 | 2
421 | 10 | 5 | 13.5 | 19 | 32 | 39 | 51 | 59 | 68.3333 | 77.8333 | 82.8333 | 93.3333 | 101.3333 | 114.3333 | 1 | 1 | 1 | 2 | 1 | 4 | 2.5 | 1 | 1.5 | 1 | 1 | 2 | 3 | 1 | 4 | 5 | 1 | 1 | 1 | 4 | 4 | 2 | 2 | 4 | 1 | 5 | 1 | 1 | 1 | 1.3333 | 4 | 3 | 1 | 2 | 2.5 | 4 | 1.5 | 1 | 1 | 1.5 | 2 | 1.5 | 5 | 2 | 1 | 1 | 1 | 5 | 1.5 | 1.5 | 5 | 5
422 | 12 | 9 | 16 | 24 | 30.1667 | 38.8333 | 45.3333 | 54.3333 | 64.6667 | 72.6667 | 84.6667 | 93.1667 | 104.6667 | 113.5 | 3 | 1 | 4 | 1 | 2 | 1 | 3 | 1 | 4 | 2 | 1 | 1 | 1.6667 | 1 | 1 | 2.5 | 4 | 2 | 1.6667 | 1 | 1.5 | 1 | 2.5 | 1.5 | 3 | 1 | 1 | 4 | 2 | 1.3333 | 2 | 5 | 2 | 1 | 1 | 4 | 1 | 1 | 5 | 5 | 2 | 3 | 1 | 2.5 | 1.5 | 4 | 2 | 4 | 2 | 1.5 | 4 | 1.3333
423 | 15.6667 | 9 | 18 | 26 | 30.6667 | 39.1667 | 45.3333 | 53.5 | 63.5 | 68 | 73.6667 | 83.6667 | 91.6667 | 98.6667 | 2 | 3 | 2.5 | 1.5 | 5 | 1.6667 | 1 | 1.3333 | 1 | 5 | 1 | 1 | 1 | 1 | 1.6667 | 1 | 1.5 | 1 | 1 | 5 | 1.5 | 1.6667 | 2 | 1 | 1.5 | 1 | 1.6667 | 4 | 4 | 1 | 3 | 2 | 1 | 1 | 1 | 1.5 | 1 | 1.6667 | 2 | 1 | 4 | 1 | 4 | 1 | 3 | 3 | 1 | 1 | 2 | 2 | 2 | 1
424 | 11.3333 | 8 | 14.3333 | 21 | 28.6667 | 37 | 48 | 58.1667 | 62.6667 | 69.6667 | 76.1667 | 83.1667 | 89.8333 | 98.5 | 3 | 2 | 1 | 2 | 1.3333 | 2 | 1 | 2 | 1 | 1.6667 | 2 | 2 | 3 | 2 | 1.6667 | 1 | 2 | 1.6667 | 3 | 1.6667 | 4 | 3 | 3 | 1 | 1.6667 | 2 | 4 | 2.5 | 1 | 1 | 1.5 | 1 | 4 | 1 | 1 | 1 | 2.5 | 1 | 2 | 1 | 2.5 | 1 | 1 | 2.5 | 2.5 | 1.6667 | 1.5 | 1 | 1 | 1.6667 | 1 | 5
425 | 7.3333 | 5 | 10.8333 | 23.8333 | 30.8333 | 37.8333 | 47.6667 | 57.1667 | 65.1667 | 74.6667 | 82.6667 | 89.6667 | 99.1667 | 106.1667 | 1 | 1 | 2 | 1 | 1.3333 | 1 | 2.5 | 1 | 5 | 1 | 2 | 5 | 1 | 1 | 1 | 4 | 1 | 1 | 3 | 2 | 2.5 | 5 | 1 | 1.3333 | 2.5 | 1 | 5 | 1 | 3 | 1 | 3 | 1 | 1.6667 | 2.5 | 1.3333 | 4 | 1 | 1 | 5 | 1 | 1.5 | 1.5 | 3 | 1 | 2.5 | 3 | 2 | 2 | 1 | 2 | 1 | 3
426 | 14.5 | 8 | 17.1667 | 22.1667 | 30.6667 | 35.3333 | 47 | 53.8333 | 60.5 | 65 | 69.3333 | 76.5 | 81.5 | 91 | 3 | 2 | 1 | 2 | 5 | 1.5 | 1 | 1.6667 | 1 | 2 | 1 | 1 | 1 | 1 | 1.5 | 5 | 1 | 1.6667 | 1 | 1 | 4 | 1 | 5 | 1.6667 | 1.5 | 2 | 1.3333 | 2 | 2 | 1 | 2 | 1.6667 | 1 | 1 | 1.5 | 1 | 1 | 1 | 1 | 1.3333 | 2 | 1.6667 | 1 | 2.5 | 1 | 1 | 1 | 2 | 4 | 1 | 3 | 1.5
427 | 7.5 | 5.5 | 10.5 | 18.6667 | 26.1667 | 36.1667 | 44.6667 | 55.8333 | 62.8333 | 73.8333 | 86.8333 | 94.5 | 104.3333 | 114.8333 | 1 | 2 | 1.5 | 1 | 1 | 1 | 2 | 1 | 1.6667 | 1.5 | 1 | 4 | 2 | 2 | 2 | 1.5 | 4 | 1 | 4 | 1 | 3 | 2.5 | 2 | 1 | 4 | 1.6667 | 4 | 1.5 | 1 | 4 | 1 | 1 | 1.5 | 2 | 5 | 2.5 | 2 | 5 | 5 | 1 | 1.6667 | 2 | 1 | 3 | 1.3333 | 2 | 2.5 | 4 | 5 | 2.5 | 1 | 2
428 | 10.6667 | 6.1667 | 12.6667 | 21.5 | 30.1667 | 34.5 | 40 | 45.3333 | 51.8333 | 65.8333 | 76.3333 | 81.8333 | 87.1667 | 93 | 1 | 1 | 2.5 | 1.6667 | 2.5 | 2 | 1 | 1 | 2.5 | 4 | 1.3333 | 1 | 1.6667 | 1 | 2 | 4 | 1 | 1 | 1 | 1.3333 | 1 | 2 | 1 | 1.5 | 1 | 1 | 2 | 1.3333 | 2 | 1 | 1 | 2.5 | 1 | 5 | 3 | 5 | 2 | 1 | 2.5 | 5 | 1 | 1 | 2.5 | 1 | 1 | 1.3333 | 1 | 2 | 1.5 | 1 | 1.3333 | 2
429 | 8.3333 | 4.5 | 13.3333 | 21.3333 | 29.8333 | 36.5 | 41.8333 | 46.3333 | 51 | 61.3333 | 65.8333 | 72.8333 | 80.8333 | 87.1667 | 1 | 1 | 1.5 | 1 | 2.5 | 1.3333 | 4 | 1 | 1 | 1 | 1 | 5 | 2 | 4 | 1.5 | 1 | 1.6667 | 2 | 2 | 1 | 2 | 1 | 1 | 1.3333 | 1 | 1.5 | 1 | 1 | 1 | 1 | 1.6667 | 1 | 3 | 4 | 1.6667 | 1.6667 | 1 | 1.5 | 1 | 1 | 1.3333 | 1 | 3 | 1.6667 | 1 | 1 | 4 | 2 | 1.3333 | 1 | 1 | 3
430 | 13.6667 | 7.6667 | 21.6667 | 31.3333 | 45.8333 | 52.1667 | 60.8333 | 72 | 82 | 87 | 97 | 104 | 110.5 | 119.3333 | 1.6667 | 1.6667 | 3 | 1.3333 | 5 | 1 | 4 | 4 | 2 | 4 | 1.6667 | 2 | 5 | 5 | 2.5 | 2 | 2 | 1 | 2 | 1.3333 | 2 | 4 | 1 | 1.6667 | 1.6667 | 3 | 5 | 1.5 | 1 | 5 | 2 | 2 | 1 | 1.6667 | 1.3333 | 1 | 2.5 | 1 | 2.5 | 4 | 2.5 | 1 | 2.5 | 1 | 2 | 1.3333 | 1.6667 | 1.5 | 4 | 1.3333 | 1.5 | 2
431 | 13 | 7 | 19 | 25.3333 | 30.3333 | 35.8333 | 43.5 | 50.8333 | 60.5 | 65.5 | 75.3333 | 84.3333 | 92 | 97.8333 | 3 | 1 | 1 | 2 | 1 | 5 | 5 | 1 | 2 | 1 | 1.6667 | 1.6667 | 1 | 1.5 | 1 | 1.5 | 1 | 1 | 2.5 | 1 | 3 | 1.6667 | 1 | 2 | 1 | 4 | 1 | 1.3333 | 1.6667 | 1 | 5 | 2 | 2 | 1 | 1 | 1 | 1 | 2.5 | 1.3333 | 5 | 1 | 5 | 2 | 1 | 1 | 2.5 | 1.6667 | 2.5 | 1.5 | 2 | 1 | 1.3333
432 | 10.8333 | 6.3333 | 13.8333 | 25.5 | 33.1667 | 41.5 | 55 | 63 | 73.3333 | 81.6667 | 86.5 | 92.5 | 97.8333 | 102.8333 | 1.3333 | 3 | 1 | 1 | 2.5 | 2 | 1 | 2 | 2.5 | 1.6667 | 5 | 2.5 | 1 | 4 | 1 | 1.6667 | 5 | 1 | 1.3333 | 1 | 5 | 2 | 5 | 1.5 | 5 | 1 | 1 | 1 | 1 | 1.3333 | 4 | 4 | 5 | 1 | 1.3333 | 1 | 1 | 1.3333 | 1 | 1.5 | 2 | 1 | 2 | 1 | 1.3333 | 1 | 1 | 2 | 1 | 1.5 | 1 | 1.5
433 | 13 | 6.3333 | 16 | 23 | 29 | 38.3333 | 46.8333 | 52.8333 | 58.5 | 64.8333 | 72.8333 | 80.1667 | 89 | 95.5 | 1.3333 | 2.5 | 1 | 1.5 | 1.6667 | 5 | 2 | 1 | 1 | 1 | 2 | 3 | 1 | 3 | 1 | 1 | 1.6667 | 5 | 1.6667 | 1 | 2.5 | 1 | 1 | 4 | 1 | 1 | 1 | 3 | 1.6667 | 1.5 | 1.5 | 1 | 1.5 | 2.5 | 1 | 1.3333 | 1 | 5 | 1 | 1 | 1.3333 | 1 | 2 | 3 | 1 | 1.3333 | 5 | 1.5 | 1 | 2.5 | 1 | 2
434 | 8.3333 | 6.3333 | 10.6667 | 18 | 29.3333 | 42.3333 | 51.8333 | 62.3333 | 70 | 76.6667 | 85 | 94 | 100 | 105.5 | 1 | 1.3333 | 1.5 | 2.5 | 1 | 1 | 1.3333 | 1 | 2 | 1.3333 | 1 | 3 | 1 | 1.3333 | 4 | 5 | 2 | 3 | 3 | 5 | 5 | 1 | 2.5 | 1 | 1.5 | 5 | 2.5 | 1.5 | 1.3333 | 4 | 1.3333 | 1 | 2 | 1.6667 | 1 | 2 | 1 | 1.3333 | 5 | 1 | 1 | 1.3333 | 5 | 1.6667 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 2.5
435 | 16 | 12.3333 | 18.6667 | 25.6667 | 34 | 42.5 | 50 | 58 | 64.6667 | 71.6667 | 78.5 | 89.8333 | 101.3333 | 110.6667 | 5 | 1.3333 | 5 | 1 | 2 | 1.6667 | 1.6667 | 1 | 4 | 1 | 1 | 1 | 5 | 1 | 1 | 1.3333 | 4 | 2.5 | 1 | 1 | 2.5 | 1.5 | 1 | 2.5 | 4 | 1 | 2 | 1 | 1.6667 | 1 | 2 | 2 | 1 | 4 | 1 | 1 | 2 | 1 | 2.5 | 1.3333 | 1 | 4 | 5 | 1.3333 | 1.5 | 5 | 4 | 1 | 1 | 2 | 1.3333 | 5
436 | 11.8333 | 6.1667 | 15.8333 | 20.5 | 25 | 33 | 37.5 | 43.3333 | 47.8333 | 56.5 | 62 | 69.5 | 75.8333 | 85.3333 | 1 | 1.5 | 2 | 1.6667 | 4 | 1.6667 | 2 | 2 | 1.6667 | 1 | 1 | 1 | 1 | 1.5 | 1 | 1 | 4 | 2 | 1 | 1 | 1 | 1 | 1 | 1.5 | 2.5 | 1 | 1.3333 | 1 | 1.5 | 1 | 1 | 1 | 1.6667 | 1 | 1 | 5 | 1 | 2.5 | 1 | 1 | 1.5 | 4 | 1 | 1 | 1.3333 | 2 | 2 | 1 | 4 | 1.3333 | 1.6667 | 2.5
437 | 12.3333 | 8.8333 | 14.3333 | 26 | 33.5 | 43.5 | 47.5 | 53 | 58.5 | 70 | 80.6667 | 89.6667 | 100.8333 | 110.5 | 1 | 4 | 1.3333 | 2.5 | 2.5 | 1 | 1 | 1 | 3 | 2 | 5 | 1.6667 | 2.5 | 1.5 | 1 | 2.5 | 2 | 1.5 | 1.5 | 5 | 1 | 1 | 1 | 1 | 1 | 1 | 1.5 | 2 | 1.5 | 1 | 2 | 1 | 1 | 4 | 1.5 | 5 | 3 | 1.6667 | 2 | 4 | 4 | 1 | 2 | 2 | 3 | 2.5 | 1.6667 | 4 | 1 | 2 | 5 | 1.6667
438 | 7.6667 | 4.6667 | 10 | 22 | 29 | 35.8333 | 42.3333 | 50.3333 | 55.3333 | 61.1667 | 67.6667 | 77.6667 | 90.6667 | 97 | 1 | 1 | 1.6667 | 1 | 1.3333 | 1.6667 | 1 | 1.3333 | 2.5 | 3 | 5 | 1.5 | 2 | 2 | 2 | 1 | 1.5 | 3 | 1 | 1.3333 | 2 | 2.5 | 1 | 1 | 1 | 1 | 2 | 4 | 2 | 1 | 1 | 1 | 1 | 1.3333 | 1 | 2.5 | 1 | 1.5 | 3 | 1 | 2 | 1 | 2 | 5 | 2 | 1 | 5 | 5 | 1 | 1 | 3 | 1.3333
439 | 10.6667 | 8.6667 | 12.6667 | 20.6667 | 28.1667 | 35.5 | 43.8333 | 51.5 | 57.5 | 62.6667 | 74.5 | 81 | 88.3333 | 92.3333 | 5 | 1.6667 | 1 | 1 | 1 | 1 | 1 | 1 | 5 | 1 | 1 | 1 | 4 | 1.5 | 1 | 1 | 3 | 1 | 1.3333 | 2 | 5 | 1 | 1.3333 | 1 | 1 | 1 | 1.6667 | 4 | 2 | 1.5 | 1.5 | 1 | 1.6667 | 1 | 1 | 1.5 | 2.5 | 5 | 3 | 1.3333 | 2 | 1 | 1 | 2.5 | 1 | 4 | 1.3333 | 1 | 1 | 1 | 1 | 1
440 | 7.1667 | 5.1667 | 9.5 | 17.5 | 24.5 | 30.3333 | 37 | 41.6667 | 51.1667 | 59.8333 | 67.8333 | 75.8333 | 80.5 | 89.3333 | 1.5 | 1 | 1 | 1.6667 | 1 | 1 | 1 | 1.3333 | 4 | 1 | 1.5 | 1.5 | 1.3333 | 1 | 3 | 1.6667 | 1.3333 | 2 | 1.5 | 1 | 1 | 1 | 1.6667 | 3 | 1 | 1 | 1 | 1.6667 | 1 | 1 | 5 | 2.5 | 1 | 1.6667 | 1 | 5 | 2 | 1 | 3 | 2 | 1 | 1 | 5 | 1 | 1 | 1 | 1 | 1.6667 | 1 | 1.3333 | 2.5 | 4
441 | 8.1667 | 5.1667 | 10.1667 | 17.5 | 22.8333 | 32.8333 | 40.5 | 45.5 | 50.5 | 58.5 | 66.5 | 71.1667 | 83.1667 | 94.8333 | 1.3333 | 1.5 | 1 | 1.3333 | 2 | 1 | 1 | 1 | 1.5 | 1.5 | 1.3333 | 3 | 1.6667 | 1 | 1.6667 | 1 | 2 | 4 | 2 | 2 | 1.6667 | 1 | 3 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 3 | 2.5 | 1 | 1.5 | 2.5 | 1 | 2.5 | 2 | 1 | 1.6667 | 1 | 1 | 1 | 5 | 1 | 5 | 1.6667 | 5 | 2 | 3
442 | 15 | 6 | 21 | 29 | 37 | 45 | 53 | 61.1667 | 68.5 | 74 | 81 | 86.5 | 93 | 101.5 | 1 | 3 | 1 | 1 | 4 | 5 | 1 | 5 | 1.3333 | 1 | 1.6667 | 4 | 2 | 4 | 1 | 1 | 1 | 5 | 1 | 1 | 2 | 2 | 2 | 2 | 1.6667 | 1.5 | 3 | 2 | 1 | 1.3333 | 4 | 1 | 1 | 2 | 1.5 | 1 | 3 | 2 | 1 | 1 | 1.5 | 1 | 1.5 | 1.5 | 2 | 2.5 | 1 | 1 | 2 | 1 | 1.5 | 4
443 | 11 | 6 | 13 | 18.5 | 25.5 | 35.5 | 41 | 47.3333 | 55.3333 | 65.3333 | 76.3333 | 80.8333 | 89.1667 | 94.6667 | 2 | 2 | 1 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 2.5 | 4 | 1 | 1 | 1 | 1 | 3 | 1 | 5 | 1.5 | 1 | 2 | 1 | 1.5 | 1.3333 | 2.5 | 1 | 1 | 1 | 4 | 2 | 4 | 2 | 2.5 | 1.5 | 2 | 2.5 | 1.5 | 5 | 1 | 1 | 1.5 | 1 | 2.5 | 3 | 1.5 | 1.3333 | 1 | 2 | 1.5 | 1
444 | 10 | 6.5 | 12.5 | 21.5 | 31 | 36.8333 | 43.8333 | 51.1667 | 58.8333 | 66.3333 | 75.1667 | 81 | 87.5 | 95.5 | 1 | 2 | 2.5 | 1 | 1 | 2.5 | 1 | 1.5 | 2 | 1 | 1 | 5 | 4 | 1 | 3 | 1.5 | 1.3333 | 1 | 1 | 2.5 | 2 | 1 | 1 | 3 | 1 | 2 | 1.3333 | 3 | 1 | 1.6667 | 4 | 1 | 1.6667 | 1.5 | 1.3333 | 3 | 2.5 | 1.3333 | 1 | 4 | 1.3333 | 1 | 2 | 1.5 | 1 | 1.5 | 3 | 1 | 1 | 1 | 1 | 5
445 | 12 | 9 | 14 | 18.6667 | 27.1667 | 34.5 | 45.5 | 54.5 | 60.5 | 73.5 | 80.5 | 85.1667 | 95.5 | 103.6667 | 4 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1.6667 | 1 | 3 | 2 | 2.5 | 1 | 1.3333 | 1.5 | 1.5 | 3 | 5 | 2 | 3 | 1 | 1 | 2 | 1 | 5 | 1 | 2.5 | 1.5 | 1 | 4 | 3 | 2 | 4 | 1 | 1 | 2 | 3 | 1.6667 | 1 | 1 | 1 | 1 | 1.3333 | 3 | 5 | 1.6667 | 2.5 | 2.5 | 1.5
446 | 9 | 7 | 14 | 19.5 | 24.8333 | 33.8333 | 41.8333 | 47.3333 | 54.6667 | 63.1667 | 71.8333 | 75.8333 | 80.6667 | 94 | 1 | 1 | 1 | 4 | 1 | 1 | 1 | 4 | 1 | 1 | 1.5 | 2 | 2 | 1 | 1 | 1.3333 | 1 | 1 | 4 | 3 | 1.6667 | 1.3333 | 1 | 4 | 1 | 1 | 1 | 2.5 | 2 | 1.3333 | 3 | 1 | 1.5 | 1 | 5 | 1 | 1 | 1.3333 | 1.3333 | 5 | 1 | 1 | 1 | 1 | 1 | 1.5 | 1.3333 | 1 | 4 | 4 | 1.3333 | 4
447 | 12.3333 | 8.3333 | 15.8333 | 22 | 32 | 42.5 | 53.5 | 59.8333 | 71.8333 | 81.3333 | 87.8333 | 96.3333 | 102.3333 | 110.3333 | 3 | 1.3333 | 3 | 1 | 3 | 1 | 2.5 | 1 | 1.3333 | 2.5 | 1 | 1.3333 | 5 | 1 | 2 | 2 | 4 | 1 | 3 | 2.5 | 4 | 5 | 1 | 1 | 1 | 1.3333 | 1 | 3 | 3 | 3 | 4 | 2 | 5 | 2 | 1.5 | 1 | 1.6667 | 1.3333 | 2 | 1.5 | 4 | 1 | 2.5 | 1 | 1 | 3 | 1 | 1 | 4 | 1 | 1 | 2
448 | 17.5 | 10.5 | 21.5 | 25.5 | 34 | 39.5 | 45 | 50.6667 | 57.5 | 64.1667 | 72.1667 | 78.8333 | 83.8333 | 95.8333 | 4 | 2 | 2 | 2.5 | 2 | 5 | 1 | 3 | 1 | 1 | 1 | 1 | 1.5 | 1 | 1 | 5 | 1.5 | 1 | 2 | 1 | 1 | 1 | 1 | 2.5 | 1.6667 | 1 | 2 | 1 | 2.5 | 1.6667 | 1 | 1.6667 | 3 | 1 | 1.6667 | 1 | 5 | 1 | 1 | 1 | 2 | 1.6667 | 2 | 1 | 1 | 1 | 2 | 1 | 5 | 4 | 1 | 2
449 | 10.6667 | 4.6667 | 14.1667 | 19.6667 | 30.6667 | 37.1667 | 45.1667 | 54.1667 | 64.1667 | 76.1667 | 84.5 | 89.8333 | 95.1667 | 103 | 1.3333 | 1 | 1 | 1.3333 | 1 | 5 | 2.5 | 1 | 1 | 1 | 1 | 2.5 | 5 | 2 | 1 | 3 | 1 | 1.5 | 1 | 3 | 3 | 1 | 2 | 2 | 5 | 1 | 1.3333 | 1.6667 | 1 | 5 | 3 | 1 | 2 | 3 | 5 | 2 | 1.3333 | 1 | 5 | 1 | 1.6667 | 1.6667 | 1 | 1 | 1.3333 | 1.3333 | 1 | 1.6667 | 2.5 | 1.3333 | 1.5 | 2.5
450 | 7.1667 | 4.3333 | 12.1667 | 20.6667 | 26.5 | 33.6667 | 40.3333 | 47.8333 | 53.5 | 64.6667 | 74.6667 | 84.6667 | 95.1667 | 105.6667 | 1.3333 | 1 | 1 | 1 | 1.5 | 1.3333 | 1 | 4 | 2 | 3 | 1 | 2.5 | 1.3333 | 1 | 2.5 | 1 | 2.5 | 1.5 | 1.6667 | 1.5 | 3 | 1.6667 | 1 | 1 | 1.5 | 1 | 1 | 4 | 1 | 1 | 2 | 1.6667 | 2.5 | 3 | 4 | 1.6667 | 3 | 1 | 5 | 1 | 2 | 1 | 3 | 4 | 2.5 | 4 | 2 | 2 | 1 | 2.5 | 2 | 5
451 | 16 | 14 | 18 | 25 | 32 | 38 | 43 | 47 | 52.1667 | 61.3333 | 68 | 73 | 85.3333 | 94.3333 | 4 | 2 | 4 | 4 | 1 | 1 | 1 | 1 | 4 | 1 | 1 | 1 | 2.5 | 1 | 2.5 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1.5 | 1 | 1.6667 | 2.5 | 4 | 1.6667 | 1 | 1.5 | 1 | 1.6667 | 2.5 | 1 | 1.5 | 1 | 1.5 | 5 | 1.6667 | 4 | 1.6667 | 5 | 2 | 1 | 1
452 | 10.6667 | 7.6667 | 15.6667 | 20.6667 | 28.1667 | 35.3333 | 44.8333 | 55.5 | 61.3333 | 65.3333 | 71.6667 | 81 | 91 | 97 | 4 | 1.6667 | 1 | 1 | 2 | 1 | 1 | 4 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 2.5 | 3 | 1.5 | 1 | 1.6667 | 4 | 1.5 | 2 | 2 | 1 | 1.6667 | 5 | 3 | 1.5 | 2 | 1.3333 | 1 | 1 | 1 | 1 | 1 | 3 | 1.3333 | 1 | 1 | 5 | 1 | 1.6667 | 1.6667 | 1 | 5 | 2 | 2 | 1.3333 | 1.6667 | 2 | 1
453 | 11 | 7 | 17.5 | 24.1667 | 33.1667 | 40.8333 | 47.8333 | 56.3333 | 60.8333 | 66.1667 | 75.8333 | 85 | 91.3333 | 98.3333 | 2 | 1 | 2 | 2 | 3 | 1 | 1.5 | 5 | 2 | 1.3333 | 2 | 1.3333 | 4 | 1 | 3 | 1 | 1 | 1.3333 | 4 | 1.3333 | 1 | 1 | 1 | 4 | 4 | 1 | 1 | 2.5 | 1 | 1 | 1.5 | 1 | 2 | 1 | 1 | 1.3333 | 2 | 1 | 1.6667 | 5 | 1.3333 | 1.3333 | 5 | 1.5 | 2 | 1 | 2 | 1.3333 | 1 | 2.5 | 1.5 | 2
454 | 13.3333 | 10.3333 | 16 | 23.1667 | 29.6667 | 36.6667 | 42.8333 | 47.5 | 58.1667 | 64.6667 | 74.1667 | 80.6667 | 88.6667 | 93.3333 | 5 | 1.3333 | 3 | 1 | 2 | 1 | 1.6667 | 1 | 1.3333 | 2.5 | 1.3333 | 2 | 1 | 3 | 1 | 1.5 | 2 | 1 | 3 | 1 | 1 | 1 | 2.5 | 1.6667 | 1.6667 | 1 | 1 | 1 | 4 | 1.6667 | 2 | 3 | 2 | 1 | 1 | 2.5 | 1.5 | 5 | 1 | 2 | 2.5 | 2 | 1 | 1 | 2 | 1 | 1 | 4 | 1.6667 | 1 | 1 | 1
455 | 16.8333 | 9.8333 | 21.1667 | 33.1667 | 39.8333 | 50.8333 | 60.3333 | 69.5 | 75 | 85.3333 | 93.6667 | 98.8333 | 105 | 110.6667 | 1.3333 | 1.5 | 2 | 5 | 5 | 2 | 3 | 1.3333 | 4 | 1 | 5 | 2 | 1.6667 | 2.5 | 1.5 | 1 | 1 | 4 | 5 | 1 | 3 | 1 | 3 | 2.5 | 1.6667 | 4 | 1 | 2.5 | 1 | 1.5 | 2 | 1 | 2 | 1.3333 | 5 | 2 | 1.3333 | 1 | 2 | 4 | 1 | 1.5 | 1.3333 | 1.3333 | 1.5 | 1.6667 | 2 | 1 | 1.6667 | 1 | 2 | 1
456 | 9 | 5 | 13 | 17.3333 | 23.8333 | 30.8333 | 36.3333 | 43.6667 | 50.6667 | 59.1667 | 65.5 | 70.8333 | 76.1667 | 84.1667 | 1 | 2 | 1 | 1 | 1 | 3 | 2 | 2 | 1 | 1 | 1.3333 | 1 | 1 | 2.5 | 1 | 2 | 1 | 3 | 2 | 1 | 2.5 | 1 | 1 | 1 | 2 | 1 | 1.3333 | 3 | 1 | 2 | 1 | 3 | 2.5 | 2 | 1 | 3 | 1 | 1 | 3 | 1.3333 | 1.3333 | 2 | 1 | 1 | 1.3333 | 2 | 1 | 1 | 1 | 3 | 1.5 | 2.5
457 | 9.6667 | 7.3333 | 13.6667 | 19.8333 | 27.8333 | 36.5 | 42.3333 | 50.3333 | 64.3333 | 73.6667 | 78.3333 | 83.5 | 93 | 101 | 1.3333 | 4 | 1 | 1 | 1 | 1.3333 | 3 | 1 | 1 | 1.6667 | 1.5 | 2 | 1 | 1 | 2 | 4 | 1 | 5 | 1.6667 | 1 | 2 | 1 | 1.3333 | 1.5 | 1 | 2 | 2 | 3 | 5 | 3 | 5 | 1 | 2 | 4 | 2 | 1.3333 | 1.6667 | 1 | 1 | 1 | 1 | 1.5 | 1.6667 | 1 | 2.5 | 4 | 2 | 1 | 1 | 2 | 3 | 2
458 | 10.1667 | 7.8333 | 13.6667 | 21.8333 | 26.1667 | 31.8333 | 42.3333 | 47.3333 | 54.8333 | 64.8333 | 79.1667 | 89.6667 | 97.6667 | 103.3333 | 1.5 | 4 | 1.3333 | 1 | 1.3333 | 1 | 2 | 1.5 | 1.6667 | 1.5 | 3 | 2 | 1 | 1.3333 | 1 | 1 | 1 | 1.6667 | 1 | 2 | 2.5 | 3 | 4 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 4 | 1.5 | 1 | 1 | 3 | 5 | 5 | 1.3333 | 3 | 5 | 3 | 3 | 2.5 | 2 | 1.5 | 2.5 | 1 | 3 | 1.6667 | 2 | 1 | 1
459 | 11 | 6 | 15 | 25 | 30.3333 | 37.1667 | 41.8333 | 48.3333 | 57.8333 | 62.8333 | 69.3333 | 77.6667 | 83.6667 | 93.6667 | 3 | 1 | 1 | 1 | 3 | 2 | 2 | 2 | 3 | 4 | 1 | 2 | 1.3333 | 1 | 2 | 1 | 1.3333 | 1.5 | 2.5 | 1.5 | 1 | 1 | 1 | 1.6667 | 1 | 1 | 2 | 2.5 | 2.5 | 1 | 1 | 5 | 2 | 1 | 1 | 1 | 1.5 | 2 | 2 | 1 | 1 | 1 | 1.3333 | 5 | 1 | 1 | 1 | 3 | 1 | 4 | 1 | 4
460 | 8.1667 | 5.8333 | 14.8333 | 23.5 | 32.5 | 40 | 51 | 60.8333 | 67.5 | 72.1667 | 77.6667 | 85.1667 | 90.6667 | 95.5 | 1.3333 | 1.5 | 1 | 2 | 1.3333 | 1 | 1.6667 | 5 | 1 | 1.6667 | 5 | 1 | 3 | 2 | 2 | 2 | 1 | 1 | 4 | 1.5 | 5 | 2.5 | 2.5 | 1 | 1 | 1.3333 | 2.5 | 5 | 1.5 | 2.5 | 1.6667 | 1 | 1 | 1.6667 | 1 | 1 | 1.5 | 1 | 2 | 1 | 1 | 3 | 1 | 2.5 | 1 | 1 | 2.5 | 1 | 1.5 | 1.3333 | 1 | 1
461 | 10 | 8 | 13.6667 | 18.3333 | 24.8333 | 31.1667 | 36.6667 | 46.3333 | 54.8333 | 60.8333 | 69.3333 | 82.3333 | 91 | 97 | 1 | 4 | 1 | 2 | 1 | 1 | 2 | 1.6667 | 1.6667 | 1 | 1 | 1 | 1 | 1 | 2 | 2.5 | 1 | 3 | 1.3333 | 1 | 1 | 1.3333 | 1.5 | 1.6667 | 2 | 5 | 1 | 1.6667 | 1 | 2 | 3 | 2.5 | 1.5 | 2.5 | 1 | 1 | 2 | 4 | 1 | 1.5 | 1 | 5 | 3 | 4 | 1 | 5 | 1 | 1.6667 | 3 | 1 | 1 | 1
462 | 13 | 9 | 15.5 | 23.1667 | 30 | 37 | 41 | 50.8333 | 57.1667 | 65.1667 | 70.8333 | 76.8333 | 87.1667 | 96.6667 | 2 | 2.5 | 2.5 | 2 | 1 | 3 | 1 | 1.5 | 1.6667 | 2 | 3 | 1 | 2.5 | 1.3333 | 1 | 2 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 5 | 2.5 | 1.3333 | 1 | 1 | 2 | 2 | 1.3333 | 4 | 2 | 1 | 1 | 1 | 2 | 1 | 1.6667 | 3 | 1 | 1 | 1 | 5 | 1.3333 | 3 | 1 | 1 | 2.5 | 5 | 1
463 | 9.6667 | 5.6667 | 12.5 | 19.8333 | 24.3333 | 32.3333 | 45.8333 | 56.6667 | 66 | 73.5 | 84 | 93 | 106 | 114.3333 | 1 | 2 | 1.6667 | 1 | 1 | 3 | 1.3333 | 1.5 | 1 | 1 | 1.3333 | 4 | 1 | 1 | 1.5 | 1 | 1 | 1 | 2 | 4 | 2.5 | 4 | 5 | 2 | 1.5 | 4 | 1.3333 | 4 | 2 | 1.3333 | 4 | 2 | 1 | 1 | 1.5 | 4 | 2.5 | 1 | 3 | 4 | 5 | 1 | 1 | 2 | 4 | 4 | 3 | 2 | 1 | 1.3333 | 5 | 1
464 | 7.8333 | 5.3333 | 11.8333 | 20.3333 | 30.3333 | 41.3333 | 48.8333 | 54 | 62 | 71 | 75 | 80.5 | 90 | 99 | 1.6667 | 1 | 1 | 1.6667 | 1.5 | 1 | 2 | 2 | 1 | 4 | 2.5 | 1 | 5 | 3 | 1 | 1 | 1 | 3 | 4 | 3 | 1 | 1.5 | 1 | 4 | 1 | 1.5 | 1.6667 | 1 | 5 | 1 | 1 | 1 | 4 | 2.5 | 1 | 1.5 | 1 | 1 | 1 | 1 | 2 | 1 | 1.5 | 1 | 2.5 | 5 | 1 | 1 | 4 | 2 | 1.5 | 1.5
465 | 14.6667 | 8.6667 | 16.6667 | 21.6667 | 31 | 36.5 | 41.1667 | 45.8333 | 52 | 57.8333 | 72.3333 | 81.5 | 92 | 102.5 | 1.6667 | 5 | 1 | 1 | 2 | 4 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1.6667 | 5 | 1.6667 | 1 | 1.5 | 1 | 2 | 1 | 1 | 1 | 1.6667 | 1.6667 | 1 | 1 | 1 | 2 | 1.6667 | 1.5 | 1 | 1.3333 | 2.5 | 1 | 1 | 5 | 5 | 2.5 | 2 | 1.3333 | 1.3333 | 2.5 | 4 | 2.5 | 4 | 3 | 1 | 2.5 | 2 | 5 | 1
466 | 10.5 | 5 | 13.5 | 19.5 | 30.5 | 38.1667 | 42.5 | 51 | 59.3333 | 67.6667 | 75.6667 | 79.6667 | 85.1667 | 91.1667 | 1 | 1 | 1 | 2 | 3 | 2.5 | 1 | 2 | 1.5 | 1.5 | 2 | 1 | 5 | 4 | 1 | 1 | 1.6667 | 4 | 1 | 1 | 1 | 1.3333 | 1 | 1 | 4 | 2.5 | 1 | 1 | 4 | 1.3333 | 1 | 2 | 2.5 | 2.5 | 1.3333 | 2 | 1 | 4 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1.5 | 1 | 1 | 1 | 3
467 | 8.1667 | 5.6667 | 10.1667 | 16 | 20 | 29.5 | 34.5 | 39.3333 | 43.8333 | 54.3333 | 62.8333 | 67.8333 | 75.5 | 84 | 1 | 2 | 1.3333 | 1.3333 | 1.5 | 1 | 1 | 1 | 1 | 2.5 | 1.3333 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 2.5 | 3 | 1.6667 | 1 | 1.3333 | 1 | 1.5 | 1 | 1.3333 | 1 | 1 | 1 | 1.5 | 1 | 1 | 5 | 2.5 | 2 | 1 | 2.5 | 4 | 1 | 1 | 2 | 1 | 1 | 4 | 1 | 1 | 1.6667 | 4 | 1 | 2.5 | 1
468 | 10 | 4 | 12.5 | 21.5 | 29.5 | 35.5 | 42 | 48.6667 | 55.1667 | 60.1667 | 65.1667 | 72.5 | 79 | 87 | 1 | 1 | 1 | 1 | 1 | 5 | 1.5 | 1 | 1.5 | 1 | 1.5 | 5 | 1 | 1 | 1 | 5 | 1.6667 | 2 | 1.3333 | 1 | 2 | 1.5 | 2 | 1 | 3 | 1 | 1.6667 | 1 | 3 | 1 | 1.5 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 2 | 1.5 | 1.3333 | 2.5 | 1 | 1 | 1.5 | 3 | 1.6667 | 2 | 1.3333 | 3
469 | 12 | 10 | 19 | 28 | 35.5 | 41.1667 | 48 | 57.6667 | 64.6667 | 75.1667 | 85 | 90 | 98.6667 | 105.6667 | 1 | 3 | 4 | 2 | 1 | 1 | 2 | 5 | 5 | 1 | 1 | 2 | 2 | 2.5 | 1 | 2 | 1 | 1 | 1.6667 | 2 | 1.5 | 1 | 1.3333 | 3 | 1.6667 | 5 | 2 | 1 | 1 | 4 | 1 | 1 | 5 | 3 | 1.5 | 1 | 5 | 1.3333 | 1 | 2.5 | 2 | 1 | 1 | 1 | 1 | 1.6667 | 4 | 2 | 1 | 2 | 1 | 3
470 | 17 | 13 | 19.3333 | 24.1667 | 30.8333 | 37 | 45 | 53.5 | 58.6667 | 65 | 72 | 78.3333 | 86.6667 | 96.1667 | 5 | 5 | 2 | 1 | 1 | 3 | 1.3333 | 1 | 1.5 | 1 | 1 | 1.3333 | 3 | 1 | 1.6667 | 1 | 2 | 1 | 1.6667 | 1.5 | 4 | 2 | 1 | 1 | 2.5 | 3 | 1 | 2 | 1 | 1.5 | 1.6667 | 1 | 1.3333 | 2 | 1 | 2 | 1 | 4 | 1 | 1 | 1.3333 | 2 | 1.6667 | 1.3333 | 1 | 1.3333 | 5 | 1 | 5 | 1 | 2.5 | 1
471 | 9.1667 | 5.6667 | 11.1667 | 21.1667 | 26.1667 | 30.1667 | 36.3333 | 43 | 48 | 59.5 | 69.5 | 74.8333 | 84.8333 | 94.6667 | 1.6667 | 1 | 2 | 1 | 1.5 | 2 | 1 | 1 | 5 | 2 | 1.3333 | 1.6667 | 1.6667 | 1 | 1.3333 | 1 | 1 | 1 | 1 | 1 | 1.6667 | 1 | 1 | 2.5 | 1.3333 | 2 | 2 | 1.3333 | 1 | 2 | 1 | 1 | 1.5 | 1 | 5 | 4 | 1 | 4 | 4 | 1 | 1 | 1.5 | 1.5 | 1.3333 | 4 | 4 | 1 | 1 | 2.5 | 5 | 1.3333 | 1
472 | 9.8333 | 4.8333 | 12.6667 | 21.3333 | 28.6667 | 39.1667 | 44.6667 | 53.6667 | 59.1667 | 66.6667 | 74.5 | 87 | 93.3333 | 100.3333 | 1 | 1 | 1.5 | 1.3333 | 4 | 1 | 1.3333 | 1.5 | 1.6667 | 1 | 5 | 1 | 2 | 1 | 1.3333 | 3 | 2.5 | 4 | 1 | 3 | 1 | 2 | 1.5 | 1 | 1 | 2 | 2 | 4 | 1.5 | 2 | 1 | 1 | 2 | 3 | 1.5 | 1 | 1 | 2.5 | 3 | 1.3333 | 1 | 1.5 | 5 | 5 | 1.6667 | 1 | 1.6667 | 2 | 2.5 | 1 | 1 | 2.5
473 | 13.1667 | 9 | 17.1667 | 22.5 | 29.3333 | 42.3333 | 51.3333 | 60.8333 | 64.8333 | 68.8333 | 74.3333 | 82.3333 | 89.6667 | 94.8333 | 5 | 1 | 1 | 2 | 2.5 | 1.6667 | 2 | 2 | 1.6667 | 1.6667 | 1 | 1 | 2.5 | 2 | 1.3333 | 1 | 5 | 2 | 5 | 1 | 2 | 2 | 1 | 4 | 1 | 3 | 1.5 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1.5 | 2 | 3 | 1.5 | 2.5 | 1 | 1.3333 | 1 | 2 | 3 | 1.5 | 1 | 1.6667 | 1
474 | 7.3333 | 4.8333 | 10 | 20.6667 | 28.6667 | 34.1667 | 40.1667 | 51 | 62 | 67 | 80.6667 | 85.6667 | 94.6667 | 102.5 | 1 | 1 | 1.5 | 1.3333 | 1 | 1.5 | 1.6667 | 1 | 4 | 1.6667 | 1 | 4 | 1 | 1 | 5 | 1 | 1.5 | 2 | 1 | 1 | 2 | 1 | 1.6667 | 1.3333 | 3 | 2.5 | 1.3333 | 4 | 5 | 1 | 2 | 3 | 1 | 1 | 1.5 | 1.5 | 4 | 5 | 3 | 1.6667 | 1.5 | 1 | 1 | 1.5 | 1 | 2 | 5 | 1 | 3 | 1 | 1.3333 | 2.5
475 | 16.5 | 9.8333 | 20.5 | 31.5 | 36.1667 | 47.1667 | 53.6667 | 61.1667 | 66.8333 | 73.3333 | 83 | 87 | 102 | 111 | 1.3333 | 5 | 1 | 2.5 | 1.6667 | 5 | 2 | 2 | 5 | 2 | 2 | 2 | 1 | 1 | 1.6667 | 1 | 3 | 1 | 2 | 5 | 1 | 1 | 2.5 | 2 | 4 | 1.5 | 1 | 1 | 1 | 1 | 1.6667 | 2 | 1 | 2.5 | 2 | 1 | 2 | 4 | 1.6667 | 2 | 1 | 1 | 1 | 1 | 3 | 4 | 5 | 3 | 1 | 1 | 5 | 2
476 | 10.1667 | 6.6667 | 13.1667 | 18.1667 | 26.6667 | 36.1667 | 42.5 | 55.8333 | 60.8333 | 70.8333 | 76.3333 | 87.3333 | 96.3333 | 103.6667 | 1.3333 | 2 | 2 | 1.3333 | 1 | 2.5 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 4 | 2.5 | 1 | 2.5 | 1 | 5 | 1.6667 | 1.6667 | 1 | 2 | 3 | 4 | 1.3333 | 5 | 1.6667 | 1 | 1.3333 | 1 | 1 | 2 | 5 | 2 | 1 | 2.5 | 1 | 1 | 3 | 1 | 2 | 5 | 1 | 5 | 2 | 1 | 2.5 | 1.3333 | 2.5 | 1
477 | 8.5 | 6.5 | 12.5 | 18 | 25 | 35.3333 | 44.3333 | 49.1667 | 54.1667 | 58.8333 | 65.3333 | 74.6667 | 81.6667 | 88.3333 | 1 | 1.5 | 1 | 3 | 1 | 1 | 2 | 2 | 1 | 1 | 2.5 | 1 | 2 | 3 | 1 | 1 | 3 | 4 | 2 | 1.3333 | 1 | 2.5 | 3 | 2.5 | 1.3333 | 1 | 1 | 1.5 | 2 | 1 | 1 | 1 | 1.6667 | 1 | 1 | 1 | 1 | 2.5 | 2 | 1 | 1.6667 | 4 | 1.6667 | 2 | 1 | 2.5 | 2.5 | 1 | 2 | 2 | 1.6667 | 1
478 | 10.8333 | 4.3333 | 13.5 | 21.5 | 31.1667 | 40.1667 | 50.1667 | 57.1667 | 63.6667 | 71 | 77 | 81 | 88.3333 | 98.8333 | 1 | 1.3333 | 1 | 1 | 4 | 2.5 | 1.6667 | 1 | 1 | 2 | 4 | 1 | 2 | 5 | 1.6667 | 1 | 3 | 4 | 1 | 1 | 1.3333 | 1.6667 | 2 | 5 | 3 | 1 | 2 | 1 | 1 | 2 | 1 | 2.5 | 1 | 2 | 3 | 1.3333 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 2.5 | 2.5 | 1.3333 | 2 | 2 | 1.5 | 5
479 | 14.8333 | 7.3333 | 18.8333 | 26.6667 | 36.8333 | 45.5 | 53 | 65 | 71.1667 | 80.3333 | 93.3333 | 98.3333 | 104.8333 | 115.3333 | 1 | 1.3333 | 4 | 1 | 2.5 | 5 | 1 | 3 | 1 | 1.3333 | 2.5 | 3 | 1.5 | 4 | 1.6667 | 3 | 1.5 | 4 | 1.5 | 1.6667 | 1 | 2.5 | 1 | 3 | 5 | 4 | 1 | 2 | 1.6667 | 1 | 1 | 2.5 | 3 | 1.6667 | 2.5 | 2 | 3 | 5 | 2.5 | 2.5 | 1 | 1 | 2 | 1 | 2 | 1.5 | 1 | 2 | 2.5 | 5 | 1 | 2
480 | 12.5 | 6.5 | 14.5 | 22 | 28.1667 | 38.1667 | 45.5 | 57 | 64.1667 | 71.5 | 77.5 | 85.1667 | 93.6667 | 103.6667 | 2.5 | 1 | 2 | 1 | 3 | 3 | 1 | 1 | 4 | 1 | 1.5 | 1 | 1 | 1 | 1.6667 | 2.5 | 2 | 2 | 1 | 5 | 1.5 | 1.3333 | 2 | 2.5 | 1 | 4 | 5 | 1.5 | 2 | 2.5 | 1.6667 | 1 | 1.3333 | 1 | 4 | 1 | 1 | 3 | 1 | 1 | 1.6667 | 1 | 1 | 4 | 4 | 1 | 1 | 2.5 | 2.5 | 5 | 1 | 1.5
481 | 10 | 6 | 13 | 18.6667 | 30.1667 | 38.3333 | 47.3333 | 52.5 | 60.5 | 65.5 | 78.5 | 87.1667 | 96.1667 | 108.1667 | 1 | 1 | 3 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 2 | 1.6667 | 1 | 5 | 3 | 2.5 | 1 | 1.6667 | 2.5 | 3 | 1 | 3 | 4 | 1 | 1 | 1.6667 | 1.5 | 1 | 1 | 1 | 1 | 5 | 1.6667 | 1 | 1 | 1.3333 | 5 | 5 | 2 | 1 | 5 | 1.3333 | 1 | 1.3333 | 2.5 | 1.5 | 4 | 1 | 2.5 | 5 | 3 | 1.5
482 | 11.6667 | 8 | 17 | 23.1667 | 29.5 | 35.8333 | 42.1667 | 49.1667 | 56.1667 | 63.1667 | 69.1667 | 74.6667 | 84.6667 | 96.6667 | 1 | 1 | 2 | 4 | 2 | 1.6667 | 1.3333 | 4 | 1 | 1.5 | 2 | 1.6667 | 1.3333 | 1 | 1 | 3 | 1.5 | 2.5 | 1.3333 | 1 | 1 | 1.6667 | 1.6667 | 2 | 1.6667 | 1 | 3 | 1.3333 | 2 | 2 | 1.6667 | 1.3333 | 3 | 1 | 2 | 1 | 1 | 2 | 2 | 1 | 2.5 | 1 | 1 | 1 | 3 | 1 | 3 | 3 | 4 | 2.5 | 3 | 2.5
483 | 9.3333 | 5.8333 | 15.3333 | 23.8333 | 34.3333 | 40.3333 | 52.3333 | 56.3333 | 64.3333 | 73.5 | 80 | 88 | 97.5 | 109.5 | 2 | 1.3333 | 1 | 1.5 | 1 | 2.5 | 4 | 2 | 2 | 1 | 2.5 | 3 | 5 | 2 | 1 | 2.5 | 1 | 2.5 | 1.5 | 1 | 1 | 3 | 4 | 4 | 1 | 1 | 1 | 1 | 1 | 5 | 1 | 1 | 1.3333 | 4 | 2.5 | 1.3333 | 1 | 1.6667 | 2.5 | 1.3333 | 3 | 1.5 | 2.5 | 1 | 1 | 4 | 2 | 2.5 | 1 | 5 | 1 | 5
484 | 13.5 | 11 | 18.5 | 27.5 | 35.1667 | 51.6667 | 60.3333 | 71 | 80 | 86.5 | 93 | 98 | 104.8333 | 115.5 | 2 | 4 | 2 | 3 | 1.5 | 1 | 4 | 1 | 1 | 4 | 1 | 3 | 1 | 4 | 1.3333 | 1.3333 | 4 | 5 | 2.5 | 5 | 4 | 1.6667 | 2 | 1 | 1 | 4 | 4 | 1.6667 | 4 | 3 | 1 | 1 | 2 | 1 | 2 | 1.5 | 2 | 2 | 1.5 | 1 | 1 | 2 | 1 | 1 | 2.5 | 1.6667 | 1.3333 | 1.3333 | 5 | 3 | 1.3333 | 1.3333
485 | 9.1667 | 7.1667 | 11.6667 | 17.1667 | 25.5 | 32.5 | 39.8333 | 49.8333 | 59 | 67 | 79.3333 | 85.8333 | 94.8333 | 101.8333 | 1.6667 | 2.5 | 2 | 1 | 1 | 1 | 1 | 1.5 | 1 | 1 | 2.5 | 1 | 1 | 5 | 1 | 1.3333 | 1 | 3 | 1 | 2 | 1.3333 | 1 | 1 | 4 | 1 | 5 | 1 | 3 | 1 | 1.6667 | 1.5 | 5 | 2 | 1 | 4 | 1 | 1.3333 | 5 | 3 | 3 | 2.5 | 2 | 1 | 1 | 1 | 1 | 3 | 4 | 4 | 1 | 1 | 1
486 | 7.1667 | 5.1667 | 10.3333 | 14.3333 | 18.3333 | 29.3333 | 34 | 40.3333 | 47.6667 | 55.6667 | 60.6667 | 67.8333 | 74.8333 | 84.3333 | 1 | 1 | 1.5 | 1.6667 | 1 | 1 | 1.5 | 1.6667 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 5 | 1 | 1 | 1 | 1 | 1 | 1.6667 | 1 | 2 | 1.3333 | 2 | 1 | 1.3333 | 1 | 4 | 1 | 1 | 1 | 5 | 2 | 1 | 1 | 1 | 2 | 1 | 2.5 | 1.6667 | 1 | 2 | 2 | 2 | 2 | 1.5 | 5 | 1
487 | 9.3333 | 6.3333 | 15.3333 | 19.6667 | 32.8333 | 37.8333 | 52.8333 | 56.8333 | 62.8333 | 74.3333 | 80.8333 | 88 | 95.5 | 102 | 3 | 1 | 1.3333 | 1 | 1.5 | 1.5 | 1 | 5 | 1 | 1 | 1 | 1.3333 | 1.6667 | 4 | 2.5 | 5 | 1 | 2 | 1 | 1 | 5 | 1 | 5 | 4 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 3 | 2.5 | 5 | 1 | 2 | 1 | 2.5 | 1 | 2 | 1.6667 | 1.5 | 2 | 1 | 2.5 | 3 | 1 | 1 | 1 | 1.5 | 3
488 | 13.5 | 7.5 | 19.5 | 23.5 | 32.1667 | 39.6667 | 44.6667 | 50.3333 | 61.8333 | 71.1667 | 79.1667 | 85.1667 | 95.1667 | 100.6667 | 2 | 2 | 2.5 | 1 | 1 | 5 | 1 | 5 | 1 | 1 | 1 | 1 | 1.5 | 3 | 1.6667 | 2.5 | 1 | 1 | 2.5 | 3 | 1 | 2 | 1 | 1 | 2 | 1 | 1.6667 | 1 | 1 | 5 | 3 | 2.5 | 5 | 2 | 1 | 1.3333 | 1 | 2 | 1 | 4 | 1 | 2 | 1 | 2 | 5 | 1.3333 | 1.6667 | 2 | 1.5 | 2 | 1 | 1
489 | 9.5 | 5.5 | 13 | 17 | 25 | 33.1667 | 41.6667 | 46.6667 | 54.8333 | 64.8333 | 70.3333 | 76.8333 | 85.8333 | 93.8333 | 1.6667 | 1.3333 | 1.5 | 1 | 3 | 1 | 1 | 2.5 | 1 | 1 | 1 | 1 | 2 | 2 | 2.5 | 1.5 | 3 | 2 | 1.5 | 1.6667 | 1.5 | 2.5 | 2.5 | 2 | 1 | 2 | 1 | 1 | 2.5 | 1.6667 | 3 | 1 | 1.5 | 5 | 1 | 2.5 | 1.5 | 1.5 | 1.5 | 1 | 1.5 | 1.5 | 2.5 | 1 | 2 | 1 | 5 | 1 | 1 | 1 | 4 | 2
490 | 15.1667 | 9.1667 | 17.1667 | 29.5 | 37.8333 | 42.8333 | 50.1667 | 55.6667 | 65.6667 | 75.6667 | 80.6667 | 90.5 | 98.5 | 105.8333 | 5 | 1.6667 | 1 | 1.5 | 4 | 2 | 1 | 1 | 1.3333 | 5 | 3 | 3 | 5 | 1 | 1 | 1.3333 | 1 | 1 | 1 | 2 | 1 | 2 | 3 | 1.3333 | 1 | 2.5 | 1 | 1 | 1 | 3 | 5 | 1 | 4 | 1 | 4 | 1 | 1 | 1 | 1.5 | 1.5 | 1.3333 | 5 | 2.5 | 1 | 3 | 3 | 1 | 1 | 1 | 2.5 | 1.3333 | 2.5
491 | 7.5 | 4 | 13.5 | 18.5 | 27.5 | 34.1667 | 39.1667 | 47.6667 | 54.5 | 63.6667 | 71.3333 | 84.1667 | 93 | 102 | 1 | 1 | 1 | 1 | 2 | 1.5 | 5 | 1 | 1 | 2 | 1 | 1 | 1.3333 | 1.6667 | 1 | 5 | 1.6667 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 1 | 2.5 | 4 | 1 | 1.5 | 3 | 1 | 1.3333 | 1.6667 | 5 | 1.5 | 1 | 1 | 4 | 1.3333 | 1.3333 | 1.5 | 5 | 5 | 1.3333 | 4 | 1.3333 | 2.5 | 1 | 1 | 2 | 5 | 1
492 | 18.6667 | 13.6667 | 24.6667 | 36.6667 | 44.1667 | 51.1667 | 62.1667 | 75.3333 | 79.8333 | 89 | 98 | 108 | 113 | 118.6667 | 3 | 1.6667 | 5 | 4 | 1 | 4 | 2 | 4 | 4 | 1.3333 | 1.6667 | 5 | 3 | 1.5 | 2 | 1 | 1 | 1 | 1 | 4 | 1 | 3 | 2 | 5 | 1.6667 | 2.5 | 5 | 4 | 1 | 1 | 1.5 | 1 | 4 | 1.5 | 1.6667 | 2 | 5 | 2 | 1 | 1 | 1 | 4 | 3 | 2 | 1 | 1 | 2 | 1 | 1.6667 | 1 | 1 | 2
493 | 6.5 | 4.5 | 9.5 | 16.6667 | 30.3333 | 39 | 50 | 55 | 63 | 76 | 87 | 100 | 110.5 | 126.1667 | 1 | 1 | 1 | 1.5 | 1 | 1 | 1 | 2 | 1.6667 | 1 | 3 | 1.5 | 5 | 2 | 1.6667 | 5 | 5 | 1 | 1 | 1.6667 | 2 | 3 | 2 | 4 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 4 | 1 | 5 | 2 | 5 | 2 | 3 | 5 | 1 | 1 | 3 | 5 | 4 | 1 | 2.5 | 3 | 4 | 5 | 4 | 1.6667 | 5
494 | 9.8333 | 4.8333 | 12.5 | 22.5 | 30 | 37 | 44.5 | 51 | 59.5 | 66.8333 | 71.8333 | 79.5 | 86 | 95.6667 | 1.3333 | 1 | 1 | 1.5 | 1 | 4 | 1 | 1.6667 | 3 | 1 | 1 | 5 | 1 | 2.5 | 3 | 1 | 1 | 3 | 1 | 2 | 2.5 | 1 | 2.5 | 1.5 | 2 | 1 | 2.5 | 1 | 4 | 1 | 2.5 | 1 | 2.5 | 2 | 1.3333 | 1.5 | 1 | 2 | 1 | 1 | 1 | 1.6667 | 4 | 1 | 3 | 1 | 1.5 | 1 | 4 | 1.3333 | 3 | 1.3333
495 | 9.1667 | 5.6667 | 12.1667 | 23.1667 | 35.1667 | 44.1667 | 52.5 | 58 | 70 | 80.6667 | 87.6667 | 97.1667 | 103.5 | 113.5 | 2 | 1 | 1 | 1.6667 | 1.5 | 2 | 1 | 2 | 2 | 2 | 5 | 2 | 5 | 1 | 1 | 5 | 2 | 1 | 4 | 2 | 5 | 1 | 1.3333 | 1 | 1.3333 | 1.6667 | 1 | 1.5 | 1 | 5 | 1 | 5 | 5 | 1.3333 | 1.3333 | 3 | 2 | 1 | 1 | 3 | 2.5 | 5 | 1 | 1 | 1.3333 | 3 | 1 | 1 | 2 | 1 | 5 | 2
496 | 10 | 6.5 | 12.6667 | 21.3333 | 25.8333 | 32.8333 | 38.5 | 45.1667 | 53.1667 | 60.1667 | 65.8333 | 74.8333 | 79.6667 | 89.6667 | 2.5 | 1.6667 | 1 | 1.3333 | 2 | 1.5 | 1 | 1.6667 | 2 | 2 | 1.6667 | 3 | 1.5 | 1 | 1 | 1 | 3 | 1 | 2 | 1 | 1.3333 | 1 | 1.3333 | 2 | 3 | 1 | 1.6667 | 1 | 1 | 4 | 1.6667 | 1.3333 | 1 | 1 | 4 | 1 | 1.6667 | 1.6667 | 1.3333 | 1 | 1 | 2 | 4 | 2 | 1 | 1 | 1.5 | 1.3333 | 2.5 | 2.5 | 1 | 4
497 | 10.1667 | 6.6667 | 12.1667 | 19.5 | 26.1667 | 35.5 | 41.5 | 51 | 58.5 | 64.1667 | 76.6667 | 83.5 | 93.6667 | 100 | 1.3333 | 3 | 1 | 1.3333 | 2.5 | 1 | 1 | 1 | 1.3333 | 1 | 2 | 3 | 2.5 | 1.6667 | 1 | 1.5 | 2 | 1.3333 | 3 | 3 | 3 | 1 | 1 | 1 | 4 | 2 | 1 | 2.5 | 2.5 | 1 | 3 | 1 | 2 | 1 | 1.6667 | 1 | 1 | 5 | 1.5 | 5 | 1.6667 | 1.6667 | 2.5 | 1 | 5 | 1 | 1.6667 | 2.5 | 1.3333 | 3 | 1 | 1
498 | 18 | 10 | 23 | 31.5 | 42.5 | 46.8333 | 52.5 | 61.5 | 73.5 | 84 | 88.3333 | 101 | 110 | 115.6667 | 1.3333 | 1.6667 | 3 | 4 | 3 | 5 | 2 | 3 | 3 | 1 | 2 | 2.5 | 5 | 2 | 3 | 1 | 1 | 1.3333 | 1 | 1 | 1 | 1 | 1.6667 | 2 | 1 | 1 | 3 | 4 | 5 | 5 | 1 | 1 | 3 | 5 | 1 | 1.5 | 1 | 1 | 1.3333 | 1 | 1.6667 | 4 | 5 | 2 | 2 | 2 | 2 | 3 | 1 | 2 | 1.6667 | 1
499 | 10.3333 | 5.3333 | 13 | 17.3333 | 25.3333 | 31.3333 | 37.3333 | 43.3333 | 55.3333 | 62.6667 | 69.1667 | 75.8333 | 84.6667 | 97.6667 | 1.3333 | 2 | 1 | 1 | 3 | 2 | 1.6667 | 1 | 1 | 1 | 1.3333 | 1 | 1 | 1 | 1 | 5 | 1 | 2 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 5 | 4 | 1 | 4 | 1 | 1.3333 | 1 | 2 | 1 | 2.5 | 1 | 1 | 1.6667 | 3 | 1 | 5 | 1.3333 | 1.5 | 5 | 5 | 1 | 2
500 | 10.3333 | 4.3333 | 13 | 22.5 | 29 | 40 | 46.6667 | 51.3333 | 58.3333 | 76.3333 | 83.5 | 89 | 96.8333 | 105.3333 | 1 | 1.3333 | 1 | 1 | 1 | 5 | 1 | 1.6667 | 1 | 5 | 2.5 | 1 | 1 | 3 | 1.5 | 1 | 5 | 1 | 1 | 4 | 3 | 1 | 1.3333 | 1.3333 | 1.3333 | 1 | 1.3333 | 1 | 2 | 1 | 1 | 3 | 4 | 5 | 5 | 4 | 1 | 3 | 1.5 | 1.6667 | 2 | 1 | 1 | 1.5 | 1.5 | 1 | 4 | 1.3333 | 1.5 | 1 | 4 | 2
| 6 | Sum4: 4; Sum8: 8; Sum12: 12; Sum16: 16; Sum20: 20; Sum24: 24; Sum28: 28; Sum32: 32; Sum36: 36; Sum40: 40; Sum44: 44; Sum48: 48; Sum52: 52
1% | 6.665 | Sum4: 4; Sum8: 9.5; Sum12: 14.995; Sum16: 21.4983; Sum20: 28.825; Sum24: 35.1633; Sum28: 41.3267; Sum32: 47.9983; Sum36: 55.665; Sum40: 62.4983; Sum44: 68.6633; Sum48: 75.83; Sum52: 83.6633
2% | 6.8333 | Sum4: 4; Sum8: 9.6667; Sum12: 15.6667; Sum16: 22.8333; Sum20: 29.33; Sum24: 36.1667; Sum28: 42.6667; Sum32: 49.49; Sum36: 57; Sum40: 63.1633; Sum44: 70.5; Sum48: 76.6633; Sum52: 84.33
3% | 7 | Sum4: 4; Sum8: 10; Sum12: 16.6667; Sum16: 23.3233; Sum20: 29.6667; Sum24: 36.6567; Sum28: 43.495; Sum32: 50.495; Sum36: 57.995; Sum40: 64.8233; Sum44: 71.3333; Sum48: 78.6617; Sum52: 85.495
4% | 7.1667 | Sum4: 4.3333; Sum8: 10.1667; Sum12: 17; Sum16: 23.5; Sum20: 30.1667; Sum24: 37; Sum28: 43.6667; Sum32: 51.1667; Sum36: 58.4867; Sum40: 65.3333; Sum44: 71.8333; Sum48: 79; Sum52: 86.32
5% | 7.3333 | Sum4: 4.3333; Sum8: 10.5; Sum12: 17.1667; Sum16: 23.6667; Sum20: 30.3333; Sum24: 37.3333; Sum28: 43.9917; Sum32: 51.6583; Sum36: 58.8333; Sum40: 65.8333; Sum44: 72.8333; Sum48: 79.6583; Sum52: 87
6% | 7.5 | Sum4: 4.5; Sum8: 10.6667; Sum12: 17.49; Sum16: 24.1567; Sum20: 30.8333; Sum24: 37.5; Sum28: 44.5; Sum32: 51.8233; Sum36: 59.1667; Sum40: 66.1667; Sum44: 73.3333; Sum48: 80.6567; Sum52: 87.5
7% | 7.655 | Sum4: 4.6667; Sum8: 10.8333; Sum12: 17.5; Sum16: 24.655; Sum20: 31.1667; Sum24: 37.8333; Sum28: 45; Sum32: 52; Sum36: 59.5; Sum40: 66.81; Sum44: 73.8333; Sum48: 81.3217; Sum52: 88.3333
8% | 7.6667 | Sum4: 4.6667; Sum8: 11; Sum12: 17.9867; Sum16: 24.82; Sum20: 31.5; Sum24: 38.3333; Sum28: 45.3333; Sum32: 52.4733; Sum36: 59.9867; Sum40: 67.32; Sum44: 74.32; Sum48: 81.6533; Sum52: 88.82
9% | 7.8333 | Sum4: 4.8333; Sum8: 11.1517; Sum12: 18; Sum16: 25; Sum20: 31.8333; Sum24: 38.5; Sum28: 45.6517; Sum32: 52.6667; Sum36: 60.1667; Sum40: 67.6517; Sum44: 74.6667; Sum48: 82; Sum52: 89.3183
10% | 8 | Sum4: 4.8333; Sum8: 11.3333; Sum12: 18.1667; Sum16: 25; Sum20: 32.15; Sum24: 38.8333; Sum28: 45.8333; Sum32: 53.15; Sum36: 60.65; Sum40: 67.9833; Sum44: 74.9833; Sum48: 82.65; Sum52: 89.5
11% | 8.1483 | Sum4: 5; Sum8: 11.5; Sum12: 18.1667; Sum16: 25; Sum20: 32.3333; Sum24: 39.1667; Sum28: 46; Sum32: 53.315; Sum36: 60.9817; Sum40: 68; Sum44: 75.6667; Sum48: 82.6667; Sum52: 89.9633
12% | 8.1667 | Sum4: 5; Sum8: 11.5; Sum12: 18.3333; Sum16: 25.3133; Sum20: 32.5; Sum24: 39.3133; Sum28: 46.3333; Sum32: 53.6467; Sum36: 61.48; Sum40: 68.1667; Sum44: 75.8333; Sum48: 83.1467; Sum52: 90.3333
13% | 8.3333 | Sum4: 5; Sum8: 11.6667; Sum12: 18.5; Sum16: 25.3333; Sum20: 32.8333; Sum24: 39.6667; Sum28: 46.6667; Sum32: 54.3117; Sum36: 61.9783; Sum40: 68.6667; Sum44: 76; Sum48: 83.5; Sum52: 90.8333
14% | 8.3333 | Sum4: 5; Sum8: 11.8333; Sum12: 18.6667; Sum16: 25.5; Sum20: 32.8333; Sum24: 39.8333; Sum28: 47; Sum32: 54.6667; Sum36: 62.1667; Sum40: 69; Sum44: 76.3333; Sum48: 83.8333; Sum52: 91.1433
15% | 8.5 | Sum4: 5.1417; Sum8: 12; Sum12: 18.6667; Sum16: 25.8333; Sum20: 33; Sum24: 40.1417; Sum28: 47.3083; Sum32: 54.8333; Sum36: 62.1667; Sum40: 69.3333; Sum44: 76.5; Sum48: 84.1667; Sum52: 91.5
16% | 8.5 | Sum4: 5.3333; Sum8: 12.14; Sum12: 18.9733; Sum16: 25.8333; Sum20: 33.1667; Sum24: 40.5; Sum28: 47.5; Sum32: 55; Sum36: 62.5; Sum40: 69.5; Sum44: 76.8333; Sum48: 84.5; Sum52: 91.8333
17% | 8.5 | Sum4: 5.3333; Sum8: 12.1667; Sum12: 19; Sum16: 25.9717; Sum20: 33.4717; Sum24: 40.805; Sum28: 47.805; Sum32: 55.1667; Sum36: 62.805; Sum40: 69.805; Sum44: 77.305; Sum48: 84.6667; Sum52: 92.1383
18% | 8.6667 | Sum4: 5.5; Sum8: 12.3333; Sum12: 19.1667; Sum16: 26.1667; Sum20: 33.6667; Sum24: 40.8333; Sum28: 48; Sum32: 55.3333; Sum36: 62.97; Sum40: 70; Sum44: 77.5; Sum48: 84.8333; Sum52: 92.3333
19% | 8.8333 | Sum4: 5.5; Sum8: 12.5; Sum12: 19.3333; Sum16: 26.3333; Sum20: 33.8017; Sum24: 41.1667; Sum28: 48.1667; Sum32: 55.6667; Sum36: 63.1667; Sum40: 70.3333; Sum44: 77.6667; Sum48: 85; Sum52: 92.635
20% | 9 | Sum4: 5.5; Sum8: 12.5; Sum12: 19.5; Sum16: 26.5; Sum20: 33.8333; Sum24: 41.3; Sum28: 48.3333; Sum32: 55.8333; Sum36: 63.3333; Sum40: 70.6667; Sum44: 77.6667; Sum48: 85.1667; Sum52: 93.1333
21% | 9 | Sum4: 5.6667; Sum8: 12.5; Sum12: 19.5; Sum16: 26.6667; Sum20: 34.1317; Sum24: 41.5; Sum28: 48.6317; Sum32: 56.2983; Sum36: 63.5; Sum40: 71; Sum44: 78; Sum48: 85.3333; Sum52: 93.465
22% | 9 | Sum4: 5.6667; Sum8: 12.6667; Sum12: 19.6667; Sum16: 26.8333; Sum20: 34.1667; Sum24: 41.6667; Sum28: 48.8333; Sum32: 56.4633; Sum36: 63.6667; Sum40: 71.1667; Sum44: 78.1667; Sum48: 85.6667; Sum52: 93.63
23% | 9.1283 | Sum4: 5.6667; Sum8: 12.6667; Sum12: 19.8333; Sum16: 27; Sum20: 34.5; Sum24: 41.8333; Sum28: 49.1667; Sum32: 56.795; Sum36: 63.8333; Sum40: 71.3333; Sum44: 78.5; Sum48: 85.9617; Sum52: 93.8333
24% | 9.1667 | Sum4: 5.6667; Sum8: 12.8333; Sum12: 19.8333; Sum16: 27.1667; Sum20: 34.6267; Sum24: 42; Sum28: 49.3333; Sum32: 57; Sum36: 64; Sum40: 71.5; Sum44: 78.6667; Sum48: 86.3333; Sum52: 94
25% | 9.3333 | Sum4: 5.8333; Sum8: 13; Sum12: 19.9583; Sum16: 27.3333; Sum20: 34.7917; Sum24: 42.2917; Sum28: 49.5; Sum32: 57.1667; Sum36: 64.1667; Sum40: 71.6667; Sum44: 78.9583; Sum48: 86.625; Sum52: 94.1667
26% | 9.3333 | Sum4: 5.8333; Sum8: 13; Sum12: 20; Sum16: 27.4567; Sum20: 34.9567; Sum24: 42.3333; Sum28: 49.6667; Sum32: 57.29; Sum36: 64.5; Sum40: 71.9567; Sum44: 79; Sum48: 86.8333; Sum52: 94.5
27% | 9.5 | Sum4: 6; Sum8: 13; Sum12: 20.1667; Sum16: 27.5; Sum20: 35; Sum24: 42.5; Sum28: 49.8333; Sum32: 57.3333; Sum36: 64.6667; Sum40: 72.1667; Sum44: 79.1667; Sum48: 87.1217; Sum52: 94.6667
28% | 9.5 | Sum4: 6; Sum8: 13.2867; Sum12: 20.3333; Sum16: 27.6667; Sum20: 35.1667; Sum24: 42.6667; Sum28: 50; Sum32: 57.5; Sum36: 64.8333; Sum40: 72.1667; Sum44: 79.5; Sum48: 87.1667; Sum52: 94.9533
29% | 9.6667 | Sum4: 6; Sum8: 13.3333; Sum12: 20.4517; Sum16: 27.8333; Sum20: 35.3333; Sum24: 42.8333; Sum28: 50.1667; Sum32: 57.6667; Sum36: 64.8333; Sum40: 72.5; Sum44: 79.8333; Sum48: 87.5; Sum52: 95.3333
30% | 9.6667 | Sum4: 6; Sum8: 13.3333; Sum12: 20.5; Sum16: 28; Sum20: 35.5; Sum24: 42.8333; Sum28: 50.3333; Sum32: 57.6667; Sum36: 65; Sum40: 72.5; Sum44: 80.1167; Sum48: 87.6667; Sum52: 95.5
31% | 9.8333 | Sum4: 6; Sum8: 13.5; Sum12: 20.6667; Sum16: 28.1667; Sum20: 35.615; Sum24: 43; Sum28: 50.5; Sum32: 57.8333; Sum36: 65.1667; Sum40: 72.6667; Sum44: 80.1667; Sum48: 88; Sum52: 95.615
32% | 9.8333 | Sum4: 6; Sum8: 13.5; Sum12: 20.78; Sum16: 28.28; Sum20: 35.8333; Sum24: 43; Sum28: 50.6667; Sum32: 58; Sum36: 65.3333; Sum40: 72.8333; Sum44: 80.3333; Sum48: 88.1667; Sum52: 95.78
33% | 10 | Sum4: 6.1667; Sum8: 13.6667; Sum12: 21; Sum16: 28.445; Sum20: 35.8333; Sum24: 43.2783; Sum28: 50.8333; Sum32: 58.1667; Sum36: 65.5; Sum40: 73; Sum44: 80.5; Sum48: 88.3333; Sum52: 96
34% | 10 | Sum4: 6.1667; Sum8: 13.6667; Sum12: 21; Sum16: 28.5; Sum20: 36.11; Sum24: 43.5; Sum28: 50.9433; Sum32: 58.3333; Sum36: 65.6667; Sum40: 73.1667; Sum44: 80.6667; Sum48: 88.5; Sum52: 96.11
35% | 10 | Sum4: 6.1667; Sum8: 13.775; Sum12: 21; Sum16: 28.6667; Sum20: 36.275; Sum24: 43.6667; Sum28: 51; Sum32: 58.4417; Sum36: 65.775; Sum40: 73.3333; Sum44: 80.8333; Sum48: 88.6667; Sum52: 96.1667
36% | 10 | Sum4: 6.3333; Sum8: 13.8333; Sum12: 21.1667; Sum16: 28.7733; Sum20: 36.44; Sum24: 43.8333; Sum28: 51.1067; Sum32: 58.5; Sum36: 65.94; Sum40: 73.5; Sum44: 81; Sum48: 89; Sum52: 96.5
37% | 10 | Sum4: 6.3333; Sum8: 14; Sum12: 21.1667; Sum16: 29; Sum20: 36.5; Sum24: 43.8333; Sum28: 51.3333; Sum32: 58.6667; Sum36: 66; Sum40: 73.6667; Sum44: 81.2717; Sum48: 89.2717; Sum52: 96.6667
38% | 10.1667 | Sum4: 6.5; Sum8: 14; Sum12: 21.3333; Sum16: 29.1667; Sum20: 36.6667; Sum24: 44; Sum28: 51.3333; Sum32: 58.8333; Sum36: 66.1033; Sum40: 73.8333; Sum44: 81.5; Sum48: 89.3333; Sum52: 97
39% | 10.1667 | Sum4: 6.5; Sum8: 14; Sum12: 21.3333; Sum16: 29.1667; Sum20: 36.8333; Sum24: 44.3333; Sum28: 51.6017; Sum32: 59; Sum36: 66.3333; Sum40: 74.1667; Sum44: 81.5; Sum48: 89.6667; Sum52: 97
40% | 10.3333 | Sum4: 6.5; Sum8: 14.1667; Sum12: 21.5; Sum16: 29.2667; Sum20: 37; Sum24: 44.3333; Sum28: 51.6667; Sum32: 59.1667; Sum36: 66.6667; Sum40: 74.3333; Sum44: 81.8333; Sum48: 89.8333; Sum52: 97.1667
41% | 10.5 | Sum4: 6.5; Sum8: 14.1667; Sum12: 21.5; Sum16: 29.3333; Sum20: 37; Sum24: 44.5983; Sum28: 51.8333; Sum32: 59.4317; Sum36: 66.8333; Sum40: 74.5; Sum44: 82; Sum48: 89.9317; Sum52: 97.3333
42% | 10.5 | Sum4: 6.6667; Sum8: 14.3333; Sum12: 21.6667; Sum16: 29.5; Sum20: 37.0967; Sum24: 44.6667; Sum28: 52.0967; Sum32: 59.5; Sum36: 66.8333; Sum40: 74.8333; Sum44: 82.1667; Sum48: 90; Sum52: 97.43
43% | 10.6667 | Sum4: 6.8333; Sum8: 14.3333; Sum12: 21.8333; Sum16: 29.6667; Sum20: 37.1667; Sum24: 44.8333; Sum28: 52.2617; Sum32: 59.6667; Sum36: 66.9283; Sum40: 75; Sum44: 82.3333; Sum48: 90.1667; Sum52: 97.5
44% | 10.6667 | Sum4: 7; Sum8: 14.3333; Sum12: 22; Sum16: 29.6667; Sum20: 37.3333; Sum24: 44.9267; Sum28: 52.3333; Sum32: 59.8333; Sum36: 67.1667; Sum40: 75.1667; Sum44: 82.4267; Sum48: 90.1667; Sum52: 97.8333
45% | 10.6667 | Sum4: 7; Sum8: 14.425; Sum12: 22; Sum16: 29.7583; Sum20: 37.425; Sum24: 45; Sum28: 52.6667; Sum32: 59.925; Sum36: 67.5; Sum40: 75.3333; Sum44: 82.8333; Sum48: 90.3333; Sum52: 98.1667
46% | 10.8333 | Sum4: 7; Sum8: 14.5; Sum12: 22.1667; Sum16: 29.8333; Sum20: 37.5; Sum24: 45.1667; Sum28: 52.6667; Sum32: 60.1667; Sum36: 67.6667; Sum40: 75.5; Sum44: 83; Sum48: 90.59; Sum52: 98.3333
47% | 11 | Sum4: 7; Sum8: 14.5; Sum12: 22.1667; Sum16: 29.8333; Sum20: 37.6667; Sum24: 45.3333; Sum28: 52.8333; Sum32: 60.3333; Sum36: 67.8333; Sum40: 75.6667; Sum44: 83.0883; Sum48: 90.6667; Sum52: 98.5883
48% | 11 | Sum4: 7.0867; Sum8: 14.6667; Sum12: 22.5; Sum16: 30; Sum20: 37.6667; Sum24: 45.5; Sum28: 53; Sum32: 60.5; Sum36: 67.92; Sum40: 75.92; Sum44: 83.1667; Sum48: 90.8333; Sum52: 98.8333
49% | 11 | Sum4: 7.3333; Sum8: 14.7517; Sum12: 22.5; Sum16: 30.1667; Sum20: 37.8333; Sum24: 45.5; Sum28: 53.1667; Sum32: 60.5; Sum36: 68; Sum40: 76; Sum44: 83.5; Sum48: 91; Sum52: 99
50% | 11.0833 | Sum4: 7.3333; Sum8: 14.8333; Sum12: 22.6667; Sum16: 30.1667; Sum20: 38; Sum24: 45.75; Sum28: 53.4167; Sum32: 60.6667; Sum36: 68.25; Sum40: 76.1667; Sum44: 83.6667; Sum48: 91.3333; Sum52: 99.0833
51% | 11.3333 | Sum4: 7.415; Sum8: 15; Sum12: 22.6667; Sum16: 30.3333; Sum20: 38.0817; Sum24: 46; Sum28: 53.5; Sum32: 60.8333; Sum36: 68.3333; Sum40: 76.3333; Sum44: 84; Sum48: 91.5; Sum52: 99.3333
52% | 11.3333 | Sum4: 7.5; Sum8: 15; Sum12: 22.8333; Sum16: 30.3333; Sum20: 38.1667; Sum24: 46.1667; Sum28: 53.58; Sum32: 61.1667; Sum36: 68.6667; Sum40: 76.3333; Sum44: 84.1667; Sum48: 91.6667; Sum52: 99.5
53% | 11.4117 | Sum4: 7.5; Sum8: 15.1667; Sum12: 23; Sum16: 30.5; Sum20: 38.1667; Sum24: 46.3333; Sum28: 53.6667; Sum32: 61.3333; Sum36: 68.8333; Sum40: 76.5; Sum44: 84.3333; Sum48: 92; Sum52: 99.8333
54% | 11.5 | Sum4: 7.5767; Sum8: 15.3333; Sum12: 23.1667; Sum16: 30.6667; Sum20: 38.3333; Sum24: 46.5; Sum28: 53.8333; Sum32: 61.5; Sum36: 69.1667; Sum40: 76.6667; Sum44: 84.41; Sum48: 92.0767; Sum52: 100
55% | 11.6667 | Sum4: 7.6667; Sum8: 15.5; Sum12: 23.1667; Sum16: 30.6667; Sum20: 38.3333; Sum24: 46.5; Sum28: 54; Sum32: 61.8333; Sum36: 69.4083; Sum40: 77; Sum44: 84.6667; Sum48: 92.2417; Sum52: 100.1667
56% | 11.9067 | Sum4: 7.8333; Sum8: 15.5; Sum12: 23.3333; Sum16: 30.8333; Sum20: 38.6667; Sum24: 46.6667; Sum28: 54.1667; Sum32: 62; Sum36: 69.5; Sum40: 77.1667; Sum44: 84.9067; Sum48: 92.3333; Sum52: 100.3333
57% | 12 | Sum4: 8; Sum8: 15.6667; Sum12: 23.3333; Sum16: 30.8333; Sum20: 38.8333; Sum24: 46.8333; Sum28: 54.3333; Sum32: 62.1667; Sum36: 69.6667; Sum40: 77.3333; Sum44: 85.0717; Sum48: 92.5717; Sum52: 100.6667
58% | 12 | Sum4: 8; Sum8: 15.6667; Sum12: 23.5; Sum16: 31; Sum20: 39; Sum24: 46.8333; Sum28: 54.5; Sum32: 62.3333; Sum36: 70; Sum40: 77.6667; Sum44: 85.1667; Sum48: 93; Sum52: 100.8333
59% | 12 | Sum4: 8; Sum8: 15.8333; Sum12: 23.6667; Sum16: 31; Sum20: 39; Sum24: 47; Sum28: 54.5; Sum32: 62.5; Sum36: 70.1667; Sum40: 77.8333; Sum44: 85.3333; Sum48: 93.3333; Sum52: 101
60% | 12.1667 | Sum4: 8; Sum8: 16; Sum12: 23.8333; Sum16: 31.1667; Sum20: 39.1667; Sum24: 47.0667; Sum28: 54.5667; Sum32: 62.5; Sum36: 70.1667; Sum40: 78; Sum44: 85.4; Sum48: 93.5; Sum52: 101.1667
61% | 12.2317 | Sum4: 8; Sum8: 16; Sum12: 23.8333; Sum16: 31.3333; Sum20: 39.3333; Sum24: 47.3333; Sum28: 54.7317; Sum32: 62.6667; Sum36: 70.3983; Sum40: 78.1667; Sum44: 85.6667; Sum48: 93.565; Sum52: 101.565
62% | 12.3333 | Sum4: 8; Sum8: 16.1667; Sum12: 24; Sum16: 31.6667; Sum20: 39.5; Sum24: 47.5; Sum28: 55; Sum32: 62.8333; Sum36: 70.6667; Sum40: 78.3333; Sum44: 86; Sum48: 93.6667; Sum52: 101.8967
63% | 12.3333 | Sum4: 8; Sum8: 16.3333; Sum12: 24.1667; Sum16: 31.8333; Sum20: 39.6667; Sum24: 47.6667; Sum28: 55.3333; Sum32: 63; Sum36: 71; Sum40: 78.5; Sum44: 86.3333; Sum48: 94.2283; Sum52: 102.0617
64% | 12.5 | Sum4: 8.1667; Sum8: 16.3333; Sum12: 24.1667; Sum16: 32; Sum20: 39.8333; Sum24: 47.8333; Sum28: 55.3333; Sum32: 63.1667; Sum36: 71.1667; Sum40: 78.6667; Sum44: 86.5; Sum48: 94.6667; Sum52: 102.3933
65% | 12.5 | Sum4: 8.3333; Sum8: 16.5; Sum12: 24.3333; Sum16: 32.0583; Sum20: 40; Sum24: 47.8333; Sum28: 55.5; Sum32: 63.3333; Sum36: 71.2833; Sum40: 78.8917; Sum44: 86.5; Sum48: 94.8333; Sum52: 102.5583
66% | 12.5 | Sum4: 8.5; Sum8: 16.5; Sum12: 24.5567; Sum16: 32.1667; Sum20: 40.1667; Sum24: 48; Sum28: 55.6667; Sum32: 63.5; Sum36: 71.5567; Sum40: 79.3333; Sum44: 87; Sum48: 95.0567; Sum52: 102.8333
67% | 12.555 | Sum4: 8.6667; Sum8: 16.6667; Sum12: 24.6667; Sum16: 32.1667; Sum20: 40.2217; Sum24: 48.055; Sum28: 55.8333; Sum32: 63.6667; Sum36: 71.8333; Sum40: 79.555; Sum44: 87.2217; Sum48: 95.1667; Sum52: 102.8883
68% | 12.6667 | Sum4: 8.6667; Sum8: 16.6667; Sum12: 24.8333; Sum16: 32.5; Sum20: 40.5; Sum24: 48.1667; Sum28: 56.0533; Sum32: 63.8867; Sum36: 72.0533; Sum40: 80; Sum44: 87.5; Sum48: 95.5; Sum52: 103.0533
69% | 12.8333 | Sum4: 8.7183; Sum8: 16.885; Sum12: 25; Sum16: 32.6667; Sum20: 40.5; Sum24: 48.2183; Sum28: 56.3333; Sum32: 64.1667; Sum36: 72.2183; Sum40: 80; Sum44: 87.8333; Sum48: 95.5517; Sum52: 103.3333
70% | 13 | Sum4: 8.8333; Sum8: 17; Sum12: 25; Sum16: 32.8333; Sum20: 40.6667; Sum24: 48.55; Sum28: 56.5; Sum32: 64.2167; Sum36: 72.55; Sum40: 80.1667; Sum44: 88.3333; Sum48: 96; Sum52: 103.5
71% | 13 | Sum4: 9; Sum8: 17.1667; Sum12: 25; Sum16: 33; Sum20: 40.8333; Sum24: 48.8333; Sum28: 56.6667; Sum32: 64.3333; Sum36: 72.8333; Sum40: 80.3333; Sum44: 88.5483; Sum48: 96.1667; Sum52: 103.715
72% | 13.1667 | Sum4: 9; Sum8: 17.3333; Sum12: 25.2133; Sum16: 33.1667; Sum20: 41.0467; Sum24: 49; Sum28: 56.8333; Sum32: 64.5; Sum36: 73.1667; Sum40: 80.5; Sum44: 88.8333; Sum48: 96.3333; Sum52: 104.5467
73% | 13.2117 | Sum4: 9; Sum8: 17.5; Sum12: 25.5; Sum16: 33.1667; Sum20: 41.1667; Sum24: 49.1667; Sum28: 57; Sum32: 64.6667; Sum36: 73.3783; Sum40: 80.6667; Sum44: 89; Sum48: 96.3333; Sum52: 104.8333
74% | 13.3767 | Sum4: 9; Sum8: 17.5; Sum12: 25.6667; Sum16: 33.5; Sum20: 41.3333; Sum24: 49.1667; Sum28: 57.1667; Sum32: 64.8333; Sum36: 73.6667; Sum40: 80.71; Sum44: 89.21; Sum48: 96.6667; Sum52: 105.0433
75% | 13.5 | Sum4: 9; Sum8: 17.6667; Sum12: 25.8333; Sum16: 33.5417; Sum20: 41.6667; Sum24: 49.375; Sum28: 57.3333; Sum32: 65; Sum36: 73.8333; Sum40: 81; Sum44: 89.5417; Sum48: 97.375; Sum52: 105.5
76% | 13.5 | Sum4: 9.04; Sum8: 18; Sum12: 26; Sum16: 34; Sum20: 41.7067; Sum24: 49.6667; Sum28: 57.5; Sum32: 65.1667; Sum36: 74; Sum40: 81.3333; Sum44: 89.6667; Sum48: 97.6667; Sum52: 105.8733
77% | 13.6667 | Sum4: 9.3333; Sum8: 18.205; Sum12: 26.0383; Sum16: 34.0383; Sum20: 42.0383; Sum24: 49.8333; Sum28: 57.6667; Sum32: 65.5; Sum36: 74.205; Sum40: 81.5383; Sum44: 90; Sum48: 98.5; Sum52: 106.1667
78% | 14 | Sum4: 9.5; Sum8: 18.5; Sum12: 26.3333; Sum16: 34.3333; Sum20: 42.1667; Sum24: 50; Sum28: 57.8333; Sum32: 65.6667; Sum36: 74.5; Sum40: 82.5; Sum44: 90.2033; Sum48: 98.5367; Sum52: 106.5
79% | 14 | Sum4: 9.535; Sum8: 18.5; Sum12: 26.5; Sum16: 34.3683; Sum20: 42.3333; Sum24: 50; Sum28: 58.1667; Sum32: 65.8683; Sum36: 74.6667; Sum40: 82.6667; Sum44: 90.6667; Sum48: 99.1667; Sum52: 106.8683
80% | 14 | Sum4: 9.6667; Sum8: 18.5333; Sum12: 26.5; Sum16: 34.5333; Sum20: 42.3333; Sum24: 50.2; Sum28: 58.3333; Sum32: 66.1667; Sum36: 75; Sum40: 83.0333; Sum44: 91; Sum48: 99.3333; Sum52: 107.1667
81% | 14.3333 | Sum4: 9.865; Sum8: 18.8333; Sum12: 26.6667; Sum16: 34.6667; Sum20: 42.5; Sum24: 50.5317; Sum28: 58.5; Sum32: 66.5; Sum36: 75.1667; Sum40: 83.3333; Sum44: 91.1667; Sum48: 99.8333; Sum52: 107.5
82% | 14.3633 | Sum4: 10; Sum8: 18.8333; Sum12: 26.8333; Sum16: 35; Sum20: 42.6667; Sum24: 51; Sum28: 58.8633; Sum32: 66.8333; Sum36: 75.5; Sum40: 83.5; Sum44: 91.5; Sum48: 100.1667; Sum52: 107.8333
83% | 14.5283 | Sum4: 10; Sum8: 19; Sum12: 26.8333; Sum16: 35.0283; Sum20: 42.8333; Sum24: 51.1667; Sum28: 59; Sum32: 67.1667; Sum36: 75.695; Sum40: 83.5283; Sum44: 92.2233; Sum48: 100.6667; Sum52: 108
84% | 14.6667 | Sum4: 10; Sum8: 19; Sum12: 27.0267; Sum16: 35.1667; Sum20: 43.3333; Sum24: 51.36; Sum28: 59.36; Sum32: 67.5267; Sum36: 76; Sum40: 84; Sum44: 92.6933; Sum48: 101.1933; Sum52: 108.1667
85% | 14.8333 | Sum4: 10.025; Sum8: 19.1667; Sum12: 27.3583; Sum16: 35.5; Sum20: 43.525; Sum24: 51.6667; Sum28: 59.6917; Sum32: 67.8583; Sum36: 76.1667; Sum40: 84.5; Sum44: 93.1667; Sum48: 101.6667; Sum52: 109.025
86% | 15 | Sum4: 10.3333; Sum8: 19.3333; Sum12: 27.69; Sum16: 35.6667; Sum20: 43.6667; Sum24: 52.3333; Sum28: 59.8333; Sum32: 68.1667; Sum36: 76.5; Sum40: 85; Sum44: 93.3567; Sum48: 102; Sum52: 109.6667
87% | 15 | Sum4: 10.5; Sum8: 19.5; Sum12: 28; Sum16: 35.8333; Sum20: 43.8333; Sum24: 52.3333; Sum28: 60.1883; Sum32: 68.3333; Sum36: 76.8333; Sum40: 85.1883; Sum44: 94; Sum48: 102.5; Sum52: 109.855
88% | 15.02 | Sum4: 10.5; Sum8: 19.6667; Sum12: 28.1867; Sum16: 36.3333; Sum20: 44.1867; Sum24: 52.8333; Sum28: 60.5; Sum32: 68.6867; Sum36: 77.3533; Sum40: 86.3333; Sum44: 94.3333; Sum48: 102.8533; Sum52: 110.52
89% | 15.3333 | Sum4: 10.8333; Sum8: 20; Sum12: 28.5; Sum16: 36.5183; Sum20: 44.5367; Sum24: 53.0183; Sum28: 61.1667; Sum32: 69.0183; Sum36: 78; Sum40: 86.8333; Sum44: 94.5; Sum48: 103.3333; Sum52: 110.8333
90% | 15.5 | Sum4: 11; Sum8: 20.1667; Sum12: 28.6667; Sum16: 37; Sum20: 45.0167; Sum24: 53.35; Sum28: 61.5167; Sum32: 69.35; Sum36: 78.5; Sum40: 87.1667; Sum44: 94.8333; Sum48: 103.5167; Sum52: 111.35
91% | 15.6667 | Sum4: 11; Sum8: 20.3333; Sum12: 28.8483; Sum16: 37.3333; Sum20: 45.3483; Sum24: 53.6967; Sum28: 62.3483; Sum32: 70; Sum36: 80.015; Sum40: 87.6817; Sum44: 95.3633; Sum48: 104.3333; Sum52: 112.1967
92% | 15.8467 | Sum4: 11.3333; Sum8: 20.68; Sum12: 29.1667; Sum16: 37.8333; Sum20: 45.8333; Sum24: 54.5133; Sum28: 63.8467; Sum32: 71.18; Sum36: 80.68; Sum40: 88.3333; Sum44: 96.0133; Sum48: 104.8333; Sum52: 113.5
93% | 16 | Sum4: 11.6667; Sum8: 21; Sum12: 29.345; Sum16: 38; Sum20: 46.0117; Sum24: 55.3333; Sum28: 64.3567; Sum32: 72.1783; Sum36: 81.3333; Sum40: 88.8333; Sum44: 96.3567; Sum48: 104.845; Sum52: 114.1667
94% | 16.01 | Sum4: 12; Sum8: 21; Sum12: 29.8533; Sum16: 38.3333; Sum20: 47.1667; Sum24: 55.8533; Sum28: 65.1667; Sum32: 73.1767; Sum36: 81.6767; Sum40: 89.6767; Sum44: 97.1667; Sum48: 105.52; Sum52: 114.3433
95% | 16.5 | Sum4: 12.0083; Sum8: 21.175; Sum12: 31; Sum16: 38.8667; Sum20: 48.0083; Sum24: 57.1667; Sum28: 66.0083; Sum32: 73.5167; Sum36: 82.5167; Sum40: 90.3417; Sum44: 97.8417; Sum48: 106.175; Sum52: 115.175
96% | 16.6667 | Sum4: 12.5; Sum8: 21.5067; Sum12: 31.34; Sum16: 39.84; Sum20: 48.84; Sum24: 58.5067; Sum28: 67.1667; Sum32: 74.84; Sum36: 84.0133; Sum40: 91; Sum44: 98.8333; Sum48: 107.0133; Sum52: 115.6733
97% | 17 | Sum4: 12.505; Sum8: 22.005; Sum12: 31.505; Sum16: 40.5; Sum20: 50.6717; Sum24: 60; Sum28: 67.505; Sum32: 75.6717; Sum36: 85.01; Sum40: 92.015; Sum44: 99.8383; Sum48: 109.3383; Sum52: 116.3433
98% | 18.0067 | Sum4: 13; Sum8: 22.67; Sum12: 32.6767; Sum16: 41.18; Sum20: 51.3367; Sum24: 60.67; Sum28: 69.1733; Sum32: 78.67; Sum36: 85.8467; Sum40: 93.8533; Sum44: 103.01; Sum48: 110.5; Sum52: 118.68
99% | 18.67 | Sum4: 13.6667; Sum8: 24.67; Sum12: 36.17; Sum16: 44.17; Sum20: 52.17; Sum24: 61.34; Sum28: 71.1683; Sum32: 80.0067; Sum36: 88.505; Sum40: 96.505; Sum44: 105.5133; Sum48: 113.505; Sum52: 120.17
100% | 22 | Sum4: 15.5; Sum8: 27.5; Sum12: 40.3333; Sum16: 48.5; Sum20: 54.5; Sum24: 65.8333; Sum28: 75.3333; Sum32: 82; Sum36: 93.5; Sum40: 100.3333; Sum44: 108.1667; Sum48: 116.5; Sum52: 127