## Instructions
Single Feature Forecaster
Always get the latest version of this spreadsheet here.
Version history:
| 1 | 2015-04-07 | Initial beta release for feedback.
| 1.01 | 2015-05-22 | Fixed validation usability errors.
| 1.1 | 2015-05-26 | Added risks and charts.
| 1.2 | 2015-06-01 | Updated instructions and charts.
| 1.3 | 2016-02-12 | Added split rate inputs.
| 1.4 | 2016-06-01 | Added actual plot.
| 1.5 | 2016-06-02 | Added story count forecast by period.
| 1.6 | 2017-06-09 | Added risk impact scores and increased risks to 10 entries
What is this: This spreadsheet helps to probabilistically forecast how long it will take to complete features and stories based on range estimates.
How does it work? Given your estimates, this spreadsheet hypothetically completes all work 500 times. It calculates likelihood result as the number of simulated trials that finished on or before a given date.
Why is this better than burndowns and traditional Agile forecasting? Most forecasting techniques give a single date result and hide the likelihood of that date. Most often the date given as the result is 50% because work is divided by an average (or median). Thats the odds of a toin-coss. This method allows the reader to choose the amount of schedule risk they wish to sign-up for. 85% is a common middle ground used in the industry.
Is it reliable? It has no mathematical errors (that we know of!), and all we guarentee is its better than intuition alone and better than simple regression models. But, help us improve it by letting us know when it misses the actual results you are seeing.
How to: Fill in the orange boxes in the Forecast worksheet and read off the dates in the results table adjacent to the likelihood/certainty you think is appropriate. 85% is a common industry level of certainty used.
What is throughput? Where do I get that data? Throughput is the number of DONE stories completed by a team per week or per sprint (you choose in this spreadsheet, default is per week). We will be providing a viz that gathers this data for your team. Stay tuned.
What is this: This spreadsheet helps to probabilistically forecast how long it will take to complete features based on story count range estimates and either estimated team throughput or historical team throughput samples.
How does it work? Given your estimates, this spreadsheet hypothetically completes all work 500 times. It calculates likelihood result as the number of simulated trials that finished on or before a given date. Given your desired scenario order, features are completed in order and the dates computed based on specified likelihood.
Why is this better than burndowns and traditional Agile forecasting? Most forecasting techniques give a single date result and hide the likelihood of that date. Most often the date given as the result is 50% because work is divided by an average (or median). Thats the odds of a toin-coss. This method allows the reader to choose the amount of schedule risk they wish to sign-up for. 85% is a common middle ground used in the industry.
Is it reliable? It has no mathematical errors (that we know of!), and all we guarantee is its better than intuition alone and better than simple regression models. But, help us improve it by letting us know when it misses the actual results you are seeing.
How to: Fill in the orange boxes in the Forecast worksheet and read off the dates in the results table adjacent to the likelihood/certainty you think is appropriate. 85% is a common industry level of certainty used - a good balance of better than average but not susceptible to extreme outliers.
What is throughput? Where do I get that data? Throughput is the number of DONE stories completed by a team per week or per sprint (you choose in this spreadsheet, default is per week). Also see our Throughput and Cycle Time Calculator spreadsheet for convertinf story/item data to throughput values. Also see our tutorials on how to use Excel to calculate throughput rates.
Ideas, errors, requests? Email: troy.magennis@focusedobjective.com
Work licensed under a Creative Commons Attribution-NonCommercial-ShareAlike 4.0 International License.
Get more tools like this from: http://bit.ly/SimResources
About us: Focused Objective LLC offers tools, training and expert advice on metrics, risk and forecasting. We have more advanced tools to model Agile teams and projects that help analyze staffing options and risk, and a proven track record of positive results. We are always happy to discuss next steps and training opportunities should this tool prove useful. See our website: http://www.focusedobjective.com or email me at troy.magennis@focusedobjective.com.

## Forecast
Forecast Completion Date | [7 empty] | Results
Duration in
1. Start Date |  |  | 2017-06-09 |  |  |  |  | Likelihood | 1 week's | Date
[8 empty] | 100% | 15 | 2017-09-22
2. How many stories are remaining to be completed? | [7 empty] | 95% | 12 | 2017-09-01
(enter the range estimate of stories. Tip: start wide and narrow as certainty increases) | [7 empty] | 90% | 11 | 2017-08-25
| Low guess |  | 20 |  | Highest guess |  | 30 | 85% | 11 | 2017-08-25
[8 empty] | 80% | 10 | 2017-08-18
3. Stories are often split before and whilst being worked on. Estimate the split rate low and high bounds. | [7 empty] | 75% | 10 | 2017-08-18
(often the throughput in the backlog is pre-split, but captured throughput post-split. Adjust for this here) | [7 empty] | 70% | 10 | 2017-08-18
| Low guess |  | 1 |  | Highest guess |  | 1 | 65% | 9 | 2017-08-11
[8 empty] | 60% | 9 | 2017-08-11
4. Throughput. How many completed stories per week or sprint do you estimate low and high bounds? | [7 empty] | 55% | 9 | 2017-08-11
[8 empty] | 50% | 9 | 2017-08-11
Throughput/velocity data or estimate is for |  |  |  | 1 week | 7 | days |  | 45% | 8 | 2017-08-04
(choose a time interval that throughput of velocity is measured in weeks from the list in the orange cell above) | [7 empty] | 40% | 8 | 2017-08-04
Use historical throughput data OR enter a low and high estimate below. Use: | [6 empty] | Estimate | 35% | 8 | 2017-08-04
[8 empty] | 30% | 8 | 2017-08-04
[8 empty] | 25% | 8 | 2017-08-04
| Low guess |  | 1 |  | Highest guess |  | 5 | 20% | 7 | 2017-07-28
[8 empty] | 15% | 7 | 2017-07-28
[8 empty] | 10% | 7 | 2017-07-28
[8 empty] | 5% | 6 | 2017-07-21
[8 empty] | 0% | 5 | 2017-07-14
Forecast Story Count Completion by Time Period
5. How long? |  | 6 | 1 weeks |  | Result: Total Pre-split Stories in 6 1 weeks
(To forecast story counts, enter the how long. |  |  |  |  | (Pre-split means, splitting IS accounted for)
To change unit, change input 4. above.) |  |  |  |  | 95% | 12
[5 empty] | 85% | 14 | <--- Tip: This is your forecasted # storiess for this period at 85% confidence
[5 empty] | 5% | 23
Almost certain
Somewhat certain
Less than coin-toss odds. But if you are game?
Can I use velocity rather than throughput?
Yes. If you do have estimates in story points, then you can sume all of the estimates and use that for input 2 and estimate or use historical team velocity for input 4. The benefit of using throughput (count of completed stories per week/sprint) is that the individual stories don't require estimation in story points.
Enter data in Orange cells
Please Remember: This forecast is only as good as the estimates you enter into it. Always look for multiple ways to forecast your project and compare the outcomes, especially if making a financially critical decision. In the end - any decision to proceed with a project is YOURS.
How do I use this story count forecast?
This forecast aims to show how many stories might be completed given the team data or estimates entered above. Enter all data for inputs 3. and 4. above. This forecast simulates 500 times to determine what number of stories will be completed for the period you entered for input 5. It also creates a chart view of this forecast in the charts tab. This forecast ignores risk data, and un-necessary inputs 1 and 2 from above.
Note on I16: Troy Magennis: This is the measure of how two random groups of your sample data would align when forecasting. Anything below 25% is good, but lower is better. It grows if there is too little data, and ALSO if the process changes over time and you use too much data.

## Risks
Likelihood | Impact Low | Impact High | Description | Combined Impact (higher is worse) | Est. impact in 1 week's | Impact Rank (fix lowest first)
Calculations -
Likelihood | Impact Low | Impact High | Description | average story count | 25
30% | 10 | 15 | Server performance issues | duration at 85th P | 11
15% | 5 | 10 | Layout issues when text localized | count per period | 2.2727
20% | 5 | 15 | Layout in Safari issues
Why would I use risks?
Risks allow you to put a probability on work being expanded because of something more than plan. For eample, there might be a chance that more work is needed to improve performance characteristics. If you think there is a 20% chance, put 20 in the likelihood column. Have the team estimate the low and high story count to rectify and add these to the low and high impact columns.
Risk impact analysis
It can be hard to determine what risks are most impactful when they have different likelihoods and impacts. The risks are ranked here from most impactful (Rank = 1) to least impactful.
This is a simple ranking. It helps quickly see what is the most important to decrease likelihood or impact.

## Charts
[14 empty] | Week | Frequency
[14 empty] | 2017-07-14 | 3
[14 empty] | 2017-07-21 | 31
[14 empty] | 2017-07-28 | 75
[14 empty] | 2017-08-04 | 121
[14 empty] | 2017-08-11 | 110
[14 empty] | 2017-08-18 | 85
[14 empty] | 2017-08-25 | 43
[14 empty] | 2017-09-01 | 22
[14 empty] | 2017-09-08 | 6
[14 empty] | 2017-09-15 | 4
[14 empty] | 2017-09-22 | 1
0
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
Story count results in table form. For the probabilities entered, how many stories for each period?
| 4 1 weeks | 8 1 weeks | 12 1 weeks | 16 1 weeks | 20 1 weeks | 24 1 weeks | 28 1 weeks | 32 1 weeks | 36 1 weeks | 40 1 weeks | 44 1 weeks | 48 1 weeks | 52 1 weeks
95% | 7 | 17 | 28 | 39 | 50 | 61 | 72 | 83 | 96 | 106 | 117 | 129 | 140.95
85% | 9 | 20 | 31 | 42 | 54 | 65 | 76 | 88 | 99 | 111 | 123 | 134 | 146
5% | 16 | 31 | 44 | 56 | 69 | 83 | 96 | 109 | 121 | 135 | 148.05 | 160 | 173
What is this chart?
This chart shows how many simulated trials completed on or before the x-axis date. The higher the bar, the more likely that outcome.
What is this chart?
This chart shows the simulated burn-down trends. It shows the first 50 trials and visually shows the general hotspots and outlier dates. Enter actual stories remaining in the Reamining Stories Actual worksheet to see progress.
What is this chart?
This chart shows the number of completed (pre-split) stories for a given period. Select the time period on the forecast worksheet. The forecast is shown at three confidence intervals specified on the forecast worksheet.

## Throughput Samples
Enter Samples Below | Group | Unique Rank
3 | 1 | 3
5 | 1 | 5
2 | 2 | 2
1 | 1 | 1
5 | 2 | 6
3 | 2 | 4
Stability Between Two Random Groups of the Samples
|  |  | Group | All | 1 | 2 | Diff
|  |  | count | 6 | 3 | 3 | 0
|  |  | min | 1 | 1 | 2
|  |  | max | 5 | 5 | 5
|  |  | avg | 3.1667 | 3 | 3.3333 | -0.33333
|  |  | median | 3 | 3 | 3 | 0
|  |  | avg error |  |  |  | 0.33333 | I also tried average of the mean and median error….but think average will do.
|  |  | error/range |  |  |  | 8.333% | Aim to keep this below 25%. By adding more sample data. You will see where to stop.
Transportable data formats
|  |  | Total Count |  | 6 |  |  |  |  | CSV | 3,5,2,1,5,3
|  |  | Data |  | 5 | 5 | 5 | 5 | 3 | SIP 2.0 | <sip name="dist" type="CSV" ver="1.0" count="6" average="3.16666666666667" median="3">3,5,2,1,5,3</sip>
|  |  | Estimate |  | 1 | 1 | 3 | 5 | 4 | Distribution | <distribution name="dist" shape="fromSamples">3,5,2,1,5,3</distribution>
|  |  | Samples Or Data |  | 3 | 4 | 1 | 5 | 3
Instructions.
If you have team historic throughput samples, you can use them when forecasting forward. If not, estimate the range in the forecast sheet. When actual data becomes available, add it here and your forecast will become more indicative.
Add seven (7) minimum, and twenty five (25) maximum recent throughput samples for your team. These samples will be used as throughput values picked at random. By using your teams data, the forecast will follow the patterns your teams throughput historically follows.
Remember to set the unit of throughput measure.
No blank rows within sample range, leave rows after the last sample blank.
Data beyond 24 weeks is most likely out of date. When adding, add most recent samples to the top and remove older samples from the bottom.
These are for testing the formulas that return random ssamples from data or between the estimates. They are included here for education and reference.
These formats are to help share throughput samples with others or teams should the need arise.
CSV = simple comma separated value list
SIP 2.0 = ProbabilityManagement.org's SIP standard for sharing data
Distribution = FocusedObjective.com's distribution format for sharing and creating random data from samples in their simulation software
What is throughput? Where do I get that data? Throughput is the number of DONE stories completed by a team per week or per sprint (you choose in this spreadsheet, default is per week). Also see our Throughput and Cycle Time Calculator spreadsheet for convertinf story/item data to throughput values. Also see our tutorials on how to use Excel to calculate throughput rates.
How many amples?
You could make this spreadsheet use more historical data, but its not statistically necessary. My advice: use the most recent 15 samples if you have them to avoid using "old" data that was cptured when the team was performing differently than it is now. You should use the most recent data where the error percentage is less than 10%

## Remaining Stories Actuals
Date (week ending) | Number of Incompleted (but in scope) stories | Notes
2017-06-09 | 27
2017-06-16 | 25
2017-06-23 | 20
2017-06-30 | 19
2017-07-07
2017-07-14
2017-07-21
2017-07-28
2017-08-04
2017-08-11
2017-08-18
2017-08-25
2017-09-01
2017-09-08
2017-09-15
2017-09-22
2017-09-29
2017-10-06
2017-10-13
2017-10-20
2017-10-27
2017-11-03
2017-11-10
2017-11-17
2017-11-24
2017-12-01
2017-12-08
2017-12-15
2017-12-22
2017-12-29
2018-01-05
2018-01-12
2018-01-19
2018-01-26
2018-02-02
2018-02-09
2018-02-16
2018-02-23
2018-03-02
2018-03-09
2018-03-16
2018-03-23
2018-03-30
2018-04-06
2018-04-13
2018-04-20
2018-04-27
2018-05-04
2018-05-11
2018-05-18
2018-05-25
Instructions.
Enter the actual number of IN-COMPLETE items in the backlog in column B for the dates shown in column A. This line will be charted on the burndown chart.

## Settings
Duration name | days
1 week | 7
2 weeks | 14
3 weeks | 21
4 weeks | 28
This table converts throughput duration name to number of days. Add more or edit these here. The days is used to increment forecasting periods. Resolution of forecast will also be in increments of this value.

## Monte Carlo (hidden)
Trial | Weeks to Zero | End of Zero Week | TotalStories | End period 1 | End period 2 | End period 3 | End period 4 | End period 5 | End period 6 | End period 7 | End period 8 | End period 9 | End period 10 | End period 11 | End period 12 | End period 13 | End period 14 | End period 15 | End period 16 | End period 17 | End period 18 | End period 19 | End period 20 | End period 21 | End period 22 | End period 23 | End period 24 | End period 25 | End period 26 | End period 27 | End period 28 | End period 29 | End period 30 | End period 31 | End period 32 | End period 33 | End period 34 | End period 35 | End period 36 | End period 37 | End period 38 | End period 39 | End period 40 | End period 41 | End period 42 | End period 43 | End period 44 | End period 45 | End period 46 | End period 47 | End period 48 | End period 49 | End period 50 | End period 51 | End period 52
 | time axis 2017-06-09 to 2018-06-08
1 | 9 | 2017-08-11 | 21 | 17 | 12 | 10 | 9 | 7 | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 11 | 2017-08-25 | 30 | 28 | 26 | 25 | 23 | 20 | 15 | 10 | 7 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 9 | 2017-08-11 | 27 | 24 | 22 | 20 | 15 | 13 | 10 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 8 | 2017-08-04 | 21 | 17 | 14 | 13 | 11 | 6 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 11 | 2017-08-25 | 28 | 25 | 21 | 18 | 15 | 11 | 10 | 9 | 8 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 14 | 2017-09-15 | 26 | 25 | 21 | 20 | 19 | 18 | 17 | 16 | 15 | 11 | 9 | 8 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 8 | 2017-08-04 | 27 | 25 | 20 | 15 | 14 | 9 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 9 | 2017-08-11 | 21 | 18 | 16 | 14 | 12 | 11 | 10 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 9 | 2017-08-11 | 24 | 19 | 17 | 13 | 11 | 7 | 6 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | 7 | 2017-07-28 | 21 | 18 | 17 | 14 | 12 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | 8 | 2017-08-04 | 20 | 15 | 12 | 9 | 8 | 7 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 10 | 2017-08-18 | 23 | 20 | 15 | 10 | 8 | 7 | 6 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | 9 | 2017-08-11 | 28 | 23 | 20 | 17 | 15 | 11 | 7 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 9 | 2017-08-11 | 29 | 28 | 26 | 24 | 21 | 16 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | 10 | 2017-08-18 | 27 | 26 | 24 | 23 | 20 | 15 | 14 | 11 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | 6 | 2017-07-21 | 23 | 21 | 19 | 14 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 8 | 2017-08-04 | 27 | 25 | 23 | 18 | 16 | 13 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 10 | 2017-08-18 | 24 | 22 | 21 | 19 | 16 | 12 | 11 | 7 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | 8 | 2017-08-04 | 23 | 19 | 16 | 13 | 12 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | 11 | 2017-08-25 | 20 | 19 | 18 | 15 | 14 | 13 | 12 | 9 | 8 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 9 | 2017-08-11 | 28 | 25 | 23 | 20 | 15 | 14 | 9 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | 10 | 2017-08-18 | 30 | 28 | 23 | 22 | 19 | 17 | 14 | 9 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | 9 | 2017-08-11 | 26 | 23 | 18 | 13 | 12 | 9 | 6 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 9 | 2017-08-11 | 23 | 22 | 20 | 18 | 13 | 11 | 8 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | 12 | 2017-09-01 | 27 | 26 | 23 | 20 | 15 | 13 | 12 | 10 | 9 | 6 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | 7 | 2017-07-28 | 24 | 21 | 20 | 16 | 12 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | 8 | 2017-08-04 | 29 | 24 | 19 | 14 | 10 | 7 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | 6 | 2017-07-21 | 21 | 17 | 15 | 12 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | 9 | 2017-08-11 | 21 | 18 | 14 | 10 | 9 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | 7 | 2017-07-28 | 23 | 20 | 17 | 12 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | 7 | 2017-07-28 | 20 | 19 | 15 | 14 | 9 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | 10 | 2017-08-18 | 28 | 25 | 22 | 18 | 17 | 14 | 11 | 9 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | 8 | 2017-08-04 | 20 | 15 | 12 | 10 | 5 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | 9 | 2017-08-11 | 26 | 21 | 20 | 16 | 11 | 9 | 6 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | 10 | 2017-08-18 | 21 | 18 | 16 | 14 | 12 | 11 | 9 | 8 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | 9 | 2017-08-11 | 29 | 24 | 21 | 17 | 16 | 12 | 7 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | 11 | 2017-08-25 | 26 | 24 | 22 | 20 | 17 | 15 | 14 | 10 | 8 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | 10 | 2017-08-18 | 23 | 20 | 19 | 14 | 11 | 10 | 8 | 6 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | 7 | 2017-07-28 | 20 | 15 | 10 | 9 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | 8 | 2017-08-04 | 29 | 25 | 21 | 18 | 13 | 8 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | 10 | 2017-08-18 | 30 | 25 | 20 | 19 | 15 | 12 | 11 | 8 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | 9 | 2017-08-11 | 27 | 25 | 22 | 21 | 19 | 14 | 10 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | 8 | 2017-08-04 | 27 | 24 | 20 | 15 | 14 | 10 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | 8 | 2017-08-04 | 20 | 18 | 15 | 13 | 12 | 11 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | 11 | 2017-08-25 | 29 | 26 | 23 | 19 | 18 | 14 | 11 | 10 | 8 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | 11 | 2017-08-25 | 30 | 25 | 24 | 19 | 14 | 13 | 12 | 11 | 10 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | 6 | 2017-07-21 | 20 | 16 | 12 | 7 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 10 | 2017-08-18 | 26 | 23 | 19 | 16 | 13 | 11 | 7 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | 9 | 2017-08-11 | 29 | 24 | 23 | 21 | 17 | 13 | 10 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | 7 | 2017-07-28 | 21 | 19 | 16 | 12 | 8 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | 7 | 2017-07-28 | 20 | 19 | 14 | 12 | 8 | 7 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 | 8 | 2017-08-04 | 20 | 19 | 18 | 16 | 11 | 7 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | 10 | 2017-08-18 | 27 | 25 | 24 | 23 | 21 | 17 | 12 | 8 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | 10 | 2017-08-18 | 27 | 24 | 19 | 18 | 14 | 12 | 10 | 8 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 | 5 | 2017-07-14 | 20 | 16 | 11 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56 | 9 | 2017-08-11 | 29 | 25 | 20 | 18 | 15 | 12 | 9 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57 | 7 | 2017-07-28 | 23 | 18 | 15 | 12 | 7 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58 | 8 | 2017-08-04 | 28 | 25 | 21 | 16 | 11 | 9 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
59 | 8 | 2017-08-04 | 30 | 26 | 22 | 17 | 13 | 8 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 | 7 | 2017-07-28 | 27 | 22 | 19 | 15 | 11 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
61 | 6 | 2017-07-21 | 20 | 16 | 12 | 10 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
62 | 9 | 2017-08-11 | 26 | 22 | 17 | 16 | 15 | 13 | 11 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | 8 | 2017-08-04 | 21 | 17 | 15 | 10 | 8 | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
64 | 10 | 2017-08-18 | 27 | 22 | 20 | 19 | 14 | 11 | 8 | 6 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
65 | 9 | 2017-08-11 | 22 | 20 | 16 | 14 | 13 | 9 | 5 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
66 | 9 | 2017-08-11 | 29 | 26 | 25 | 20 | 18 | 15 | 12 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
67 | 8 | 2017-08-04 | 23 | 19 | 15 | 10 | 8 | 7 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
68 | 12 | 2017-09-01 | 30 | 28 | 23 | 20 | 17 | 15 | 12 | 11 | 9 | 7 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
69 | 9 | 2017-08-11 | 27 | 23 | 18 | 17 | 14 | 10 | 7 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 | 6 | 2017-07-21 | 22 | 19 | 15 | 12 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
71 | 7 | 2017-07-28 | 20 | 16 | 12 | 8 | 6 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 9 | 2017-08-11 | 30 | 28 | 27 | 22 | 18 | 13 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
73 | 8 | 2017-08-04 | 29 | 24 | 19 | 15 | 13 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
74 | 13 | 2017-09-08 | 26 | 25 | 23 | 21 | 20 | 17 | 16 | 14 | 10 | 7 | 6 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
75 | 8 | 2017-08-04 | 25 | 22 | 19 | 17 | 12 | 9 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
76 | 9 | 2017-08-11 | 23 | 19 | 18 | 16 | 13 | 12 | 7 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
77 | 12 | 2017-09-01 | 30 | 29 | 28 | 25 | 21 | 19 | 16 | 15 | 10 | 7 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
78 | 8 | 2017-08-04 | 24 | 20 | 16 | 11 | 7 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
79 | 9 | 2017-08-11 | 30 | 25 | 23 | 22 | 17 | 14 | 10 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | 6 | 2017-07-21 | 21 | 16 | 14 | 9 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 | 10 | 2017-08-18 | 27 | 24 | 23 | 18 | 16 | 12 | 8 | 7 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
82 | 10 | 2017-08-18 | 27 | 23 | 20 | 19 | 16 | 14 | 13 | 11 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | 9 | 2017-08-11 | 28 | 25 | 21 | 20 | 15 | 11 | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | 9 | 2017-08-11 | 28 | 26 | 25 | 20 | 17 | 14 | 9 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
85 | 9 | 2017-08-11 | 20 | 17 | 16 | 15 | 10 | 7 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 | 11 | 2017-08-25 | 30 | 28 | 23 | 22 | 18 | 15 | 14 | 10 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | 12 | 2017-09-01 | 30 | 29 | 26 | 22 | 19 | 17 | 14 | 11 | 7 | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 | 9 | 2017-08-11 | 30 | 27 | 24 | 20 | 15 | 12 | 10 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
89 | 10 | 2017-08-18 | 27 | 25 | 20 | 18 | 14 | 9 | 8 | 7 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | 7 | 2017-07-28 | 26 | 24 | 19 | 17 | 12 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 | 7 | 2017-07-28 | 27 | 22 | 18 | 14 | 10 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 | 10 | 2017-08-18 | 27 | 25 | 24 | 20 | 17 | 15 | 11 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 | 6 | 2017-07-21 | 21 | 18 | 14 | 10 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 | 8 | 2017-08-04 | 27 | 24 | 19 | 14 | 11 | 8 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 | 8 | 2017-08-04 | 22 | 18 | 14 | 12 | 9 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 | 10 | 2017-08-18 | 29 | 27 | 24 | 20 | 17 | 15 | 14 | 11 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
97 | 6 | 2017-07-21 | 21 | 16 | 11 | 8 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 | 7 | 2017-07-28 | 26 | 21 | 16 | 14 | 9 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | 8 | 2017-08-04 | 23 | 21 | 19 | 14 | 11 | 9 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100 | 11 | 2017-08-25 | 28 | 26 | 25 | 22 | 18 | 14 | 11 | 8 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
101 | 11 | 2017-08-25 | 30 | 29 | 28 | 27 | 22 | 20 | 16 | 11 | 10 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
102 | 10 | 2017-08-18 | 26 | 23 | 20 | 18 | 15 | 12 | 11 | 9 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
103 | 10 | 2017-08-18 | 24 | 22 | 21 | 16 | 15 | 13 | 10 | 8 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
104 | 7 | 2017-07-28 | 20 | 19 | 14 | 10 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
105 | 7 | 2017-07-28 | 23 | 18 | 14 | 9 | 7 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
106 | 6 | 2017-07-21 | 23 | 19 | 14 | 10 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
107 | 8 | 2017-08-04 | 20 | 15 | 13 | 12 | 11 | 8 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
108 | 9 | 2017-08-11 | 25 | 22 | 20 | 18 | 13 | 12 | 7 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
109 | 10 | 2017-08-18 | 28 | 25 | 20 | 19 | 15 | 13 | 12 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
110 | 8 | 2017-08-04 | 30 | 28 | 23 | 19 | 15 | 13 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
111 | 9 | 2017-08-11 | 26 | 22 | 18 | 13 | 12 | 10 | 9 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
112 | 11 | 2017-08-25 | 29 | 26 | 24 | 20 | 16 | 15 | 11 | 6 | 4 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
113 | 12 | 2017-09-01 | 23 | 22 | 21 | 20 | 19 | 17 | 12 | 11 | 6 | 5 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
114 | 11 | 2017-08-25 | 26 | 25 | 23 | 20 | 18 | 17 | 14 | 12 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
115 | 9 | 2017-08-11 | 24 | 21 | 18 | 13 | 12 | 11 | 7 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
116 | 9 | 2017-08-11 | 24 | 22 | 20 | 19 | 16 | 14 | 10 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
117 | 11 | 2017-08-25 | 29 | 28 | 27 | 25 | 23 | 18 | 15 | 10 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
118 | 11 | 2017-08-25 | 22 | 19 | 17 | 16 | 13 | 12 | 11 | 9 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
119 | 11 | 2017-08-25 | 30 | 29 | 28 | 25 | 20 | 16 | 14 | 11 | 6 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
120 | 9 | 2017-08-11 | 30 | 25 | 23 | 18 | 13 | 9 | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
121 | 8 | 2017-08-04 | 20 | 18 | 15 | 10 | 8 | 6 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
122 | 9 | 2017-08-11 | 25 | 24 | 22 | 21 | 18 | 13 | 12 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
123 | 10 | 2017-08-18 | 30 | 29 | 26 | 25 | 22 | 17 | 12 | 9 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
124 | 10 | 2017-08-18 | 24 | 20 | 17 | 13 | 9 | 8 | 7 | 6 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
125 | 9 | 2017-08-11 | 24 | 23 | 20 | 15 | 11 | 10 | 8 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
126 | 8 | 2017-08-04 | 22 | 20 | 17 | 14 | 13 | 8 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
127 | 10 | 2017-08-18 | 30 | 25 | 21 | 19 | 18 | 16 | 13 | 9 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
128 | 8 | 2017-08-04 | 24 | 19 | 17 | 16 | 12 | 8 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
129 | 13 | 2017-09-08 | 30 | 26 | 25 | 21 | 18 | 16 | 14 | 11 | 9 | 8 | 7 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
130 | 14 | 2017-09-15 | 30 | 29 | 28 | 25 | 24 | 22 | 17 | 14 | 12 | 11 | 7 | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
131 | 8 | 2017-08-04 | 28 | 24 | 22 | 19 | 14 | 11 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
132 | 9 | 2017-08-11 | 23 | 20 | 15 | 14 | 13 | 11 | 9 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
133 | 9 | 2017-08-11 | 30 | 27 | 24 | 21 | 17 | 13 | 10 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
134 | 8 | 2017-08-04 | 21 | 19 | 14 | 12 | 10 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
135 | 8 | 2017-08-04 | 22 | 18 | 15 | 10 | 9 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
136 | 8 | 2017-08-04 | 27 | 22 | 21 | 16 | 15 | 11 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
137 | 11 | 2017-08-25 | 30 | 28 | 24 | 22 | 20 | 16 | 11 | 10 | 7 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
138 | 8 | 2017-08-04 | 28 | 25 | 20 | 15 | 12 | 11 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
139 | 9 | 2017-08-11 | 24 | 23 | 21 | 19 | 18 | 15 | 11 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
140 | 12 | 2017-09-01 | 27 | 26 | 25 | 24 | 19 | 18 | 16 | 15 | 13 | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
141 | 10 | 2017-08-18 | 27 | 25 | 24 | 22 | 21 | 20 | 17 | 13 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
142 | 9 | 2017-08-11 | 27 | 22 | 21 | 19 | 14 | 12 | 8 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
143 | 8 | 2017-08-04 | 20 | 18 | 16 | 14 | 11 | 9 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
144 | 8 | 2017-08-04 | 25 | 23 | 18 | 13 | 9 | 7 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
145 | 9 | 2017-08-11 | 29 | 26 | 23 | 20 | 15 | 10 | 8 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
146 | 12 | 2017-09-01 | 30 | 27 | 24 | 22 | 18 | 16 | 14 | 11 | 10 | 8 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
147 | 8 | 2017-08-04 | 26 | 21 | 20 | 17 | 12 | 8 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
148 | 7 | 2017-07-28 | 23 | 22 | 19 | 15 | 10 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
149 | 8 | 2017-08-04 | 23 | 21 | 20 | 16 | 12 | 7 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
150 | 9 | 2017-08-11 | 23 | 22 | 19 | 17 | 13 | 12 | 10 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
151 | 7 | 2017-07-28 | 26 | 25 | 22 | 17 | 13 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
152 | 8 | 2017-08-04 | 20 | 17 | 14 | 12 | 7 | 6 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
153 | 11 | 2017-08-25 | 28 | 27 | 23 | 18 | 16 | 15 | 12 | 9 | 8 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
154 | 9 | 2017-08-11 | 23 | 20 | 17 | 16 | 14 | 9 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
155 | 8 | 2017-08-04 | 24 | 21 | 19 | 16 | 15 | 11 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
156 | 10 | 2017-08-18 | 29 | 25 | 21 | 18 | 15 | 13 | 10 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
157 | 11 | 2017-08-25 | 30 | 26 | 23 | 21 | 19 | 15 | 13 | 11 | 7 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
158 | 9 | 2017-08-11 | 22 | 20 | 18 | 15 | 12 | 8 | 7 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
159 | 9 | 2017-08-11 | 27 | 26 | 23 | 20 | 15 | 12 | 7 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
160 | 8 | 2017-08-04 | 24 | 19 | 14 | 11 | 9 | 6 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
161 | 8 | 2017-08-04 | 24 | 19 | 18 | 17 | 13 | 8 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
162 | 6 | 2017-07-21 | 25 | 22 | 17 | 14 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
163 | 8 | 2017-08-04 | 20 | 18 | 14 | 13 | 11 | 7 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
164 | 7 | 2017-07-28 | 27 | 23 | 18 | 17 | 12 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
165 | 8 | 2017-08-04 | 25 | 21 | 18 | 15 | 13 | 9 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
166 | 8 | 2017-08-04 | 27 | 26 | 23 | 20 | 15 | 14 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
167 | 6 | 2017-07-21 | 21 | 18 | 14 | 11 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
168 | 8 | 2017-08-04 | 28 | 23 | 18 | 15 | 13 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
169 | 9 | 2017-08-11 | 29 | 24 | 22 | 17 | 12 | 11 | 8 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
170 | 10 | 2017-08-18 | 30 | 25 | 23 | 18 | 16 | 13 | 11 | 8 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
171 | 12 | 2017-09-01 | 29 | 28 | 25 | 23 | 19 | 18 | 17 | 15 | 13 | 9 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
172 | 6 | 2017-07-21 | 23 | 19 | 15 | 10 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
173 | 9 | 2017-08-11 | 26 | 22 | 20 | 19 | 15 | 14 | 13 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
174 | 10 | 2017-08-18 | 28 | 25 | 21 | 19 | 18 | 14 | 13 | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
175 | 8 | 2017-08-04 | 30 | 25 | 20 | 18 | 13 | 10 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
176 | 10 | 2017-08-18 | 24 | 19 | 15 | 13 | 12 | 11 | 7 | 6 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
177 | 7 | 2017-07-28 | 24 | 21 | 19 | 15 | 12 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
178 | 7 | 2017-07-28 | 21 | 18 | 13 | 8 | 7 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
179 | 8 | 2017-08-04 | 22 | 20 | 16 | 11 | 10 | 8 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
180 | 7 | 2017-07-28 | 25 | 20 | 19 | 15 | 11 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
181 | 7 | 2017-07-28 | 23 | 19 | 16 | 15 | 10 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
182 | 7 | 2017-07-28 | 29 | 24 | 19 | 14 | 13 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
183 | 7 | 2017-07-28 | 21 | 17 | 13 | 11 | 8 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
184 | 10 | 2017-08-18 | 25 | 22 | 21 | 19 | 14 | 13 | 10 | 6 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
185 | 8 | 2017-08-04 | 21 | 18 | 15 | 10 | 7 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
186 | 8 | 2017-08-04 | 23 | 21 | 20 | 18 | 16 | 12 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
187 | 12 | 2017-09-01 | 27 | 26 | 24 | 20 | 16 | 15 | 14 | 9 | 6 | 5 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
188 | 11 | 2017-08-25 | 30 | 25 | 23 | 20 | 18 | 14 | 10 | 9 | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
189 | 14 | 2017-09-15 | 29 | 28 | 27 | 25 | 24 | 23 | 21 | 17 | 16 | 14 | 12 | 10 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
190 | 8 | 2017-08-04 | 30 | 26 | 23 | 21 | 16 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
191 | 7 | 2017-07-28 | 22 | 17 | 16 | 12 | 11 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
192 | 7 | 2017-07-28 | 24 | 19 | 14 | 10 | 7 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
193 | 7 | 2017-07-28 | 21 | 19 | 18 | 13 | 10 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
194 | 10 | 2017-08-18 | 28 | 27 | 22 | 17 | 16 | 14 | 10 | 9 | 7 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
195 | 9 | 2017-08-11 | 27 | 25 | 20 | 15 | 13 | 10 | 6 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
196 | 8 | 2017-08-04 | 26 | 25 | 22 | 19 | 15 | 13 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
197 | 11 | 2017-08-25 | 27 | 26 | 23 | 18 | 17 | 12 | 9 | 8 | 7 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
198 | 8 | 2017-08-04 | 23 | 20 | 17 | 12 | 8 | 7 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
199 | 8 | 2017-08-04 | 27 | 22 | 19 | 18 | 14 | 11 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
200 | 8 | 2017-08-04 | 20 | 15 | 12 | 10 | 6 | 5 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
201 | 9 | 2017-08-11 | 26 | 21 | 19 | 18 | 13 | 10 | 6 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
202 | 9 | 2017-08-11 | 25 | 24 | 21 | 18 | 14 | 10 | 6 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
203 | 9 | 2017-08-11 | 30 | 27 | 23 | 22 | 17 | 13 | 10 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
204 | 7 | 2017-07-28 | 26 | 21 | 16 | 12 | 9 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
205 | 9 | 2017-08-11 | 26 | 22 | 20 | 16 | 11 | 10 | 8 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
206 | 9 | 2017-08-11 | 25 | 24 | 21 | 18 | 14 | 12 | 10 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
207 | 8 | 2017-08-04 | 22 | 21 | 16 | 12 | 11 | 9 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
208 | 7 | 2017-07-28 | 20 | 16 | 12 | 7 | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
209 | 8 | 2017-08-04 | 22 | 18 | 16 | 14 | 11 | 8 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
210 | 8 | 2017-08-04 | 22 | 21 | 18 | 13 | 10 | 6 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
211 | 9 | 2017-08-11 | 28 | 26 | 23 | 19 | 16 | 13 | 8 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
212 | 11 | 2017-08-25 | 28 | 24 | 22 | 18 | 17 | 16 | 12 | 9 | 7 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
213 | 10 | 2017-08-18 | 28 | 25 | 22 | 18 | 15 | 12 | 10 | 7 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
214 | 7 | 2017-07-28 | 24 | 21 | 16 | 13 | 9 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
215 | 10 | 2017-08-18 | 28 | 27 | 26 | 23 | 21 | 16 | 12 | 10 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
216 | 8 | 2017-08-04 | 23 | 21 | 19 | 16 | 12 | 9 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
217 | 12 | 2017-09-01 | 28 | 24 | 23 | 18 | 15 | 14 | 13 | 12 | 9 | 7 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
218 | 8 | 2017-08-04 | 23 | 19 | 15 | 11 | 8 | 6 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
219 | 7 | 2017-07-28 | 23 | 20 | 17 | 13 | 10 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
220 | 8 | 2017-08-04 | 22 | 19 | 17 | 14 | 10 | 6 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
221 | 11 | 2017-08-25 | 26 | 25 | 24 | 21 | 19 | 14 | 9 | 8 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
222 | 10 | 2017-08-18 | 22 | 18 | 13 | 11 | 10 | 9 | 7 | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
223 | 11 | 2017-08-25 | 29 | 28 | 24 | 22 | 19 | 16 | 15 | 14 | 11 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
224 | 10 | 2017-08-18 | 23 | 22 | 19 | 16 | 14 | 9 | 8 | 7 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
225 | 8 | 2017-08-04 | 26 | 22 | 20 | 18 | 13 | 10 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
226 | 7 | 2017-07-28 | 24 | 21 | 16 | 14 | 9 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
227 | 8 | 2017-08-04 | 26 | 23 | 20 | 16 | 13 | 9 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
228 | 11 | 2017-08-25 | 30 | 27 | 23 | 22 | 19 | 16 | 15 | 13 | 12 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
229 | 9 | 2017-08-11 | 26 | 21 | 19 | 15 | 12 | 9 | 8 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
230 | 9 | 2017-08-11 | 29 | 24 | 20 | 16 | 11 | 10 | 7 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
231 | 7 | 2017-07-28 | 20 | 16 | 12 | 8 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
232 | 10 | 2017-08-18 | 26 | 24 | 20 | 19 | 17 | 16 | 13 | 8 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
233 | 9 | 2017-08-11 | 25 | 24 | 20 | 15 | 10 | 7 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
234 | 10 | 2017-08-18 | 25 | 24 | 19 | 17 | 13 | 12 | 10 | 9 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
235 | 9 | 2017-08-11 | 27 | 24 | 20 | 17 | 16 | 12 | 8 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
236 | 8 | 2017-08-04 | 26 | 25 | 21 | 19 | 15 | 12 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
237 | 11 | 2017-08-25 | 29 | 27 | 26 | 22 | 20 | 15 | 14 | 13 | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
238 | 11 | 2017-08-25 | 28 | 23 | 22 | 18 | 16 | 12 | 8 | 7 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
239 | 10 | 2017-08-18 | 30 | 26 | 22 | 21 | 17 | 12 | 10 | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
240 | 11 | 2017-08-25 | 30 | 27 | 25 | 22 | 20 | 16 | 11 | 9 | 8 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
241 | 7 | 2017-07-28 | 22 | 20 | 17 | 12 | 7 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
242 | 9 | 2017-08-11 | 30 | 27 | 25 | 20 | 16 | 13 | 12 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
243 | 9 | 2017-08-11 | 26 | 25 | 20 | 16 | 14 | 11 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
244 | 11 | 2017-08-25 | 30 | 28 | 23 | 18 | 17 | 16 | 13 | 9 | 8 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
245 | 11 | 2017-08-25 | 24 | 23 | 20 | 16 | 14 | 10 | 9 | 8 | 7 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
246 | 13 | 2017-09-08 | 28 | 25 | 23 | 22 | 20 | 18 | 15 | 11 | 6 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
247 | 8 | 2017-08-04 | 25 | 20 | 16 | 11 | 10 | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
248 | 10 | 2017-08-18 | 28 | 26 | 23 | 21 | 17 | 13 | 12 | 9 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
249 | 5 | 2017-07-14 | 20 | 16 | 12 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
250 | 8 | 2017-08-04 | 22 | 20 | 17 | 13 | 11 | 8 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
251 | 6 | 2017-07-21 | 20 | 15 | 10 | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
252 | 7 | 2017-07-28 | 23 | 19 | 18 | 17 | 12 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
253 | 8 | 2017-08-04 | 29 | 25 | 23 | 20 | 15 | 11 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
254 | 11 | 2017-08-25 | 26 | 23 | 22 | 18 | 15 | 14 | 12 | 7 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
255 | 10 | 2017-08-18 | 30 | 26 | 21 | 16 | 13 | 12 | 9 | 7 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
256 | 10 | 2017-08-18 | 27 | 26 | 23 | 22 | 19 | 16 | 11 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
257 | 7 | 2017-07-28 | 23 | 19 | 15 | 13 | 10 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
258 | 10 | 2017-08-18 | 22 | 21 | 18 | 15 | 12 | 11 | 10 | 6 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
259 | 8 | 2017-08-04 | 28 | 23 | 19 | 14 | 12 | 11 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
260 | 9 | 2017-08-11 | 25 | 20 | 18 | 17 | 12 | 11 | 9 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
261 | 7 | 2017-07-28 | 22 | 17 | 14 | 12 | 8 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
262 | 8 | 2017-08-04 | 22 | 21 | 18 | 14 | 12 | 8 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
263 | 10 | 2017-08-18 | 26 | 22 | 20 | 18 | 13 | 9 | 8 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
264 | 8 | 2017-08-04 | 22 | 17 | 15 | 13 | 11 | 10 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
265 | 10 | 2017-08-18 | 25 | 23 | 21 | 17 | 14 | 13 | 12 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
266 | 9 | 2017-08-11 | 24 | 21 | 20 | 19 | 14 | 9 | 6 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
267 | 13 | 2017-09-08 | 27 | 25 | 24 | 21 | 18 | 15 | 11 | 10 | 9 | 8 | 5 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
268 | 10 | 2017-08-18 | 27 | 23 | 22 | 20 | 16 | 15 | 13 | 8 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
269 | 8 | 2017-08-04 | 26 | 23 | 20 | 17 | 12 | 8 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
270 | 13 | 2017-09-08 | 26 | 23 | 21 | 20 | 19 | 18 | 17 | 16 | 14 | 13 | 8 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
271 | 8 | 2017-08-04 | 25 | 22 | 17 | 16 | 12 | 8 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
272 | 8 | 2017-08-04 | 21 | 19 | 15 | 14 | 13 | 9 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
273 | 7 | 2017-07-28 | 21 | 18 | 17 | 12 | 9 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
274 | 6 | 2017-07-21 | 22 | 19 | 15 | 10 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
275 | 9 | 2017-08-11 | 29 | 25 | 23 | 18 | 14 | 9 | 6 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
276 | 6 | 2017-07-21 | 22 | 18 | 13 | 10 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
277 | 7 | 2017-07-28 | 21 | 19 | 18 | 14 | 9 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
278 | 6 | 2017-07-21 | 20 | 15 | 11 | 8 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
279 | 10 | 2017-08-18 | 25 | 24 | 23 | 22 | 17 | 15 | 12 | 8 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
280 | 8 | 2017-08-04 | 26 | 25 | 20 | 17 | 12 | 8 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
281 | 11 | 2017-08-25 | 23 | 20 | 17 | 16 | 13 | 12 | 9 | 7 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
282 | 8 | 2017-08-04 | 26 | 21 | 16 | 12 | 11 | 10 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
283 | 10 | 2017-08-18 | 21 | 20 | 15 | 12 | 7 | 6 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
284 | 10 | 2017-08-18 | 28 | 23 | 20 | 19 | 18 | 13 | 10 | 7 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
285 | 9 | 2017-08-11 | 30 | 26 | 23 | 22 | 19 | 17 | 13 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
286 | 10 | 2017-08-18 | 29 | 26 | 25 | 20 | 18 | 17 | 12 | 9 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
287 | 9 | 2017-08-11 | 20 | 18 | 16 | 15 | 13 | 12 | 9 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
288 | 5 | 2017-07-14 | 23 | 19 | 14 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
289 | 9 | 2017-08-11 | 22 | 21 | 19 | 16 | 14 | 11 | 8 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
290 | 12 | 2017-09-01 | 30 | 28 | 24 | 22 | 20 | 17 | 15 | 13 | 8 | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
291 | 9 | 2017-08-11 | 30 | 29 | 26 | 22 | 17 | 12 | 8 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
292 | 6 | 2017-07-21 | 20 | 17 | 12 | 9 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
293 | 11 | 2017-08-25 | 30 | 29 | 26 | 23 | 21 | 19 | 16 | 12 | 8 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
294 | 10 | 2017-08-18 | 30 | 28 | 25 | 23 | 20 | 15 | 11 | 8 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
295 | 9 | 2017-08-11 | 25 | 22 | 19 | 17 | 16 | 13 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
296 | 9 | 2017-08-11 | 28 | 23 | 21 | 16 | 14 | 10 | 9 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
297 | 7 | 2017-07-28 | 23 | 22 | 18 | 13 | 8 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
298 | 7 | 2017-07-28 | 26 | 21 | 17 | 13 | 10 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
299 | 9 | 2017-08-11 | 22 | 20 | 18 | 17 | 12 | 10 | 9 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
300 | 10 | 2017-08-18 | 29 | 24 | 20 | 19 | 15 | 12 | 11 | 7 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
301 | 9 | 2017-08-11 | 22 | 19 | 18 | 17 | 16 | 11 | 10 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
302 | 10 | 2017-08-18 | 22 | 20 | 17 | 16 | 14 | 12 | 11 | 6 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
303 | 8 | 2017-08-04 | 23 | 22 | 21 | 17 | 15 | 10 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
304 | 9 | 2017-08-11 | 20 | 17 | 14 | 13 | 11 | 8 | 7 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
305 | 6 | 2017-07-21 | 20 | 16 | 11 | 10 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
306 | 8 | 2017-08-04 | 27 | 26 | 21 | 17 | 12 | 9 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
307 | 6 | 2017-07-21 | 21 | 16 | 12 | 9 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
308 | 9 | 2017-08-11 | 29 | 28 | 23 | 18 | 13 | 11 | 7 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
309 | 8 | 2017-08-04 | 21 | 19 | 14 | 13 | 11 | 7 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
310 | 10 | 2017-08-18 | 23 | 22 | 21 | 18 | 17 | 16 | 12 | 10 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
311 | 8 | 2017-08-04 | 24 | 19 | 16 | 13 | 10 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
312 | 11 | 2017-08-25 | 28 | 25 | 21 | 20 | 19 | 16 | 14 | 11 | 7 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
313 | 7 | 2017-07-28 | 25 | 20 | 18 | 14 | 10 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
314 | 9 | 2017-08-11 | 26 | 22 | 21 | 16 | 12 | 8 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
315 | 8 | 2017-08-04 | 20 | 18 | 15 | 12 | 11 | 8 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
316 | 8 | 2017-08-04 | 26 | 21 | 20 | 17 | 12 | 9 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
317 | 9 | 2017-08-11 | 27 | 24 | 22 | 21 | 16 | 12 | 11 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
318 | 10 | 2017-08-18 | 30 | 28 | 25 | 23 | 18 | 14 | 9 | 7 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
319 | 12 | 2017-09-01 | 29 | 27 | 26 | 24 | 22 | 21 | 18 | 16 | 13 | 9 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
320 | 9 | 2017-08-11 | 26 | 21 | 18 | 16 | 12 | 9 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
321 | 8 | 2017-08-04 | 22 | 18 | 15 | 13 | 11 | 10 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
322 | 9 | 2017-08-11 | 25 | 22 | 20 | 17 | 14 | 10 | 6 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
323 | 9 | 2017-08-11 | 24 | 22 | 18 | 17 | 14 | 12 | 8 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
324 | 8 | 2017-08-04 | 23 | 21 | 20 | 18 | 16 | 11 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
325 | 9 | 2017-08-11 | 26 | 21 | 19 | 16 | 13 | 11 | 7 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
326 | 9 | 2017-08-11 | 27 | 23 | 19 | 18 | 14 | 9 | 8 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
327 | 6 | 2017-07-21 | 21 | 16 | 13 | 8 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
328 | 7 | 2017-07-28 | 21 | 18 | 14 | 10 | 8 | 7 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
329 | 11 | 2017-08-25 | 28 | 26 | 22 | 21 | 20 | 15 | 13 | 11 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
330 | 9 | 2017-08-11 | 23 | 19 | 16 | 14 | 13 | 10 | 9 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
331 | 13 | 2017-09-08 | 27 | 26 | 22 | 19 | 16 | 14 | 13 | 10 | 8 | 7 | 5 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
332 | 9 | 2017-08-11 | 30 | 27 | 24 | 20 | 15 | 14 | 12 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
333 | 9 | 2017-08-11 | 23 | 19 | 16 | 12 | 11 | 9 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
334 | 10 | 2017-08-18 | 25 | 23 | 22 | 17 | 14 | 11 | 8 | 5 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
335 | 8 | 2017-08-04 | 26 | 25 | 21 | 19 | 14 | 10 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
336 | 9 | 2017-08-11 | 23 | 21 | 20 | 18 | 13 | 10 | 5 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
337 | 6 | 2017-07-21 | 20 | 15 | 12 | 9 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
338 | 8 | 2017-08-04 | 24 | 22 | 18 | 14 | 12 | 8 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
339 | 8 | 2017-08-04 | 21 | 18 | 17 | 14 | 9 | 6 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
340 | 11 | 2017-08-25 | 30 | 27 | 23 | 19 | 18 | 15 | 14 | 13 | 9 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
341 | 9 | 2017-08-11 | 24 | 19 | 18 | 13 | 12 | 11 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
342 | 7 | 2017-07-28 | 20 | 17 | 13 | 9 | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
343 | 10 | 2017-08-18 | 29 | 24 | 23 | 21 | 16 | 11 | 8 | 7 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
344 | 9 | 2017-08-11 | 26 | 24 | 23 | 22 | 19 | 14 | 10 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
345 | 8 | 2017-08-04 | 24 | 22 | 17 | 14 | 12 | 11 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
346 | 7 | 2017-07-28 | 20 | 16 | 11 | 8 | 6 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
347 | 8 | 2017-08-04 | 23 | 22 | 17 | 13 | 8 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
348 | 7 | 2017-07-28 | 27 | 22 | 17 | 13 | 10 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
349 | 12 | 2017-09-01 | 27 | 25 | 22 | 21 | 19 | 14 | 13 | 11 | 8 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
350 | 15 | 2017-09-22 | 30 | 27 | 24 | 22 | 19 | 18 | 16 | 13 | 12 | 9 | 7 | 6 | 5 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
351 | 8 | 2017-08-04 | 23 | 20 | 18 | 16 | 11 | 7 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
352 | 10 | 2017-08-18 | 26 | 23 | 20 | 16 | 14 | 12 | 11 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
353 | 10 | 2017-08-18 | 28 | 24 | 20 | 18 | 16 | 14 | 13 | 9 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
354 | 9 | 2017-08-11 | 30 | 25 | 23 | 22 | 20 | 15 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
355 | 11 | 2017-08-25 | 29 | 28 | 26 | 21 | 20 | 16 | 15 | 13 | 8 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
356 | 10 | 2017-08-18 | 27 | 26 | 24 | 23 | 21 | 20 | 15 | 11 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
357 | 7 | 2017-07-28 | 22 | 20 | 18 | 13 | 10 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
358 | 9 | 2017-08-11 | 22 | 21 | 20 | 17 | 16 | 11 | 9 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
359 | 9 | 2017-08-11 | 24 | 22 | 21 | 16 | 15 | 11 | 10 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
360 | 10 | 2017-08-18 | 25 | 24 | 19 | 18 | 15 | 11 | 10 | 7 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
361 | 11 | 2017-08-25 | 27 | 22 | 20 | 17 | 16 | 15 | 14 | 9 | 8 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
362 | 6 | 2017-07-21 | 22 | 17 | 12 | 7 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
363 | 8 | 2017-08-04 | 25 | 23 | 19 | 18 | 15 | 11 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
364 | 6 | 2017-07-21 | 21 | 19 | 15 | 11 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
365 | 8 | 2017-08-04 | 27 | 25 | 22 | 18 | 13 | 8 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
366 | 12 | 2017-09-01 | 30 | 28 | 25 | 22 | 21 | 17 | 16 | 13 | 10 | 9 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
367 | 7 | 2017-07-28 | 26 | 21 | 17 | 13 | 8 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
368 | 7 | 2017-07-28 | 25 | 20 | 16 | 12 | 8 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
369 | 10 | 2017-08-18 | 26 | 24 | 22 | 21 | 17 | 14 | 11 | 6 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
370 | 8 | 2017-08-04 | 25 | 24 | 21 | 17 | 12 | 11 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
371 | 10 | 2017-08-18 | 24 | 19 | 18 | 16 | 15 | 11 | 10 | 8 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
372 | 6 | 2017-07-21 | 23 | 20 | 17 | 13 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
373 | 6 | 2017-07-21 | 22 | 18 | 15 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
374 | 12 | 2017-09-01 | 30 | 27 | 24 | 19 | 18 | 17 | 14 | 9 | 8 | 7 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
375 | 8 | 2017-08-04 | 22 | 20 | 17 | 15 | 14 | 11 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
376 | 9 | 2017-08-11 | 28 | 23 | 20 | 19 | 15 | 10 | 8 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
377 | 9 | 2017-08-11 | 28 | 25 | 21 | 19 | 18 | 16 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
378 | 12 | 2017-09-01 | 27 | 25 | 24 | 23 | 19 | 18 | 14 | 11 | 8 | 7 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
379 | 9 | 2017-08-11 | 26 | 23 | 18 | 17 | 12 | 7 | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
380 | 7 | 2017-07-28 | 25 | 21 | 17 | 12 | 9 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
381 | 8 | 2017-08-04 | 25 | 22 | 17 | 14 | 10 | 9 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
382 | 8 | 2017-08-04 | 25 | 22 | 21 | 16 | 14 | 11 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
383 | 7 | 2017-07-28 | 21 | 19 | 15 | 14 | 9 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
384 | 6 | 2017-07-21 | 22 | 20 | 16 | 12 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
385 | 9 | 2017-08-11 | 30 | 25 | 21 | 17 | 12 | 10 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
386 | 9 | 2017-08-11 | 26 | 25 | 20 | 15 | 11 | 10 | 6 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
387 | 9 | 2017-08-11 | 22 | 20 | 16 | 13 | 8 | 7 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
388 | 8 | 2017-08-04 | 26 | 22 | 18 | 15 | 14 | 10 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
389 | 9 | 2017-08-11 | 26 | 24 | 23 | 19 | 15 | 14 | 12 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
390 | 8 | 2017-08-04 | 25 | 24 | 20 | 19 | 15 | 13 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
391 | 10 | 2017-08-18 | 25 | 21 | 19 | 17 | 16 | 12 | 10 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
392 | 6 | 2017-07-21 | 23 | 19 | 18 | 13 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
393 | 9 | 2017-08-11 | 24 | 19 | 17 | 15 | 14 | 10 | 7 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
394 | 7 | 2017-07-28 | 22 | 19 | 18 | 13 | 10 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
395 | 7 | 2017-07-28 | 22 | 17 | 15 | 13 | 10 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
396 | 8 | 2017-08-04 | 30 | 26 | 21 | 18 | 15 | 10 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
397 | 10 | 2017-08-18 | 30 | 27 | 26 | 25 | 23 | 19 | 14 | 12 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
398 | 7 | 2017-07-28 | 21 | 17 | 13 | 12 | 10 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
399 | 9 | 2017-08-11 | 23 | 20 | 19 | 17 | 12 | 11 | 8 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
400 | 8 | 2017-08-04 | 21 | 18 | 13 | 10 | 9 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
401 | 10 | 2017-08-18 | 27 | 24 | 22 | 19 | 14 | 9 | 7 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
402 | 7 | 2017-07-28 | 21 | 20 | 15 | 11 | 10 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
403 | 10 | 2017-08-18 | 25 | 22 | 19 | 15 | 13 | 12 | 11 | 9 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
404 | 10 | 2017-08-18 | 30 | 29 | 28 | 23 | 19 | 17 | 13 | 9 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
405 | 10 | 2017-08-18 | 28 | 24 | 21 | 20 | 19 | 16 | 12 | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
406 | 9 | 2017-08-11 | 23 | 21 | 18 | 17 | 12 | 11 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
407 | 7 | 2017-07-28 | 23 | 22 | 17 | 14 | 9 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
408 | 9 | 2017-08-11 | 28 | 25 | 24 | 21 | 17 | 12 | 7 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
409 | 10 | 2017-08-18 | 27 | 22 | 18 | 15 | 14 | 13 | 10 | 8 | 7 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
410 | 10 | 2017-08-18 | 29 | 25 | 20 | 18 | 16 | 15 | 10 | 7 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
411 | 9 | 2017-08-11 | 22 | 19 | 17 | 16 | 15 | 11 | 8 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
412 | 11 | 2017-08-25 | 30 | 26 | 25 | 20 | 17 | 16 | 14 | 11 | 8 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
413 | 11 | 2017-08-25 | 30 | 27 | 26 | 21 | 17 | 14 | 10 | 9 | 8 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
414 | 12 | 2017-09-01 | 27 | 26 | 24 | 19 | 18 | 16 | 14 | 13 | 10 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
415 | 7 | 2017-07-28 | 23 | 20 | 19 | 14 | 10 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
416 | 8 | 2017-08-04 | 28 | 27 | 23 | 18 | 16 | 11 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
417 | 10 | 2017-08-18 | 28 | 25 | 21 | 18 | 15 | 11 | 9 | 7 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
418 | 8 | 2017-08-04 | 20 | 19 | 18 | 16 | 11 | 8 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
419 | 10 | 2017-08-18 | 27 | 26 | 22 | 19 | 18 | 15 | 11 | 7 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
420 | 7 | 2017-07-28 | 21 | 19 | 15 | 13 | 12 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
421 | 7 | 2017-07-28 | 20 | 15 | 13 | 11 | 8 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
422 | 9 | 2017-08-11 | 27 | 22 | 20 | 18 | 15 | 11 | 10 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
423 | 9 | 2017-08-11 | 20 | 16 | 12 | 9 | 8 | 6 | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
424 | 10 | 2017-08-18 | 21 | 18 | 14 | 13 | 11 | 9 | 8 | 7 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
425 | 10 | 2017-08-18 | 25 | 22 | 20 | 18 | 15 | 12 | 10 | 6 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
426 | 6 | 2017-07-21 | 20 | 19 | 15 | 10 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
427 | 7 | 2017-07-28 | 21 | 16 | 14 | 10 | 7 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
428 | 10 | 2017-08-18 | 27 | 25 | 20 | 19 | 15 | 12 | 9 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
429 | 7 | 2017-07-28 | 23 | 18 | 15 | 11 | 8 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
430 | 7 | 2017-07-28 | 22 | 18 | 17 | 16 | 11 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
431 | 10 | 2017-08-18 | 29 | 27 | 23 | 18 | 14 | 11 | 8 | 5 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
432 | 7 | 2017-07-28 | 23 | 20 | 17 | 15 | 13 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
433 | 8 | 2017-08-04 | 25 | 21 | 20 | 16 | 11 | 7 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
434 | 9 | 2017-08-11 | 28 | 23 | 19 | 18 | 14 | 10 | 9 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
435 | 8 | 2017-08-04 | 21 | 19 | 16 | 15 | 11 | 8 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
436 | 7 | 2017-07-28 | 21 | 16 | 15 | 13 | 8 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
437 | 7 | 2017-07-28 | 24 | 22 | 18 | 13 | 10 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
438 | 7 | 2017-07-28 | 26 | 22 | 20 | 15 | 10 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
439 | 8 | 2017-08-04 | 25 | 22 | 17 | 14 | 11 | 6 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
440 | 8 | 2017-08-04 | 26 | 22 | 21 | 18 | 17 | 12 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
441 | 9 | 2017-08-11 | 28 | 24 | 19 | 14 | 12 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
442 | 10 | 2017-08-18 | 23 | 22 | 21 | 17 | 16 | 11 | 8 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
443 | 8 | 2017-08-04 | 23 | 20 | 17 | 14 | 11 | 7 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
444 | 6 | 2017-07-21 | 20 | 15 | 11 | 7 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
445 | 7 | 2017-07-28 | 25 | 21 | 17 | 12 | 11 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
446 | 7 | 2017-07-28 | 21 | 19 | 17 | 14 | 9 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
447 | 8 | 2017-08-04 | 20 | 17 | 12 | 10 | 6 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
448 | 9 | 2017-08-11 | 25 | 24 | 20 | 19 | 14 | 13 | 8 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
449 | 6 | 2017-07-21 | 20 | 18 | 13 | 8 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
450 | 7 | 2017-07-28 | 26 | 21 | 16 | 14 | 10 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
451 | 11 | 2017-08-25 | 29 | 27 | 26 | 22 | 17 | 16 | 12 | 10 | 9 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
452 | 10 | 2017-08-18 | 25 | 23 | 22 | 20 | 17 | 16 | 12 | 8 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
453 | 9 | 2017-08-11 | 23 | 19 | 18 | 16 | 13 | 10 | 8 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
454 | 8 | 2017-08-04 | 27 | 26 | 22 | 21 | 18 | 13 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
455 | 7 | 2017-07-28 | 27 | 22 | 17 | 13 | 9 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
456 | 9 | 2017-08-11 | 27 | 25 | 24 | 21 | 18 | 13 | 9 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
457 | 6 | 2017-07-21 | 20 | 18 | 13 | 9 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
458 | 9 | 2017-08-11 | 25 | 23 | 18 | 16 | 13 | 11 | 10 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
459 | 10 | 2017-08-18 | 26 | 25 | 20 | 19 | 14 | 13 | 11 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
460 | 8 | 2017-08-04 | 24 | 21 | 18 | 13 | 8 | 5 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
461 | 8 | 2017-08-04 | 30 | 25 | 21 | 17 | 15 | 10 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
462 | 9 | 2017-08-11 | 25 | 20 | 17 | 13 | 12 | 11 | 6 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
463 | 10 | 2017-08-18 | 24 | 23 | 22 | 20 | 18 | 16 | 11 | 9 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
464 | 9 | 2017-08-11 | 25 | 24 | 21 | 20 | 16 | 12 | 8 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
465 | 8 | 2017-08-04 | 24 | 19 | 15 | 11 | 10 | 9 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
466 | 9 | 2017-08-11 | 23 | 20 | 16 | 13 | 8 | 7 | 5 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
467 | 8 | 2017-08-04 | 20 | 17 | 15 | 12 | 11 | 8 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
468 | 8 | 2017-08-04 | 23 | 18 | 17 | 14 | 10 | 9 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
469 | 12 | 2017-09-01 | 30 | 26 | 21 | 19 | 18 | 16 | 15 | 11 | 10 | 7 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
470 | 7 | 2017-07-28 | 25 | 21 | 19 | 14 | 9 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
471 | 8 | 2017-08-04 | 24 | 23 | 19 | 16 | 15 | 11 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
472 | 7 | 2017-07-28 | 24 | 20 | 16 | 12 | 9 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
473 | 10 | 2017-08-18 | 26 | 24 | 21 | 18 | 15 | 13 | 12 | 7 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
474 | 11 | 2017-08-25 | 26 | 24 | 21 | 20 | 15 | 10 | 5 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
475 | 8 | 2017-08-04 | 22 | 18 | 16 | 14 | 13 | 12 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
476 | 12 | 2017-09-01 | 28 | 27 | 25 | 23 | 22 | 20 | 15 | 12 | 11 | 7 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
477 | 10 | 2017-08-18 | 27 | 24 | 19 | 18 | 17 | 13 | 10 | 8 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
478 | 8 | 2017-08-04 | 20 | 16 | 14 | 9 | 7 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
479 | 8 | 2017-08-04 | 26 | 23 | 20 | 18 | 13 | 12 | 7 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
480 | 7 | 2017-07-28 | 20 | 18 | 13 | 8 | 5 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
481 | 12 | 2017-09-01 | 30 | 26 | 25 | 21 | 19 | 18 | 15 | 14 | 10 | 7 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
482 | 11 | 2017-08-25 | 30 | 28 | 26 | 25 | 20 | 17 | 12 | 10 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
483 | 11 | 2017-08-25 | 23 | 22 | 18 | 14 | 12 | 11 | 9 | 6 | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
484 | 8 | 2017-08-04 | 24 | 21 | 16 | 12 | 9 | 8 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
485 | 10 | 2017-08-18 | 28 | 25 | 21 | 20 | 18 | 15 | 11 | 6 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
486 | 8 | 2017-08-04 | 29 | 24 | 19 | 15 | 13 | 10 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
487 | 7 | 2017-07-28 | 27 | 22 | 19 | 15 | 10 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
488 | 7 | 2017-07-28 | 21 | 20 | 15 | 12 | 9 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
489 | 8 | 2017-08-04 | 21 | 18 | 16 | 15 | 13 | 12 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
490 | 8 | 2017-08-04 | 25 | 20 | 16 | 12 | 7 | 6 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
491 | 14 | 2017-09-15 | 30 | 25 | 23 | 22 | 21 | 18 | 17 | 15 | 13 | 12 | 10 | 8 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
492 | 10 | 2017-08-18 | 24 | 23 | 21 | 19 | 16 | 13 | 10 | 7 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
493 | 8 | 2017-08-04 | 27 | 23 | 19 | 14 | 11 | 9 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
494 | 12 | 2017-09-01 | 28 | 26 | 23 | 21 | 17 | 16 | 13 | 9 | 8 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
495 | 9 | 2017-08-11 | 24 | 22 | 20 | 19 | 17 | 12 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
496 | 8 | 2017-08-04 | 22 | 20 | 15 | 14 | 11 | 9 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
497 | 10 | 2017-08-18 | 26 | 25 | 22 | 20 | 19 | 16 | 11 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
498 | 11 | 2017-08-25 | 28 | 27 | 25 | 22 | 18 | 14 | 13 | 10 | 7 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
499 | 10 | 2017-08-18 | 30 | 25 | 20 | 19 | 16 | 13 | 11 | 10 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
500 | 12 | 2017-09-01 | 25 | 22 | 19 | 15 | 12 | 10 | 9 | 8 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
501 | 8 | 2017-08-04 | 22 | 20 | 17 | 13 | 9 | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Formulas:
End of Zero Week = IF([Weeks to Zero]<>"",INDEX(D2:BD2,1,[Weeks to Zero]+1),"")

## Risk Impact Monte Carlo (hidden)
 | time axis 2017-06-09 to 2018-06-08
Risk 1 - Reduce Probability
Trial | Weeks to Zero | End of Zero Week | TotalStories | End period 1 | End period 2 | End period 3 | End period 4 | End period 5 | End period 6 | End period 7 | End period 8 | End period 9 | End period 10 | End period 11 | End period 12 | End period 13 | End period 14 | End period 15 | End period 16 | End period 17 | End period 18 | End period 19 | End period 20 | End period 21 | End period 22 | End period 23 | End period 24 | End period 25 | End period 26 | End period 27 | End period 28 | End period 29 | End period 30 | End period 31 | End period 32 | End period 33 | End period 34 | End period 35 | End period 36 | End period 37 | End period 38 | End period 39 | End period 40 | End period 41 | End period 42 | End period 43 | End period 44 | End period 45 | End period 46 | End period 47 | End period 48 | End period 49 | End period 50 | End period 51 | End period 52
1 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
4 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
6 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
8 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
9 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
10 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
11 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
12 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
13 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
14 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
15 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
16 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
17 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
18 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
19 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
20 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
21 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
22 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
23 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
24 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
25 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
26 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
27 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
28 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
29 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
30 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
31 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
32 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
33 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
34 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
35 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
36 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
37 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
38 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
39 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
40 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
41 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
42 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
43 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
44 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
45 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
46 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
47 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
48 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
49 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
50 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
51 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
52 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
53 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
54 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
55 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
56 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
57 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
58 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
59 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
60 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
61 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
62 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
63 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
64 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
65 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
66 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
67 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
68 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
69 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
70 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
71 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
72 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
73 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
74 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
75 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
76 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
77 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
78 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
79 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
80 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
81 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
82 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
83 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
84 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
85 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
86 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
87 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
88 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
89 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
90 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
91 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
92 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
93 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
94 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
95 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
96 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
97 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
98 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
99 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
100 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Risk 1 - Reduce Impact
Trial | Weeks to Zero | End of Zero Week | TotalStories | End period 1 | End period 2 | End period 3 | End period 4 | End period 5 | End period 6 | End period 7 | End period 8 | End period 9 | End period 10 | End period 11 | End period 12 | End period 13 | End period 14 | End period 15 | End period 16 | End period 17 | End period 18 | End period 19 | End period 20 | End period 21 | End period 22 | End period 23 | End period 24 | End period 25 | End period 26 | End period 27 | End period 28 | End period 29 | End period 30 | End period 31 | End period 32 | End period 33 | End period 34 | End period 35 | End period 36 | End period 37 | End period 38 | End period 39 | End period 40 | End period 41 | End period 42 | End period 43 | End period 44 | End period 45 | End period 46 | End period 47 | End period 48 | End period 49 | End period 50 | End period 51 | End period 52
1 | 8 | 2017-08-04 | 23 | 22 | 19 | 14 | 13 | 10 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 6 | 2017-07-21 | 20 | 15 | 10 | 6 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 10 | 2017-08-18 | 26 | 24 | 23 | 20 | 19 | 14 | 11 | 8 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 9 | 2017-08-11 | 26 | 22 | 20 | 16 | 14 | 13 | 10 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 6 | 2017-07-21 | 22 | 20 | 15 | 11 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 10 | 2017-08-18 | 29 | 25 | 22 | 21 | 17 | 12 | 8 | 7 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 8 | 2017-08-04 | 21 | 16 | 13 | 9 | 6 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 11 | 2017-08-25 | 28 | 26 | 23 | 22 | 17 | 13 | 11 | 10 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 10 | 2017-08-18 | 21 | 19 | 17 | 16 | 15 | 10 | 9 | 8 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | 9 | 2017-08-11 | 28 | 24 | 23 | 19 | 14 | 12 | 8 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | 8 | 2017-08-04 | 26 | 21 | 18 | 15 | 11 | 6 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 12 | 2017-09-01 | 29 | 27 | 24 | 23 | 21 | 20 | 17 | 13 | 12 | 10 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | 9 | 2017-08-11 | 24 | 23 | 20 | 16 | 12 | 9 | 8 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 7 | 2017-07-28 | 20 | 19 | 17 | 14 | 11 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | 7 | 2017-07-28 | 20 | 15 | 14 | 13 | 10 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | 8 | 2017-08-04 | 23 | 21 | 16 | 15 | 12 | 10 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 5 | 2017-07-14 | 21 | 17 | 12 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 8 | 2017-08-04 | 23 | 21 | 16 | 13 | 11 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | 7 | 2017-07-28 | 23 | 18 | 13 | 9 | 7 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | 6 | 2017-07-21 | 24 | 20 | 15 | 11 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 9 | 2017-08-11 | 28 | 24 | 23 | 20 | 18 | 14 | 12 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | 9 | 2017-08-11 | 24 | 19 | 18 | 13 | 9 | 8 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | 8 | 2017-08-04 | 23 | 21 | 19 | 14 | 12 | 10 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 6 | 2017-07-21 | 20 | 16 | 13 | 8 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | 9 | 2017-08-11 | 25 | 21 | 20 | 15 | 11 | 6 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | 7 | 2017-07-28 | 24 | 21 | 17 | 13 | 10 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | 9 | 2017-08-11 | 28 | 24 | 23 | 18 | 13 | 10 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | 9 | 2017-08-11 | 24 | 21 | 20 | 15 | 14 | 9 | 6 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | 6 | 2017-07-21 | 22 | 20 | 17 | 12 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | 8 | 2017-08-04 | 26 | 23 | 20 | 17 | 13 | 8 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | 6 | 2017-07-21 | 20 | 17 | 12 | 10 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | 10 | 2017-08-18 | 30 | 25 | 24 | 21 | 18 | 13 | 8 | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | 10 | 2017-08-18 | 30 | 28 | 26 | 22 | 19 | 14 | 11 | 9 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | 9 | 2017-08-11 | 22 | 17 | 16 | 15 | 12 | 9 | 8 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | 9 | 2017-08-11 | 25 | 21 | 19 | 15 | 11 | 8 | 7 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | 8 | 2017-08-04 | 20 | 19 | 15 | 13 | 9 | 8 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | 8 | 2017-08-04 | 24 | 21 | 17 | 15 | 12 | 7 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | 8 | 2017-08-04 | 29 | 25 | 21 | 16 | 15 | 10 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | 12 | 2017-09-01 | 29 | 26 | 25 | 21 | 19 | 17 | 13 | 12 | 11 | 7 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | 8 | 2017-08-04 | 26 | 22 | 17 | 13 | 9 | 8 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | 8 | 2017-08-04 | 22 | 21 | 16 | 15 | 13 | 9 | 7 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | 9 | 2017-08-11 | 26 | 22 | 21 | 17 | 14 | 13 | 11 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | 8 | 2017-08-04 | 22 | 18 | 15 | 13 | 10 | 9 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | 8 | 2017-08-04 | 25 | 22 | 17 | 12 | 11 | 8 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | 8 | 2017-08-04 | 23 | 22 | 17 | 16 | 12 | 7 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | 7 | 2017-07-28 | 24 | 19 | 14 | 12 | 11 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | 11 | 2017-08-25 | 30 | 26 | 23 | 21 | 20 | 16 | 11 | 9 | 8 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 9 | 2017-08-11 | 26 | 23 | 18 | 17 | 16 | 12 | 8 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | 11 | 2017-08-25 | 27 | 22 | 20 | 18 | 16 | 15 | 11 | 10 | 7 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | 10 | 2017-08-18 | 22 | 19 | 18 | 16 | 14 | 10 | 5 | 4 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | 11 | 2017-08-25 | 27 | 26 | 23 | 19 | 17 | 14 | 12 | 10 | 8 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 | 9 | 2017-08-11 | 28 | 25 | 22 | 17 | 15 | 12 | 9 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | 10 | 2017-08-18 | 24 | 21 | 19 | 17 | 15 | 12 | 10 | 9 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | 9 | 2017-08-11 | 27 | 22 | 20 | 19 | 14 | 9 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 | 10 | 2017-08-18 | 23 | 22 | 21 | 18 | 17 | 15 | 13 | 9 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56 | 9 | 2017-08-11 | 29 | 25 | 22 | 18 | 15 | 10 | 9 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57 | 10 | 2017-08-18 | 27 | 23 | 20 | 17 | 16 | 12 | 9 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58 | 9 | 2017-08-11 | 24 | 20 | 16 | 15 | 13 | 10 | 8 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
59 | 8 | 2017-08-04 | 28 | 23 | 21 | 18 | 15 | 11 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 | 8 | 2017-08-04 | 25 | 20 | 19 | 14 | 11 | 7 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
61 | 8 | 2017-08-04 | 28 | 23 | 18 | 15 | 14 | 10 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
62 | 7 | 2017-07-28 | 21 | 19 | 14 | 12 | 11 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | 11 | 2017-08-25 | 28 | 26 | 25 | 24 | 19 | 17 | 12 | 8 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
64 | 9 | 2017-08-11 | 21 | 20 | 16 | 11 | 10 | 9 | 5 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
65 | 11 | 2017-08-25 | 23 | 21 | 18 | 14 | 12 | 11 | 10 | 8 | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
66 | 9 | 2017-08-11 | 30 | 25 | 20 | 19 | 16 | 12 | 8 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
67 | 10 | 2017-08-18 | 29 | 26 | 25 | 20 | 15 | 14 | 12 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
68 | 9 | 2017-08-11 | 21 | 20 | 16 | 11 | 10 | 9 | 7 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
69 | 7 | 2017-07-28 | 23 | 20 | 18 | 17 | 12 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 | 9 | 2017-08-11 | 28 | 23 | 20 | 19 | 16 | 14 | 12 | 7 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
71 | 10 | 2017-08-18 | 25 | 24 | 23 | 21 | 17 | 12 | 11 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 9 | 2017-08-11 | 20 | 18 | 16 | 12 | 10 | 8 | 6 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
73 | 10 | 2017-08-18 | 25 | 23 | 21 | 16 | 12 | 10 | 9 | 5 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
74 | 11 | 2017-08-25 | 27 | 23 | 20 | 15 | 13 | 11 | 9 | 8 | 6 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
75 | 11 | 2017-08-25 | 28 | 26 | 23 | 20 | 18 | 17 | 16 | 13 | 11 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
76 | 10 | 2017-08-18 | 29 | 28 | 23 | 22 | 17 | 13 | 10 | 9 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
77 | 7 | 2017-07-28 | 20 | 16 | 15 | 12 | 8 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
78 | 8 | 2017-08-04 | 22 | 21 | 16 | 15 | 10 | 5 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
79 | 9 | 2017-08-11 | 27 | 23 | 20 | 17 | 12 | 7 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | 7 | 2017-07-28 | 26 | 21 | 16 | 14 | 10 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 | 9 | 2017-08-11 | 21 | 18 | 17 | 15 | 12 | 10 | 7 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
82 | 8 | 2017-08-04 | 30 | 26 | 23 | 18 | 13 | 10 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | 10 | 2017-08-18 | 30 | 29 | 28 | 23 | 20 | 15 | 12 | 11 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | 9 | 2017-08-11 | 28 | 23 | 18 | 13 | 9 | 6 | 5 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
85 | 8 | 2017-08-04 | 20 | 19 | 17 | 12 | 10 | 5 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 | 7 | 2017-07-28 | 27 | 22 | 19 | 15 | 11 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | 9 | 2017-08-11 | 25 | 23 | 19 | 17 | 13 | 11 | 9 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 | 7 | 2017-07-28 | 23 | 19 | 15 | 11 | 9 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
89 | 11 | 2017-08-25 | 24 | 23 | 22 | 17 | 13 | 10 | 7 | 5 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | 6 | 2017-07-21 | 21 | 16 | 13 | 10 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 | 10 | 2017-08-18 | 24 | 21 | 20 | 17 | 15 | 14 | 12 | 10 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 | 6 | 2017-07-21 | 21 | 17 | 13 | 9 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 | 9 | 2017-08-11 | 25 | 20 | 16 | 13 | 12 | 10 | 8 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 | 14 | 2017-09-15 | 30 | 28 | 24 | 21 | 20 | 16 | 15 | 14 | 13 | 8 | 6 | 4 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 | 10 | 2017-08-18 | 24 | 22 | 20 | 18 | 17 | 16 | 13 | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 | 7 | 2017-07-28 | 20 | 17 | 15 | 10 | 6 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
97 | 8 | 2017-08-04 | 22 | 21 | 17 | 16 | 11 | 9 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 | 9 | 2017-08-11 | 30 | 25 | 24 | 19 | 15 | 10 | 8 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | 7 | 2017-07-28 | 22 | 19 | 16 | 13 | 11 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100 | 8 | 2017-08-04 | 24 | 20 | 16 | 12 | 11 | 9 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Formulas:
End of Zero Week = IF([Weeks to Zero]<>"",INDEX(D1:BD1,1,[Weeks to Zero]+1),"")

## Throughput Monte Carlo Weeks (hidden)
Trial # | Sumx | Sum4 | Sum8 | Sum12 | Sum16 | Sum20 | Sum24 | Sum28 | Sum32 | Sum36 | Sum40 | Sum44 | Sum48 | Sum52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
1 | 15 | 9 | 19 | 32 | 48 | 53 | 65 | 77 | 89 | 104 | 117 | 133 | 150 | 161 | 3 | 4 | 1 | 1 | 2 | 4 | 1 | 3 | 2 | 2 | 4 | 5 | 4 | 4 | 5 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 5 | 5 | 5 | 2 | 2 | 3 | 1 | 2 | 4 | 5 | 4 | 5 | 1 | 5 | 5 | 2 | 2 | 4 | 5 | 2 | 5 | 4 | 4 | 3 | 5 | 5 | 1 | 1 | 4 | 5
2 | 11 | 8 | 14 | 27 | 39 | 53 | 64 | 73 | 86 | 98 | 109 | 122 | 137 | 146 | 2 | 1 | 4 | 1 | 2 | 1 | 1 | 2 | 5 | 4 | 1 | 3 | 4 | 1 | 3 | 4 | 4 | 3 | 2 | 5 | 5 | 3 | 1 | 2 | 1 | 4 | 1 | 3 | 1 | 4 | 4 | 4 | 3 | 3 | 1 | 5 | 5 | 1 | 1 | 4 | 4 | 3 | 3 | 3 | 4 | 1 | 5 | 5 | 5 | 2 | 1 | 1
3 | 21 | 12 | 25 | 40 | 51 | 66 | 79 | 92 | 101 | 113 | 121 | 134 | 146 | 161 | 4 | 2 | 4 | 2 | 4 | 5 | 3 | 1 | 5 | 3 | 2 | 5 | 3 | 3 | 1 | 4 | 5 | 5 | 1 | 4 | 3 | 2 | 3 | 5 | 3 | 5 | 4 | 1 | 3 | 1 | 2 | 3 | 4 | 4 | 2 | 2 | 2 | 1 | 4 | 1 | 5 | 4 | 3 | 1 | 2 | 4 | 5 | 1 | 4 | 4 | 3 | 4
4 | 18 | 14 | 23 | 33 | 46 | 59 | 66 | 76 | 90 | 101 | 113 | 130 | 140 | 156 | 5 | 3 | 3 | 3 | 1 | 3 | 3 | 2 | 2 | 3 | 3 | 2 | 5 | 1 | 4 | 3 | 3 | 1 | 4 | 5 | 2 | 2 | 1 | 2 | 3 | 1 | 1 | 5 | 4 | 3 | 4 | 3 | 5 | 2 | 2 | 2 | 2 | 5 | 2 | 3 | 4 | 5 | 4 | 4 | 4 | 1 | 1 | 4 | 4 | 5 | 2 | 5
5 | 12 | 8 | 19 | 33 | 45 | 54 | 71 | 79 | 88 | 100 | 112 | 124 | 132 | 140 | 2 | 2 | 2 | 2 | 1 | 3 | 5 | 2 | 4 | 4 | 4 | 2 | 1 | 5 | 5 | 1 | 3 | 3 | 1 | 2 | 4 | 3 | 5 | 5 | 3 | 2 | 1 | 2 | 1 | 2 | 5 | 1 | 3 | 4 | 4 | 1 | 2 | 4 | 3 | 3 | 4 | 1 | 5 | 2 | 2 | 3 | 2 | 1 | 1 | 4 | 2 | 1
6 | 20 | 15 | 24 | 31 | 40 | 52 | 62 | 71 | 80 | 96 | 111 | 117 | 131 | 142 | 2 | 4 | 4 | 5 | 2 | 3 | 2 | 2 | 1 | 2 | 3 | 1 | 3 | 1 | 3 | 2 | 2 | 3 | 2 | 5 | 4 | 1 | 1 | 4 | 2 | 4 | 1 | 2 | 3 | 1 | 3 | 2 | 4 | 4 | 5 | 3 | 2 | 4 | 4 | 5 | 1 | 1 | 3 | 1 | 4 | 5 | 2 | 3 | 1 | 3 | 4 | 3
7 | 21 | 13 | 30 | 45 | 56 | 66 | 80 | 90 | 99 | 115 | 135 | 143 | 153 | 168 | 3 | 5 | 2 | 3 | 4 | 4 | 5 | 4 | 4 | 4 | 2 | 5 | 2 | 2 | 4 | 3 | 3 | 2 | 2 | 3 | 2 | 3 | 4 | 5 | 1 | 4 | 3 | 2 | 2 | 2 | 1 | 4 | 5 | 5 | 3 | 3 | 5 | 5 | 5 | 5 | 2 | 1 | 2 | 3 | 1 | 3 | 2 | 4 | 4 | 4 | 3 | 4
8 | 24 | 15 | 29 | 40 | 55 | 69 | 85 | 94 | 110 | 121 | 131 | 144 | 155 | 166 | 4 | 3 | 5 | 3 | 4 | 5 | 4 | 1 | 3 | 3 | 1 | 4 | 3 | 3 | 5 | 4 | 5 | 3 | 4 | 2 | 5 | 5 | 1 | 5 | 2 | 1 | 4 | 2 | 4 | 4 | 3 | 5 | 2 | 1 | 4 | 4 | 1 | 3 | 1 | 5 | 4 | 2 | 3 | 4 | 2 | 3 | 1 | 5 | 3 | 3 | 3 | 2
9 | 17 | 12 | 20 | 34 | 48 | 58 | 66 | 77 | 87 | 97 | 114 | 123 | 140 | 151 | 2 | 1 | 5 | 4 | 2 | 3 | 2 | 1 | 5 | 5 | 1 | 3 | 4 | 4 | 2 | 4 | 2 | 2 | 5 | 1 | 1 | 5 | 1 | 1 | 1 | 2 | 5 | 3 | 3 | 2 | 4 | 1 | 4 | 3 | 2 | 1 | 2 | 5 | 5 | 5 | 1 | 4 | 1 | 3 | 5 | 4 | 3 | 5 | 3 | 2 | 4 | 2
10 | 23 | 16 | 31 | 45 | 51 | 65 | 80 | 95 | 109 | 122 | 135 | 147 | 155 | 168 | 5 | 1 | 5 | 5 | 4 | 3 | 4 | 4 | 1 | 4 | 5 | 4 | 2 | 1 | 2 | 1 | 4 | 4 | 3 | 3 | 4 | 2 | 5 | 4 | 5 | 5 | 3 | 2 | 3 | 3 | 5 | 3 | 4 | 4 | 2 | 3 | 4 | 3 | 3 | 3 | 3 | 1 | 4 | 4 | 2 | 4 | 1 | 1 | 5 | 4 | 3 | 1
11 | 14 | 10 | 23 | 34 | 47 | 60 | 73 | 89 | 100 | 113 | 123 | 134 | 144 | 156 | 2 | 4 | 2 | 2 | 2 | 2 | 5 | 4 | 3 | 1 | 4 | 3 | 3 | 1 | 4 | 5 | 3 | 5 | 2 | 3 | 5 | 4 | 3 | 1 | 5 | 3 | 3 | 5 | 3 | 4 | 1 | 3 | 4 | 5 | 2 | 2 | 1 | 2 | 3 | 4 | 4 | 2 | 1 | 4 | 4 | 1 | 3 | 2 | 1 | 4 | 5 | 2
12 | 20 | 13 | 27 | 37 | 44 | 57 | 71 | 88 | 101 | 110 | 123 | 139 | 149 | 164 | 3 | 5 | 4 | 1 | 2 | 5 | 5 | 2 | 2 | 2 | 4 | 2 | 1 | 2 | 3 | 1 | 4 | 5 | 3 | 1 | 4 | 4 | 5 | 1 | 5 | 5 | 3 | 4 | 5 | 2 | 5 | 1 | 1 | 3 | 4 | 1 | 3 | 3 | 5 | 2 | 5 | 4 | 2 | 5 | 5 | 1 | 3 | 1 | 2 | 5 | 5 | 3
13 | 21 | 14 | 24 | 39 | 50 | 68 | 84 | 95 | 110 | 119 | 131 | 143 | 159 | 172 | 5 | 2 | 4 | 3 | 5 | 2 | 1 | 2 | 3 | 4 | 5 | 3 | 2 | 1 | 5 | 3 | 5 | 5 | 3 | 5 | 3 | 5 | 3 | 5 | 2 | 4 | 1 | 4 | 2 | 5 | 3 | 5 | 4 | 1 | 3 | 1 | 3 | 3 | 2 | 4 | 3 | 2 | 3 | 4 | 2 | 5 | 4 | 5 | 4 | 2 | 5 | 2
14 | 13 | 9 | 19 | 29 | 45 | 60 | 75 | 90 | 102 | 114 | 125 | 139 | 148 | 161 | 2 | 4 | 1 | 2 | 3 | 1 | 3 | 3 | 3 | 2 | 3 | 2 | 5 | 3 | 5 | 3 | 4 | 3 | 5 | 3 | 4 | 5 | 1 | 5 | 4 | 4 | 4 | 3 | 5 | 2 | 2 | 3 | 1 | 3 | 5 | 3 | 3 | 2 | 4 | 2 | 3 | 5 | 1 | 5 | 2 | 1 | 4 | 2 | 1 | 5 | 3 | 4
15 | 11 | 7 | 18 | 28 | 40 | 54 | 66 | 78 | 93 | 104 | 116 | 136 | 148 | 161 | 1 | 3 | 1 | 2 | 1 | 3 | 5 | 2 | 5 | 1 | 3 | 1 | 1 | 5 | 4 | 2 | 5 | 3 | 5 | 1 | 4 | 4 | 1 | 3 | 5 | 1 | 5 | 1 | 4 | 3 | 4 | 4 | 4 | 2 | 1 | 4 | 4 | 1 | 4 | 3 | 5 | 5 | 5 | 5 | 5 | 2 | 4 | 1 | 3 | 3 | 5 | 2
16 | 17 | 15 | 25 | 33 | 41 | 50 | 63 | 75 | 86 | 97 | 106 | 117 | 128 | 140 | 5 | 5 | 3 | 2 | 1 | 1 | 3 | 5 | 2 | 1 | 3 | 2 | 2 | 3 | 2 | 1 | 4 | 3 | 1 | 1 | 5 | 2 | 1 | 5 | 2 | 4 | 2 | 4 | 3 | 2 | 4 | 2 | 2 | 2 | 2 | 5 | 1 | 3 | 3 | 2 | 2 | 3 | 3 | 3 | 1 | 5 | 3 | 2 | 2 | 2 | 3 | 5
17 | 14 | 10 | 18 | 30 | 37 | 48 | 61 | 72 | 84 | 95 | 106 | 117 | 132 | 145 | 2 | 4 | 2 | 2 | 2 | 2 | 3 | 1 | 2 | 4 | 2 | 4 | 1 | 1 | 4 | 1 | 2 | 4 | 3 | 2 | 4 | 2 | 3 | 4 | 2 | 1 | 4 | 4 | 2 | 3 | 4 | 3 | 2 | 3 | 2 | 4 | 1 | 5 | 1 | 4 | 3 | 3 | 3 | 2 | 3 | 4 | 5 | 3 | 3 | 5 | 4 | 1
18 | 14 | 12 | 19 | 32 | 50 | 57 | 64 | 76 | 92 | 98 | 111 | 119 | 132 | 141 | 2 | 5 | 4 | 1 | 1 | 1 | 2 | 3 | 3 | 1 | 5 | 4 | 4 | 4 | 5 | 5 | 1 | 2 | 1 | 3 | 2 | 2 | 2 | 1 | 5 | 3 | 3 | 1 | 3 | 5 | 3 | 5 | 1 | 1 | 1 | 3 | 5 | 2 | 5 | 1 | 4 | 1 | 1 | 2 | 4 | 4 | 2 | 3 | 5 | 1 | 1 | 2
19 | 16 | 8 | 24 | 33 | 43 | 57 | 70 | 85 | 97 | 112 | 121 | 131 | 144 | 158 | 1 | 3 | 2 | 2 | 5 | 3 | 4 | 4 | 1 | 2 | 5 | 1 | 1 | 2 | 5 | 2 | 2 | 2 | 5 | 5 | 4 | 5 | 1 | 3 | 4 | 5 | 2 | 4 | 5 | 2 | 3 | 2 | 1 | 5 | 5 | 4 | 1 | 4 | 1 | 3 | 3 | 4 | 1 | 2 | 5 | 1 | 4 | 3 | 3 | 2 | 5 | 4
20 | 14 | 8 | 21 | 34 | 47 | 60 | 76 | 86 | 103 | 112 | 121 | 133 | 142 | 155 | 4 | 2 | 1 | 1 | 5 | 1 | 2 | 5 | 2 | 4 | 5 | 2 | 5 | 2 | 2 | 4 | 5 | 3 | 4 | 1 | 5 | 4 | 5 | 2 | 1 | 4 | 2 | 3 | 4 | 4 | 4 | 5 | 1 | 2 | 2 | 4 | 1 | 1 | 2 | 5 | 3 | 1 | 3 | 5 | 2 | 5 | 1 | 1 | 5 | 4 | 3 | 1
21 | 22 | 16 | 30 | 46 | 53 | 69 | 83 | 96 | 114 | 127 | 142 | 156 | 170 | 184 | 3 | 5 | 4 | 4 | 4 | 2 | 3 | 5 | 3 | 5 | 5 | 3 | 3 | 2 | 1 | 1 | 2 | 5 | 4 | 5 | 3 | 4 | 3 | 4 | 4 | 3 | 5 | 1 | 4 | 4 | 5 | 5 | 1 | 4 | 4 | 4 | 5 | 3 | 2 | 5 | 5 | 5 | 2 | 2 | 5 | 2 | 2 | 5 | 2 | 5 | 3 | 4
22 | 15 | 10 | 21 | 32 | 44 | 51 | 61 | 72 | 87 | 102 | 118 | 132 | 142 | 155 | 2 | 1 | 3 | 4 | 2 | 3 | 2 | 4 | 2 | 2 | 4 | 3 | 3 | 2 | 4 | 3 | 2 | 1 | 1 | 3 | 4 | 3 | 2 | 1 | 3 | 2 | 3 | 3 | 5 | 3 | 5 | 2 | 5 | 3 | 4 | 3 | 5 | 5 | 4 | 2 | 4 | 2 | 3 | 5 | 1 | 2 | 2 | 5 | 3 | 3 | 4 | 3
23 | 18 | 11 | 24 | 33 | 43 | 54 | 63 | 76 | 90 | 106 | 117 | 129 | 139 | 153 | 3 | 5 | 1 | 2 | 4 | 3 | 4 | 2 | 4 | 1 | 2 | 2 | 1 | 5 | 1 | 3 | 2 | 3 | 1 | 5 | 5 | 1 | 2 | 1 | 3 | 2 | 3 | 5 | 2 | 5 | 3 | 4 | 2 | 4 | 5 | 5 | 2 | 2 | 2 | 5 | 4 | 1 | 2 | 5 | 2 | 5 | 2 | 1 | 2 | 5 | 2 | 5
24 | 20 | 14 | 25 | 36 | 46 | 62 | 77 | 89 | 99 | 105 | 119 | 132 | 142 | 154 | 4 | 1 | 5 | 4 | 2 | 4 | 3 | 2 | 4 | 1 | 1 | 5 | 4 | 2 | 1 | 3 | 4 | 3 | 4 | 5 | 4 | 4 | 2 | 5 | 2 | 4 | 1 | 5 | 2 | 2 | 4 | 2 | 1 | 2 | 2 | 1 | 4 | 5 | 3 | 2 | 5 | 1 | 5 | 2 | 1 | 3 | 3 | 3 | 2 | 1 | 4 | 5
25 | 21 | 14 | 27 | 38 | 55 | 66 | 83 | 96 | 102 | 113 | 125 | 133 | 143 | 155 | 5 | 5 | 2 | 2 | 2 | 5 | 1 | 5 | 1 | 5 | 1 | 4 | 4 | 4 | 4 | 5 | 3 | 3 | 3 | 2 | 4 | 5 | 4 | 4 | 1 | 4 | 5 | 3 | 3 | 1 | 1 | 1 | 1 | 2 | 4 | 4 | 5 | 3 | 1 | 3 | 2 | 1 | 1 | 4 | 3 | 1 | 2 | 4 | 1 | 5 | 5 | 1
26 | 14 | 8 | 22 | 28 | 45 | 58 | 72 | 84 | 97 | 110 | 118 | 131 | 141 | 150 | 3 | 2 | 2 | 1 | 2 | 4 | 4 | 4 | 1 | 1 | 2 | 2 | 3 | 4 | 5 | 5 | 4 | 4 | 3 | 2 | 5 | 4 | 4 | 1 | 5 | 2 | 4 | 1 | 3 | 5 | 4 | 1 | 5 | 5 | 2 | 1 | 1 | 3 | 3 | 1 | 5 | 1 | 3 | 4 | 5 | 1 | 2 | 2 | 2 | 1 | 2 | 4
27 | 11 | 7 | 17 | 32 | 44 | 55 | 68 | 75 | 83 | 97 | 109 | 122 | 133 | 144 | 1 | 1 | 1 | 4 | 3 | 1 | 1 | 5 | 5 | 5 | 4 | 1 | 2 | 2 | 5 | 3 | 2 | 3 | 3 | 3 | 4 | 3 | 3 | 3 | 1 | 1 | 1 | 4 | 2 | 2 | 3 | 1 | 3 | 2 | 4 | 5 | 1 | 2 | 4 | 5 | 5 | 5 | 1 | 2 | 5 | 1 | 4 | 1 | 2 | 3 | 1 | 5
28 | 23 | 17 | 29 | 40 | 54 | 64 | 78 | 91 | 109 | 116 | 129 | 141 | 149 | 160 | 5 | 5 | 5 | 2 | 4 | 2 | 2 | 4 | 3 | 1 | 3 | 4 | 5 | 5 | 2 | 2 | 3 | 2 | 1 | 4 | 3 | 3 | 4 | 4 | 5 | 5 | 2 | 1 | 5 | 3 | 5 | 5 | 3 | 2 | 1 | 1 | 3 | 3 | 5 | 2 | 1 | 4 | 2 | 5 | 1 | 5 | 1 | 1 | 3 | 1 | 3 | 4
29 | 20 | 17 | 30 | 44 | 54 | 67 | 76 | 84 | 96 | 108 | 117 | 128 | 139 | 151 | 5 | 4 | 5 | 3 | 1 | 2 | 5 | 5 | 5 | 2 | 4 | 3 | 5 | 2 | 2 | 1 | 1 | 4 | 3 | 5 | 4 | 2 | 2 | 1 | 1 | 3 | 1 | 3 | 4 | 1 | 4 | 3 | 4 | 2 | 5 | 1 | 5 | 1 | 1 | 2 | 3 | 5 | 1 | 2 | 1 | 2 | 3 | 5 | 5 | 5 | 1 | 1
30 | 15 | 10 | 18 | 37 | 49 | 58 | 72 | 86 | 95 | 109 | 118 | 134 | 148 | 158 | 4 | 1 | 4 | 1 | 1 | 4 | 2 | 1 | 5 | 4 | 5 | 5 | 1 | 1 | 5 | 5 | 4 | 1 | 2 | 2 | 5 | 3 | 1 | 5 | 4 | 4 | 3 | 3 | 3 | 1 | 3 | 2 | 3 | 5 | 2 | 4 | 2 | 1 | 3 | 3 | 5 | 3 | 4 | 4 | 3 | 2 | 4 | 5 | 3 | 3 | 2 | 2
31 | 12 | 5 | 17 | 32 | 44 | 54 | 62 | 77 | 95 | 108 | 114 | 129 | 142 | 153 | 1 | 2 | 1 | 1 | 5 | 2 | 2 | 3 | 5 | 2 | 3 | 5 | 2 | 1 | 4 | 5 | 2 | 1 | 3 | 4 | 2 | 4 | 1 | 1 | 3 | 4 | 5 | 3 | 5 | 5 | 3 | 5 | 3 | 1 | 5 | 4 | 1 | 2 | 1 | 2 | 5 | 5 | 4 | 1 | 3 | 4 | 5 | 1 | 4 | 3 | 2 | 2
32 | 16 | 11 | 19 | 29 | 37 | 51 | 67 | 76 | 87 | 98 | 114 | 123 | 134 | 146 | 3 | 1 | 4 | 3 | 3 | 2 | 2 | 1 | 2 | 5 | 1 | 2 | 2 | 1 | 1 | 4 | 1 | 5 | 5 | 3 | 5 | 2 | 4 | 5 | 2 | 1 | 2 | 4 | 1 | 2 | 5 | 3 | 3 | 2 | 2 | 4 | 3 | 5 | 5 | 3 | 1 | 5 | 1 | 2 | 4 | 3 | 3 | 1 | 1 | 3 | 5 | 3
33 | 16 | 14 | 19 | 33 | 44 | 62 | 76 | 92 | 104 | 119 | 136 | 149 | 164 | 177 | 4 | 1 | 4 | 5 | 1 | 1 | 1 | 2 | 1 | 5 | 5 | 3 | 3 | 3 | 1 | 4 | 4 | 5 | 4 | 5 | 3 | 4 | 2 | 5 | 5 | 5 | 1 | 5 | 5 | 1 | 4 | 2 | 4 | 4 | 4 | 3 | 4 | 4 | 5 | 4 | 3 | 3 | 2 | 5 | 5 | 4 | 1 | 5 | 3 | 3 | 5 | 2
34 | 12 | 6 | 17 | 31 | 41 | 53 | 66 | 80 | 91 | 103 | 107 | 117 | 127 | 141 | 3 | 1 | 1 | 1 | 4 | 2 | 4 | 1 | 3 | 3 | 5 | 3 | 3 | 1 | 1 | 5 | 1 | 3 | 4 | 4 | 1 | 5 | 3 | 4 | 2 | 3 | 5 | 4 | 3 | 3 | 4 | 1 | 2 | 4 | 3 | 3 | 1 | 1 | 1 | 1 | 3 | 4 | 2 | 1 | 2 | 1 | 2 | 5 | 2 | 4 | 4 | 4
35 | 14 | 9 | 24 | 38 | 51 | 62 | 75 | 85 | 97 | 111 | 124 | 138 | 144 | 151 | 1 | 3 | 4 | 1 | 1 | 4 | 5 | 5 | 5 | 1 | 3 | 5 | 1 | 3 | 5 | 4 | 2 | 4 | 1 | 4 | 5 | 3 | 4 | 1 | 4 | 3 | 2 | 1 | 3 | 2 | 2 | 5 | 4 | 5 | 1 | 4 | 3 | 4 | 5 | 1 | 2 | 5 | 4 | 3 | 2 | 1 | 1 | 2 | 3 | 2 | 1 | 1
36 | 17 | 8 | 23 | 35 | 44 | 57 | 65 | 75 | 91 | 104 | 115 | 132 | 148 | 163 | 1 | 1 | 4 | 2 | 4 | 5 | 3 | 3 | 2 | 4 | 1 | 5 | 1 | 3 | 4 | 1 | 4 | 4 | 4 | 1 | 1 | 4 | 1 | 2 | 5 | 1 | 2 | 2 | 4 | 5 | 3 | 4 | 3 | 2 | 3 | 5 | 3 | 2 | 2 | 4 | 5 | 5 | 3 | 4 | 3 | 4 | 4 | 5 | 3 | 4 | 3 | 5
37 | 11 | 7 | 19 | 30 | 46 | 60 | 74 | 85 | 93 | 106 | 112 | 124 | 135 | 144 | 2 | 2 | 2 | 1 | 3 | 1 | 3 | 5 | 2 | 5 | 3 | 1 | 3 | 3 | 5 | 5 | 3 | 5 | 4 | 2 | 3 | 5 | 2 | 4 | 5 | 1 | 1 | 4 | 1 | 1 | 3 | 3 | 4 | 4 | 2 | 3 | 1 | 3 | 1 | 1 | 4 | 2 | 2 | 4 | 3 | 2 | 3 | 3 | 3 | 1 | 4 | 1
38 | 15 | 11 | 20 | 35 | 52 | 60 | 78 | 89 | 104 | 113 | 128 | 141 | 152 | 163 | 3 | 1 | 2 | 5 | 2 | 2 | 3 | 2 | 5 | 3 | 5 | 2 | 3 | 4 | 5 | 5 | 1 | 5 | 1 | 1 | 5 | 5 | 4 | 4 | 5 | 1 | 4 | 1 | 5 | 4 | 1 | 5 | 2 | 3 | 2 | 2 | 5 | 5 | 3 | 2 | 4 | 4 | 1 | 4 | 2 | 1 | 3 | 5 | 2 | 5 | 2 | 2
39 | 19 | 15 | 27 | 37 | 47 | 54 | 67 | 76 | 86 | 100 | 116 | 129 | 137 | 151 | 4 | 5 | 3 | 3 | 1 | 3 | 3 | 5 | 2 | 1 | 2 | 5 | 2 | 1 | 5 | 2 | 2 | 2 | 2 | 1 | 5 | 3 | 3 | 2 | 1 | 2 | 5 | 1 | 3 | 1 | 1 | 5 | 5 | 3 | 1 | 5 | 5 | 5 | 5 | 1 | 5 | 1 | 3 | 4 | 5 | 1 | 1 | 1 | 4 | 4 | 4 | 2
40 | 17 | 8 | 19 | 26 | 38 | 48 | 60 | 66 | 78 | 92 | 110 | 120 | 138 | 150 | 1 | 2 | 2 | 3 | 5 | 4 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 5 | 1 | 5 | 1 | 2 | 2 | 5 | 4 | 4 | 2 | 2 | 1 | 1 | 1 | 3 | 3 | 4 | 3 | 2 | 4 | 5 | 2 | 3 | 3 | 5 | 5 | 5 | 2 | 2 | 4 | 2 | 5 | 4 | 5 | 4 | 5 | 4 | 1 | 2
41 | 18 | 11 | 25 | 36 | 49 | 57 | 72 | 89 | 104 | 114 | 126 | 137 | 151 | 158 | 2 | 2 | 4 | 3 | 3 | 4 | 3 | 4 | 4 | 3 | 1 | 3 | 3 | 3 | 4 | 3 | 2 | 3 | 1 | 2 | 5 | 5 | 2 | 3 | 2 | 5 | 5 | 5 | 5 | 1 | 4 | 5 | 2 | 5 | 1 | 2 | 3 | 3 | 5 | 1 | 4 | 2 | 2 | 3 | 3 | 4 | 3 | 4 | 3 | 1 | 2 | 1
42 | 17 | 12 | 23 | 30 | 40 | 52 | 58 | 68 | 82 | 96 | 112 | 123 | 139 | 150 | 4 | 5 | 2 | 1 | 4 | 1 | 3 | 3 | 2 | 1 | 2 | 2 | 1 | 5 | 3 | 1 | 3 | 2 | 5 | 2 | 1 | 3 | 1 | 1 | 3 | 2 | 1 | 4 | 4 | 4 | 1 | 5 | 5 | 2 | 4 | 3 | 3 | 4 | 4 | 5 | 1 | 5 | 1 | 4 | 3 | 5 | 5 | 3 | 3 | 4 | 3 | 1
43 | 13 | 7 | 20 | 31 | 41 | 49 | 66 | 77 | 88 | 98 | 112 | 123 | 132 | 144 | 1 | 3 | 2 | 1 | 3 | 3 | 2 | 5 | 3 | 5 | 1 | 2 | 5 | 1 | 1 | 3 | 3 | 1 | 1 | 3 | 5 | 4 | 4 | 4 | 3 | 3 | 3 | 2 | 1 | 3 | 4 | 3 | 1 | 5 | 1 | 3 | 1 | 5 | 4 | 4 | 2 | 5 | 3 | 1 | 1 | 2 | 5 | 1 | 4 | 3 | 3 | 2
44 | 15 | 8 | 24 | 36 | 43 | 54 | 63 | 78 | 90 | 96 | 110 | 126 | 137 | 153 | 1 | 1 | 1 | 5 | 2 | 5 | 4 | 5 | 4 | 4 | 1 | 3 | 2 | 2 | 1 | 2 | 2 | 3 | 3 | 3 | 1 | 2 | 5 | 1 | 3 | 3 | 5 | 4 | 1 | 2 | 4 | 5 | 2 | 1 | 1 | 2 | 5 | 5 | 2 | 2 | 5 | 5 | 1 | 5 | 3 | 2 | 1 | 5 | 5 | 4 | 3 | 4
45 | 18 | 12 | 24 | 37 | 50 | 56 | 62 | 72 | 82 | 94 | 103 | 114 | 125 | 137 | 4 | 4 | 1 | 3 | 4 | 2 | 1 | 5 | 3 | 5 | 3 | 2 | 3 | 4 | 1 | 5 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 2 | 1 | 2 | 5 | 4 | 2 | 3 | 1 | 5 | 2 | 2 | 3 | 1 | 3 | 4 | 1 | 2 | 1 | 3 | 5 | 4 | 2 | 3 | 2 | 4 | 2 | 2 | 4
46 | 19 | 12 | 22 | 30 | 42 | 54 | 63 | 78 | 89 | 99 | 113 | 121 | 133 | 145 | 2 | 3 | 4 | 3 | 5 | 2 | 2 | 1 | 1 | 2 | 3 | 2 | 4 | 3 | 4 | 1 | 2 | 4 | 1 | 5 | 2 | 1 | 5 | 1 | 5 | 5 | 1 | 4 | 4 | 2 | 2 | 3 | 4 | 1 | 3 | 2 | 4 | 2 | 5 | 3 | 1 | 2 | 3 | 2 | 1 | 3 | 4 | 4 | 2 | 3 | 5 | 2
47 | 17 | 10 | 25 | 34 | 52 | 63 | 74 | 79 | 95 | 108 | 116 | 128 | 146 | 157 | 2 | 2 | 2 | 4 | 4 | 3 | 5 | 3 | 1 | 3 | 3 | 2 | 5 | 5 | 5 | 3 | 1 | 4 | 1 | 5 | 3 | 3 | 3 | 2 | 1 | 2 | 1 | 1 | 4 | 5 | 2 | 5 | 4 | 3 | 2 | 4 | 5 | 1 | 1 | 1 | 5 | 2 | 1 | 4 | 5 | 5 | 5 | 3 | 1 | 2 | 3 | 5
48 | 16 | 14 | 21 | 33 | 45 | 58 | 75 | 82 | 95 | 105 | 114 | 125 | 134 | 148 | 5 | 2 | 2 | 5 | 1 | 1 | 3 | 2 | 5 | 4 | 2 | 1 | 4 | 2 | 3 | 3 | 5 | 2 | 1 | 5 | 5 | 5 | 4 | 3 | 2 | 2 | 1 | 2 | 1 | 5 | 5 | 2 | 4 | 2 | 3 | 1 | 5 | 2 | 1 | 1 | 2 | 5 | 2 | 2 | 2 | 4 | 2 | 1 | 5 | 4 | 3 | 2
49 | 17 | 10 | 24 | 35 | 42 | 58 | 70 | 83 | 97 | 111 | 125 | 136 | 149 | 162 | 5 | 1 | 1 | 3 | 2 | 5 | 2 | 5 | 3 | 2 | 1 | 5 | 3 | 1 | 2 | 1 | 5 | 3 | 5 | 3 | 2 | 4 | 5 | 1 | 4 | 1 | 4 | 4 | 5 | 4 | 4 | 1 | 4 | 4 | 4 | 2 | 4 | 3 | 5 | 2 | 3 | 2 | 5 | 1 | 2 | 3 | 5 | 3 | 3 | 3 | 5 | 2
50 | 17 | 9 | 22 | 37 | 48 | 58 | 72 | 84 | 97 | 108 | 119 | 131 | 144 | 153 | 1 | 3 | 3 | 2 | 3 | 5 | 4 | 1 | 5 | 1 | 4 | 5 | 2 | 1 | 5 | 3 | 2 | 3 | 4 | 1 | 2 | 5 | 2 | 5 | 1 | 4 | 5 | 2 | 5 | 2 | 2 | 4 | 5 | 1 | 4 | 1 | 4 | 1 | 4 | 2 | 3 | 5 | 2 | 2 | 5 | 2 | 3 | 3 | 4 | 1 | 3 | 1
51 | 18 | 12 | 22 | 34 | 47 | 60 | 73 | 84 | 97 | 110 | 126 | 136 | 149 | 167 | 4 | 3 | 2 | 3 | 2 | 4 | 1 | 3 | 1 | 5 | 3 | 3 | 2 | 5 | 1 | 5 | 5 | 3 | 4 | 1 | 4 | 3 | 3 | 3 | 1 | 4 | 2 | 4 | 5 | 2 | 5 | 1 | 3 | 5 | 3 | 2 | 5 | 4 | 5 | 2 | 1 | 3 | 1 | 5 | 2 | 4 | 3 | 4 | 5 | 5 | 4 | 4
52 | 24 | 15 | 29 | 36 | 49 | 65 | 79 | 94 | 106 | 118 | 134 | 150 | 166 | 178 | 4 | 3 | 5 | 3 | 4 | 5 | 3 | 2 | 1 | 1 | 1 | 4 | 4 | 3 | 4 | 2 | 4 | 2 | 5 | 5 | 4 | 5 | 4 | 1 | 5 | 5 | 3 | 2 | 1 | 2 | 4 | 5 | 5 | 3 | 1 | 3 | 4 | 2 | 5 | 5 | 5 | 2 | 4 | 5 | 1 | 5 | 5 | 5 | 5 | 1 | 3 | 3
53 | 18 | 16 | 23 | 41 | 52 | 65 | 77 | 88 | 98 | 113 | 122 | 132 | 146 | 160 | 5 | 5 | 2 | 4 | 1 | 1 | 3 | 2 | 5 | 5 | 5 | 3 | 1 | 1 | 4 | 5 | 4 | 5 | 1 | 3 | 4 | 3 | 4 | 1 | 4 | 2 | 1 | 4 | 3 | 1 | 4 | 2 | 2 | 5 | 5 | 3 | 2 | 4 | 2 | 1 | 4 | 1 | 2 | 3 | 5 | 4 | 1 | 4 | 5 | 1 | 3 | 5
54 | 20 | 13 | 25 | 36 | 47 | 56 | 68 | 77 | 86 | 102 | 114 | 123 | 136 | 147 | 2 | 5 | 4 | 2 | 3 | 4 | 2 | 3 | 3 | 1 | 4 | 3 | 4 | 2 | 1 | 4 | 2 | 3 | 2 | 2 | 4 | 5 | 2 | 1 | 2 | 4 | 1 | 2 | 5 | 2 | 1 | 1 | 4 | 5 | 3 | 4 | 4 | 3 | 4 | 1 | 1 | 3 | 3 | 2 | 2 | 1 | 5 | 5 | 3 | 1 | 4 | 3
55 | 19 | 12 | 22 | 34 | 43 | 58 | 73 | 90 | 100 | 115 | 127 | 135 | 146 | 155 | 2 | 2 | 3 | 5 | 4 | 3 | 2 | 1 | 3 | 4 | 2 | 3 | 1 | 2 | 4 | 2 | 1 | 5 | 5 | 4 | 4 | 5 | 1 | 5 | 4 | 5 | 3 | 5 | 2 | 2 | 2 | 4 | 5 | 5 | 2 | 3 | 2 | 5 | 1 | 4 | 1 | 1 | 4 | 2 | 5 | 4 | 1 | 1 | 3 | 1 | 2 | 3
56 | 20 | 14 | 24 | 34 | 47 | 66 | 80 | 96 | 106 | 118 | 123 | 132 | 145 | 158 | 3 | 5 | 1 | 5 | 1 | 5 | 2 | 2 | 2 | 3 | 4 | 1 | 5 | 2 | 4 | 2 | 5 | 5 | 5 | 4 | 3 | 4 | 3 | 4 | 4 | 5 | 2 | 5 | 3 | 4 | 2 | 1 | 3 | 5 | 3 | 1 | 1 | 2 | 1 | 1 | 5 | 1 | 2 | 1 | 5 | 2 | 3 | 3 | 4 | 2 | 3 | 4
57 | 23 | 19 | 30 | 40 | 53 | 64 | 76 | 89 | 105 | 112 | 124 | 137 | 157 | 172 | 5 | 5 | 5 | 4 | 3 | 1 | 3 | 4 | 4 | 1 | 4 | 1 | 5 | 4 | 1 | 3 | 1 | 5 | 3 | 2 | 5 | 3 | 3 | 1 | 5 | 2 | 1 | 5 | 5 | 1 | 5 | 5 | 1 | 2 | 1 | 3 | 1 | 4 | 5 | 2 | 5 | 1 | 2 | 5 | 5 | 5 | 5 | 5 | 1 | 5 | 4 | 5
58 | 20 | 12 | 26 | 41 | 49 | 62 | 71 | 76 | 90 | 97 | 112 | 122 | 132 | 142 | 2 | 5 | 4 | 1 | 4 | 4 | 1 | 5 | 4 | 2 | 4 | 5 | 2 | 1 | 4 | 1 | 4 | 1 | 3 | 5 | 1 | 1 | 2 | 5 | 1 | 1 | 2 | 1 | 5 | 1 | 4 | 4 | 2 | 2 | 2 | 1 | 4 | 2 | 4 | 5 | 2 | 2 | 2 | 4 | 1 | 3 | 1 | 5 | 2 | 2 | 2 | 4
59 | 20 | 16 | 26 | 36 | 45 | 59 | 69 | 82 | 87 | 99 | 109 | 123 | 135 | 146 | 5 | 5 | 2 | 4 | 2 | 2 | 5 | 1 | 2 | 2 | 2 | 4 | 1 | 1 | 5 | 2 | 2 | 3 | 4 | 5 | 4 | 1 | 2 | 3 | 3 | 4 | 4 | 2 | 1 | 2 | 1 | 1 | 4 | 2 | 5 | 1 | 2 | 1 | 4 | 3 | 3 | 5 | 1 | 5 | 5 | 1 | 1 | 5 | 4 | 3 | 3 | 1
60 | 17 | 10 | 24 | 37 | 46 | 57 | 63 | 74 | 89 | 96 | 111 | 119 | 133 | 146 | 2 | 2 | 3 | 3 | 5 | 2 | 4 | 3 | 2 | 4 | 3 | 4 | 2 | 2 | 3 | 2 | 2 | 5 | 1 | 3 | 1 | 2 | 1 | 2 | 1 | 5 | 3 | 2 | 5 | 3 | 5 | 2 | 1 | 3 | 1 | 2 | 5 | 4 | 1 | 5 | 1 | 4 | 2 | 1 | 1 | 5 | 5 | 3 | 5 | 3 | 3 | 2
61 | 20 | 13 | 29 | 41 | 52 | 69 | 83 | 96 | 111 | 123 | 133 | 139 | 146 | 157 | 4 | 3 | 5 | 1 | 2 | 5 | 4 | 5 | 3 | 1 | 4 | 4 | 3 | 1 | 4 | 3 | 4 | 4 | 4 | 5 | 5 | 4 | 1 | 4 | 3 | 5 | 4 | 1 | 5 | 4 | 4 | 2 | 1 | 3 | 5 | 3 | 3 | 1 | 1 | 5 | 1 | 2 | 1 | 2 | 1 | 1 | 3 | 2 | 1 | 4 | 4 | 2
62 | 16 | 13 | 19 | 34 | 48 | 60 | 71 | 85 | 96 | 112 | 125 | 139 | 151 | 167 | 4 | 4 | 1 | 4 | 1 | 2 | 1 | 2 | 5 | 4 | 2 | 4 | 3 | 5 | 2 | 4 | 4 | 5 | 1 | 2 | 1 | 4 | 1 | 5 | 5 | 2 | 2 | 5 | 2 | 1 | 4 | 4 | 4 | 2 | 5 | 5 | 3 | 4 | 3 | 3 | 5 | 3 | 5 | 1 | 1 | 5 | 5 | 1 | 4 | 2 | 5 | 5
63 | 14 | 9 | 21 | 30 | 42 | 55 | 62 | 73 | 84 | 92 | 105 | 123 | 133 | 146 | 1 | 1 | 3 | 4 | 3 | 2 | 5 | 2 | 2 | 2 | 1 | 4 | 1 | 4 | 2 | 5 | 2 | 3 | 4 | 4 | 2 | 2 | 2 | 1 | 2 | 4 | 1 | 4 | 2 | 3 | 2 | 4 | 4 | 2 | 1 | 1 | 1 | 2 | 5 | 5 | 4 | 5 | 5 | 4 | 4 | 3 | 2 | 1 | 4 | 4 | 3 | 2
64 | 18 | 10 | 28 | 37 | 50 | 61 | 70 | 82 | 92 | 102 | 110 | 121 | 132 | 142 | 5 | 1 | 2 | 2 | 3 | 5 | 5 | 5 | 3 | 1 | 1 | 4 | 4 | 2 | 4 | 3 | 2 | 3 | 1 | 5 | 1 | 2 | 1 | 5 | 4 | 1 | 4 | 3 | 1 | 3 | 3 | 3 | 3 | 1 | 1 | 5 | 3 | 1 | 3 | 1 | 1 | 2 | 4 | 4 | 4 | 2 | 1 | 4 | 4 | 3 | 1 | 2
65 | 22 | 16 | 31 | 44 | 55 | 65 | 73 | 83 | 98 | 110 | 120 | 129 | 140 | 151 | 2 | 4 | 5 | 5 | 5 | 1 | 4 | 5 | 3 | 4 | 1 | 5 | 2 | 3 | 2 | 4 | 3 | 1 | 4 | 2 | 4 | 1 | 1 | 2 | 4 | 1 | 1 | 4 | 3 | 3 | 5 | 4 | 4 | 3 | 1 | 4 | 1 | 5 | 1 | 3 | 1 | 4 | 2 | 2 | 3 | 1 | 5 | 2 | 1 | 5 | 2 | 3
66 | 17 | 12 | 24 | 33 | 44 | 60 | 75 | 90 | 104 | 113 | 124 | 135 | 148 | 159 | 2 | 5 | 2 | 3 | 4 | 1 | 3 | 4 | 2 | 2 | 1 | 4 | 5 | 1 | 3 | 2 | 3 | 5 | 5 | 3 | 2 | 4 | 5 | 4 | 4 | 2 | 4 | 5 | 5 | 4 | 1 | 4 | 1 | 2 | 3 | 3 | 4 | 4 | 2 | 1 | 1 | 3 | 5 | 2 | 2 | 4 | 4 | 3 | 2 | 1 | 4 | 4
67 | 15 | 12 | 21 | 27 | 40 | 54 | 67 | 77 | 85 | 98 | 107 | 119 | 129 | 140 | 5 | 5 | 1 | 1 | 1 | 2 | 5 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 5 | 4 | 3 | 4 | 3 | 4 | 3 | 2 | 4 | 4 | 4 | 1 | 3 | 2 | 2 | 2 | 1 | 3 | 2 | 5 | 1 | 5 | 3 | 3 | 1 | 2 | 4 | 2 | 4 | 2 | 4 | 1 | 3 | 2 | 4 | 4 | 1 | 2
68 | 19 | 14 | 23 | 33 | 45 | 53 | 63 | 76 | 91 | 100 | 117 | 128 | 138 | 149 | 2 | 3 | 4 | 5 | 3 | 2 | 2 | 2 | 5 | 2 | 1 | 2 | 3 | 2 | 3 | 4 | 3 | 1 | 3 | 1 | 2 | 4 | 3 | 1 | 5 | 5 | 2 | 1 | 4 | 4 | 4 | 3 | 1 | 2 | 5 | 1 | 4 | 5 | 5 | 3 | 4 | 1 | 1 | 5 | 2 | 1 | 3 | 4 | 1 | 3 | 3 | 4
69 | 22 | 14 | 30 | 40 | 54 | 65 | 78 | 88 | 96 | 110 | 123 | 134 | 139 | 147 | 5 | 3 | 3 | 3 | 4 | 4 | 5 | 3 | 1 | 5 | 3 | 1 | 3 | 5 | 4 | 2 | 5 | 2 | 1 | 3 | 5 | 2 | 5 | 1 | 1 | 4 | 1 | 4 | 4 | 2 | 1 | 1 | 3 | 5 | 5 | 1 | 1 | 4 | 5 | 3 | 3 | 3 | 1 | 4 | 1 | 1 | 1 | 2 | 1 | 5 | 1 | 1
70 | 27 | 17 | 31 | 49 | 61 | 74 | 88 | 103 | 116 | 129 | 133 | 143 | 157 | 170 | 4 | 5 | 3 | 5 | 5 | 5 | 3 | 1 | 4 | 4 | 5 | 5 | 1 | 4 | 5 | 2 | 4 | 4 | 3 | 2 | 5 | 4 | 3 | 2 | 2 | 5 | 3 | 5 | 4 | 1 | 5 | 3 | 4 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 5 | 3 | 2 | 3 | 5 | 4 | 4 | 4 | 2 | 3
71 | 16 | 14 | 22 | 39 | 51 | 63 | 74 | 83 | 92 | 101 | 111 | 124 | 140 | 154 | 1 | 4 | 5 | 4 | 1 | 1 | 2 | 4 | 5 | 2 | 5 | 5 | 4 | 2 | 4 | 2 | 2 | 2 | 5 | 3 | 4 | 1 | 2 | 4 | 1 | 2 | 2 | 4 | 4 | 3 | 1 | 1 | 2 | 3 | 2 | 2 | 3 | 3 | 3 | 1 | 3 | 2 | 3 | 5 | 3 | 5 | 3 | 5 | 4 | 4 | 4 | 2
72 | 14 | 7 | 22 | 33 | 49 | 61 | 66 | 75 | 86 | 94 | 106 | 118 | 131 | 148 | 1 | 2 | 3 | 1 | 4 | 3 | 4 | 4 | 4 | 1 | 4 | 2 | 5 | 5 | 5 | 1 | 5 | 4 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 5 | 2 | 1 | 4 | 3 | 1 | 3 | 1 | 3 | 1 | 3 | 4 | 1 | 5 | 2 | 4 | 3 | 4 | 1 | 2 | 1 | 5 | 5 | 5 | 2 | 5 | 5
73 | 16 | 13 | 22 | 33 | 46 | 59 | 72 | 89 | 101 | 118 | 133 | 149 | 165 | 177 | 5 | 1 | 3 | 4 | 2 | 1 | 2 | 4 | 1 | 5 | 1 | 4 | 3 | 4 | 4 | 2 | 2 | 4 | 2 | 5 | 5 | 3 | 1 | 4 | 4 | 5 | 5 | 3 | 1 | 4 | 3 | 4 | 5 | 4 | 5 | 3 | 5 | 1 | 4 | 5 | 4 | 5 | 5 | 2 | 4 | 5 | 5 | 2 | 2 | 3 | 3 | 4
74 | 14 | 12 | 19 | 31 | 42 | 58 | 65 | 77 | 85 | 100 | 113 | 124 | 132 | 141 | 3 | 1 | 5 | 3 | 1 | 1 | 1 | 4 | 2 | 4 | 3 | 3 | 2 | 4 | 2 | 3 | 5 | 5 | 4 | 2 | 4 | 1 | 1 | 1 | 4 | 2 | 5 | 1 | 1 | 1 | 4 | 2 | 5 | 3 | 2 | 5 | 2 | 5 | 5 | 1 | 3 | 4 | 2 | 2 | 1 | 4 | 2 | 1 | 3 | 2 | 3 | 1
75 | 23 | 15 | 28 | 43 | 56 | 67 | 77 | 87 | 94 | 107 | 124 | 133 | 144 | 158 | 1 | 4 | 5 | 5 | 5 | 3 | 2 | 3 | 5 | 4 | 2 | 4 | 4 | 3 | 4 | 2 | 1 | 1 | 5 | 4 | 3 | 2 | 4 | 1 | 3 | 1 | 2 | 4 | 2 | 2 | 2 | 1 | 3 | 4 | 4 | 2 | 4 | 5 | 5 | 3 | 3 | 4 | 1 | 1 | 3 | 5 | 2 | 1 | 4 | 5 | 4 | 1
76 | 9 | 5 | 17 | 26 | 36 | 45 | 57 | 72 | 81 | 94 | 106 | 118 | 135 | 148 | 1 | 1 | 1 | 2 | 2 | 2 | 4 | 4 | 2 | 5 | 1 | 1 | 1 | 5 | 2 | 2 | 1 | 3 | 4 | 1 | 4 | 2 | 4 | 2 | 1 | 5 | 4 | 5 | 4 | 2 | 1 | 2 | 3 | 5 | 1 | 4 | 1 | 5 | 3 | 3 | 4 | 4 | 2 | 2 | 5 | 4 | 3 | 5 | 3 | 3 | 2 | 5
77 | 12 | 9 | 19 | 34 | 46 | 63 | 73 | 88 | 103 | 115 | 132 | 149 | 165 | 181 | 2 | 2 | 4 | 1 | 2 | 1 | 4 | 3 | 4 | 3 | 5 | 3 | 5 | 4 | 1 | 2 | 4 | 4 | 4 | 5 | 2 | 4 | 1 | 3 | 3 | 5 | 2 | 5 | 4 | 2 | 4 | 5 | 1 | 4 | 5 | 2 | 5 | 5 | 5 | 2 | 5 | 4 | 4 | 4 | 3 | 5 | 5 | 3 | 4 | 3 | 5 | 4
78 | 21 | 14 | 28 | 41 | 57 | 68 | 76 | 89 | 104 | 118 | 136 | 149 | 156 | 163 | 1 | 4 | 5 | 4 | 4 | 3 | 2 | 5 | 1 | 5 | 5 | 2 | 4 | 4 | 3 | 5 | 5 | 2 | 2 | 2 | 3 | 1 | 3 | 1 | 1 | 5 | 3 | 4 | 5 | 4 | 1 | 5 | 4 | 2 | 3 | 5 | 4 | 5 | 4 | 5 | 5 | 1 | 2 | 5 | 2 | 1 | 1 | 3 | 1 | 2 | 1 | 3
79 | 21 | 16 | 27 | 41 | 51 | 60 | 71 | 83 | 95 | 111 | 126 | 136 | 146 | 158 | 4 | 5 | 3 | 4 | 1 | 4 | 5 | 1 | 5 | 2 | 2 | 5 | 3 | 1 | 5 | 1 | 1 | 2 | 4 | 2 | 4 | 2 | 2 | 3 | 4 | 3 | 1 | 4 | 5 | 1 | 3 | 3 | 5 | 2 | 5 | 4 | 3 | 3 | 4 | 5 | 5 | 1 | 1 | 3 | 1 | 3 | 3 | 3 | 5 | 3 | 1 | 3
80 | 21 | 14 | 27 | 36 | 47 | 65 | 80 | 91 | 109 | 124 | 141 | 152 | 160 | 169 | 5 | 5 | 3 | 1 | 4 | 3 | 1 | 5 | 3 | 2 | 2 | 2 | 1 | 1 | 5 | 4 | 5 | 4 | 5 | 4 | 2 | 4 | 5 | 4 | 1 | 4 | 5 | 1 | 5 | 5 | 4 | 4 | 5 | 5 | 2 | 3 | 5 | 2 | 5 | 5 | 2 | 2 | 5 | 2 | 1 | 1 | 2 | 4 | 4 | 1 | 2 | 2
81 | 13 | 7 | 23 | 34 | 46 | 58 | 72 | 81 | 93 | 99 | 114 | 131 | 149 | 158 | 1 | 2 | 2 | 2 | 5 | 1 | 5 | 5 | 4 | 2 | 1 | 4 | 5 | 3 | 2 | 2 | 3 | 3 | 4 | 2 | 2 | 5 | 2 | 5 | 2 | 2 | 3 | 2 | 1 | 3 | 3 | 5 | 1 | 3 | 1 | 1 | 3 | 5 | 4 | 3 | 4 | 3 | 5 | 5 | 3 | 5 | 5 | 5 | 2 | 2 | 2 | 3
82 | 18 | 11 | 25 | 38 | 49 | 65 | 74 | 86 | 100 | 116 | 123 | 131 | 142 | 156 | 1 | 4 | 3 | 3 | 4 | 3 | 2 | 5 | 3 | 5 | 3 | 2 | 2 | 4 | 2 | 3 | 5 | 4 | 5 | 2 | 5 | 1 | 1 | 2 | 5 | 2 | 3 | 2 | 4 | 2 | 3 | 5 | 3 | 4 | 5 | 4 | 1 | 4 | 1 | 1 | 2 | 3 | 2 | 1 | 1 | 3 | 5 | 2 | 3 | 1 | 5 | 5
83 | 14 | 9 | 20 | 34 | 49 | 59 | 73 | 85 | 97 | 111 | 124 | 138 | 150 | 159 | 1 | 1 | 4 | 3 | 1 | 4 | 2 | 4 | 3 | 5 | 5 | 1 | 2 | 5 | 3 | 5 | 5 | 1 | 2 | 2 | 5 | 3 | 2 | 4 | 5 | 3 | 2 | 2 | 5 | 1 | 2 | 4 | 2 | 5 | 2 | 5 | 4 | 4 | 4 | 1 | 3 | 4 | 5 | 2 | 5 | 1 | 5 | 1 | 1 | 2 | 3 | 3
84 | 16 | 10 | 26 | 37 | 50 | 63 | 80 | 91 | 100 | 110 | 121 | 130 | 141 | 152 | 1 | 3 | 4 | 2 | 2 | 4 | 5 | 5 | 2 | 1 | 3 | 5 | 1 | 3 | 5 | 4 | 1 | 4 | 4 | 4 | 4 | 3 | 5 | 5 | 5 | 3 | 1 | 2 | 2 | 3 | 2 | 2 | 1 | 3 | 3 | 3 | 4 | 1 | 3 | 3 | 2 | 3 | 2 | 2 | 3 | 2 | 2 | 4 | 2 | 2 | 4 | 3
85 | 17 | 12 | 22 | 35 | 44 | 51 | 62 | 76 | 93 | 104 | 118 | 136 | 147 | 166 | 4 | 2 | 2 | 4 | 4 | 1 | 1 | 4 | 4 | 4 | 2 | 3 | 1 | 4 | 1 | 3 | 4 | 1 | 1 | 1 | 4 | 1 | 1 | 5 | 4 | 3 | 2 | 5 | 5 | 5 | 3 | 4 | 3 | 1 | 2 | 5 | 5 | 2 | 4 | 3 | 4 | 4 | 5 | 5 | 3 | 2 | 1 | 5 | 5 | 5 | 4 | 5
86 | 10 | 5 | 12 | 23 | 35 | 43 | 56 | 64 | 75 | 88 | 103 | 118 | 128 | 142 | 1 | 1 | 2 | 1 | 4 | 1 | 1 | 1 | 1 | 3 | 5 | 2 | 3 | 3 | 4 | 2 | 2 | 1 | 1 | 4 | 3 | 3 | 4 | 3 | 3 | 1 | 3 | 1 | 5 | 1 | 2 | 3 | 3 | 5 | 4 | 1 | 4 | 3 | 5 | 3 | 4 | 5 | 5 | 1 | 2 | 5 | 2 | 1 | 4 | 2 | 3 | 5
87 | 20 | 14 | 23 | 37 | 47 | 58 | 69 | 78 | 92 | 101 | 113 | 123 | 133 | 144 | 3 | 4 | 3 | 4 | 1 | 5 | 1 | 2 | 3 | 4 | 2 | 5 | 5 | 2 | 2 | 1 | 2 | 1 | 5 | 3 | 1 | 2 | 3 | 5 | 5 | 1 | 2 | 1 | 3 | 2 | 4 | 5 | 1 | 3 | 1 | 4 | 4 | 2 | 1 | 5 | 1 | 1 | 5 | 3 | 2 | 3 | 1 | 4 | 4 | 2 | 3 | 2
88 | 17 | 12 | 22 | 28 | 41 | 57 | 68 | 81 | 95 | 108 | 119 | 128 | 135 | 148 | 2 | 2 | 5 | 3 | 2 | 3 | 3 | 2 | 1 | 2 | 2 | 1 | 4 | 2 | 3 | 4 | 5 | 5 | 5 | 1 | 4 | 4 | 2 | 1 | 2 | 3 | 4 | 4 | 4 | 2 | 3 | 5 | 3 | 1 | 5 | 4 | 2 | 5 | 3 | 1 | 1 | 2 | 2 | 4 | 1 | 3 | 2 | 1 | 3 | 2 | 5 | 3
89 | 16 | 10 | 22 | 33 | 50 | 62 | 72 | 78 | 88 | 99 | 108 | 117 | 131 | 146 | 2 | 2 | 3 | 3 | 1 | 5 | 4 | 2 | 1 | 2 | 4 | 4 | 5 | 5 | 2 | 5 | 2 | 3 | 5 | 2 | 1 | 2 | 2 | 5 | 1 | 3 | 1 | 1 | 3 | 1 | 1 | 5 | 3 | 1 | 5 | 2 | 2 | 3 | 3 | 1 | 3 | 3 | 2 | 1 | 1 | 4 | 5 | 4 | 5 | 2 | 3 | 5
90 | 12 | 9 | 20 | 30 | 45 | 56 | 69 | 77 | 95 | 113 | 128 | 138 | 155 | 168 | 1 | 3 | 1 | 4 | 1 | 2 | 5 | 3 | 3 | 1 | 2 | 4 | 3 | 5 | 2 | 5 | 5 | 1 | 3 | 2 | 2 | 3 | 3 | 5 | 1 | 2 | 4 | 1 | 4 | 5 | 5 | 4 | 4 | 4 | 5 | 5 | 5 | 4 | 5 | 1 | 1 | 2 | 2 | 5 | 5 | 5 | 2 | 5 | 3 | 1 | 4 | 5
91 | 19 | 13 | 21 | 33 | 45 | 56 | 69 | 83 | 95 | 108 | 122 | 135 | 148 | 155 | 2 | 5 | 2 | 4 | 5 | 1 | 1 | 1 | 5 | 1 | 4 | 2 | 3 | 3 | 2 | 4 | 3 | 1 | 5 | 2 | 5 | 3 | 4 | 1 | 3 | 1 | 5 | 5 | 3 | 2 | 5 | 2 | 4 | 2 | 4 | 3 | 5 | 3 | 4 | 2 | 2 | 3 | 3 | 5 | 2 | 5 | 2 | 4 | 2 | 1 | 1 | 3
92 | 18 | 12 | 24 | 41 | 56 | 69 | 81 | 90 | 105 | 121 | 136 | 145 | 157 | 166 | 1 | 5 | 3 | 3 | 5 | 1 | 2 | 4 | 5 | 5 | 3 | 4 | 3 | 5 | 4 | 3 | 1 | 5 | 4 | 3 | 1 | 5 | 2 | 4 | 1 | 1 | 4 | 3 | 4 | 4 | 5 | 2 | 4 | 5 | 2 | 5 | 3 | 3 | 5 | 4 | 1 | 4 | 2 | 2 | 5 | 2 | 4 | 1 | 1 | 1 | 3 | 4
93 | 20 | 10 | 23 | 34 | 49 | 59 | 69 | 83 | 96 | 103 | 116 | 127 | 142 | 150 | 4 | 2 | 2 | 2 | 5 | 5 | 1 | 2 | 5 | 3 | 1 | 2 | 5 | 5 | 3 | 2 | 1 | 2 | 3 | 4 | 1 | 3 | 5 | 1 | 3 | 5 | 2 | 4 | 1 | 4 | 5 | 3 | 2 | 3 | 1 | 1 | 2 | 5 | 5 | 1 | 2 | 2 | 2 | 5 | 3 | 4 | 4 | 4 | 4 | 1 | 2 | 1
94 | 15 | 12 | 19 | 33 | 45 | 55 | 65 | 81 | 87 | 100 | 112 | 126 | 139 | 146 | 4 | 3 | 2 | 3 | 2 | 1 | 3 | 1 | 4 | 2 | 5 | 3 | 4 | 4 | 1 | 3 | 3 | 3 | 1 | 3 | 3 | 3 | 2 | 2 | 4 | 5 | 2 | 5 | 1 | 1 | 1 | 3 | 4 | 3 | 4 | 2 | 2 | 4 | 2 | 4 | 1 | 5 | 3 | 5 | 3 | 1 | 4 | 5 | 2 | 2 | 1 | 2
95 | 18 | 12 | 27 | 40 | 55 | 67 | 83 | 99 | 109 | 121 | 136 | 149 | 163 | 178 | 5 | 2 | 1 | 4 | 1 | 5 | 4 | 5 | 4 | 3 | 4 | 2 | 1 | 4 | 5 | 5 | 2 | 2 | 4 | 4 | 4 | 4 | 3 | 5 | 3 | 5 | 5 | 3 | 2 | 1 | 2 | 5 | 3 | 3 | 4 | 2 | 5 | 2 | 4 | 4 | 3 | 2 | 4 | 4 | 4 | 2 | 4 | 4 | 2 | 4 | 5 | 4
96 | 19 | 14 | 23 | 35 | 45 | 52 | 71 | 85 | 96 | 107 | 121 | 129 | 144 | 153 | 4 | 5 | 3 | 2 | 2 | 3 | 2 | 2 | 2 | 1 | 4 | 5 | 1 | 3 | 1 | 5 | 2 | 2 | 2 | 1 | 5 | 5 | 4 | 5 | 2 | 2 | 5 | 5 | 5 | 2 | 1 | 3 | 5 | 3 | 1 | 2 | 4 | 5 | 4 | 1 | 1 | 1 | 5 | 1 | 5 | 4 | 4 | 2 | 3 | 2 | 2 | 2
97 | 23 | 17 | 31 | 47 | 61 | 68 | 81 | 92 | 103 | 114 | 124 | 135 | 153 | 163 | 3 | 5 | 4 | 5 | 4 | 2 | 4 | 4 | 4 | 3 | 5 | 4 | 3 | 4 | 5 | 2 | 3 | 1 | 1 | 2 | 3 | 3 | 4 | 3 | 2 | 4 | 1 | 4 | 3 | 4 | 3 | 1 | 2 | 1 | 4 | 4 | 3 | 1 | 5 | 1 | 4 | 5 | 1 | 1 | 5 | 5 | 5 | 3 | 5 | 1 | 3 | 1
98 | 23 | 15 | 26 | 39 | 56 | 66 | 77 | 89 | 102 | 117 | 131 | 144 | 157 | 173 | 4 | 4 | 5 | 2 | 3 | 5 | 1 | 2 | 5 | 3 | 4 | 1 | 5 | 5 | 2 | 5 | 4 | 1 | 2 | 3 | 5 | 3 | 2 | 1 | 3 | 5 | 3 | 1 | 4 | 4 | 1 | 4 | 5 | 4 | 5 | 1 | 1 | 4 | 4 | 5 | 3 | 4 | 3 | 3 | 2 | 3 | 4 | 4 | 4 | 4 | 4 | 4
99 | 10 | 5 | 14 | 28 | 43 | 58 | 72 | 84 | 92 | 97 | 104 | 116 | 129 | 138 | 1 | 2 | 1 | 1 | 2 | 3 | 2 | 2 | 2 | 5 | 5 | 2 | 4 | 4 | 5 | 2 | 3 | 2 | 5 | 5 | 2 | 5 | 5 | 2 | 5 | 3 | 2 | 2 | 1 | 1 | 2 | 4 | 1 | 1 | 1 | 2 | 2 | 3 | 1 | 1 | 3 | 3 | 3 | 3 | 1 | 4 | 3 | 5 | 1 | 3 | 1 | 4
100 | 19 | 10 | 24 | 40 | 54 | 68 | 78 | 91 | 99 | 112 | 127 | 139 | 151 | 164 | 3 | 1 | 3 | 3 | 5 | 4 | 2 | 3 | 4 | 5 | 3 | 4 | 5 | 1 | 5 | 3 | 5 | 4 | 3 | 2 | 3 | 3 | 2 | 2 | 3 | 1 | 5 | 4 | 3 | 1 | 2 | 2 | 1 | 2 | 5 | 5 | 5 | 3 | 2 | 5 | 4 | 3 | 3 | 2 | 4 | 1 | 5 | 2 | 2 | 4 | 3 | 4
101 | 18 | 13 | 24 | 33 | 47 | 64 | 80 | 94 | 104 | 120 | 136 | 150 | 162 | 174 | 1 | 3 | 4 | 5 | 1 | 4 | 3 | 3 | 1 | 5 | 2 | 1 | 5 | 5 | 2 | 2 | 5 | 3 | 5 | 4 | 4 | 4 | 5 | 3 | 2 | 4 | 5 | 3 | 1 | 1 | 3 | 5 | 4 | 4 | 5 | 3 | 2 | 5 | 5 | 4 | 3 | 2 | 5 | 4 | 1 | 3 | 5 | 3 | 4 | 5 | 2 | 1
102 | 20 | 11 | 26 | 39 | 50 | 63 | 73 | 84 | 99 | 107 | 117 | 126 | 144 | 157 | 3 | 4 | 2 | 2 | 4 | 5 | 1 | 5 | 4 | 3 | 3 | 3 | 2 | 3 | 2 | 4 | 1 | 5 | 4 | 3 | 1 | 3 | 3 | 3 | 2 | 4 | 2 | 3 | 4 | 5 | 5 | 1 | 1 | 2 | 3 | 2 | 2 | 3 | 4 | 1 | 5 | 2 | 1 | 1 | 3 | 5 | 5 | 5 | 4 | 3 | 1 | 5
103 | 20 | 15 | 29 | 39 | 49 | 59 | 76 | 90 | 103 | 113 | 120 | 129 | 141 | 156 | 4 | 5 | 2 | 4 | 1 | 4 | 4 | 5 | 2 | 3 | 1 | 4 | 5 | 3 | 1 | 1 | 2 | 1 | 4 | 3 | 5 | 5 | 4 | 3 | 1 | 5 | 3 | 5 | 1 | 3 | 4 | 5 | 2 | 4 | 3 | 1 | 2 | 3 | 1 | 1 | 5 | 1 | 1 | 2 | 3 | 3 | 5 | 1 | 5 | 1 | 4 | 5
104 | 12 | 10 | 22 | 31 | 43 | 54 | 65 | 78 | 91 | 109 | 124 | 135 | 155 | 169 | 2 | 4 | 3 | 1 | 1 | 1 | 5 | 5 | 1 | 3 | 3 | 2 | 4 | 1 | 2 | 5 | 1 | 5 | 3 | 2 | 3 | 1 | 4 | 3 | 4 | 1 | 5 | 3 | 5 | 1 | 3 | 4 | 5 | 4 | 5 | 4 | 4 | 5 | 4 | 2 | 3 | 3 | 1 | 4 | 5 | 5 | 5 | 5 | 5 | 2 | 4 | 3
105 | 14 | 6 | 20 | 33 | 45 | 59 | 73 | 89 | 98 | 106 | 118 | 125 | 134 | 148 | 3 | 1 | 1 | 1 | 3 | 5 | 1 | 5 | 5 | 4 | 1 | 3 | 5 | 3 | 1 | 3 | 4 | 5 | 4 | 1 | 4 | 5 | 1 | 4 | 4 | 4 | 4 | 4 | 1 | 2 | 2 | 4 | 3 | 2 | 1 | 2 | 1 | 4 | 3 | 4 | 1 | 1 | 2 | 3 | 2 | 4 | 1 | 2 | 5 | 5 | 1 | 3
106 | 15 | 10 | 19 | 33 | 48 | 62 | 76 | 84 | 92 | 99 | 111 | 120 | 136 | 147 | 1 | 4 | 4 | 1 | 1 | 4 | 3 | 1 | 1 | 4 | 4 | 5 | 2 | 5 | 4 | 4 | 4 | 2 | 5 | 3 | 2 | 5 | 4 | 3 | 1 | 4 | 1 | 2 | 1 | 2 | 4 | 1 | 1 | 1 | 4 | 1 | 1 | 4 | 2 | 5 | 2 | 4 | 1 | 2 | 5 | 3 | 3 | 5 | 3 | 3 | 3 | 2
107 | 19 | 13 | 25 | 39 | 52 | 66 | 73 | 86 | 94 | 107 | 121 | 133 | 146 | 159 | 5 | 2 | 4 | 2 | 4 | 2 | 4 | 2 | 4 | 2 | 4 | 4 | 3 | 5 | 1 | 4 | 5 | 2 | 5 | 2 | 1 | 3 | 2 | 1 | 4 | 4 | 1 | 4 | 2 | 1 | 2 | 3 | 4 | 4 | 1 | 4 | 2 | 5 | 2 | 5 | 3 | 5 | 3 | 1 | 5 | 2 | 3 | 3 | 3 | 3 | 3 | 4
108 | 16 | 10 | 21 | 34 | 48 | 59 | 73 | 86 | 98 | 112 | 125 | 138 | 149 | 157 | 2 | 4 | 3 | 1 | 3 | 3 | 4 | 1 | 3 | 5 | 1 | 4 | 3 | 4 | 5 | 2 | 2 | 2 | 3 | 4 | 5 | 3 | 3 | 3 | 3 | 5 | 1 | 4 | 1 | 3 | 3 | 5 | 4 | 4 | 4 | 2 | 2 | 3 | 3 | 5 | 5 | 2 | 4 | 2 | 2 | 3 | 2 | 4 | 1 | 1 | 4 | 2
109 | 24 | 19 | 27 | 38 | 54 | 67 | 82 | 96 | 106 | 119 | 127 | 139 | 150 | 158 | 5 | 5 | 5 | 4 | 3 | 2 | 1 | 2 | 4 | 2 | 3 | 2 | 4 | 4 | 5 | 3 | 3 | 4 | 1 | 5 | 5 | 5 | 2 | 3 | 5 | 3 | 2 | 4 | 1 | 5 | 3 | 1 | 4 | 2 | 4 | 3 | 1 | 3 | 2 | 2 | 3 | 2 | 5 | 2 | 3 | 5 | 2 | 1 | 1 | 5 | 1 | 1
110 | 22 | 17 | 27 | 40 | 49 | 64 | 75 | 83 | 97 | 108 | 120 | 135 | 145 | 155 | 3 | 4 | 5 | 5 | 2 | 3 | 2 | 3 | 4 | 2 | 4 | 3 | 4 | 2 | 2 | 1 | 4 | 5 | 3 | 3 | 3 | 1 | 5 | 2 | 1 | 1 | 2 | 4 | 3 | 2 | 4 | 5 | 1 | 5 | 2 | 3 | 2 | 4 | 2 | 4 | 2 | 3 | 5 | 5 | 1 | 5 | 3 | 1 | 3 | 2 | 2 | 3
111 | 23 | 13 | 28 | 42 | 55 | 64 | 76 | 90 | 101 | 114 | 128 | 143 | 155 | 168 | 1 | 2 | 5 | 5 | 5 | 5 | 1 | 4 | 3 | 5 | 3 | 3 | 2 | 5 | 5 | 1 | 1 | 2 | 1 | 5 | 3 | 3 | 5 | 1 | 5 | 3 | 2 | 4 | 2 | 3 | 3 | 3 | 3 | 4 | 4 | 2 | 2 | 2 | 5 | 5 | 3 | 4 | 5 | 3 | 4 | 1 | 4 | 3 | 4 | 3 | 2 | 4
112 | 17 | 11 | 22 | 35 | 44 | 55 | 66 | 78 | 93 | 105 | 114 | 124 | 137 | 151 | 2 | 1 | 3 | 5 | 2 | 4 | 2 | 3 | 3 | 4 | 5 | 1 | 3 | 1 | 4 | 1 | 3 | 2 | 1 | 5 | 2 | 5 | 3 | 1 | 1 | 1 | 5 | 5 | 5 | 5 | 4 | 1 | 5 | 1 | 5 | 1 | 3 | 1 | 2 | 3 | 1 | 3 | 5 | 1 | 2 | 5 | 2 | 4 | 2 | 5 | 5 | 2
113 | 16 | 14 | 22 | 30 | 45 | 60 | 72 | 80 | 92 | 107 | 125 | 137 | 152 | 170 | 2 | 4 | 3 | 5 | 1 | 1 | 1 | 5 | 1 | 1 | 4 | 2 | 5 | 5 | 4 | 1 | 4 | 5 | 5 | 1 | 4 | 2 | 1 | 5 | 1 | 1 | 3 | 3 | 5 | 5 | 1 | 1 | 2 | 5 | 3 | 5 | 5 | 5 | 3 | 5 | 3 | 2 | 5 | 2 | 4 | 2 | 4 | 5 | 3 | 5 | 5 | 5
114 | 20 | 12 | 26 | 35 | 44 | 55 | 72 | 83 | 90 | 100 | 113 | 123 | 134 | 141 | 4 | 5 | 1 | 2 | 3 | 5 | 1 | 5 | 4 | 2 | 2 | 1 | 4 | 1 | 2 | 2 | 2 | 3 | 2 | 4 | 5 | 4 | 5 | 3 | 1 | 2 | 3 | 5 | 4 | 1 | 1 | 1 | 3 | 3 | 1 | 3 | 2 | 1 | 5 | 5 | 3 | 2 | 2 | 3 | 4 | 2 | 3 | 2 | 1 | 1 | 4 | 1
115 | 18 | 14 | 22 | 36 | 47 | 61 | 69 | 86 | 98 | 115 | 128 | 142 | 156 | 165 | 2 | 4 | 4 | 4 | 1 | 3 | 1 | 3 | 5 | 5 | 3 | 1 | 2 | 1 | 4 | 4 | 3 | 5 | 1 | 5 | 1 | 2 | 1 | 4 | 2 | 5 | 5 | 5 | 4 | 2 | 4 | 2 | 5 | 4 | 5 | 3 | 2 | 3 | 4 | 4 | 4 | 3 | 2 | 5 | 5 | 5 | 1 | 3 | 2 | 3 | 2 | 2
116 | 17 | 11 | 24 | 32 | 42 | 58 | 70 | 84 | 99 | 112 | 123 | 139 | 148 | 162 | 4 | 2 | 1 | 4 | 1 | 5 | 4 | 3 | 1 | 2 | 4 | 1 | 4 | 1 | 2 | 3 | 5 | 5 | 1 | 5 | 5 | 3 | 2 | 2 | 1 | 5 | 3 | 5 | 2 | 5 | 4 | 4 | 2 | 4 | 2 | 5 | 5 | 1 | 1 | 4 | 3 | 5 | 4 | 4 | 4 | 3 | 1 | 1 | 5 | 5 | 3 | 1
117 | 16 | 10 | 23 | 35 | 47 | 59 | 75 | 88 | 102 | 115 | 130 | 141 | 150 | 163 | 3 | 4 | 2 | 1 | 3 | 3 | 5 | 2 | 2 | 5 | 3 | 2 | 3 | 1 | 5 | 3 | 4 | 1 | 4 | 3 | 5 | 5 | 1 | 5 | 3 | 4 | 5 | 1 | 4 | 5 | 1 | 4 | 4 | 2 | 4 | 3 | 3 | 4 | 4 | 4 | 3 | 3 | 4 | 1 | 1 | 4 | 3 | 1 | 1 | 5 | 4 | 3
118 | 20 | 16 | 25 | 37 | 51 | 63 | 78 | 89 | 100 | 117 | 133 | 145 | 159 | 173 | 4 | 5 | 3 | 4 | 1 | 3 | 2 | 3 | 5 | 1 | 2 | 4 | 5 | 3 | 1 | 5 | 3 | 1 | 3 | 5 | 1 | 5 | 4 | 5 | 3 | 4 | 1 | 3 | 1 | 5 | 3 | 2 | 5 | 3 | 5 | 4 | 3 | 3 | 5 | 5 | 2 | 5 | 4 | 1 | 3 | 4 | 2 | 5 | 2 | 3 | 4 | 5
119 | 18 | 14 | 26 | 38 | 52 | 65 | 81 | 91 | 100 | 109 | 124 | 134 | 148 | 158 | 3 | 5 | 5 | 1 | 1 | 3 | 4 | 4 | 3 | 5 | 1 | 3 | 5 | 4 | 1 | 4 | 2 | 5 | 2 | 4 | 3 | 5 | 5 | 3 | 3 | 4 | 1 | 2 | 4 | 2 | 2 | 1 | 3 | 1 | 3 | 2 | 2 | 5 | 5 | 3 | 5 | 1 | 3 | 1 | 3 | 5 | 1 | 5 | 3 | 2 | 3 | 2
120 | 19 | 13 | 25 | 41 | 53 | 64 | 76 | 85 | 90 | 105 | 119 | 132 | 141 | 153 | 2 | 3 | 3 | 5 | 5 | 1 | 4 | 2 | 5 | 4 | 2 | 5 | 2 | 4 | 2 | 4 | 1 | 2 | 4 | 4 | 3 | 4 | 1 | 4 | 2 | 1 | 2 | 4 | 1 | 2 | 1 | 1 | 5 | 4 | 2 | 4 | 4 | 4 | 4 | 2 | 2 | 4 | 3 | 4 | 4 | 1 | 1 | 3 | 2 | 4 | 5 | 1
121 | 16 | 9 | 19 | 37 | 49 | 60 | 68 | 77 | 89 | 105 | 110 | 124 | 135 | 145 | 2 | 2 | 1 | 4 | 5 | 2 | 2 | 1 | 5 | 5 | 3 | 5 | 5 | 3 | 3 | 1 | 3 | 1 | 5 | 2 | 1 | 3 | 2 | 2 | 4 | 3 | 1 | 1 | 5 | 3 | 3 | 1 | 4 | 4 | 3 | 5 | 1 | 1 | 1 | 2 | 4 | 1 | 4 | 5 | 3 | 4 | 2 | 2 | 1 | 2 | 4 | 3
122 | 15 | 9 | 19 | 27 | 41 | 54 | 66 | 81 | 96 | 110 | 126 | 136 | 150 | 160 | 4 | 1 | 3 | 1 | 3 | 3 | 3 | 1 | 1 | 4 | 1 | 2 | 5 | 4 | 2 | 3 | 5 | 3 | 2 | 3 | 4 | 4 | 1 | 3 | 4 | 3 | 5 | 3 | 3 | 4 | 5 | 3 | 5 | 1 | 5 | 3 | 2 | 4 | 5 | 5 | 1 | 2 | 5 | 2 | 5 | 5 | 2 | 2 | 4 | 4 | 1 | 1
123 | 18 | 14 | 25 | 43 | 52 | 61 | 76 | 85 | 96 | 112 | 124 | 134 | 149 | 162 | 4 | 5 | 1 | 4 | 1 | 3 | 2 | 5 | 5 | 5 | 3 | 5 | 2 | 2 | 1 | 4 | 5 | 1 | 1 | 2 | 1 | 5 | 5 | 4 | 1 | 5 | 1 | 2 | 4 | 1 | 2 | 4 | 3 | 3 | 5 | 5 | 5 | 1 | 1 | 5 | 5 | 1 | 1 | 3 | 1 | 5 | 4 | 5 | 2 | 4 | 2 | 5
124 | 15 | 10 | 24 | 35 | 50 | 59 | 69 | 83 | 98 | 109 | 124 | 133 | 142 | 151 | 3 | 3 | 2 | 2 | 4 | 1 | 5 | 4 | 4 | 2 | 4 | 1 | 4 | 4 | 3 | 4 | 1 | 2 | 4 | 2 | 5 | 1 | 1 | 3 | 4 | 3 | 2 | 5 | 5 | 1 | 4 | 5 | 5 | 3 | 2 | 1 | 5 | 1 | 5 | 4 | 2 | 1 | 2 | 4 | 2 | 1 | 2 | 4 | 1 | 4 | 3 | 1
125 | 20 | 16 | 29 | 41 | 54 | 67 | 80 | 91 | 101 | 108 | 119 | 127 | 139 | 147 | 5 | 4 | 2 | 5 | 2 | 2 | 4 | 5 | 5 | 1 | 3 | 3 | 1 | 4 | 3 | 5 | 4 | 2 | 2 | 5 | 1 | 5 | 3 | 4 | 3 | 3 | 2 | 3 | 1 | 5 | 3 | 1 | 2 | 2 | 1 | 2 | 4 | 1 | 1 | 5 | 4 | 1 | 2 | 1 | 5 | 2 | 3 | 2 | 1 | 2 | 2 | 3
126 | 20 | 15 | 25 | 36 | 51 | 63 | 73 | 82 | 93 | 104 | 116 | 128 | 142 | 152 | 3 | 5 | 5 | 2 | 4 | 1 | 3 | 2 | 5 | 2 | 2 | 2 | 5 | 2 | 3 | 5 | 5 | 1 | 5 | 1 | 1 | 1 | 4 | 4 | 5 | 2 | 1 | 1 | 2 | 2 | 2 | 5 | 5 | 3 | 2 | 1 | 1 | 4 | 5 | 2 | 5 | 2 | 3 | 2 | 2 | 5 | 5 | 2 | 3 | 5 | 1 | 1
127 | 19 | 11 | 25 | 40 | 52 | 65 | 74 | 85 | 99 | 117 | 127 | 136 | 142 | 155 | 3 | 5 | 1 | 2 | 5 | 3 | 1 | 5 | 4 | 5 | 2 | 4 | 4 | 1 | 2 | 5 | 4 | 4 | 1 | 4 | 1 | 3 | 1 | 4 | 2 | 2 | 3 | 4 | 2 | 5 | 4 | 3 | 5 | 4 | 5 | 4 | 1 | 3 | 1 | 5 | 4 | 2 | 2 | 1 | 2 | 2 | 1 | 1 | 4 | 1 | 3 | 5
128 | 19 | 11 | 25 | 40 | 51 | 61 | 73 | 83 | 98 | 112 | 124 | 133 | 142 | 155 | 2 | 4 | 1 | 4 | 3 | 5 | 1 | 5 | 5 | 5 | 4 | 1 | 4 | 4 | 1 | 2 | 3 | 2 | 4 | 1 | 5 | 1 | 1 | 5 | 2 | 1 | 5 | 2 | 2 | 4 | 4 | 5 | 2 | 2 | 5 | 5 | 2 | 3 | 2 | 5 | 1 | 4 | 2 | 2 | 2 | 1 | 3 | 3 | 3 | 4 | 5 | 1
129 | 25 | 17 | 29 | 40 | 55 | 66 | 83 | 96 | 105 | 112 | 125 | 133 | 149 | 161 | 5 | 4 | 5 | 3 | 5 | 3 | 1 | 3 | 2 | 2 | 4 | 3 | 5 | 4 | 4 | 2 | 2 | 1 | 5 | 3 | 3 | 4 | 5 | 5 | 2 | 2 | 4 | 5 | 1 | 1 | 5 | 2 | 3 | 1 | 1 | 2 | 1 | 5 | 4 | 3 | 2 | 1 | 1 | 4 | 5 | 4 | 3 | 4 | 3 | 3 | 1 | 5
130 | 17 | 11 | 24 | 34 | 43 | 52 | 59 | 67 | 83 | 97 | 110 | 121 | 131 | 142 | 1 | 3 | 3 | 4 | 5 | 1 | 4 | 3 | 1 | 3 | 3 | 3 | 2 | 1 | 1 | 5 | 1 | 2 | 4 | 2 | 1 | 3 | 1 | 2 | 2 | 1 | 2 | 3 | 3 | 4 | 5 | 4 | 3 | 2 | 5 | 4 | 5 | 4 | 3 | 1 | 1 | 3 | 2 | 5 | 4 | 2 | 1 | 3 | 4 | 1 | 3 | 3
131 | 16 | 11 | 23 | 34 | 46 | 59 | 69 | 80 | 91 | 98 | 111 | 126 | 135 | 141 | 3 | 1 | 2 | 5 | 2 | 3 | 5 | 2 | 2 | 3 | 1 | 5 | 1 | 5 | 1 | 5 | 5 | 3 | 3 | 2 | 3 | 1 | 4 | 2 | 3 | 1 | 4 | 3 | 2 | 4 | 3 | 2 | 1 | 1 | 4 | 1 | 4 | 4 | 3 | 2 | 3 | 5 | 3 | 4 | 2 | 1 | 4 | 2 | 2 | 1 | 2 | 1
132 | 13 | 8 | 20 | 33 | 49 | 60 | 76 | 84 | 91 | 104 | 116 | 131 | 144 | 154 | 2 | 1 | 3 | 2 | 1 | 4 | 2 | 5 | 3 | 3 | 2 | 5 | 5 | 3 | 3 | 5 | 5 | 3 | 1 | 2 | 5 | 2 | 5 | 4 | 1 | 2 | 4 | 1 | 1 | 3 | 1 | 2 | 2 | 5 | 2 | 4 | 2 | 3 | 2 | 5 | 3 | 5 | 2 | 5 | 5 | 3 | 1 | 4 | 3 | 3 | 2 | 2
133 | 12 | 9 | 15 | 27 | 43 | 53 | 66 | 79 | 92 | 104 | 108 | 115 | 128 | 137 | 2 | 3 | 1 | 3 | 1 | 2 | 1 | 2 | 5 | 4 | 1 | 2 | 3 | 5 | 4 | 4 | 4 | 3 | 1 | 2 | 5 | 3 | 3 | 2 | 2 | 4 | 2 | 5 | 5 | 4 | 3 | 1 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 4 | 4 | 3 | 2 | 1 | 1 | 3 | 4
134 | 15 | 11 | 25 | 36 | 46 | 59 | 67 | 77 | 86 | 97 | 106 | 117 | 129 | 144 | 2 | 4 | 3 | 2 | 1 | 3 | 5 | 5 | 3 | 1 | 3 | 4 | 3 | 1 | 4 | 2 | 2 | 4 | 4 | 3 | 4 | 1 | 2 | 1 | 5 | 2 | 2 | 1 | 2 | 3 | 2 | 2 | 1 | 1 | 5 | 4 | 2 | 1 | 5 | 1 | 4 | 2 | 3 | 2 | 5 | 1 | 4 | 2 | 1 | 4 | 5 | 5
135 | 14 | 11 | 22 | 32 | 38 | 50 | 64 | 78 | 88 | 103 | 117 | 129 | 144 | 157 | 5 | 3 | 2 | 1 | 2 | 1 | 4 | 4 | 1 | 3 | 1 | 5 | 1 | 2 | 2 | 1 | 1 | 5 | 4 | 2 | 3 | 4 | 4 | 3 | 5 | 3 | 1 | 5 | 4 | 1 | 2 | 3 | 4 | 5 | 2 | 4 | 5 | 2 | 3 | 4 | 1 | 4 | 5 | 2 | 4 | 5 | 3 | 3 | 3 | 4 | 5 | 1
136 | 22 | 15 | 30 | 39 | 45 | 54 | 66 | 80 | 86 | 98 | 106 | 113 | 125 | 138 | 1 | 5 | 5 | 4 | 5 | 2 | 4 | 4 | 4 | 2 | 1 | 2 | 1 | 2 | 2 | 1 | 5 | 1 | 1 | 2 | 4 | 1 | 2 | 5 | 1 | 4 | 5 | 4 | 2 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 2 | 3 | 2 | 1 | 3 | 1 | 2 | 1 | 4 | 4 | 1 | 3 | 3 | 5 | 4 | 1
137 | 21 | 14 | 27 | 43 | 50 | 65 | 75 | 90 | 103 | 112 | 129 | 140 | 150 | 159 | 2 | 3 | 5 | 4 | 4 | 3 | 5 | 1 | 4 | 5 | 5 | 2 | 1 | 2 | 1 | 3 | 5 | 3 | 4 | 3 | 1 | 4 | 2 | 3 | 2 | 5 | 3 | 5 | 5 | 2 | 2 | 4 | 3 | 4 | 1 | 1 | 5 | 4 | 4 | 4 | 4 | 3 | 1 | 3 | 2 | 3 | 3 | 2 | 2 | 4 | 1 | 2
138 | 19 | 11 | 25 | 38 | 46 | 57 | 72 | 83 | 95 | 105 | 117 | 129 | 137 | 150 | 2 | 5 | 2 | 2 | 3 | 5 | 5 | 1 | 5 | 3 | 3 | 2 | 1 | 3 | 1 | 3 | 1 | 2 | 3 | 5 | 4 | 4 | 2 | 5 | 1 | 4 | 3 | 3 | 5 | 2 | 3 | 2 | 3 | 1 | 3 | 3 | 2 | 4 | 2 | 4 | 1 | 1 | 5 | 5 | 1 | 1 | 1 | 5 | 5 | 4 | 3 | 1
139 | 22 | 15 | 29 | 42 | 54 | 67 | 82 | 96 | 112 | 131 | 145 | 156 | 170 | 183 | 4 | 2 | 4 | 5 | 5 | 2 | 5 | 2 | 4 | 2 | 5 | 2 | 2 | 2 | 4 | 4 | 2 | 3 | 5 | 3 | 5 | 2 | 3 | 5 | 2 | 3 | 4 | 5 | 4 | 4 | 3 | 5 | 5 | 5 | 5 | 4 | 3 | 3 | 5 | 3 | 5 | 1 | 3 | 2 | 3 | 3 | 5 | 3 | 5 | 1 | 2 | 5
140 | 12 | 8 | 16 | 35 | 47 | 58 | 66 | 78 | 93 | 100 | 110 | 118 | 130 | 142 | 3 | 2 | 2 | 1 | 3 | 1 | 1 | 3 | 5 | 4 | 5 | 5 | 5 | 2 | 3 | 2 | 1 | 2 | 3 | 5 | 1 | 1 | 1 | 5 | 3 | 2 | 5 | 2 | 5 | 2 | 4 | 4 | 2 | 3 | 1 | 1 | 3 | 2 | 4 | 1 | 3 | 1 | 2 | 2 | 5 | 2 | 2 | 3 | 4 | 2 | 5 | 1
141 | 18 | 9 | 23 | 36 | 53 | 64 | 76 | 86 | 97 | 113 | 126 | 138 | 153 | 162 | 1 | 3 | 4 | 1 | 4 | 5 | 2 | 3 | 5 | 3 | 1 | 4 | 5 | 4 | 3 | 5 | 5 | 1 | 1 | 4 | 4 | 2 | 4 | 2 | 2 | 2 | 1 | 5 | 5 | 1 | 3 | 2 | 3 | 5 | 5 | 3 | 1 | 5 | 2 | 5 | 5 | 1 | 5 | 1 | 2 | 5 | 5 | 3 | 1 | 2 | 2 | 4
142 | 14 | 10 | 23 | 34 | 52 | 62 | 74 | 86 | 97 | 108 | 113 | 127 | 137 | 147 | 2 | 1 | 5 | 2 | 2 | 2 | 4 | 5 | 5 | 2 | 3 | 1 | 5 | 5 | 5 | 3 | 2 | 1 | 5 | 2 | 1 | 5 | 1 | 5 | 2 | 4 | 1 | 5 | 5 | 1 | 3 | 2 | 1 | 5 | 1 | 4 | 1 | 1 | 1 | 2 | 3 | 5 | 3 | 3 | 3 | 4 | 1 | 2 | 2 | 5 | 2 | 1
143 | 16 | 10 | 22 | 32 | 44 | 54 | 69 | 79 | 87 | 98 | 106 | 118 | 128 | 143 | 2 | 5 | 1 | 2 | 2 | 4 | 3 | 3 | 5 | 1 | 1 | 3 | 1 | 1 | 5 | 5 | 3 | 1 | 1 | 5 | 4 | 5 | 1 | 5 | 1 | 1 | 5 | 3 | 1 | 3 | 1 | 3 | 2 | 3 | 5 | 1 | 1 | 1 | 1 | 5 | 1 | 2 | 5 | 4 | 2 | 4 | 3 | 1 | 4 | 5 | 2 | 4
144 | 13 | 10 | 19 | 30 | 43 | 54 | 66 | 81 | 94 | 101 | 113 | 125 | 140 | 152 | 5 | 3 | 1 | 1 | 1 | 2 | 3 | 3 | 2 | 3 | 1 | 5 | 5 | 2 | 3 | 3 | 2 | 2 | 3 | 4 | 2 | 5 | 3 | 2 | 5 | 2 | 5 | 3 | 4 | 2 | 2 | 5 | 1 | 4 | 1 | 1 | 3 | 4 | 4 | 1 | 2 | 3 | 4 | 3 | 2 | 5 | 3 | 5 | 1 | 4 | 2 | 5
145 | 18 | 11 | 25 | 39 | 51 | 63 | 76 | 88 | 99 | 114 | 125 | 138 | 149 | 165 | 3 | 5 | 1 | 2 | 5 | 2 | 5 | 2 | 1 | 4 | 4 | 5 | 2 | 2 | 3 | 5 | 2 | 4 | 3 | 3 | 1 | 5 | 2 | 5 | 1 | 3 | 5 | 3 | 2 | 2 | 2 | 5 | 5 | 4 | 3 | 3 | 5 | 2 | 1 | 3 | 3 | 4 | 5 | 1 | 5 | 4 | 1 | 1 | 5 | 3 | 4 | 4
146 | 17 | 12 | 25 | 36 | 41 | 55 | 71 | 85 | 95 | 104 | 111 | 125 | 137 | 148 | 3 | 2 | 2 | 5 | 3 | 2 | 5 | 3 | 4 | 1 | 4 | 2 | 1 | 2 | 1 | 1 | 2 | 4 | 4 | 4 | 4 | 2 | 5 | 5 | 1 | 4 | 5 | 4 | 2 | 3 | 4 | 1 | 1 | 2 | 3 | 3 | 1 | 2 | 2 | 2 | 3 | 5 | 3 | 3 | 4 | 3 | 1 | 4 | 1 | 3 | 4 | 3
147 | 19 | 14 | 29 | 42 | 52 | 64 | 80 | 87 | 101 | 112 | 126 | 140 | 148 | 162 | 4 | 5 | 4 | 1 | 3 | 2 | 5 | 5 | 4 | 1 | 5 | 3 | 1 | 2 | 2 | 5 | 1 | 4 | 4 | 3 | 2 | 5 | 5 | 4 | 2 | 3 | 1 | 1 | 5 | 4 | 1 | 4 | 2 | 3 | 2 | 4 | 5 | 4 | 3 | 2 | 5 | 3 | 4 | 2 | 5 | 1 | 1 | 1 | 5 | 2 | 5 | 2
148 | 18 | 8 | 27 | 34 | 45 | 53 | 68 | 75 | 90 | 100 | 114 | 131 | 147 | 159 | 1 | 1 | 1 | 5 | 5 | 5 | 5 | 4 | 1 | 1 | 4 | 1 | 3 | 1 | 4 | 3 | 1 | 2 | 3 | 2 | 4 | 4 | 4 | 3 | 2 | 1 | 3 | 1 | 4 | 5 | 5 | 1 | 1 | 4 | 2 | 3 | 4 | 2 | 4 | 4 | 4 | 5 | 4 | 4 | 2 | 4 | 5 | 5 | 2 | 2 | 5 | 3
149 | 19 | 10 | 25 | 36 | 50 | 62 | 75 | 83 | 92 | 103 | 115 | 131 | 144 | 153 | 4 | 2 | 3 | 1 | 5 | 4 | 4 | 2 | 2 | 2 | 2 | 5 | 4 | 2 | 3 | 5 | 3 | 2 | 3 | 4 | 5 | 5 | 2 | 1 | 2 | 1 | 2 | 3 | 5 | 2 | 1 | 1 | 2 | 3 | 4 | 2 | 2 | 5 | 4 | 1 | 5 | 5 | 4 | 2 | 5 | 2 | 4 | 2 | 2 | 2 | 3 | 2
150 | 16 | 10 | 25 | 36 | 49 | 62 | 74 | 81 | 96 | 107 | 117 | 127 | 139 | 150 | 4 | 2 | 2 | 2 | 2 | 4 | 4 | 5 | 2 | 4 | 1 | 4 | 1 | 4 | 3 | 5 | 4 | 3 | 4 | 2 | 1 | 4 | 4 | 3 | 2 | 1 | 1 | 3 | 4 | 1 | 5 | 5 | 5 | 1 | 4 | 1 | 1 | 5 | 3 | 1 | 4 | 1 | 2 | 3 | 5 | 2 | 4 | 1 | 1 | 4 | 2 | 4
151 | 17 | 11 | 20 | 29 | 40 | 57 | 71 | 85 | 96 | 109 | 117 | 126 | 136 | 151 | 2 | 1 | 4 | 4 | 5 | 1 | 2 | 1 | 1 | 5 | 2 | 1 | 4 | 4 | 2 | 1 | 5 | 4 | 4 | 4 | 2 | 5 | 3 | 4 | 3 | 4 | 5 | 2 | 4 | 2 | 2 | 3 | 4 | 5 | 1 | 3 | 3 | 1 | 3 | 1 | 2 | 2 | 2 | 3 | 1 | 3 | 5 | 1 | 4 | 3 | 4 | 4
152 | 16 | 11 | 22 | 35 | 47 | 56 | 72 | 85 | 95 | 106 | 124 | 139 | 152 | 161 | 4 | 5 | 1 | 1 | 4 | 1 | 1 | 5 | 5 | 2 | 3 | 3 | 2 | 3 | 3 | 4 | 1 | 3 | 1 | 4 | 5 | 5 | 1 | 5 | 5 | 2 | 5 | 1 | 2 | 2 | 3 | 3 | 4 | 1 | 1 | 5 | 5 | 4 | 5 | 4 | 5 | 3 | 3 | 4 | 1 | 3 | 5 | 4 | 5 | 1 | 1 | 2
153 | 16 | 7 | 19 | 37 | 51 | 63 | 75 | 89 | 104 | 116 | 125 | 134 | 141 | 155 | 4 | 1 | 1 | 1 | 5 | 4 | 2 | 1 | 5 | 5 | 3 | 5 | 5 | 5 | 2 | 2 | 3 | 3 | 1 | 5 | 3 | 4 | 4 | 1 | 3 | 5 | 3 | 3 | 4 | 4 | 3 | 4 | 2 | 2 | 4 | 4 | 1 | 1 | 4 | 3 | 1 | 1 | 5 | 2 | 1 | 1 | 1 | 4 | 3 | 5 | 5 | 1
154 | 13 | 9 | 15 | 27 | 40 | 51 | 63 | 75 | 84 | 94 | 104 | 114 | 125 | 138 | 1 | 2 | 1 | 5 | 1 | 3 | 1 | 1 | 3 | 4 | 2 | 3 | 3 | 2 | 4 | 4 | 1 | 4 | 4 | 2 | 2 | 4 | 5 | 1 | 2 | 4 | 4 | 2 | 1 | 5 | 2 | 1 | 1 | 1 | 3 | 5 | 4 | 3 | 1 | 2 | 1 | 3 | 3 | 3 | 1 | 1 | 4 | 5 | 3 | 1 | 5 | 4
155 | 17 | 10 | 22 | 30 | 44 | 57 | 67 | 83 | 97 | 109 | 118 | 131 | 139 | 153 | 5 | 2 | 1 | 2 | 4 | 3 | 2 | 3 | 1 | 3 | 2 | 2 | 4 | 2 | 3 | 5 | 5 | 4 | 1 | 3 | 2 | 1 | 2 | 5 | 5 | 5 | 4 | 2 | 3 | 5 | 2 | 4 | 5 | 1 | 2 | 4 | 3 | 3 | 2 | 1 | 1 | 3 | 4 | 5 | 4 | 1 | 2 | 1 | 2 | 5 | 2 | 5
156 | 23 | 13 | 31 | 40 | 50 | 60 | 72 | 83 | 95 | 114 | 126 | 136 | 145 | 160 | 4 | 3 | 4 | 2 | 5 | 5 | 5 | 3 | 2 | 1 | 5 | 1 | 4 | 1 | 1 | 4 | 1 | 2 | 4 | 3 | 5 | 1 | 1 | 5 | 4 | 5 | 1 | 1 | 3 | 2 | 2 | 5 | 5 | 4 | 5 | 5 | 2 | 1 | 5 | 4 | 1 | 3 | 2 | 4 | 2 | 1 | 2 | 4 | 5 | 5 | 1 | 4
157 | 15 | 10 | 23 | 35 | 49 | 62 | 75 | 84 | 97 | 106 | 124 | 131 | 143 | 156 | 1 | 3 | 3 | 3 | 1 | 4 | 5 | 3 | 3 | 2 | 5 | 2 | 2 | 5 | 3 | 4 | 3 | 4 | 1 | 5 | 4 | 3 | 4 | 2 | 4 | 1 | 2 | 2 | 4 | 5 | 2 | 2 | 3 | 1 | 3 | 2 | 5 | 4 | 4 | 5 | 2 | 2 | 2 | 1 | 5 | 1 | 3 | 3 | 5 | 2 | 4 | 2
158 | 24 | 14 | 29 | 44 | 55 | 64 | 79 | 91 | 100 | 115 | 122 | 135 | 151 | 164 | 5 | 2 | 5 | 2 | 5 | 5 | 4 | 1 | 5 | 5 | 4 | 1 | 3 | 5 | 2 | 1 | 3 | 4 | 1 | 1 | 3 | 4 | 4 | 4 | 5 | 1 | 1 | 5 | 1 | 4 | 1 | 3 | 5 | 3 | 5 | 2 | 2 | 2 | 1 | 2 | 5 | 3 | 3 | 2 | 3 | 3 | 5 | 5 | 5 | 4 | 3 | 1
159 | 20 | 14 | 27 | 38 | 50 | 58 | 72 | 82 | 94 | 104 | 119 | 131 | 144 | 158 | 5 | 3 | 1 | 5 | 4 | 2 | 5 | 2 | 2 | 4 | 4 | 1 | 1 | 4 | 4 | 3 | 2 | 1 | 2 | 3 | 4 | 2 | 4 | 4 | 2 | 2 | 1 | 5 | 5 | 1 | 2 | 4 | 3 | 4 | 2 | 1 | 5 | 2 | 5 | 3 | 2 | 4 | 1 | 5 | 3 | 3 | 3 | 4 | 4 | 1 | 5 | 4
160 | 15 | 12 | 20 | 32 | 46 | 53 | 61 | 72 | 84 | 97 | 108 | 119 | 133 | 147 | 1 | 5 | 1 | 5 | 2 | 1 | 4 | 1 | 4 | 5 | 2 | 1 | 1 | 4 | 5 | 4 | 1 | 3 | 1 | 2 | 1 | 1 | 4 | 2 | 1 | 5 | 2 | 3 | 5 | 2 | 4 | 1 | 3 | 3 | 3 | 4 | 2 | 4 | 2 | 3 | 3 | 5 | 2 | 1 | 3 | 5 | 2 | 4 | 2 | 5 | 2 | 5
161 | 16 | 11 | 21 | 28 | 42 | 53 | 66 | 78 | 86 | 96 | 108 | 115 | 127 | 139 | 3 | 1 | 3 | 4 | 3 | 2 | 1 | 4 | 2 | 1 | 3 | 1 | 4 | 4 | 4 | 2 | 3 | 5 | 1 | 2 | 3 | 4 | 2 | 4 | 5 | 2 | 2 | 3 | 1 | 2 | 2 | 3 | 2 | 5 | 1 | 2 | 5 | 2 | 3 | 2 | 1 | 1 | 3 | 2 | 4 | 5 | 1 | 2 | 4 | 4 | 2 | 2
162 | 17 | 11 | 21 | 32 | 47 | 57 | 68 | 81 | 89 | 101 | 116 | 126 | 140 | 148 | 4 | 1 | 1 | 5 | 2 | 4 | 2 | 2 | 3 | 3 | 3 | 2 | 2 | 3 | 5 | 5 | 5 | 2 | 2 | 1 | 5 | 2 | 3 | 1 | 1 | 4 | 3 | 5 | 1 | 3 | 1 | 3 | 5 | 3 | 2 | 2 | 4 | 5 | 5 | 1 | 3 | 2 | 1 | 4 | 4 | 3 | 5 | 2 | 2 | 1 | 4 | 1
163 | 21 | 15 | 30 | 39 | 50 | 61 | 73 | 87 | 105 | 119 | 135 | 147 | 157 | 172 | 5 | 5 | 3 | 2 | 3 | 3 | 4 | 5 | 2 | 3 | 1 | 3 | 2 | 1 | 3 | 5 | 4 | 2 | 2 | 3 | 3 | 1 | 5 | 3 | 2 | 5 | 5 | 2 | 4 | 5 | 4 | 5 | 3 | 3 | 4 | 4 | 4 | 4 | 5 | 3 | 5 | 3 | 1 | 3 | 4 | 2 | 3 | 1 | 4 | 3 | 3 | 5
164 | 21 | 14 | 28 | 37 | 45 | 59 | 71 | 84 | 96 | 109 | 120 | 129 | 140 | 146 | 2 | 2 | 5 | 5 | 5 | 2 | 2 | 5 | 2 | 4 | 2 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 5 | 3 | 3 | 3 | 1 | 5 | 1 | 3 | 4 | 5 | 5 | 1 | 3 | 3 | 2 | 4 | 2 | 5 | 2 | 4 | 4 | 1 | 2 | 1 | 3 | 3 | 3 | 1 | 2 | 5 | 1 | 1 | 3 | 1
165 | 18 | 13 | 27 | 35 | 51 | 65 | 82 | 97 | 111 | 127 | 137 | 152 | 162 | 175 | 2 | 4 | 3 | 4 | 3 | 2 | 5 | 4 | 1 | 5 | 1 | 1 | 5 | 5 | 5 | 1 | 2 | 3 | 5 | 4 | 5 | 5 | 5 | 2 | 3 | 3 | 4 | 5 | 3 | 2 | 5 | 4 | 2 | 5 | 5 | 4 | 4 | 1 | 3 | 2 | 2 | 3 | 5 | 5 | 4 | 2 | 3 | 1 | 2 | 1 | 5 | 5
166 | 19 | 11 | 25 | 41 | 52 | 62 | 68 | 80 | 90 | 102 | 116 | 130 | 145 | 155 | 4 | 2 | 3 | 2 | 3 | 5 | 2 | 4 | 5 | 4 | 3 | 4 | 5 | 1 | 4 | 1 | 3 | 1 | 3 | 3 | 2 | 1 | 2 | 1 | 4 | 1 | 2 | 5 | 1 | 4 | 4 | 1 | 5 | 4 | 2 | 1 | 1 | 4 | 5 | 4 | 4 | 3 | 5 | 2 | 4 | 1 | 5 | 5 | 3 | 1 | 4 | 2
167 | 20 | 12 | 26 | 36 | 48 | 58 | 74 | 84 | 99 | 110 | 122 | 132 | 142 | 155 | 4 | 3 | 3 | 2 | 3 | 5 | 5 | 1 | 5 | 2 | 2 | 1 | 4 | 1 | 5 | 2 | 1 | 2 | 5 | 2 | 4 | 3 | 4 | 5 | 4 | 1 | 4 | 1 | 4 | 2 | 5 | 4 | 2 | 4 | 4 | 1 | 3 | 1 | 3 | 5 | 3 | 3 | 2 | 2 | 4 | 2 | 3 | 1 | 4 | 5 | 1 | 3
168 | 16 | 10 | 24 | 42 | 54 | 66 | 76 | 91 | 101 | 115 | 126 | 143 | 155 | 165 | 1 | 2 | 2 | 5 | 4 | 2 | 3 | 5 | 4 | 5 | 5 | 4 | 2 | 1 | 5 | 4 | 5 | 2 | 4 | 1 | 1 | 1 | 4 | 4 | 3 | 2 | 5 | 5 | 2 | 3 | 3 | 2 | 3 | 2 | 5 | 4 | 2 | 4 | 3 | 2 | 4 | 3 | 5 | 5 | 2 | 2 | 3 | 5 | 5 | 3 | 1 | 1
169 | 13 | 8 | 18 | 31 | 44 | 58 | 73 | 88 | 103 | 113 | 130 | 143 | 158 | 171 | 2 | 1 | 4 | 1 | 2 | 3 | 2 | 3 | 5 | 3 | 3 | 2 | 5 | 3 | 4 | 1 | 5 | 3 | 4 | 2 | 4 | 1 | 5 | 5 | 3 | 2 | 5 | 5 | 3 | 4 | 4 | 4 | 2 | 4 | 2 | 2 | 4 | 5 | 3 | 5 | 4 | 3 | 5 | 1 | 4 | 4 | 4 | 3 | 2 | 5 | 5 | 1
170 | 16 | 12 | 22 | 35 | 47 | 60 | 68 | 82 | 93 | 104 | 116 | 128 | 141 | 150 | 5 | 4 | 2 | 1 | 1 | 3 | 3 | 3 | 2 | 1 | 5 | 5 | 5 | 3 | 1 | 3 | 3 | 2 | 4 | 4 | 1 | 2 | 1 | 4 | 4 | 5 | 2 | 3 | 3 | 3 | 4 | 1 | 1 | 1 | 5 | 4 | 3 | 5 | 1 | 3 | 2 | 2 | 3 | 5 | 3 | 4 | 1 | 5 | 3 | 1 | 3 | 2
171 | 15 | 10 | 21 | 33 | 46 | 54 | 72 | 80 | 93 | 103 | 118 | 130 | 145 | 156 | 4 | 3 | 2 | 1 | 2 | 3 | 2 | 4 | 4 | 1 | 5 | 2 | 4 | 4 | 3 | 2 | 1 | 3 | 2 | 2 | 5 | 4 | 5 | 4 | 1 | 4 | 1 | 2 | 5 | 4 | 3 | 1 | 4 | 1 | 1 | 4 | 5 | 2 | 4 | 4 | 3 | 4 | 1 | 4 | 4 | 4 | 5 | 2 | 5 | 1 | 4 | 1
172 | 11 | 8 | 15 | 24 | 41 | 49 | 60 | 77 | 91 | 103 | 115 | 129 | 139 | 153 | 2 | 1 | 1 | 4 | 1 | 2 | 3 | 1 | 3 | 1 | 1 | 4 | 3 | 4 | 5 | 5 | 4 | 1 | 1 | 2 | 3 | 2 | 1 | 5 | 5 | 3 | 5 | 4 | 1 | 5 | 3 | 5 | 3 | 1 | 5 | 3 | 3 | 5 | 3 | 1 | 4 | 2 | 4 | 4 | 1 | 5 | 3 | 1 | 4 | 2 | 3 | 5
173 | 23 | 20 | 29 | 44 | 55 | 63 | 74 | 90 | 97 | 112 | 127 | 136 | 151 | 165 | 5 | 5 | 5 | 5 | 1 | 2 | 2 | 4 | 5 | 4 | 5 | 1 | 3 | 4 | 2 | 2 | 3 | 1 | 2 | 2 | 4 | 1 | 4 | 2 | 5 | 4 | 2 | 5 | 1 | 2 | 1 | 3 | 3 | 4 | 5 | 3 | 5 | 5 | 1 | 4 | 2 | 1 | 2 | 4 | 1 | 5 | 5 | 4 | 5 | 3 | 1 | 5
174 | 15 | 10 | 21 | 36 | 52 | 57 | 69 | 81 | 95 | 105 | 118 | 126 | 138 | 144 | 2 | 3 | 1 | 4 | 2 | 3 | 4 | 2 | 2 | 5 | 4 | 4 | 5 | 4 | 5 | 2 | 2 | 1 | 1 | 1 | 3 | 1 | 4 | 4 | 1 | 5 | 4 | 2 | 5 | 2 | 4 | 3 | 2 | 5 | 1 | 2 | 3 | 1 | 5 | 4 | 1 | 2 | 1 | 4 | 1 | 2 | 5 | 4 | 3 | 1 | 1 | 1
175 | 21 | 17 | 27 | 38 | 48 | 55 | 65 | 79 | 88 | 100 | 116 | 130 | 144 | 154 | 2 | 5 | 5 | 5 | 2 | 2 | 1 | 5 | 4 | 1 | 4 | 2 | 3 | 4 | 1 | 2 | 1 | 1 | 4 | 1 | 2 | 4 | 2 | 2 | 3 | 3 | 5 | 3 | 1 | 5 | 1 | 2 | 5 | 1 | 1 | 5 | 5 | 5 | 2 | 4 | 4 | 1 | 4 | 5 | 4 | 4 | 5 | 1 | 4 | 4 | 1 | 1
176 | 16 | 10 | 24 | 35 | 45 | 59 | 73 | 84 | 95 | 107 | 117 | 129 | 141 | 153 | 2 | 3 | 1 | 4 | 5 | 1 | 5 | 3 | 4 | 2 | 4 | 1 | 1 | 1 | 5 | 3 | 3 | 5 | 4 | 2 | 5 | 5 | 2 | 2 | 1 | 1 | 4 | 5 | 5 | 4 | 1 | 1 | 4 | 5 | 2 | 1 | 2 | 3 | 1 | 4 | 2 | 4 | 4 | 2 | 3 | 4 | 2 | 3 | 1 | 4 | 4 | 3
177 | 14 | 12 | 19 | 37 | 47 | 54 | 62 | 67 | 82 | 90 | 108 | 118 | 127 | 139 | 4 | 2 | 5 | 1 | 1 | 1 | 2 | 3 | 5 | 3 | 5 | 5 | 2 | 3 | 4 | 1 | 1 | 3 | 1 | 2 | 3 | 1 | 3 | 1 | 1 | 1 | 1 | 2 | 5 | 3 | 2 | 5 | 2 | 3 | 1 | 2 | 5 | 5 | 3 | 5 | 4 | 1 | 3 | 2 | 1 | 3 | 4 | 1 | 3 | 2 | 2 | 5
178 | 14 | 10 | 19 | 28 | 39 | 53 | 69 | 82 | 94 | 107 | 117 | 129 | 143 | 155 | 1 | 4 | 2 | 3 | 1 | 3 | 1 | 4 | 3 | 1 | 4 | 1 | 2 | 4 | 4 | 1 | 4 | 4 | 5 | 1 | 4 | 4 | 5 | 3 | 4 | 4 | 4 | 1 | 5 | 2 | 4 | 1 | 5 | 1 | 4 | 3 | 2 | 3 | 4 | 1 | 2 | 2 | 5 | 3 | 5 | 4 | 4 | 1 | 4 | 3 | 4 | 1
179 | 23 | 15 | 29 | 41 | 52 | 63 | 72 | 81 | 89 | 107 | 123 | 136 | 146 | 159 | 5 | 5 | 4 | 1 | 5 | 3 | 3 | 3 | 4 | 3 | 1 | 4 | 3 | 1 | 2 | 5 | 3 | 2 | 1 | 5 | 3 | 3 | 1 | 2 | 1 | 4 | 3 | 1 | 1 | 1 | 1 | 5 | 5 | 5 | 5 | 3 | 1 | 5 | 5 | 5 | 1 | 5 | 2 | 5 | 3 | 2 | 4 | 1 | 5 | 3 | 2 | 3
180 | 13 | 8 | 18 | 27 | 41 | 53 | 61 | 77 | 88 | 96 | 104 | 115 | 130 | 145 | 2 | 2 | 2 | 2 | 1 | 4 | 4 | 1 | 1 | 1 | 5 | 2 | 4 | 1 | 5 | 4 | 2 | 1 | 5 | 4 | 1 | 2 | 4 | 1 | 5 | 3 | 4 | 4 | 2 | 3 | 4 | 2 | 3 | 1 | 1 | 3 | 2 | 1 | 4 | 1 | 1 | 2 | 4 | 4 | 5 | 1 | 4 | 5 | 5 | 2 | 3 | 5
181 | 20 | 13 | 25 | 36 | 47 | 62 | 72 | 81 | 94 | 106 | 115 | 126 | 136 | 148 | 2 | 4 | 3 | 4 | 5 | 2 | 3 | 2 | 4 | 3 | 2 | 2 | 4 | 1 | 2 | 4 | 2 | 4 | 5 | 4 | 1 | 2 | 4 | 3 | 2 | 2 | 1 | 4 | 2 | 1 | 5 | 5 | 4 | 4 | 1 | 3 | 1 | 2 | 5 | 1 | 2 | 4 | 1 | 4 | 2 | 3 | 1 | 4 | 1 | 5 | 2 | 4
182 | 18 | 12 | 23 | 36 | 48 | 52 | 71 | 81 | 88 | 105 | 114 | 127 | 138 | 155 | 3 | 2 | 2 | 5 | 1 | 5 | 4 | 1 | 5 | 1 | 3 | 4 | 5 | 1 | 1 | 5 | 1 | 1 | 1 | 1 | 5 | 5 | 4 | 5 | 2 | 4 | 3 | 1 | 1 | 1 | 4 | 1 | 2 | 5 | 5 | 5 | 1 | 2 | 5 | 1 | 2 | 2 | 4 | 5 | 5 | 1 | 1 | 4 | 4 | 5 | 4 | 4
183 | 14 | 9 | 23 | 33 | 44 | 53 | 68 | 75 | 87 | 102 | 114 | 119 | 137 | 148 | 1 | 5 | 1 | 2 | 2 | 3 | 4 | 5 | 3 | 1 | 4 | 2 | 4 | 5 | 1 | 1 | 2 | 1 | 4 | 2 | 5 | 1 | 5 | 4 | 2 | 3 | 1 | 1 | 2 | 4 | 4 | 2 | 3 | 2 | 5 | 5 | 2 | 4 | 4 | 2 | 1 | 1 | 2 | 1 | 5 | 5 | 3 | 5 | 1 | 2 | 5 | 3
184 | 13 | 7 | 22 | 33 | 44 | 58 | 69 | 79 | 88 | 100 | 112 | 122 | 128 | 137 | 1 | 1 | 1 | 4 | 4 | 2 | 5 | 4 | 1 | 3 | 3 | 4 | 2 | 3 | 5 | 1 | 2 | 3 | 4 | 5 | 5 | 2 | 1 | 3 | 4 | 2 | 2 | 2 | 1 | 1 | 4 | 3 | 5 | 1 | 2 | 4 | 5 | 2 | 2 | 3 | 1 | 2 | 3 | 4 | 2 | 2 | 1 | 1 | 1 | 2 | 2 | 4
185 | 13 | 10 | 20 | 36 | 49 | 64 | 77 | 92 | 103 | 116 | 131 | 141 | 152 | 167 | 5 | 1 | 3 | 1 | 1 | 2 | 2 | 5 | 4 | 3 | 5 | 4 | 5 | 3 | 2 | 3 | 3 | 5 | 2 | 5 | 3 | 3 | 5 | 2 | 4 | 5 | 1 | 5 | 1 | 3 | 4 | 3 | 2 | 5 | 3 | 3 | 5 | 2 | 5 | 3 | 5 | 1 | 1 | 3 | 2 | 1 | 5 | 3 | 2 | 4 | 5 | 4
186 | 19 | 13 | 29 | 41 | 51 | 64 | 79 | 89 | 101 | 111 | 126 | 141 | 156 | 171 | 1 | 4 | 5 | 3 | 5 | 1 | 5 | 5 | 3 | 4 | 1 | 4 | 2 | 2 | 3 | 3 | 5 | 4 | 3 | 1 | 4 | 3 | 5 | 3 | 2 | 4 | 3 | 1 | 1 | 5 | 4 | 2 | 1 | 4 | 2 | 3 | 4 | 3 | 4 | 4 | 1 | 4 | 5 | 5 | 5 | 2 | 5 | 3 | 4 | 4 | 2 | 5
187 | 18 | 12 | 23 | 35 | 46 | 61 | 71 | 86 | 96 | 109 | 125 | 140 | 159 | 173 | 3 | 2 | 5 | 2 | 1 | 5 | 1 | 4 | 2 | 3 | 4 | 3 | 3 | 2 | 1 | 5 | 3 | 3 | 4 | 5 | 5 | 2 | 2 | 1 | 3 | 3 | 4 | 5 | 1 | 3 | 1 | 5 | 1 | 4 | 3 | 5 | 4 | 5 | 2 | 5 | 5 | 4 | 4 | 2 | 5 | 4 | 5 | 5 | 4 | 2 | 4 | 4
188 | 19 | 13 | 27 | 38 | 51 | 62 | 73 | 84 | 95 | 108 | 118 | 133 | 144 | 159 | 3 | 3 | 3 | 4 | 2 | 4 | 4 | 4 | 2 | 5 | 2 | 2 | 5 | 2 | 2 | 4 | 1 | 5 | 2 | 3 | 1 | 5 | 2 | 3 | 2 | 2 | 4 | 3 | 3 | 5 | 2 | 1 | 2 | 5 | 5 | 1 | 3 | 3 | 2 | 2 | 4 | 3 | 3 | 5 | 5 | 3 | 2 | 1 | 5 | 3 | 2 | 5
189 | 15 | 12 | 23 | 33 | 48 | 62 | 79 | 91 | 102 | 112 | 123 | 140 | 152 | 161 | 4 | 2 | 3 | 3 | 1 | 2 | 5 | 3 | 4 | 2 | 2 | 2 | 4 | 3 | 5 | 3 | 3 | 2 | 4 | 5 | 5 | 5 | 3 | 4 | 5 | 2 | 2 | 3 | 2 | 4 | 2 | 3 | 3 | 1 | 2 | 4 | 2 | 2 | 3 | 4 | 4 | 5 | 5 | 3 | 3 | 4 | 1 | 4 | 2 | 2 | 2 | 3
190 | 15 | 8 | 22 | 32 | 46 | 63 | 69 | 86 | 97 | 112 | 127 | 143 | 156 | 171 | 1 | 1 | 4 | 2 | 5 | 2 | 4 | 3 | 3 | 1 | 2 | 4 | 5 | 2 | 2 | 5 | 3 | 5 | 4 | 5 | 1 | 2 | 1 | 2 | 3 | 5 | 5 | 4 | 3 | 2 | 5 | 1 | 3 | 4 | 5 | 3 | 4 | 5 | 2 | 4 | 5 | 2 | 4 | 5 | 1 | 4 | 4 | 4 | 3 | 2 | 5 | 5
191 | 16 | 10 | 24 | 35 | 46 | 60 | 71 | 81 | 95 | 106 | 114 | 119 | 132 | 140 | 4 | 1 | 4 | 1 | 1 | 5 | 3 | 5 | 5 | 2 | 3 | 1 | 5 | 2 | 2 | 2 | 3 | 1 | 5 | 5 | 5 | 2 | 3 | 1 | 3 | 1 | 3 | 3 | 3 | 5 | 5 | 1 | 3 | 3 | 2 | 3 | 1 | 2 | 3 | 2 | 2 | 1 | 1 | 1 | 4 | 2 | 3 | 4 | 3 | 2 | 2 | 1
192 | 19 | 13 | 23 | 39 | 53 | 64 | 77 | 87 | 95 | 103 | 111 | 121 | 131 | 147 | 3 | 1 | 4 | 5 | 2 | 4 | 2 | 2 | 2 | 5 | 4 | 5 | 4 | 5 | 1 | 4 | 1 | 3 | 2 | 5 | 4 | 1 | 4 | 4 | 4 | 2 | 3 | 1 | 1 | 3 | 1 | 3 | 1 | 1 | 3 | 3 | 1 | 2 | 2 | 3 | 4 | 1 | 3 | 2 | 4 | 3 | 1 | 2 | 5 | 3 | 4 | 4
193 | 18 | 13 | 23 | 33 | 44 | 61 | 77 | 86 | 99 | 115 | 129 | 141 | 149 | 159 | 2 | 3 | 5 | 3 | 3 | 2 | 1 | 4 | 3 | 3 | 2 | 2 | 1 | 1 | 4 | 5 | 3 | 5 | 5 | 4 | 2 | 4 | 5 | 5 | 1 | 5 | 2 | 1 | 1 | 4 | 3 | 5 | 5 | 5 | 3 | 3 | 4 | 3 | 3 | 4 | 3 | 3 | 5 | 1 | 2 | 1 | 4 | 1 | 1 | 5 | 3 | 1
194 | 21 | 16 | 24 | 33 | 43 | 56 | 65 | 73 | 84 | 97 | 110 | 122 | 130 | 142 | 4 | 2 | 5 | 5 | 2 | 3 | 1 | 2 | 2 | 1 | 4 | 2 | 2 | 1 | 4 | 3 | 3 | 2 | 5 | 3 | 4 | 2 | 1 | 2 | 3 | 3 | 1 | 1 | 4 | 2 | 3 | 2 | 3 | 5 | 1 | 4 | 5 | 2 | 3 | 3 | 3 | 2 | 2 | 5 | 2 | 1 | 4 | 1 | 1 | 5 | 5 | 1
195 | 18 | 12 | 27 | 39 | 50 | 63 | 76 | 88 | 99 | 110 | 123 | 138 | 155 | 169 | 3 | 4 | 2 | 3 | 5 | 1 | 5 | 4 | 2 | 4 | 2 | 4 | 1 | 5 | 4 | 1 | 4 | 1 | 5 | 3 | 3 | 5 | 4 | 1 | 4 | 2 | 3 | 3 | 3 | 1 | 4 | 3 | 5 | 1 | 2 | 3 | 1 | 2 | 5 | 5 | 2 | 3 | 5 | 5 | 4 | 5 | 5 | 3 | 4 | 4 | 5 | 1
196 | 23 | 13 | 27 | 39 | 50 | 65 | 81 | 90 | 101 | 117 | 135 | 146 | 155 | 168 | 4 | 2 | 3 | 4 | 5 | 5 | 1 | 3 | 1 | 4 | 3 | 4 | 4 | 2 | 4 | 1 | 1 | 4 | 5 | 5 | 5 | 3 | 3 | 5 | 4 | 1 | 3 | 1 | 3 | 1 | 3 | 4 | 2 | 5 | 5 | 4 | 5 | 4 | 5 | 4 | 2 | 3 | 5 | 1 | 1 | 1 | 3 | 4 | 3 | 2 | 5 | 3
197 | 19 | 14 | 26 | 40 | 51 | 62 | 76 | 90 | 98 | 107 | 123 | 138 | 144 | 157 | 4 | 4 | 4 | 2 | 4 | 1 | 4 | 3 | 5 | 1 | 3 | 5 | 5 | 1 | 1 | 4 | 4 | 2 | 2 | 3 | 4 | 4 | 2 | 4 | 2 | 3 | 5 | 4 | 3 | 2 | 2 | 1 | 1 | 1 | 2 | 5 | 5 | 4 | 4 | 3 | 5 | 1 | 4 | 5 | 1 | 1 | 2 | 2 | 3 | 2 | 4 | 4
198 | 19 | 9 | 28 | 37 | 51 | 58 | 71 | 82 | 99 | 115 | 127 | 136 | 143 | 155 | 1 | 2 | 5 | 1 | 5 | 5 | 5 | 4 | 2 | 4 | 1 | 2 | 5 | 3 | 4 | 2 | 2 | 3 | 1 | 1 | 4 | 2 | 2 | 5 | 1 | 2 | 3 | 5 | 3 | 4 | 5 | 5 | 5 | 5 | 4 | 2 | 4 | 2 | 4 | 2 | 2 | 3 | 2 | 2 | 1 | 2 | 1 | 3 | 2 | 5 | 2 | 3
199 | 19 | 9 | 21 | 33 | 39 | 52 | 68 | 81 | 90 | 104 | 117 | 127 | 138 | 152 | 3 | 4 | 1 | 1 | 5 | 5 | 1 | 1 | 1 | 3 | 5 | 3 | 2 | 2 | 1 | 1 | 4 | 2 | 5 | 2 | 4 | 5 | 3 | 4 | 2 | 4 | 5 | 2 | 2 | 1 | 4 | 2 | 1 | 4 | 5 | 4 | 2 | 2 | 4 | 5 | 4 | 1 | 3 | 2 | 4 | 1 | 2 | 4 | 4 | 3 | 3 | 4
200 | 23 | 15 | 29 | 41 | 51 | 63 | 73 | 84 | 101 | 112 | 128 | 140 | 153 | 164 | 2 | 3 | 5 | 5 | 3 | 5 | 2 | 4 | 3 | 2 | 2 | 5 | 2 | 2 | 5 | 1 | 3 | 4 | 4 | 1 | 4 | 1 | 4 | 1 | 4 | 2 | 3 | 2 | 5 | 3 | 4 | 5 | 2 | 4 | 3 | 2 | 5 | 2 | 4 | 5 | 4 | 3 | 4 | 1 | 3 | 4 | 2 | 4 | 4 | 3 | 3 | 1
201 | 19 | 14 | 25 | 36 | 50 | 63 | 76 | 92 | 106 | 115 | 131 | 139 | 148 | 158 | 3 | 5 | 2 | 4 | 1 | 4 | 2 | 4 | 1 | 2 | 4 | 4 | 2 | 5 | 3 | 4 | 1 | 3 | 5 | 4 | 1 | 5 | 4 | 3 | 2 | 5 | 4 | 5 | 2 | 3 | 5 | 4 | 2 | 4 | 1 | 2 | 4 | 5 | 2 | 5 | 3 | 1 | 3 | 1 | 1 | 4 | 3 | 1 | 2 | 2 | 1 | 5
202 | 20 | 14 | 26 | 38 | 54 | 70 | 80 | 90 | 103 | 115 | 127 | 138 | 152 | 165 | 3 | 5 | 3 | 3 | 4 | 2 | 1 | 5 | 3 | 2 | 2 | 5 | 4 | 5 | 2 | 5 | 5 | 5 | 4 | 2 | 2 | 2 | 2 | 4 | 1 | 5 | 2 | 2 | 3 | 2 | 3 | 5 | 1 | 2 | 4 | 5 | 4 | 1 | 4 | 3 | 5 | 3 | 1 | 2 | 4 | 4 | 2 | 4 | 2 | 4 | 3 | 4
203 | 15 | 8 | 23 | 41 | 51 | 68 | 79 | 87 | 98 | 112 | 120 | 128 | 140 | 154 | 1 | 4 | 2 | 1 | 3 | 4 | 3 | 5 | 5 | 5 | 5 | 3 | 1 | 4 | 2 | 3 | 4 | 4 | 4 | 5 | 1 | 4 | 3 | 3 | 3 | 1 | 1 | 3 | 1 | 4 | 3 | 3 | 4 | 1 | 5 | 4 | 1 | 3 | 1 | 3 | 2 | 2 | 1 | 3 | 3 | 2 | 4 | 3 | 1 | 3 | 5 | 5
204 | 15 | 8 | 22 | 39 | 54 | 67 | 79 | 89 | 105 | 114 | 127 | 139 | 152 | 168 | 3 | 1 | 3 | 1 | 5 | 2 | 5 | 2 | 4 | 5 | 4 | 4 | 3 | 4 | 4 | 4 | 4 | 5 | 2 | 2 | 3 | 3 | 3 | 3 | 2 | 3 | 2 | 3 | 2 | 4 | 5 | 5 | 1 | 4 | 3 | 1 | 3 | 4 | 5 | 1 | 2 | 4 | 1 | 5 | 4 | 3 | 2 | 4 | 4 | 4 | 4 | 4
205 | 16 | 7 | 21 | 31 | 46 | 56 | 65 | 79 | 93 | 103 | 114 | 126 | 141 | 151 | 1 | 1 | 1 | 4 | 4 | 5 | 3 | 2 | 1 | 3 | 1 | 5 | 5 | 5 | 3 | 2 | 2 | 3 | 1 | 4 | 2 | 2 | 2 | 3 | 4 | 3 | 4 | 3 | 3 | 4 | 3 | 4 | 2 | 1 | 5 | 2 | 2 | 4 | 2 | 3 | 3 | 3 | 5 | 1 | 2 | 3 | 5 | 5 | 3 | 1 | 3 | 3
206 | 15 | 12 | 23 | 36 | 49 | 63 | 77 | 90 | 102 | 117 | 129 | 143 | 153 | 164 | 4 | 5 | 1 | 2 | 2 | 1 | 4 | 4 | 3 | 4 | 1 | 5 | 3 | 3 | 4 | 3 | 5 | 4 | 2 | 3 | 3 | 1 | 5 | 5 | 4 | 1 | 4 | 4 | 5 | 4 | 1 | 2 | 4 | 3 | 5 | 3 | 3 | 5 | 1 | 3 | 5 | 3 | 4 | 2 | 3 | 2 | 4 | 1 | 5 | 1 | 4 | 1
207 | 21 | 14 | 25 | 37 | 48 | 57 | 68 | 80 | 92 | 100 | 113 | 127 | 136 | 148 | 5 | 1 | 4 | 4 | 3 | 4 | 2 | 2 | 1 | 5 | 4 | 2 | 5 | 1 | 1 | 4 | 1 | 4 | 3 | 1 | 3 | 3 | 2 | 3 | 2 | 3 | 2 | 5 | 1 | 3 | 4 | 4 | 1 | 1 | 1 | 5 | 5 | 2 | 2 | 4 | 5 | 4 | 2 | 3 | 4 | 1 | 1 | 3 | 4 | 2 | 1 | 5
208 | 14 | 8 | 18 | 26 | 40 | 50 | 63 | 72 | 88 | 98 | 110 | 122 | 134 | 149 | 1 | 1 | 3 | 3 | 4 | 2 | 3 | 1 | 5 | 1 | 1 | 1 | 3 | 4 | 3 | 4 | 3 | 4 | 2 | 1 | 1 | 4 | 3 | 5 | 1 | 2 | 3 | 3 | 3 | 5 | 5 | 3 | 1 | 3 | 2 | 4 | 2 | 1 | 5 | 4 | 3 | 2 | 3 | 4 | 1 | 5 | 5 | 1 | 4 | 2 | 4 | 5
209 | 19 | 11 | 26 | 38 | 54 | 67 | 80 | 93 | 105 | 114 | 126 | 131 | 144 | 151 | 3 | 3 | 2 | 3 | 4 | 4 | 4 | 3 | 2 | 5 | 2 | 3 | 5 | 5 | 5 | 1 | 5 | 3 | 4 | 1 | 5 | 5 | 1 | 2 | 5 | 2 | 4 | 2 | 4 | 2 | 3 | 3 | 4 | 1 | 1 | 3 | 5 | 1 | 3 | 3 | 1 | 2 | 1 | 1 | 3 | 3 | 5 | 2 | 2 | 1 | 1 | 3
210 | 22 | 16 | 31 | 43 | 53 | 66 | 81 | 90 | 97 | 111 | 121 | 138 | 147 | 160 | 5 | 1 | 5 | 5 | 4 | 2 | 5 | 4 | 2 | 2 | 4 | 4 | 5 | 1 | 1 | 3 | 2 | 3 | 3 | 5 | 5 | 3 | 4 | 3 | 1 | 3 | 3 | 2 | 1 | 1 | 4 | 1 | 5 | 2 | 2 | 5 | 3 | 2 | 4 | 1 | 5 | 3 | 5 | 4 | 2 | 3 | 1 | 3 | 3 | 5 | 4 | 1
211 | 18 | 15 | 25 | 36 | 47 | 57 | 71 | 81 | 90 | 102 | 118 | 128 | 137 | 148 | 3 | 3 | 4 | 5 | 1 | 2 | 2 | 5 | 1 | 1 | 4 | 5 | 5 | 2 | 1 | 3 | 4 | 3 | 1 | 2 | 3 | 2 | 4 | 5 | 1 | 2 | 2 | 5 | 3 | 1 | 4 | 1 | 5 | 3 | 3 | 1 | 5 | 5 | 1 | 5 | 2 | 4 | 2 | 2 | 1 | 3 | 1 | 4 | 2 | 3 | 1 | 5
212 | 15 | 12 | 24 | 39 | 50 | 63 | 74 | 84 | 96 | 105 | 120 | 134 | 144 | 154 | 1 | 4 | 5 | 2 | 2 | 1 | 4 | 5 | 2 | 4 | 4 | 5 | 3 | 2 | 4 | 2 | 3 | 1 | 4 | 5 | 1 | 3 | 5 | 2 | 1 | 5 | 1 | 3 | 2 | 4 | 1 | 5 | 2 | 2 | 3 | 2 | 3 | 4 | 4 | 4 | 1 | 4 | 5 | 4 | 2 | 4 | 3 | 1 | 3 | 2 | 1 | 4
213 | 17 | 8 | 25 | 39 | 50 | 60 | 70 | 83 | 92 | 102 | 109 | 117 | 130 | 143 | 4 | 1 | 1 | 2 | 5 | 4 | 4 | 4 | 2 | 5 | 4 | 3 | 1 | 5 | 3 | 2 | 3 | 2 | 2 | 3 | 5 | 2 | 1 | 2 | 5 | 3 | 3 | 2 | 2 | 4 | 1 | 2 | 1 | 3 | 2 | 4 | 1 | 2 | 3 | 1 | 1 | 2 | 1 | 4 | 2 | 4 | 3 | 4 | 4 | 5 | 3 | 1
214 | 16 | 12 | 24 | 39 | 51 | 58 | 64 | 73 | 81 | 90 | 100 | 110 | 123 | 137 | 4 | 1 | 4 | 3 | 2 | 2 | 4 | 4 | 5 | 3 | 2 | 5 | 3 | 5 | 3 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 3 | 4 | 2 | 2 | 1 | 2 | 2 | 3 | 1 | 4 | 1 | 3 | 1 | 3 | 1 | 2 | 4 | 1 | 4 | 4 | 1 | 3 | 2 | 4 | 4 | 2 | 3 | 5 | 4
215 | 22 | 15 | 25 | 36 | 53 | 61 | 75 | 86 | 97 | 108 | 118 | 128 | 145 | 152 | 4 | 3 | 4 | 4 | 4 | 3 | 1 | 2 | 1 | 4 | 1 | 5 | 4 | 3 | 5 | 5 | 2 | 3 | 1 | 2 | 2 | 5 | 4 | 3 | 1 | 4 | 1 | 5 | 1 | 3 | 5 | 2 | 4 | 1 | 4 | 2 | 5 | 1 | 3 | 1 | 3 | 2 | 2 | 3 | 3 | 5 | 5 | 4 | 2 | 1 | 1 | 3
216 | 16 | 11 | 21 | 33 | 52 | 64 | 77 | 89 | 105 | 116 | 127 | 137 | 148 | 159 | 2 | 2 | 5 | 2 | 3 | 2 | 2 | 3 | 2 | 5 | 2 | 3 | 5 | 5 | 5 | 4 | 2 | 4 | 4 | 2 | 1 | 4 | 4 | 4 | 2 | 4 | 5 | 1 | 3 | 5 | 5 | 3 | 5 | 2 | 1 | 3 | 1 | 2 | 5 | 3 | 4 | 2 | 1 | 3 | 2 | 2 | 5 | 2 | 4 | 2 | 1 | 4
217 | 19 | 12 | 26 | 39 | 52 | 61 | 76 | 92 | 104 | 117 | 129 | 141 | 155 | 166 | 3 | 1 | 3 | 5 | 4 | 3 | 2 | 5 | 1 | 3 | 4 | 5 | 5 | 5 | 1 | 2 | 1 | 3 | 1 | 4 | 5 | 3 | 2 | 5 | 5 | 4 | 4 | 3 | 2 | 3 | 5 | 2 | 1 | 5 | 2 | 5 | 3 | 5 | 1 | 3 | 3 | 1 | 5 | 3 | 5 | 3 | 1 | 5 | 4 | 3 | 2 | 2
218 | 20 | 12 | 25 | 40 | 53 | 65 | 73 | 82 | 90 | 108 | 117 | 131 | 140 | 153 | 2 | 4 | 1 | 5 | 3 | 5 | 4 | 1 | 3 | 3 | 5 | 4 | 3 | 2 | 4 | 4 | 1 | 3 | 4 | 4 | 1 | 2 | 3 | 2 | 1 | 5 | 2 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 4 | 5 | 2 | 2 | 4 | 1 | 3 | 2 | 4 | 5 | 1 | 1 | 5 | 2 | 2 | 3 | 5 | 3
219 | 13 | 8 | 19 | 32 | 46 | 58 | 71 | 85 | 96 | 108 | 124 | 137 | 148 | 160 | 1 | 2 | 2 | 3 | 1 | 4 | 2 | 4 | 5 | 5 | 1 | 2 | 4 | 2 | 5 | 3 | 5 | 4 | 1 | 2 | 2 | 5 | 3 | 3 | 2 | 5 | 5 | 2 | 1 | 3 | 3 | 4 | 2 | 1 | 4 | 5 | 4 | 5 | 3 | 4 | 3 | 2 | 5 | 3 | 2 | 4 | 1 | 4 | 3 | 2 | 4 | 3
220 | 25 | 16 | 30 | 40 | 58 | 68 | 79 | 97 | 106 | 116 | 131 | 142 | 152 | 167 | 3 | 5 | 5 | 3 | 5 | 4 | 1 | 4 | 2 | 1 | 5 | 2 | 4 | 5 | 4 | 5 | 1 | 3 | 4 | 2 | 2 | 3 | 5 | 1 | 5 | 4 | 4 | 5 | 4 | 1 | 2 | 2 | 3 | 5 | 1 | 1 | 5 | 3 | 5 | 2 | 2 | 2 | 3 | 4 | 5 | 2 | 1 | 2 | 5 | 5 | 4 | 1
221 | 14 | 8 | 21 | 34 | 47 | 58 | 69 | 81 | 93 | 105 | 112 | 125 | 135 | 148 | 2 | 1 | 2 | 3 | 3 | 3 | 5 | 2 | 2 | 4 | 5 | 2 | 5 | 5 | 1 | 2 | 2 | 5 | 3 | 1 | 2 | 3 | 3 | 3 | 5 | 3 | 1 | 3 | 3 | 2 | 5 | 2 | 2 | 4 | 3 | 3 | 1 | 1 | 2 | 3 | 5 | 4 | 2 | 2 | 3 | 3 | 2 | 2 | 5 | 2 | 3 | 3
222 | 20 | 15 | 26 | 36 | 48 | 61 | 77 | 90 | 102 | 112 | 125 | 139 | 150 | 160 | 5 | 2 | 4 | 4 | 4 | 1 | 3 | 3 | 1 | 2 | 2 | 5 | 4 | 1 | 2 | 5 | 3 | 4 | 3 | 3 | 5 | 4 | 3 | 4 | 2 | 4 | 2 | 5 | 1 | 4 | 3 | 4 | 5 | 2 | 1 | 2 | 4 | 2 | 3 | 4 | 3 | 4 | 4 | 3 | 4 | 2 | 1 | 4 | 1 | 2 | 3 | 4
223 | 17 | 10 | 21 | 27 | 40 | 54 | 63 | 76 | 82 | 97 | 106 | 119 | 132 | 141 | 3 | 2 | 2 | 3 | 5 | 2 | 1 | 3 | 3 | 1 | 1 | 1 | 4 | 5 | 1 | 3 | 3 | 5 | 5 | 1 | 1 | 2 | 3 | 3 | 2 | 4 | 2 | 5 | 1 | 1 | 1 | 3 | 5 | 4 | 3 | 3 | 2 | 2 | 2 | 3 | 4 | 1 | 4 | 4 | 4 | 1 | 3 | 5 | 3 | 1 | 3 | 2
224 | 18 | 12 | 25 | 32 | 43 | 52 | 65 | 78 | 89 | 99 | 105 | 121 | 133 | 145 | 2 | 4 | 5 | 1 | 3 | 3 | 3 | 4 | 3 | 2 | 1 | 1 | 1 | 1 | 5 | 4 | 2 | 1 | 1 | 5 | 4 | 4 | 4 | 1 | 5 | 3 | 4 | 1 | 4 | 3 | 1 | 3 | 2 | 5 | 2 | 1 | 2 | 1 | 2 | 1 | 5 | 4 | 3 | 4 | 4 | 2 | 4 | 2 | 4 | 2 | 2 | 4
225 | 11 | 5 | 17 | 29 | 39 | 50 | 58 | 69 | 80 | 92 | 103 | 111 | 119 | 134 | 1 | 2 | 1 | 1 | 5 | 1 | 1 | 5 | 1 | 5 | 2 | 4 | 1 | 4 | 3 | 2 | 1 | 5 | 4 | 1 | 3 | 1 | 2 | 2 | 1 | 5 | 4 | 1 | 3 | 4 | 1 | 3 | 2 | 5 | 2 | 3 | 3 | 4 | 1 | 3 | 2 | 2 | 1 | 3 | 1 | 4 | 2 | 1 | 4 | 5 | 3 | 3
226 | 27 | 17 | 37 | 50 | 60 | 73 | 83 | 90 | 108 | 116 | 125 | 140 | 152 | 169 | 4 | 4 | 5 | 4 | 5 | 5 | 5 | 5 | 2 | 3 | 4 | 4 | 4 | 2 | 1 | 3 | 2 | 2 | 5 | 4 | 5 | 1 | 2 | 2 | 4 | 1 | 1 | 1 | 4 | 5 | 5 | 4 | 1 | 2 | 4 | 1 | 2 | 3 | 3 | 1 | 5 | 3 | 5 | 2 | 5 | 2 | 2 | 3 | 5 | 4 | 3 | 5
227 | 19 | 14 | 29 | 41 | 49 | 60 | 75 | 87 | 103 | 113 | 125 | 137 | 148 | 158 | 4 | 3 | 2 | 5 | 4 | 1 | 5 | 5 | 2 | 4 | 4 | 2 | 3 | 2 | 2 | 1 | 3 | 4 | 3 | 1 | 4 | 5 | 5 | 1 | 4 | 1 | 3 | 4 | 5 | 5 | 5 | 1 | 1 | 4 | 2 | 3 | 2 | 5 | 4 | 1 | 4 | 3 | 2 | 3 | 3 | 1 | 3 | 4 | 3 | 2 | 3 | 2
228 | 24 | 15 | 33 | 46 | 59 | 68 | 82 | 93 | 107 | 118 | 130 | 142 | 154 | 166 | 4 | 3 | 5 | 3 | 5 | 4 | 5 | 4 | 2 | 5 | 2 | 4 | 4 | 2 | 2 | 5 | 1 | 1 | 3 | 4 | 4 | 5 | 3 | 2 | 5 | 2 | 3 | 1 | 2 | 4 | 5 | 3 | 3 | 2 | 1 | 5 | 4 | 2 | 1 | 5 | 3 | 4 | 4 | 1 | 1 | 4 | 4 | 3 | 4 | 5 | 1 | 2
229 | 10 | 5 | 16 | 31 | 40 | 49 | 62 | 76 | 87 | 103 | 116 | 127 | 138 | 147 | 1 | 1 | 1 | 2 | 4 | 1 | 5 | 1 | 5 | 1 | 4 | 5 | 4 | 2 | 1 | 2 | 3 | 3 | 1 | 2 | 3 | 4 | 3 | 3 | 5 | 5 | 1 | 3 | 4 | 4 | 1 | 2 | 5 | 2 | 4 | 5 | 5 | 3 | 3 | 2 | 1 | 4 | 4 | 2 | 4 | 3 | 2 | 2 | 2 | 4 | 1 | 2
230 | 21 | 15 | 24 | 29 | 38 | 51 | 60 | 76 | 89 | 107 | 118 | 135 | 148 | 158 | 3 | 3 | 5 | 4 | 3 | 3 | 1 | 2 | 1 | 1 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 3 | 4 | 5 | 4 | 2 | 1 | 2 | 3 | 5 | 3 | 5 | 3 | 1 | 5 | 4 | 4 | 5 | 5 | 4 | 4 | 4 | 2 | 1 | 5 | 4 | 3 | 5 | 3 | 2 | 5 | 3 | 3 | 2 | 3 | 2
231 | 18 | 12 | 25 | 36 | 49 | 60 | 76 | 83 | 97 | 104 | 113 | 128 | 144 | 156 | 5 | 4 | 1 | 2 | 2 | 4 | 4 | 3 | 3 | 2 | 3 | 3 | 3 | 1 | 4 | 5 | 1 | 1 | 4 | 5 | 2 | 5 | 5 | 4 | 2 | 2 | 2 | 1 | 4 | 3 | 3 | 4 | 1 | 1 | 2 | 3 | 2 | 3 | 2 | 2 | 1 | 4 | 5 | 5 | 5 | 5 | 1 | 5 | 5 | 4 | 1 | 2
232 | 25 | 16 | 31 | 43 | 49 | 63 | 79 | 94 | 105 | 118 | 132 | 141 | 154 | 170 | 5 | 1 | 5 | 5 | 5 | 4 | 1 | 5 | 2 | 3 | 3 | 4 | 1 | 1 | 2 | 2 | 2 | 4 | 5 | 3 | 5 | 3 | 4 | 4 | 4 | 3 | 3 | 5 | 1 | 5 | 3 | 2 | 2 | 4 | 2 | 5 | 5 | 3 | 2 | 4 | 2 | 1 | 5 | 1 | 4 | 1 | 4 | 4 | 4 | 4 | 4 | 4
233 | 20 | 14 | 26 | 42 | 51 | 66 | 74 | 88 | 101 | 111 | 121 | 132 | 142 | 156 | 2 | 5 | 3 | 4 | 4 | 2 | 1 | 5 | 5 | 5 | 1 | 5 | 3 | 1 | 2 | 3 | 5 | 5 | 4 | 1 | 1 | 1 | 4 | 2 | 2 | 3 | 5 | 4 | 5 | 4 | 3 | 1 | 4 | 4 | 1 | 1 | 4 | 2 | 1 | 3 | 3 | 4 | 2 | 2 | 1 | 3 | 4 | 2 | 5 | 3 | 1 | 5
234 | 16 | 7 | 22 | 38 | 49 | 54 | 71 | 86 | 96 | 111 | 122 | 130 | 139 | 151 | 2 | 1 | 3 | 1 | 5 | 4 | 5 | 1 | 5 | 5 | 3 | 3 | 3 | 4 | 3 | 1 | 1 | 2 | 1 | 1 | 4 | 3 | 5 | 5 | 2 | 3 | 5 | 5 | 3 | 3 | 2 | 2 | 4 | 5 | 1 | 5 | 3 | 2 | 4 | 2 | 1 | 1 | 3 | 3 | 1 | 5 | 2 | 1 | 4 | 4 | 1 | 3
235 | 23 | 14 | 33 | 46 | 57 | 70 | 86 | 104 | 119 | 128 | 137 | 148 | 160 | 174 | 5 | 2 | 2 | 5 | 5 | 4 | 5 | 5 | 3 | 2 | 3 | 5 | 1 | 4 | 4 | 2 | 4 | 4 | 4 | 1 | 5 | 5 | 4 | 2 | 5 | 5 | 3 | 5 | 5 | 2 | 4 | 4 | 4 | 1 | 1 | 3 | 1 | 4 | 1 | 3 | 3 | 1 | 4 | 3 | 1 | 4 | 4 | 3 | 2 | 5 | 5 | 2
236 | 21 | 16 | 25 | 36 | 47 | 54 | 66 | 74 | 86 | 98 | 105 | 114 | 126 | 140 | 5 | 5 | 1 | 5 | 4 | 1 | 3 | 1 | 3 | 2 | 1 | 5 | 2 | 3 | 3 | 3 | 2 | 3 | 1 | 1 | 3 | 2 | 3 | 4 | 3 | 2 | 1 | 2 | 3 | 3 | 1 | 5 | 5 | 1 | 4 | 2 | 1 | 1 | 4 | 1 | 3 | 2 | 2 | 2 | 5 | 1 | 3 | 3 | 5 | 3 | 2 | 4
237 | 23 | 16 | 33 | 43 | 58 | 66 | 77 | 87 | 95 | 109 | 119 | 132 | 137 | 149 | 3 | 4 | 4 | 5 | 4 | 3 | 5 | 5 | 1 | 1 | 4 | 4 | 3 | 3 | 5 | 4 | 1 | 2 | 3 | 2 | 5 | 1 | 1 | 4 | 5 | 3 | 1 | 1 | 2 | 3 | 2 | 1 | 2 | 3 | 4 | 5 | 1 | 1 | 3 | 5 | 2 | 2 | 4 | 5 | 1 | 1 | 2 | 1 | 3 | 5 | 1 | 3
238 | 16 | 12 | 20 | 29 | 37 | 52 | 66 | 80 | 91 | 105 | 115 | 126 | 143 | 152 | 5 | 5 | 1 | 1 | 3 | 1 | 2 | 2 | 2 | 3 | 1 | 3 | 2 | 3 | 1 | 2 | 5 | 4 | 5 | 1 | 4 | 4 | 2 | 4 | 1 | 4 | 4 | 5 | 2 | 1 | 4 | 4 | 5 | 3 | 2 | 4 | 4 | 3 | 2 | 1 | 5 | 1 | 3 | 2 | 4 | 5 | 3 | 5 | 3 | 1 | 4 | 1
239 | 17 | 12 | 24 | 34 | 44 | 58 | 67 | 86 | 99 | 107 | 118 | 131 | 143 | 150 | 3 | 3 | 5 | 1 | 3 | 2 | 5 | 2 | 1 | 2 | 3 | 4 | 4 | 3 | 2 | 1 | 5 | 5 | 3 | 1 | 4 | 1 | 3 | 1 | 5 | 4 | 5 | 5 | 1 | 2 | 5 | 5 | 2 | 2 | 1 | 3 | 2 | 2 | 3 | 4 | 5 | 1 | 2 | 5 | 1 | 2 | 4 | 5 | 1 | 3 | 2 | 1
240 | 20 | 13 | 24 | 38 | 47 | 60 | 76 | 87 | 99 | 107 | 113 | 127 | 143 | 154 | 5 | 2 | 4 | 2 | 2 | 5 | 1 | 3 | 4 | 3 | 2 | 5 | 3 | 3 | 1 | 2 | 5 | 2 | 2 | 4 | 3 | 4 | 5 | 4 | 4 | 1 | 1 | 5 | 3 | 2 | 4 | 3 | 1 | 3 | 1 | 3 | 3 | 1 | 1 | 1 | 4 | 4 | 3 | 3 | 2 | 5 | 5 | 4 | 2 | 5 | 1 | 3
241 | 12 | 6 | 18 | 27 | 42 | 53 | 64 | 73 | 87 | 96 | 109 | 124 | 137 | 148 | 3 | 1 | 1 | 1 | 4 | 2 | 1 | 5 | 1 | 5 | 1 | 2 | 2 | 3 | 5 | 5 | 2 | 5 | 2 | 2 | 2 | 4 | 2 | 3 | 2 | 1 | 1 | 5 | 3 | 1 | 5 | 5 | 2 | 2 | 3 | 2 | 4 | 3 | 3 | 3 | 3 | 3 | 4 | 5 | 2 | 1 | 5 | 5 | 2 | 3 | 5 | 1
242 | 18 | 11 | 22 | 37 | 47 | 59 | 65 | 82 | 95 | 106 | 118 | 134 | 146 | 158 | 4 | 3 | 1 | 3 | 5 | 2 | 1 | 3 | 5 | 5 | 1 | 4 | 3 | 4 | 2 | 1 | 4 | 2 | 4 | 2 | 1 | 1 | 3 | 1 | 5 | 2 | 5 | 5 | 4 | 4 | 2 | 3 | 1 | 4 | 4 | 2 | 4 | 2 | 5 | 1 | 4 | 2 | 5 | 5 | 2 | 3 | 3 | 4 | 1 | 5 | 4 | 2
243 | 19 | 13 | 29 | 41 | 50 | 57 | 73 | 82 | 96 | 103 | 116 | 128 | 135 | 149 | 1 | 5 | 2 | 5 | 4 | 2 | 5 | 5 | 4 | 4 | 1 | 3 | 1 | 4 | 3 | 1 | 1 | 2 | 1 | 3 | 5 | 5 | 4 | 2 | 3 | 2 | 1 | 3 | 2 | 4 | 4 | 4 | 2 | 3 | 1 | 1 | 3 | 5 | 4 | 1 | 3 | 5 | 2 | 2 | 1 | 1 | 4 | 1 | 4 | 4 | 1 | 5
244 | 15 | 12 | 20 | 34 | 44 | 56 | 73 | 89 | 102 | 118 | 128 | 140 | 155 | 167 | 1 | 1 | 5 | 5 | 1 | 2 | 3 | 2 | 3 | 5 | 3 | 3 | 1 | 4 | 1 | 4 | 5 | 3 | 2 | 2 | 3 | 5 | 4 | 5 | 4 | 2 | 5 | 5 | 4 | 3 | 5 | 1 | 5 | 3 | 5 | 3 | 5 | 2 | 1 | 2 | 1 | 5 | 4 | 2 | 3 | 5 | 5 | 2 | 4 | 1 | 4 | 3
245 | 17 | 11 | 22 | 36 | 46 | 59 | 70 | 83 | 95 | 104 | 120 | 132 | 141 | 154 | 2 | 5 | 2 | 2 | 5 | 1 | 2 | 3 | 2 | 3 | 5 | 4 | 1 | 2 | 5 | 2 | 4 | 2 | 2 | 5 | 2 | 4 | 2 | 3 | 3 | 4 | 2 | 4 | 1 | 5 | 3 | 3 | 5 | 2 | 1 | 1 | 5 | 3 | 4 | 4 | 2 | 1 | 5 | 4 | 3 | 1 | 2 | 3 | 3 | 3 | 2 | 5
246 | 16 | 11 | 23 | 33 | 40 | 49 | 62 | 76 | 88 | 96 | 110 | 124 | 137 | 151 | 5 | 1 | 3 | 2 | 1 | 4 | 2 | 5 | 3 | 4 | 1 | 2 | 1 | 3 | 1 | 2 | 2 | 3 | 1 | 3 | 3 | 5 | 2 | 3 | 4 | 2 | 4 | 4 | 3 | 3 | 5 | 1 | 1 | 4 | 1 | 2 | 4 | 4 | 1 | 5 | 3 | 2 | 5 | 4 | 1 | 4 | 4 | 4 | 5 | 5 | 1 | 3
247 | 15 | 13 | 17 | 25 | 39 | 47 | 59 | 71 | 82 | 91 | 105 | 122 | 136 | 155 | 3 | 5 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 5 | 2 | 3 | 4 | 2 | 2 | 1 | 3 | 3 | 2 | 3 | 4 | 5 | 2 | 1 | 4 | 5 | 1 | 3 | 2 | 2 | 1 | 5 | 1 | 3 | 4 | 2 | 5 | 4 | 3 | 5 | 5 | 3 | 2 | 5 | 4 | 5 | 5 | 4 | 5
248 | 23 | 16 | 28 | 43 | 58 | 67 | 78 | 86 | 99 | 112 | 131 | 144 | 159 | 171 | 5 | 4 | 4 | 3 | 5 | 2 | 1 | 4 | 4 | 5 | 2 | 4 | 2 | 5 | 5 | 3 | 1 | 3 | 3 | 2 | 3 | 1 | 5 | 2 | 1 | 3 | 1 | 3 | 3 | 1 | 4 | 5 | 2 | 4 | 4 | 3 | 5 | 5 | 5 | 4 | 3 | 5 | 3 | 2 | 4 | 2 | 4 | 5 | 1 | 5 | 3 | 3
249 | 10 | 7 | 16 | 32 | 48 | 62 | 80 | 92 | 104 | 115 | 126 | 138 | 146 | 160 | 1 | 1 | 1 | 4 | 1 | 2 | 4 | 2 | 3 | 3 | 5 | 5 | 4 | 4 | 5 | 3 | 4 | 3 | 3 | 4 | 4 | 5 | 4 | 5 | 2 | 4 | 5 | 1 | 2 | 3 | 2 | 5 | 3 | 2 | 2 | 4 | 1 | 4 | 3 | 3 | 4 | 1 | 3 | 4 | 4 | 2 | 1 | 1 | 2 | 3 | 4 | 5
250 | 13 | 8 | 22 | 33 | 43 | 58 | 70 | 82 | 95 | 106 | 118 | 133 | 143 | 156 | 1 | 2 | 2 | 3 | 4 | 1 | 5 | 4 | 3 | 1 | 5 | 2 | 2 | 4 | 2 | 2 | 3 | 3 | 5 | 4 | 5 | 3 | 2 | 2 | 5 | 3 | 3 | 1 | 1 | 4 | 3 | 5 | 1 | 4 | 3 | 3 | 4 | 2 | 5 | 1 | 4 | 5 | 1 | 5 | 1 | 5 | 1 | 3 | 1 | 3 | 4 | 5
251 | 15 | 13 | 19 | 32 | 44 | 58 | 72 | 79 | 93 | 101 | 114 | 128 | 141 | 157 | 1 | 5 | 2 | 5 | 1 | 1 | 2 | 2 | 4 | 4 | 2 | 3 | 3 | 1 | 3 | 5 | 5 | 5 | 1 | 3 | 3 | 5 | 5 | 1 | 4 | 1 | 1 | 1 | 3 | 2 | 5 | 4 | 5 | 1 | 1 | 1 | 3 | 5 | 4 | 1 | 2 | 5 | 2 | 5 | 3 | 2 | 4 | 4 | 3 | 3 | 5 | 5
252 | 17 | 7 | 26 | 41 | 52 | 66 | 74 | 86 | 98 | 111 | 123 | 134 | 145 | 160 | 1 | 1 | 2 | 3 | 5 | 5 | 5 | 4 | 5 | 2 | 5 | 3 | 3 | 1 | 3 | 4 | 1 | 5 | 4 | 4 | 2 | 2 | 1 | 3 | 4 | 3 | 3 | 2 | 4 | 3 | 2 | 3 | 1 | 4 | 5 | 3 | 5 | 1 | 1 | 5 | 3 | 1 | 2 | 5 | 1 | 4 | 5 | 1 | 3 | 3 | 5 | 4
253 | 22 | 15 | 27 | 41 | 51 | 64 | 79 | 96 | 109 | 120 | 134 | 150 | 160 | 172 | 1 | 5 | 4 | 5 | 2 | 5 | 4 | 1 | 5 | 3 | 5 | 1 | 3 | 2 | 4 | 1 | 4 | 1 | 4 | 4 | 4 | 2 | 4 | 5 | 4 | 5 | 4 | 4 | 4 | 5 | 3 | 1 | 2 | 4 | 2 | 3 | 4 | 4 | 5 | 1 | 4 | 3 | 4 | 5 | 3 | 3 | 1 | 3 | 5 | 3 | 3 | 1
254 | 19 | 12 | 24 | 37 | 50 | 62 | 74 | 83 | 95 | 107 | 118 | 133 | 148 | 162 | 2 | 3 | 2 | 5 | 2 | 5 | 4 | 1 | 1 | 5 | 4 | 3 | 5 | 2 | 3 | 3 | 1 | 3 | 5 | 3 | 3 | 5 | 3 | 1 | 1 | 3 | 2 | 3 | 3 | 2 | 4 | 3 | 2 | 4 | 5 | 1 | 2 | 3 | 3 | 3 | 4 | 4 | 2 | 5 | 4 | 1 | 5 | 5 | 3 | 4 | 3 | 4
255 | 15 | 7 | 18 | 24 | 31 | 45 | 61 | 72 | 80 | 86 | 100 | 114 | 130 | 138 | 2 | 2 | 2 | 1 | 4 | 4 | 1 | 2 | 1 | 1 | 1 | 3 | 4 | 1 | 1 | 1 | 3 | 5 | 1 | 5 | 5 | 3 | 4 | 4 | 3 | 5 | 2 | 1 | 2 | 2 | 2 | 2 | 2 | 1 | 2 | 1 | 5 | 2 | 5 | 2 | 3 | 3 | 3 | 5 | 4 | 4 | 3 | 5 | 1 | 3 | 2 | 2
256 | 24 | 16 | 28 | 40 | 48 | 62 | 73 | 80 | 88 | 97 | 106 | 115 | 128 | 143 | 1 | 5 | 5 | 5 | 4 | 4 | 2 | 2 | 1 | 5 | 2 | 4 | 3 | 1 | 1 | 3 | 4 | 4 | 4 | 2 | 3 | 1 | 3 | 4 | 1 | 1 | 4 | 1 | 4 | 1 | 2 | 1 | 3 | 1 | 3 | 2 | 4 | 1 | 2 | 2 | 1 | 1 | 5 | 2 | 3 | 5 | 4 | 1 | 5 | 4 | 1 | 5
257 | 16 | 13 | 24 | 40 | 50 | 59 | 70 | 81 | 88 | 102 | 114 | 129 | 144 | 153 | 5 | 2 | 3 | 3 | 1 | 2 | 3 | 5 | 4 | 2 | 5 | 5 | 1 | 1 | 4 | 4 | 3 | 2 | 3 | 1 | 2 | 5 | 1 | 3 | 1 | 1 | 5 | 4 | 1 | 1 | 4 | 1 | 3 | 5 | 5 | 1 | 2 | 4 | 5 | 1 | 3 | 4 | 4 | 4 | 3 | 3 | 5 | 4 | 3 | 2 | 2 | 2
258 | 15 | 8 | 20 | 33 | 46 | 58 | 73 | 80 | 94 | 107 | 119 | 129 | 141 | 157 | 1 | 1 | 4 | 2 | 3 | 4 | 4 | 1 | 2 | 2 | 5 | 4 | 1 | 3 | 5 | 4 | 4 | 3 | 2 | 3 | 1 | 4 | 5 | 5 | 2 | 1 | 3 | 1 | 1 | 5 | 5 | 3 | 2 | 1 | 5 | 5 | 1 | 2 | 4 | 5 | 4 | 2 | 3 | 1 | 1 | 3 | 3 | 5 | 5 | 2 | 4 | 5
259 | 17 | 9 | 20 | 33 | 46 | 54 | 67 | 81 | 92 | 106 | 116 | 126 | 142 | 155 | 2 | 2 | 3 | 2 | 3 | 5 | 2 | 1 | 1 | 5 | 3 | 4 | 4 | 1 | 4 | 4 | 1 | 4 | 1 | 2 | 5 | 2 | 4 | 2 | 3 | 1 | 5 | 5 | 3 | 2 | 5 | 1 | 2 | 4 | 5 | 3 | 2 | 5 | 1 | 2 | 3 | 5 | 1 | 1 | 4 | 5 | 3 | 4 | 1 | 4 | 3 | 5
260 | 22 | 13 | 27 | 45 | 57 | 72 | 89 | 102 | 108 | 117 | 132 | 145 | 152 | 166 | 3 | 2 | 5 | 3 | 4 | 5 | 3 | 2 | 5 | 5 | 4 | 4 | 3 | 3 | 1 | 5 | 1 | 5 | 4 | 5 | 3 | 5 | 5 | 4 | 5 | 3 | 1 | 4 | 1 | 1 | 2 | 2 | 1 | 1 | 5 | 2 | 3 | 2 | 5 | 5 | 2 | 5 | 4 | 2 | 2 | 1 | 2 | 2 | 2 | 4 | 4 | 4
261 | 16 | 10 | 25 | 34 | 39 | 51 | 61 | 77 | 92 | 107 | 121 | 132 | 144 | 162 | 5 | 1 | 1 | 3 | 5 | 1 | 4 | 5 | 1 | 2 | 5 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 1 | 3 | 3 | 3 | 5 | 2 | 4 | 5 | 5 | 4 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 5 | 3 | 2 | 4 | 3 | 2 | 2 | 3 | 5 | 3 | 1 | 5 | 5 | 4 | 4
262 | 17 | 14 | 23 | 35 | 48 | 59 | 72 | 87 | 95 | 108 | 123 | 136 | 145 | 154 | 2 | 5 | 3 | 4 | 1 | 2 | 2 | 4 | 1 | 5 | 2 | 4 | 5 | 4 | 3 | 1 | 1 | 4 | 3 | 3 | 2 | 3 | 4 | 4 | 2 | 4 | 5 | 4 | 1 | 2 | 3 | 2 | 1 | 3 | 5 | 4 | 2 | 5 | 4 | 4 | 1 | 3 | 4 | 5 | 3 | 2 | 1 | 3 | 3 | 4 | 1 | 1
263 | 18 | 12 | 21 | 35 | 48 | 57 | 72 | 86 | 102 | 114 | 124 | 137 | 152 | 164 | 3 | 5 | 2 | 2 | 2 | 4 | 1 | 2 | 4 | 4 | 2 | 4 | 3 | 4 | 1 | 5 | 1 | 3 | 4 | 1 | 2 | 5 | 3 | 5 | 2 | 3 | 4 | 5 | 4 | 4 | 4 | 4 | 1 | 5 | 4 | 2 | 5 | 1 | 2 | 2 | 1 | 5 | 3 | 4 | 4 | 5 | 1 | 5 | 4 | 3 | 1 | 4
264 | 23 | 15 | 29 | 38 | 51 | 62 | 75 | 89 | 97 | 110 | 125 | 139 | 152 | 165 | 2 | 5 | 3 | 5 | 4 | 4 | 2 | 4 | 1 | 2 | 4 | 2 | 5 | 5 | 2 | 1 | 4 | 3 | 3 | 1 | 1 | 2 | 5 | 5 | 5 | 3 | 2 | 4 | 1 | 3 | 2 | 2 | 3 | 1 | 5 | 4 | 3 | 3 | 4 | 5 | 2 | 3 | 5 | 4 | 2 | 5 | 2 | 4 | 5 | 3 | 3 | 2
265 | 16 | 13 | 21 | 35 | 50 | 63 | 75 | 88 | 104 | 116 | 126 | 137 | 156 | 170 | 2 | 3 | 3 | 5 | 2 | 1 | 4 | 1 | 4 | 5 | 1 | 4 | 5 | 5 | 1 | 4 | 5 | 2 | 4 | 2 | 5 | 4 | 2 | 1 | 2 | 2 | 4 | 5 | 3 | 4 | 5 | 4 | 2 | 3 | 3 | 4 | 4 | 3 | 1 | 2 | 3 | 4 | 3 | 1 | 5 | 5 | 4 | 5 | 5 | 4 | 4 | 1
266 | 18 | 13 | 21 | 32 | 47 | 62 | 69 | 80 | 94 | 109 | 125 | 137 | 148 | 161 | 3 | 5 | 4 | 1 | 2 | 3 | 2 | 1 | 4 | 1 | 5 | 1 | 2 | 4 | 4 | 5 | 4 | 1 | 5 | 5 | 2 | 2 | 1 | 2 | 1 | 2 | 5 | 3 | 5 | 5 | 3 | 1 | 4 | 3 | 5 | 3 | 5 | 5 | 4 | 2 | 3 | 3 | 3 | 3 | 2 | 5 | 1 | 3 | 5 | 5 | 2 | 1
267 | 20 | 10 | 25 | 35 | 46 | 54 | 66 | 83 | 100 | 115 | 126 | 140 | 158 | 169 | 1 | 3 | 3 | 3 | 5 | 5 | 4 | 1 | 1 | 5 | 3 | 1 | 4 | 4 | 2 | 1 | 2 | 1 | 3 | 2 | 4 | 2 | 5 | 1 | 5 | 4 | 3 | 5 | 5 | 4 | 3 | 5 | 5 | 3 | 5 | 2 | 3 | 1 | 4 | 3 | 2 | 4 | 3 | 5 | 4 | 5 | 4 | 5 | 3 | 4 | 3 | 1
268 | 18 | 9 | 24 | 38 | 56 | 68 | 82 | 100 | 108 | 123 | 138 | 152 | 168 | 179 | 3 | 2 | 3 | 1 | 4 | 5 | 1 | 5 | 1 | 5 | 3 | 5 | 5 | 5 | 3 | 5 | 3 | 3 | 3 | 3 | 1 | 5 | 4 | 4 | 3 | 5 | 5 | 5 | 2 | 2 | 1 | 3 | 5 | 2 | 5 | 3 | 5 | 4 | 4 | 2 | 3 | 4 | 3 | 4 | 5 | 2 | 4 | 5 | 5 | 2 | 3 | 1
269 | 19 | 12 | 21 | 34 | 43 | 54 | 64 | 79 | 96 | 109 | 114 | 130 | 139 | 152 | 2 | 5 | 1 | 4 | 5 | 2 | 1 | 1 | 4 | 4 | 1 | 4 | 2 | 3 | 3 | 1 | 2 | 4 | 1 | 4 | 5 | 2 | 1 | 2 | 2 | 4 | 4 | 5 | 5 | 5 | 5 | 2 | 5 | 4 | 1 | 3 | 1 | 2 | 1 | 1 | 5 | 4 | 3 | 4 | 2 | 3 | 3 | 1 | 3 | 4 | 3 | 3
270 | 19 | 12 | 27 | 31 | 43 | 50 | 59 | 71 | 84 | 98 | 112 | 127 | 141 | 150 | 1 | 5 | 5 | 1 | 5 | 2 | 4 | 4 | 1 | 1 | 1 | 1 | 3 | 4 | 2 | 3 | 3 | 1 | 1 | 2 | 1 | 3 | 1 | 4 | 3 | 3 | 3 | 3 | 4 | 4 | 1 | 4 | 2 | 5 | 5 | 2 | 2 | 2 | 5 | 5 | 5 | 2 | 5 | 3 | 5 | 1 | 3 | 5 | 4 | 3 | 1 | 1
271 | 17 | 13 | 27 | 36 | 49 | 65 | 78 | 84 | 91 | 103 | 118 | 126 | 137 | 147 | 1 | 3 | 4 | 5 | 3 | 1 | 5 | 5 | 1 | 1 | 4 | 3 | 2 | 2 | 4 | 5 | 2 | 5 | 4 | 5 | 1 | 2 | 5 | 5 | 1 | 1 | 1 | 3 | 2 | 2 | 1 | 2 | 4 | 2 | 4 | 2 | 5 | 2 | 3 | 5 | 1 | 1 | 1 | 5 | 1 | 3 | 4 | 3 | 3 | 3 | 3 | 1
272 | 21 | 15 | 26 | 32 | 41 | 56 | 70 | 81 | 93 | 106 | 118 | 127 | 140 | 155 | 2 | 5 | 4 | 4 | 1 | 5 | 3 | 2 | 1 | 1 | 2 | 2 | 3 | 1 | 1 | 4 | 3 | 5 | 5 | 2 | 3 | 5 | 2 | 4 | 2 | 5 | 2 | 2 | 3 | 4 | 4 | 1 | 2 | 3 | 5 | 3 | 1 | 3 | 5 | 3 | 3 | 1 | 3 | 2 | 3 | 5 | 1 | 4 | 4 | 5 | 4 | 2
273 | 19 | 12 | 24 | 40 | 55 | 69 | 75 | 86 | 100 | 113 | 125 | 139 | 151 | 165 | 4 | 3 | 3 | 2 | 4 | 3 | 2 | 3 | 5 | 5 | 5 | 1 | 2 | 3 | 5 | 5 | 2 | 2 | 5 | 5 | 1 | 1 | 2 | 2 | 3 | 2 | 2 | 4 | 4 | 3 | 5 | 2 | 4 | 2 | 4 | 3 | 3 | 4 | 4 | 1 | 1 | 5 | 5 | 3 | 1 | 4 | 3 | 4 | 2 | 4 | 3 | 5
274 | 11 | 9 | 20 | 30 | 42 | 54 | 72 | 83 | 94 | 109 | 121 | 133 | 146 | 162 | 2 | 2 | 4 | 1 | 1 | 1 | 4 | 5 | 2 | 1 | 3 | 4 | 4 | 2 | 1 | 5 | 3 | 5 | 1 | 3 | 5 | 5 | 3 | 5 | 2 | 3 | 1 | 5 | 4 | 2 | 1 | 4 | 5 | 3 | 3 | 4 | 1 | 3 | 3 | 5 | 3 | 1 | 5 | 3 | 1 | 4 | 3 | 5 | 3 | 4 | 4 | 5
275 | 20 | 12 | 30 | 43 | 53 | 71 | 84 | 94 | 106 | 118 | 128 | 139 | 153 | 166 | 4 | 4 | 3 | 1 | 3 | 5 | 5 | 5 | 4 | 5 | 3 | 1 | 5 | 2 | 1 | 2 | 5 | 4 | 4 | 5 | 4 | 2 | 4 | 3 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 1 | 3 | 3 | 1 | 2 | 4 | 5 | 2 | 3 | 1 | 5 | 2 | 3 | 4 | 5 | 4 | 3 | 1
276 | 23 | 18 | 31 | 42 | 55 | 71 | 81 | 96 | 107 | 124 | 137 | 146 | 159 | 172 | 5 | 5 | 4 | 4 | 3 | 2 | 5 | 3 | 4 | 2 | 1 | 4 | 5 | 4 | 3 | 1 | 5 | 2 | 5 | 4 | 5 | 2 | 2 | 1 | 4 | 4 | 2 | 5 | 2 | 4 | 2 | 3 | 3 | 5 | 5 | 4 | 1 | 3 | 4 | 5 | 2 | 3 | 3 | 1 | 3 | 1 | 4 | 5 | 3 | 3 | 2 | 5
277 | 14 | 10 | 21 | 31 | 48 | 56 | 68 | 79 | 92 | 103 | 122 | 130 | 140 | 151 | 1 | 1 | 5 | 3 | 2 | 2 | 2 | 5 | 2 | 1 | 3 | 4 | 2 | 5 | 5 | 5 | 1 | 3 | 1 | 3 | 2 | 2 | 4 | 4 | 5 | 3 | 1 | 2 | 4 | 3 | 4 | 2 | 1 | 4 | 1 | 5 | 5 | 4 | 5 | 5 | 4 | 2 | 1 | 1 | 3 | 2 | 1 | 4 | 3 | 3 | 1 | 4
278 | 15 | 8 | 19 | 28 | 41 | 50 | 61 | 73 | 90 | 103 | 116 | 126 | 137 | 148 | 1 | 5 | 1 | 1 | 5 | 2 | 2 | 2 | 1 | 4 | 2 | 2 | 2 | 3 | 3 | 5 | 2 | 2 | 4 | 1 | 4 | 5 | 1 | 1 | 3 | 1 | 5 | 3 | 3 | 5 | 4 | 5 | 4 | 1 | 3 | 5 | 2 | 4 | 5 | 2 | 5 | 2 | 2 | 1 | 5 | 1 | 2 | 3 | 1 | 2 | 4 | 4
279 | 22 | 12 | 25 | 39 | 54 | 67 | 77 | 89 | 98 | 108 | 118 | 133 | 148 | 164 | 5 | 1 | 3 | 3 | 5 | 5 | 2 | 1 | 5 | 4 | 1 | 4 | 5 | 5 | 4 | 1 | 1 | 5 | 5 | 2 | 2 | 3 | 1 | 4 | 2 | 1 | 4 | 5 | 2 | 2 | 3 | 2 | 3 | 2 | 2 | 3 | 5 | 1 | 1 | 3 | 3 | 4 | 3 | 5 | 1 | 5 | 5 | 4 | 2 | 5 | 4 | 5
280 | 18 | 9 | 26 | 40 | 58 | 69 | 80 | 93 | 105 | 117 | 128 | 140 | 156 | 172 | 2 | 5 | 1 | 1 | 4 | 5 | 4 | 4 | 5 | 1 | 3 | 5 | 5 | 4 | 5 | 4 | 1 | 3 | 3 | 4 | 2 | 2 | 3 | 4 | 2 | 1 | 5 | 5 | 5 | 4 | 1 | 2 | 3 | 3 | 4 | 2 | 5 | 2 | 3 | 1 | 3 | 2 | 2 | 5 | 4 | 5 | 5 | 2 | 5 | 3 | 3 | 5
281 | 22 | 13 | 30 | 42 | 55 | 68 | 76 | 89 | 101 | 117 | 129 | 138 | 149 | 160 | 3 | 3 | 5 | 2 | 5 | 4 | 5 | 3 | 4 | 3 | 4 | 1 | 5 | 4 | 3 | 1 | 5 | 2 | 1 | 5 | 5 | 1 | 1 | 1 | 1 | 5 | 4 | 3 | 2 | 3 | 4 | 3 | 4 | 3 | 5 | 4 | 3 | 3 | 3 | 3 | 2 | 5 | 1 | 1 | 3 | 4 | 3 | 1 | 2 | 5 | 1 | 3
282 | 22 | 17 | 28 | 42 | 56 | 67 | 80 | 93 | 107 | 119 | 127 | 144 | 152 | 164 | 4 | 4 | 4 | 5 | 4 | 1 | 1 | 5 | 4 | 2 | 3 | 5 | 1 | 4 | 5 | 4 | 4 | 2 | 4 | 1 | 2 | 4 | 4 | 3 | 5 | 5 | 1 | 2 | 3 | 2 | 4 | 5 | 3 | 4 | 1 | 4 | 1 | 1 | 1 | 5 | 4 | 5 | 4 | 4 | 2 | 1 | 4 | 1 | 5 | 4 | 1 | 2
283 | 20 | 14 | 26 | 36 | 45 | 60 | 75 | 89 | 95 | 108 | 126 | 138 | 147 | 157 | 2 | 4 | 4 | 4 | 2 | 4 | 2 | 4 | 5 | 2 | 1 | 2 | 3 | 1 | 4 | 1 | 4 | 4 | 2 | 5 | 2 | 5 | 5 | 3 | 3 | 5 | 4 | 2 | 3 | 1 | 1 | 1 | 3 | 5 | 2 | 3 | 5 | 5 | 4 | 4 | 1 | 4 | 3 | 4 | 2 | 2 | 4 | 1 | 2 | 1 | 2 | 5
284 | 17 | 11 | 22 | 30 | 47 | 55 | 65 | 79 | 90 | 106 | 120 | 133 | 144 | 155 | 3 | 5 | 2 | 1 | 4 | 2 | 4 | 1 | 1 | 1 | 1 | 5 | 2 | 5 | 5 | 5 | 2 | 4 | 1 | 1 | 5 | 1 | 2 | 2 | 3 | 5 | 4 | 2 | 4 | 1 | 1 | 5 | 5 | 2 | 5 | 4 | 5 | 5 | 1 | 3 | 4 | 2 | 5 | 2 | 4 | 1 | 1 | 5 | 4 | 1 | 2 | 4
285 | 21 | 14 | 27 | 39 | 52 | 68 | 79 | 91 | 102 | 112 | 122 | 128 | 142 | 157 | 1 | 5 | 4 | 4 | 3 | 4 | 1 | 5 | 2 | 3 | 2 | 5 | 2 | 4 | 5 | 2 | 4 | 5 | 5 | 2 | 1 | 4 | 2 | 4 | 1 | 4 | 2 | 5 | 5 | 2 | 1 | 3 | 4 | 4 | 1 | 1 | 4 | 3 | 1 | 2 | 1 | 1 | 2 | 2 | 5 | 2 | 4 | 3 | 4 | 4 | 3 | 4
286 | 16 | 10 | 21 | 33 | 46 | 54 | 62 | 74 | 87 | 106 | 124 | 137 | 152 | 167 | 3 | 2 | 2 | 3 | 3 | 3 | 3 | 2 | 1 | 5 | 4 | 2 | 2 | 5 | 5 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 4 | 2 | 3 | 3 | 2 | 4 | 3 | 2 | 3 | 5 | 5 | 4 | 5 | 5 | 5 | 5 | 3 | 5 | 1 | 5 | 4 | 3 | 3 | 3 | 5 | 4 | 3 | 4 | 4 | 4
287 | 25 | 15 | 32 | 41 | 50 | 59 | 70 | 82 | 97 | 106 | 117 | 125 | 138 | 151 | 5 | 3 | 2 | 5 | 5 | 5 | 3 | 4 | 3 | 2 | 3 | 1 | 2 | 1 | 3 | 3 | 4 | 3 | 1 | 1 | 1 | 5 | 3 | 2 | 4 | 4 | 2 | 2 | 5 | 2 | 4 | 4 | 3 | 2 | 1 | 3 | 4 | 3 | 3 | 1 | 2 | 4 | 1 | 1 | 4 | 2 | 3 | 4 | 3 | 3 | 2 | 5
288 | 19 | 11 | 24 | 34 | 43 | 51 | 62 | 75 | 84 | 97 | 108 | 117 | 130 | 136 | 4 | 3 | 2 | 2 | 4 | 4 | 3 | 2 | 3 | 4 | 1 | 2 | 1 | 1 | 3 | 4 | 2 | 2 | 2 | 2 | 2 | 5 | 2 | 2 | 3 | 5 | 3 | 2 | 1 | 1 | 4 | 3 | 1 | 2 | 5 | 5 | 3 | 5 | 2 | 1 | 1 | 2 | 1 | 5 | 4 | 5 | 3 | 1 | 1 | 2 | 2 | 1
289 | 16 | 11 | 24 | 39 | 49 | 64 | 77 | 90 | 99 | 108 | 121 | 139 | 156 | 165 | 3 | 3 | 3 | 2 | 3 | 2 | 4 | 4 | 2 | 4 | 5 | 4 | 4 | 4 | 1 | 1 | 4 | 3 | 5 | 3 | 3 | 5 | 1 | 4 | 2 | 5 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 3 | 3 | 2 | 5 | 2 | 5 | 1 | 5 | 4 | 4 | 5 | 2 | 5 | 5 | 5 | 1 | 5 | 2 | 1
290 | 15 | 8 | 20 | 29 | 44 | 56 | 64 | 77 | 83 | 96 | 106 | 117 | 127 | 142 | 2 | 4 | 1 | 1 | 5 | 2 | 3 | 2 | 1 | 5 | 1 | 2 | 2 | 4 | 4 | 5 | 2 | 3 | 3 | 4 | 1 | 3 | 2 | 2 | 5 | 4 | 2 | 2 | 2 | 1 | 1 | 2 | 4 | 3 | 1 | 5 | 1 | 5 | 1 | 3 | 5 | 2 | 1 | 3 | 3 | 2 | 2 | 3 | 5 | 3 | 4 | 3
291 | 22 | 14 | 27 | 37 | 47 | 61 | 73 | 86 | 102 | 111 | 121 | 132 | 146 | 159 | 3 | 5 | 4 | 2 | 5 | 3 | 4 | 1 | 3 | 3 | 2 | 2 | 4 | 1 | 3 | 2 | 4 | 5 | 3 | 2 | 2 | 2 | 3 | 5 | 1 | 4 | 3 | 5 | 5 | 3 | 3 | 5 | 4 | 1 | 3 | 1 | 4 | 2 | 1 | 3 | 4 | 2 | 1 | 4 | 3 | 5 | 1 | 5 | 2 | 4 | 5 | 2
292 | 11 | 5 | 15 | 27 | 35 | 46 | 55 | 68 | 80 | 90 | 98 | 112 | 126 | 135 | 1 | 1 | 2 | 1 | 3 | 3 | 3 | 1 | 2 | 2 | 5 | 3 | 3 | 1 | 3 | 1 | 5 | 2 | 2 | 2 | 4 | 3 | 1 | 1 | 3 | 4 | 1 | 5 | 2 | 1 | 5 | 4 | 2 | 3 | 1 | 4 | 4 | 2 | 1 | 1 | 5 | 4 | 3 | 2 | 3 | 2 | 5 | 4 | 2 | 2 | 1 | 4
293 | 13 | 8 | 23 | 32 | 45 | 55 | 66 | 85 | 95 | 113 | 125 | 134 | 147 | 162 | 2 | 3 | 2 | 1 | 3 | 2 | 5 | 5 | 5 | 1 | 2 | 1 | 4 | 3 | 4 | 2 | 3 | 3 | 3 | 1 | 4 | 4 | 1 | 2 | 5 | 5 | 5 | 4 | 3 | 1 | 5 | 1 | 5 | 5 | 4 | 4 | 4 | 2 | 4 | 2 | 2 | 4 | 2 | 1 | 4 | 5 | 3 | 1 | 5 | 5 | 1 | 4
294 | 12 | 10 | 19 | 35 | 49 | 64 | 75 | 84 | 93 | 108 | 119 | 127 | 142 | 159 | 1 | 1 | 3 | 5 | 1 | 1 | 3 | 4 | 5 | 3 | 3 | 5 | 4 | 2 | 5 | 3 | 3 | 5 | 4 | 3 | 3 | 2 | 3 | 3 | 1 | 4 | 2 | 2 | 2 | 2 | 1 | 4 | 4 | 4 | 3 | 4 | 2 | 5 | 2 | 2 | 1 | 2 | 1 | 4 | 3 | 2 | 5 | 5 | 4 | 5 | 5 | 3
295 | 20 | 13 | 23 | 34 | 51 | 62 | 73 | 86 | 93 | 110 | 119 | 133 | 145 | 159 | 5 | 2 | 3 | 3 | 3 | 4 | 1 | 2 | 1 | 4 | 5 | 1 | 5 | 4 | 3 | 5 | 4 | 4 | 1 | 2 | 5 | 3 | 1 | 2 | 2 | 1 | 5 | 5 | 2 | 1 | 1 | 3 | 5 | 5 | 2 | 5 | 2 | 1 | 2 | 4 | 5 | 3 | 3 | 3 | 3 | 3 | 2 | 4 | 5 | 4 | 1 | 4
296 | 13 | 11 | 23 | 32 | 48 | 65 | 75 | 87 | 99 | 105 | 117 | 132 | 138 | 149 | 1 | 2 | 3 | 5 | 1 | 1 | 5 | 5 | 1 | 2 | 4 | 2 | 4 | 2 | 5 | 5 | 5 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 5 | 2 | 1 | 4 | 5 | 1 | 2 | 4 | 3 | 1 | 1 | 1 | 5 | 5 | 1 | 1 | 5 | 3 | 2 | 5 | 2 | 1 | 1 | 2 | 1 | 3 | 5 | 2
297 | 22 | 13 | 32 | 42 | 50 | 69 | 85 | 98 | 108 | 121 | 132 | 145 | 162 | 178 | 5 | 2 | 5 | 1 | 4 | 5 | 5 | 5 | 1 | 1 | 3 | 5 | 1 | 1 | 5 | 1 | 4 | 5 | 5 | 5 | 5 | 5 | 2 | 4 | 4 | 3 | 3 | 3 | 3 | 4 | 1 | 2 | 2 | 4 | 2 | 5 | 3 | 1 | 2 | 5 | 3 | 5 | 2 | 3 | 5 | 4 | 5 | 3 | 5 | 5 | 4 | 2
298 | 23 | 15 | 29 | 40 | 51 | 62 | 72 | 85 | 97 | 110 | 124 | 135 | 144 | 154 | 3 | 5 | 3 | 4 | 4 | 4 | 5 | 1 | 5 | 2 | 1 | 3 | 5 | 3 | 1 | 2 | 1 | 5 | 3 | 2 | 1 | 2 | 2 | 5 | 3 | 3 | 4 | 3 | 5 | 3 | 2 | 2 | 4 | 3 | 1 | 5 | 3 | 5 | 2 | 4 | 4 | 2 | 1 | 4 | 1 | 4 | 3 | 1 | 3 | 3 | 2 | 2
299 | 19 | 14 | 23 | 41 | 57 | 69 | 81 | 99 | 115 | 127 | 138 | 151 | 161 | 170 | 3 | 5 | 4 | 2 | 1 | 4 | 3 | 1 | 3 | 5 | 5 | 5 | 3 | 4 | 5 | 4 | 3 | 5 | 2 | 2 | 4 | 1 | 3 | 4 | 5 | 5 | 3 | 5 | 3 | 4 | 4 | 5 | 4 | 4 | 3 | 1 | 4 | 4 | 1 | 2 | 1 | 2 | 5 | 5 | 1 | 3 | 5 | 1 | 3 | 2 | 3 | 1
300 | 24 | 14 | 30 | 41 | 49 | 62 | 74 | 89 | 100 | 114 | 126 | 139 | 151 | 161 | 5 | 4 | 4 | 1 | 5 | 5 | 5 | 1 | 5 | 2 | 1 | 3 | 1 | 1 | 5 | 1 | 4 | 5 | 3 | 1 | 4 | 2 | 4 | 2 | 5 | 2 | 4 | 4 | 3 | 2 | 5 | 1 | 4 | 4 | 2 | 4 | 1 | 4 | 4 | 3 | 3 | 3 | 2 | 5 | 5 | 4 | 1 | 2 | 5 | 1 | 3 | 1
301 | 16 | 10 | 22 | 32 | 41 | 53 | 66 | 76 | 85 | 104 | 113 | 127 | 140 | 148 | 1 | 5 | 3 | 1 | 2 | 4 | 3 | 3 | 2 | 2 | 2 | 4 | 1 | 2 | 4 | 2 | 3 | 2 | 3 | 4 | 5 | 1 | 4 | 3 | 1 | 4 | 2 | 3 | 1 | 4 | 1 | 3 | 5 | 5 | 4 | 5 | 1 | 3 | 2 | 3 | 5 | 3 | 5 | 1 | 4 | 5 | 1 | 3 | 1 | 3 | 3 | 1
302 | 15 | 13 | 20 | 34 | 47 | 61 | 73 | 90 | 105 | 120 | 134 | 151 | 163 | 176 | 1 | 4 | 3 | 5 | 1 | 1 | 3 | 2 | 3 | 3 | 3 | 5 | 3 | 5 | 3 | 2 | 5 | 3 | 3 | 3 | 1 | 2 | 5 | 4 | 4 | 4 | 4 | 5 | 4 | 5 | 1 | 5 | 2 | 5 | 3 | 5 | 5 | 2 | 2 | 5 | 5 | 4 | 3 | 5 | 4 | 1 | 3 | 4 | 1 | 3 | 4 | 5
303 | 15 | 6 | 18 | 25 | 38 | 48 | 55 | 65 | 75 | 86 | 93 | 105 | 120 | 131 | 1 | 3 | 1 | 1 | 4 | 5 | 1 | 2 | 1 | 3 | 1 | 2 | 1 | 3 | 5 | 4 | 3 | 2 | 4 | 1 | 1 | 2 | 3 | 1 | 2 | 1 | 2 | 5 | 4 | 1 | 3 | 2 | 2 | 4 | 2 | 3 | 2 | 3 | 1 | 1 | 2 | 4 | 2 | 4 | 5 | 3 | 2 | 5 | 5 | 1 | 4 | 1
304 | 19 | 13 | 22 | 35 | 43 | 50 | 69 | 78 | 93 | 105 | 118 | 128 | 140 | 147 | 5 | 1 | 3 | 4 | 2 | 4 | 2 | 1 | 4 | 2 | 3 | 4 | 2 | 3 | 2 | 1 | 2 | 3 | 1 | 1 | 5 | 4 | 5 | 5 | 1 | 1 | 5 | 2 | 3 | 5 | 4 | 3 | 5 | 1 | 5 | 1 | 4 | 2 | 4 | 3 | 5 | 2 | 2 | 1 | 1 | 3 | 4 | 4 | 2 | 1 | 1 | 3
305 | 19 | 13 | 25 | 37 | 52 | 64 | 75 | 89 | 101 | 113 | 124 | 138 | 145 | 158 | 3 | 5 | 3 | 2 | 1 | 5 | 4 | 2 | 3 | 1 | 3 | 5 | 2 | 3 | 5 | 5 | 1 | 5 | 4 | 2 | 2 | 4 | 3 | 2 | 5 | 1 | 3 | 5 | 1 | 1 | 5 | 5 | 2 | 3 | 4 | 3 | 1 | 3 | 4 | 3 | 5 | 5 | 3 | 1 | 2 | 1 | 2 | 2 | 3 | 3 | 2 | 5
306 | 18 | 10 | 24 | 35 | 43 | 55 | 66 | 76 | 92 | 105 | 114 | 127 | 136 | 151 | 3 | 1 | 3 | 3 | 3 | 5 | 3 | 3 | 5 | 1 | 1 | 4 | 1 | 2 | 4 | 1 | 5 | 3 | 2 | 2 | 1 | 5 | 3 | 2 | 1 | 4 | 2 | 3 | 3 | 5 | 4 | 4 | 3 | 5 | 2 | 3 | 3 | 3 | 1 | 2 | 5 | 2 | 1 | 5 | 2 | 2 | 2 | 3 | 5 | 4 | 1 | 5
307 | 18 | 13 | 22 | 33 | 47 | 65 | 81 | 95 | 111 | 122 | 132 | 147 | 161 | 174 | 4 | 2 | 3 | 4 | 4 | 1 | 2 | 2 | 4 | 4 | 2 | 1 | 5 | 1 | 3 | 5 | 4 | 5 | 5 | 4 | 5 | 4 | 4 | 3 | 5 | 4 | 3 | 2 | 3 | 5 | 4 | 4 | 1 | 3 | 4 | 3 | 1 | 3 | 1 | 5 | 3 | 4 | 5 | 3 | 1 | 5 | 3 | 5 | 4 | 5 | 3 | 1
308 | 23 | 13 | 29 | 46 | 58 | 71 | 80 | 90 | 100 | 110 | 124 | 138 | 153 | 172 | 1 | 3 | 5 | 4 | 5 | 5 | 2 | 4 | 3 | 5 | 5 | 4 | 3 | 4 | 4 | 1 | 2 | 5 | 2 | 4 | 2 | 1 | 1 | 5 | 5 | 2 | 1 | 2 | 3 | 1 | 5 | 1 | 1 | 5 | 3 | 1 | 4 | 4 | 2 | 4 | 3 | 3 | 3 | 5 | 2 | 4 | 4 | 5 | 5 | 5 | 4 | 5
309 | 18 | 11 | 24 | 38 | 51 | 67 | 82 | 97 | 109 | 122 | 135 | 149 | 158 | 167 | 5 | 1 | 4 | 1 | 2 | 5 | 2 | 4 | 5 | 4 | 2 | 3 | 4 | 2 | 4 | 3 | 5 | 3 | 3 | 5 | 5 | 3 | 3 | 4 | 5 | 4 | 1 | 5 | 3 | 5 | 2 | 2 | 5 | 4 | 1 | 3 | 3 | 3 | 3 | 4 | 4 | 5 | 1 | 4 | 3 | 2 | 3 | 1 | 2 | 1 | 2 | 4
310 | 19 | 12 | 22 | 38 | 49 | 66 | 76 | 88 | 100 | 112 | 131 | 138 | 150 | 161 | 3 | 4 | 2 | 3 | 2 | 5 | 2 | 1 | 5 | 3 | 3 | 5 | 2 | 2 | 4 | 3 | 5 | 5 | 3 | 4 | 5 | 3 | 1 | 1 | 5 | 3 | 2 | 2 | 3 | 2 | 2 | 5 | 2 | 4 | 5 | 1 | 5 | 5 | 5 | 4 | 1 | 1 | 1 | 4 | 2 | 4 | 5 | 1 | 2 | 1 | 5 | 3
311 | 20 | 17 | 25 | 31 | 47 | 53 | 64 | 76 | 87 | 101 | 112 | 123 | 133 | 145 | 4 | 3 | 5 | 5 | 2 | 1 | 2 | 3 | 1 | 2 | 1 | 2 | 5 | 4 | 5 | 2 | 1 | 1 | 3 | 1 | 3 | 2 | 4 | 2 | 4 | 2 | 3 | 3 | 4 | 4 | 2 | 1 | 5 | 5 | 2 | 2 | 3 | 3 | 2 | 3 | 4 | 1 | 4 | 2 | 3 | 4 | 1 | 2 | 5 | 2 | 3 | 2
312 | 22 | 18 | 28 | 41 | 52 | 59 | 70 | 83 | 93 | 104 | 115 | 128 | 142 | 156 | 5 | 5 | 4 | 4 | 1 | 3 | 5 | 1 | 3 | 3 | 4 | 3 | 4 | 2 | 1 | 4 | 3 | 1 | 1 | 2 | 4 | 2 | 4 | 1 | 5 | 2 | 4 | 2 | 2 | 1 | 5 | 2 | 5 | 2 | 1 | 3 | 5 | 3 | 2 | 1 | 5 | 2 | 2 | 4 | 4 | 1 | 5 | 4 | 2 | 5 | 4 | 3
313 | 18 | 11 | 24 | 39 | 53 | 64 | 75 | 86 | 92 | 106 | 115 | 127 | 141 | 151 | 2 | 1 | 3 | 5 | 5 | 2 | 3 | 3 | 4 | 5 | 5 | 1 | 4 | 4 | 2 | 4 | 1 | 2 | 4 | 4 | 1 | 5 | 2 | 3 | 3 | 4 | 1 | 3 | 1 | 1 | 1 | 3 | 4 | 2 | 4 | 4 | 5 | 2 | 1 | 1 | 1 | 5 | 1 | 5 | 3 | 4 | 3 | 4 | 1 | 2 | 2 | 5
314 | 16 | 11 | 23 | 29 | 42 | 56 | 63 | 78 | 91 | 104 | 119 | 129 | 145 | 157 | 2 | 1 | 5 | 3 | 1 | 4 | 5 | 2 | 1 | 3 | 1 | 1 | 5 | 2 | 3 | 3 | 3 | 5 | 4 | 2 | 1 | 2 | 1 | 3 | 4 | 4 | 3 | 4 | 1 | 5 | 5 | 2 | 3 | 3 | 2 | 5 | 4 | 4 | 3 | 4 | 2 | 2 | 3 | 3 | 5 | 1 | 5 | 5 | 3 | 2 | 4 | 3
315 | 17 | 8 | 25 | 37 | 51 | 66 | 84 | 94 | 107 | 118 | 132 | 145 | 158 | 170 | 1 | 1 | 1 | 5 | 5 | 4 | 3 | 5 | 1 | 1 | 5 | 5 | 1 | 5 | 3 | 5 | 3 | 5 | 4 | 3 | 5 | 3 | 5 | 5 | 3 | 3 | 2 | 2 | 3 | 5 | 3 | 2 | 1 | 4 | 4 | 2 | 5 | 2 | 5 | 2 | 2 | 4 | 5 | 2 | 5 | 3 | 2 | 3 | 3 | 3 | 4 | 2
316 | 20 | 13 | 26 | 39 | 52 | 62 | 72 | 81 | 93 | 107 | 119 | 128 | 139 | 152 | 2 | 4 | 3 | 4 | 5 | 2 | 5 | 1 | 4 | 2 | 3 | 4 | 3 | 3 | 3 | 4 | 1 | 2 | 3 | 4 | 5 | 2 | 1 | 2 | 1 | 5 | 2 | 1 | 2 | 4 | 3 | 3 | 1 | 5 | 3 | 5 | 3 | 2 | 3 | 4 | 1 | 5 | 1 | 2 | 4 | 5 | 1 | 1 | 2 | 4 | 2 | 5
317 | 21 | 12 | 30 | 42 | 51 | 63 | 71 | 82 | 99 | 113 | 124 | 132 | 144 | 154 | 4 | 5 | 2 | 1 | 5 | 4 | 4 | 5 | 4 | 4 | 3 | 1 | 2 | 1 | 3 | 3 | 3 | 3 | 1 | 5 | 3 | 1 | 2 | 2 | 1 | 5 | 1 | 4 | 5 | 5 | 2 | 5 | 4 | 5 | 2 | 3 | 3 | 1 | 4 | 3 | 1 | 1 | 1 | 5 | 1 | 5 | 2 | 4 | 3 | 4 | 2 | 1
318 | 20 | 15 | 25 | 39 | 52 | 68 | 78 | 90 | 99 | 108 | 119 | 129 | 142 | 154 | 2 | 5 | 5 | 3 | 4 | 1 | 4 | 1 | 3 | 4 | 2 | 5 | 4 | 4 | 4 | 1 | 3 | 3 | 5 | 5 | 3 | 1 | 2 | 4 | 4 | 3 | 3 | 2 | 1 | 5 | 2 | 1 | 1 | 1 | 5 | 2 | 3 | 3 | 3 | 2 | 3 | 4 | 2 | 1 | 3 | 3 | 3 | 4 | 5 | 1 | 5 | 1
319 | 10 | 5 | 14 | 28 | 40 | 54 | 69 | 84 | 95 | 108 | 116 | 130 | 146 | 155 | 1 | 1 | 1 | 2 | 4 | 1 | 1 | 3 | 4 | 2 | 3 | 5 | 5 | 1 | 5 | 1 | 2 | 2 | 5 | 5 | 4 | 5 | 2 | 4 | 5 | 5 | 2 | 3 | 1 | 2 | 5 | 3 | 4 | 2 | 3 | 4 | 2 | 1 | 2 | 3 | 3 | 1 | 5 | 5 | 3 | 5 | 4 | 4 | 1 | 4 | 1 | 3
320 | 17 | 9 | 23 | 37 | 49 | 61 | 74 | 79 | 92 | 106 | 123 | 132 | 146 | 154 | 5 | 2 | 1 | 1 | 5 | 3 | 5 | 1 | 2 | 3 | 5 | 4 | 5 | 1 | 4 | 2 | 2 | 4 | 4 | 2 | 5 | 2 | 4 | 2 | 2 | 1 | 1 | 1 | 4 | 3 | 5 | 1 | 4 | 3 | 4 | 3 | 5 | 4 | 3 | 5 | 3 | 2 | 3 | 1 | 4 | 2 | 4 | 4 | 3 | 1 | 1 | 3
321 | 16 | 11 | 20 | 37 | 49 | 56 | 68 | 78 | 94 | 101 | 109 | 123 | 135 | 150 | 1 | 5 | 1 | 4 | 4 | 1 | 1 | 3 | 5 | 4 | 3 | 5 | 1 | 4 | 3 | 4 | 3 | 1 | 2 | 1 | 3 | 4 | 2 | 3 | 5 | 2 | 2 | 1 | 1 | 5 | 5 | 5 | 1 | 2 | 1 | 3 | 1 | 1 | 2 | 4 | 4 | 5 | 1 | 4 | 5 | 2 | 2 | 3 | 1 | 5 | 5 | 4
322 | 19 | 14 | 22 | 35 | 48 | 65 | 74 | 88 | 96 | 107 | 118 | 132 | 140 | 157 | 4 | 5 | 3 | 2 | 3 | 2 | 2 | 1 | 3 | 5 | 2 | 3 | 3 | 3 | 5 | 2 | 3 | 5 | 5 | 4 | 1 | 2 | 1 | 5 | 5 | 2 | 4 | 3 | 1 | 1 | 5 | 1 | 4 | 1 | 4 | 2 | 2 | 3 | 1 | 5 | 3 | 3 | 4 | 4 | 1 | 1 | 3 | 3 | 5 | 4 | 3 | 5
323 | 19 | 12 | 22 | 33 | 43 | 55 | 68 | 80 | 94 | 112 | 121 | 139 | 155 | 169 | 3 | 3 | 5 | 1 | 3 | 4 | 2 | 1 | 4 | 1 | 3 | 3 | 3 | 1 | 3 | 3 | 1 | 4 | 4 | 3 | 1 | 2 | 5 | 5 | 4 | 3 | 2 | 3 | 4 | 4 | 4 | 2 | 5 | 5 | 3 | 5 | 1 | 3 | 3 | 2 | 4 | 5 | 4 | 5 | 5 | 1 | 5 | 5 | 4 | 4 | 3 | 3
324 | 19 | 14 | 25 | 36 | 51 | 60 | 71 | 88 | 107 | 117 | 133 | 146 | 160 | 175 | 3 | 1 | 5 | 5 | 3 | 2 | 2 | 4 | 3 | 3 | 4 | 1 | 5 | 4 | 4 | 2 | 2 | 2 | 3 | 2 | 4 | 2 | 2 | 3 | 4 | 4 | 5 | 4 | 5 | 4 | 5 | 5 | 2 | 1 | 4 | 3 | 5 | 5 | 3 | 3 | 4 | 1 | 5 | 3 | 2 | 3 | 5 | 4 | 3 | 5 | 5 | 2
325 | 19 | 14 | 24 | 35 | 46 | 62 | 73 | 86 | 99 | 112 | 125 | 139 | 154 | 165 | 2 | 5 | 3 | 4 | 4 | 1 | 2 | 3 | 1 | 3 | 2 | 5 | 3 | 1 | 4 | 3 | 2 | 5 | 5 | 4 | 3 | 3 | 4 | 1 | 2 | 5 | 5 | 1 | 4 | 3 | 2 | 4 | 3 | 2 | 4 | 4 | 2 | 3 | 5 | 3 | 4 | 4 | 4 | 2 | 3 | 3 | 5 | 4 | 3 | 2 | 2 | 4
326 | 19 | 13 | 25 | 37 | 47 | 57 | 70 | 79 | 92 | 106 | 114 | 123 | 139 | 151 | 5 | 3 | 4 | 1 | 5 | 1 | 4 | 2 | 2 | 4 | 4 | 2 | 1 | 3 | 1 | 5 | 2 | 2 | 4 | 2 | 3 | 4 | 4 | 2 | 1 | 1 | 3 | 4 | 4 | 1 | 3 | 5 | 2 | 5 | 2 | 5 | 5 | 1 | 1 | 1 | 3 | 3 | 1 | 2 | 3 | 4 | 4 | 5 | 4 | 2 | 2 | 4
327 | 22 | 14 | 27 | 44 | 51 | 64 | 72 | 88 | 97 | 108 | 119 | 127 | 142 | 154 | 3 | 3 | 3 | 5 | 3 | 5 | 1 | 4 | 5 | 4 | 3 | 5 | 1 | 3 | 2 | 1 | 3 | 2 | 3 | 5 | 4 | 2 | 1 | 1 | 3 | 5 | 4 | 4 | 2 | 1 | 2 | 4 | 3 | 2 | 3 | 3 | 1 | 4 | 4 | 2 | 1 | 1 | 5 | 1 | 4 | 5 | 1 | 5 | 2 | 4 | 4 | 2
328 | 15 | 12 | 17 | 31 | 40 | 55 | 70 | 80 | 94 | 109 | 120 | 132 | 146 | 160 | 4 | 2 | 4 | 2 | 1 | 2 | 1 | 1 | 5 | 4 | 1 | 4 | 3 | 1 | 3 | 2 | 5 | 2 | 4 | 4 | 4 | 5 | 1 | 5 | 4 | 2 | 1 | 3 | 4 | 1 | 4 | 5 | 3 | 5 | 4 | 3 | 4 | 1 | 5 | 1 | 4 | 2 | 2 | 4 | 2 | 3 | 5 | 4 | 4 | 4 | 2 | 4
329 | 16 | 9 | 18 | 28 | 36 | 45 | 55 | 68 | 78 | 89 | 104 | 121 | 131 | 142 | 5 | 1 | 2 | 1 | 4 | 3 | 1 | 1 | 5 | 1 | 1 | 3 | 4 | 1 | 1 | 2 | 1 | 1 | 5 | 2 | 4 | 1 | 1 | 4 | 4 | 1 | 3 | 5 | 5 | 1 | 2 | 2 | 1 | 4 | 3 | 3 | 2 | 3 | 5 | 5 | 4 | 5 | 4 | 4 | 2 | 3 | 1 | 4 | 4 | 4 | 2 | 1
330 | 20 | 14 | 29 | 43 | 53 | 59 | 67 | 80 | 94 | 107 | 118 | 134 | 147 | 159 | 3 | 1 | 5 | 5 | 2 | 4 | 5 | 4 | 5 | 5 | 3 | 1 | 5 | 2 | 1 | 2 | 1 | 1 | 3 | 1 | 1 | 1 | 2 | 4 | 2 | 4 | 3 | 4 | 2 | 5 | 3 | 4 | 5 | 2 | 5 | 1 | 2 | 3 | 3 | 3 | 2 | 4 | 5 | 5 | 3 | 2 | 4 | 4 | 3 | 5 | 2 | 2
331 | 18 | 11 | 27 | 41 | 53 | 67 | 75 | 86 | 95 | 111 | 122 | 133 | 141 | 147 | 1 | 3 | 5 | 2 | 5 | 2 | 5 | 4 | 3 | 5 | 2 | 4 | 3 | 1 | 3 | 5 | 3 | 5 | 2 | 4 | 1 | 2 | 4 | 1 | 2 | 3 | 5 | 1 | 1 | 4 | 1 | 3 | 5 | 5 | 1 | 5 | 3 | 2 | 4 | 2 | 4 | 1 | 2 | 4 | 1 | 4 | 1 | 2 | 1 | 1 | 3 | 1
332 | 21 | 15 | 27 | 38 | 53 | 64 | 78 | 90 | 102 | 108 | 120 | 131 | 141 | 154 | 4 | 1 | 5 | 5 | 4 | 2 | 2 | 4 | 5 | 1 | 3 | 2 | 2 | 4 | 4 | 5 | 2 | 2 | 4 | 3 | 3 | 4 | 2 | 5 | 5 | 2 | 4 | 1 | 3 | 2 | 5 | 2 | 1 | 1 | 1 | 3 | 2 | 2 | 4 | 4 | 3 | 1 | 2 | 5 | 5 | 1 | 2 | 2 | 5 | 2 | 4 | 2
333 | 23 | 13 | 29 | 42 | 53 | 65 | 73 | 81 | 90 | 102 | 117 | 132 | 152 | 163 | 4 | 2 | 5 | 2 | 5 | 5 | 5 | 1 | 4 | 4 | 1 | 4 | 1 | 5 | 3 | 2 | 4 | 2 | 2 | 4 | 4 | 1 | 2 | 1 | 2 | 4 | 1 | 1 | 4 | 3 | 1 | 1 | 5 | 2 | 2 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 5 | 5 | 5 | 5 | 1 | 4 | 3 | 3
334 | 18 | 13 | 20 | 28 | 39 | 50 | 66 | 74 | 83 | 94 | 104 | 123 | 134 | 150 | 5 | 3 | 3 | 2 | 4 | 1 | 1 | 1 | 2 | 3 | 1 | 2 | 1 | 4 | 3 | 3 | 1 | 5 | 1 | 4 | 5 | 2 | 5 | 4 | 4 | 1 | 2 | 1 | 2 | 4 | 2 | 1 | 2 | 2 | 4 | 3 | 3 | 3 | 3 | 1 | 4 | 5 | 5 | 5 | 1 | 4 | 5 | 1 | 5 | 5 | 2 | 4
335 | 16 | 10 | 25 | 38 | 45 | 57 | 72 | 83 | 94 | 109 | 119 | 128 | 142 | 156 | 2 | 2 | 3 | 3 | 4 | 2 | 5 | 4 | 5 | 3 | 1 | 4 | 3 | 2 | 1 | 1 | 1 | 5 | 1 | 5 | 3 | 4 | 4 | 4 | 2 | 2 | 4 | 3 | 2 | 3 | 5 | 1 | 2 | 5 | 4 | 4 | 1 | 2 | 4 | 3 | 4 | 3 | 1 | 1 | 4 | 5 | 2 | 3 | 4 | 5 | 2 | 3
336 | 22 | 14 | 31 | 45 | 58 | 74 | 84 | 101 | 113 | 127 | 142 | 152 | 158 | 172 | 3 | 4 | 2 | 5 | 3 | 5 | 5 | 4 | 2 | 5 | 4 | 3 | 1 | 5 | 2 | 5 | 5 | 5 | 1 | 5 | 2 | 1 | 3 | 4 | 3 | 4 | 5 | 5 | 2 | 5 | 3 | 2 | 3 | 2 | 5 | 4 | 3 | 2 | 5 | 5 | 2 | 2 | 5 | 1 | 2 | 2 | 1 | 1 | 5 | 2 | 5 | 2
337 | 17 | 14 | 24 | 37 | 48 | 55 | 65 | 76 | 90 | 106 | 123 | 140 | 149 | 156 | 4 | 5 | 2 | 3 | 2 | 1 | 4 | 3 | 2 | 3 | 3 | 5 | 4 | 3 | 2 | 2 | 1 | 1 | 4 | 1 | 4 | 1 | 4 | 1 | 2 | 5 | 1 | 3 | 5 | 1 | 5 | 3 | 4 | 5 | 3 | 4 | 5 | 5 | 3 | 4 | 5 | 5 | 2 | 5 | 2 | 1 | 2 | 4 | 2 | 2 | 1 | 2
338 | 19 | 10 | 26 | 37 | 49 | 59 | 74 | 87 | 104 | 115 | 128 | 138 | 146 | 163 | 5 | 2 | 1 | 2 | 4 | 5 | 4 | 3 | 4 | 3 | 3 | 1 | 2 | 5 | 4 | 1 | 3 | 4 | 2 | 1 | 5 | 1 | 5 | 4 | 2 | 2 | 5 | 4 | 2 | 5 | 5 | 5 | 3 | 5 | 2 | 1 | 3 | 2 | 3 | 5 | 1 | 4 | 1 | 4 | 1 | 3 | 2 | 2 | 4 | 5 | 4 | 4
339 | 12 | 8 | 17 | 24 | 33 | 48 | 58 | 70 | 81 | 98 | 111 | 123 | 141 | 156 | 4 | 1 | 1 | 2 | 2 | 2 | 1 | 4 | 1 | 2 | 2 | 2 | 5 | 1 | 1 | 2 | 5 | 2 | 3 | 5 | 1 | 4 | 3 | 2 | 1 | 2 | 5 | 4 | 1 | 5 | 2 | 3 | 3 | 4 | 5 | 5 | 1 | 5 | 4 | 3 | 3 | 1 | 3 | 5 | 4 | 4 | 5 | 5 | 4 | 2 | 5 | 4
340 | 20 | 13 | 30 | 37 | 53 | 70 | 79 | 92 | 108 | 119 | 136 | 150 | 159 | 169 | 3 | 4 | 5 | 1 | 3 | 4 | 5 | 5 | 3 | 1 | 2 | 1 | 5 | 3 | 5 | 3 | 5 | 4 | 5 | 3 | 2 | 1 | 3 | 3 | 4 | 3 | 2 | 4 | 3 | 5 | 3 | 5 | 3 | 4 | 1 | 3 | 2 | 5 | 5 | 5 | 5 | 2 | 4 | 3 | 1 | 3 | 1 | 4 | 3 | 1 | 1 | 5
341 | 19 | 9 | 24 | 36 | 48 | 60 | 68 | 82 | 93 | 106 | 116 | 132 | 142 | 157 | 3 | 1 | 4 | 1 | 5 | 5 | 1 | 4 | 5 | 2 | 4 | 1 | 1 | 5 | 5 | 1 | 3 | 2 | 5 | 2 | 3 | 1 | 2 | 2 | 5 | 3 | 4 | 2 | 4 | 4 | 2 | 1 | 5 | 2 | 1 | 5 | 1 | 1 | 4 | 4 | 5 | 5 | 1 | 5 | 1 | 3 | 3 | 3 | 4 | 1 | 5 | 5
342 | 13 | 7 | 16 | 32 | 43 | 52 | 62 | 71 | 85 | 94 | 106 | 116 | 130 | 138 | 2 | 1 | 2 | 2 | 5 | 1 | 2 | 1 | 5 | 3 | 5 | 3 | 3 | 2 | 5 | 1 | 2 | 2 | 1 | 4 | 1 | 5 | 3 | 1 | 3 | 3 | 2 | 1 | 2 | 5 | 4 | 3 | 2 | 5 | 1 | 1 | 2 | 5 | 2 | 3 | 2 | 1 | 2 | 5 | 3 | 5 | 1 | 5 | 3 | 1 | 2 | 2
343 | 16 | 12 | 21 | 33 | 45 | 57 | 73 | 84 | 102 | 110 | 118 | 128 | 141 | 152 | 3 | 4 | 2 | 3 | 3 | 1 | 1 | 4 | 3 | 4 | 1 | 4 | 3 | 5 | 1 | 3 | 1 | 5 | 1 | 5 | 3 | 5 | 4 | 4 | 1 | 4 | 4 | 2 | 5 | 3 | 5 | 5 | 3 | 2 | 1 | 2 | 2 | 1 | 4 | 1 | 5 | 1 | 3 | 1 | 2 | 1 | 5 | 5 | 1 | 3 | 2 | 5
344 | 20 | 12 | 23 | 37 | 49 | 63 | 71 | 82 | 93 | 106 | 117 | 127 | 141 | 151 | 4 | 5 | 2 | 1 | 5 | 3 | 2 | 1 | 3 | 5 | 4 | 2 | 2 | 2 | 4 | 4 | 3 | 5 | 1 | 5 | 1 | 2 | 4 | 1 | 1 | 5 | 4 | 1 | 3 | 2 | 3 | 3 | 4 | 4 | 2 | 3 | 1 | 2 | 4 | 4 | 3 | 4 | 1 | 2 | 5 | 5 | 1 | 3 | 4 | 1 | 1 | 4
345 | 17 | 14 | 26 | 40 | 55 | 68 | 78 | 90 | 104 | 116 | 127 | 143 | 155 | 165 | 4 | 3 | 2 | 5 | 1 | 2 | 4 | 5 | 4 | 3 | 3 | 4 | 2 | 5 | 4 | 4 | 1 | 3 | 4 | 5 | 3 | 2 | 1 | 4 | 3 | 4 | 1 | 4 | 2 | 4 | 3 | 5 | 3 | 3 | 4 | 2 | 3 | 4 | 3 | 1 | 5 | 4 | 3 | 4 | 2 | 3 | 3 | 4 | 3 | 1 | 5 | 1
346 | 14 | 10 | 22 | 30 | 39 | 50 | 60 | 73 | 91 | 104 | 117 | 127 | 140 | 152 | 1 | 1 | 4 | 4 | 2 | 2 | 3 | 5 | 1 | 2 | 3 | 2 | 2 | 2 | 3 | 2 | 4 | 1 | 5 | 1 | 4 | 1 | 2 | 3 | 5 | 4 | 1 | 3 | 5 | 5 | 4 | 4 | 1 | 5 | 2 | 5 | 4 | 2 | 5 | 2 | 4 | 3 | 2 | 1 | 1 | 5 | 5 | 2 | 4 | 2 | 2 | 4
347 | 18 | 12 | 28 | 37 | 49 | 60 | 76 | 87 | 96 | 108 | 116 | 130 | 143 | 157 | 5 | 3 | 1 | 3 | 1 | 5 | 5 | 5 | 2 | 3 | 3 | 1 | 4 | 4 | 1 | 3 | 4 | 3 | 3 | 1 | 4 | 5 | 4 | 3 | 4 | 3 | 2 | 2 | 5 | 1 | 1 | 2 | 3 | 5 | 1 | 3 | 2 | 2 | 1 | 3 | 2 | 4 | 4 | 4 | 5 | 4 | 3 | 1 | 1 | 4 | 4 | 5
348 | 18 | 13 | 22 | 39 | 49 | 57 | 70 | 81 | 91 | 106 | 118 | 133 | 146 | 159 | 2 | 5 | 5 | 1 | 3 | 2 | 2 | 2 | 5 | 5 | 4 | 3 | 1 | 2 | 2 | 5 | 2 | 1 | 3 | 2 | 1 | 4 | 4 | 4 | 3 | 3 | 2 | 3 | 3 | 2 | 4 | 1 | 2 | 4 | 5 | 4 | 3 | 3 | 4 | 2 | 2 | 5 | 3 | 5 | 5 | 3 | 4 | 1 | 5 | 4 | 2 | 2
349 | 17 | 14 | 22 | 39 | 54 | 68 | 80 | 93 | 101 | 115 | 130 | 145 | 150 | 162 | 3 | 1 | 5 | 5 | 2 | 1 | 2 | 3 | 5 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 5 | 3 | 3 | 3 | 3 | 3 | 5 | 1 | 2 | 4 | 3 | 4 | 3 | 1 | 3 | 1 | 3 | 2 | 5 | 4 | 3 | 2 | 5 | 5 | 4 | 5 | 5 | 1 | 1 | 1 | 1 | 2 | 4 | 4 | 1 | 3
350 | 12 | 6 | 22 | 31 | 40 | 51 | 61 | 73 | 85 | 96 | 106 | 118 | 131 | 144 | 1 | 2 | 2 | 1 | 4 | 2 | 5 | 5 | 1 | 1 | 3 | 4 | 1 | 3 | 3 | 2 | 1 | 3 | 5 | 2 | 2 | 2 | 3 | 3 | 5 | 2 | 1 | 4 | 5 | 1 | 2 | 4 | 3 | 1 | 5 | 2 | 4 | 2 | 2 | 2 | 2 | 4 | 1 | 5 | 3 | 5 | 4 | 1 | 5 | 4 | 3 | 1
351 | 21 | 11 | 29 | 43 | 51 | 62 | 72 | 82 | 96 | 112 | 129 | 138 | 150 | 165 | 5 | 2 | 3 | 1 | 5 | 5 | 4 | 4 | 5 | 2 | 5 | 2 | 3 | 3 | 1 | 1 | 1 | 4 | 1 | 5 | 2 | 2 | 1 | 5 | 1 | 2 | 5 | 2 | 4 | 3 | 2 | 5 | 5 | 1 | 5 | 5 | 4 | 5 | 3 | 5 | 3 | 2 | 2 | 2 | 5 | 3 | 2 | 2 | 4 | 5 | 3 | 3
352 | 22 | 16 | 30 | 45 | 61 | 74 | 88 | 100 | 114 | 125 | 134 | 148 | 160 | 177 | 3 | 5 | 3 | 5 | 5 | 1 | 3 | 5 | 5 | 3 | 5 | 2 | 3 | 3 | 5 | 5 | 3 | 5 | 1 | 4 | 1 | 4 | 4 | 5 | 3 | 4 | 4 | 1 | 5 | 5 | 1 | 3 | 5 | 4 | 1 | 1 | 3 | 4 | 1 | 1 | 4 | 5 | 4 | 1 | 2 | 2 | 3 | 5 | 4 | 4 | 4 | 5
353 | 14 | 10 | 22 | 29 | 40 | 54 | 71 | 84 | 97 | 110 | 118 | 129 | 144 | 154 | 1 | 3 | 2 | 4 | 3 | 1 | 4 | 4 | 1 | 1 | 2 | 3 | 5 | 4 | 1 | 1 | 5 | 2 | 3 | 4 | 5 | 5 | 3 | 4 | 3 | 1 | 4 | 5 | 3 | 1 | 4 | 5 | 4 | 3 | 2 | 4 | 2 | 3 | 1 | 2 | 4 | 2 | 4 | 1 | 2 | 4 | 4 | 5 | 4 | 3 | 1 | 2
354 | 12 | 10 | 17 | 34 | 43 | 52 | 65 | 77 | 87 | 100 | 112 | 125 | 134 | 145 | 4 | 1 | 1 | 4 | 1 | 1 | 2 | 3 | 3 | 4 | 5 | 5 | 4 | 3 | 1 | 1 | 2 | 4 | 2 | 1 | 1 | 5 | 2 | 5 | 2 | 4 | 5 | 1 | 2 | 4 | 1 | 3 | 2 | 1 | 5 | 5 | 2 | 4 | 3 | 3 | 2 | 3 | 4 | 4 | 4 | 2 | 1 | 2 | 5 | 1 | 3 | 2
355 | 18 | 13 | 22 | 36 | 50 | 65 | 71 | 85 | 94 | 106 | 117 | 134 | 142 | 156 | 5 | 5 | 1 | 2 | 4 | 1 | 3 | 1 | 3 | 5 | 2 | 4 | 4 | 4 | 5 | 1 | 4 | 2 | 4 | 5 | 1 | 1 | 3 | 1 | 1 | 3 | 5 | 5 | 4 | 2 | 2 | 1 | 3 | 1 | 3 | 5 | 2 | 1 | 5 | 3 | 5 | 4 | 5 | 3 | 4 | 1 | 2 | 1 | 5 | 5 | 1 | 3
356 | 22 | 15 | 27 | 42 | 57 | 66 | 80 | 97 | 109 | 128 | 141 | 149 | 165 | 173 | 2 | 5 | 3 | 5 | 3 | 4 | 1 | 4 | 3 | 4 | 3 | 5 | 5 | 3 | 2 | 5 | 3 | 3 | 1 | 2 | 4 | 3 | 3 | 4 | 4 | 4 | 4 | 5 | 5 | 2 | 3 | 2 | 5 | 4 | 5 | 5 | 3 | 4 | 5 | 1 | 2 | 3 | 1 | 2 | 5 | 4 | 4 | 3 | 4 | 2 | 1 | 1
357 | 16 | 6 | 24 | 35 | 48 | 57 | 66 | 74 | 90 | 104 | 117 | 133 | 146 | 157 | 1 | 1 | 2 | 2 | 5 | 5 | 4 | 4 | 1 | 4 | 1 | 5 | 4 | 2 | 5 | 2 | 1 | 5 | 2 | 1 | 1 | 3 | 1 | 4 | 2 | 1 | 2 | 3 | 2 | 5 | 4 | 5 | 5 | 1 | 5 | 3 | 2 | 5 | 5 | 1 | 4 | 3 | 5 | 4 | 2 | 5 | 4 | 2 | 1 | 2 | 5 | 3
358 | 17 | 12 | 22 | 31 | 43 | 54 | 70 | 80 | 90 | 101 | 112 | 123 | 135 | 144 | 5 | 2 | 2 | 3 | 2 | 3 | 1 | 4 | 4 | 1 | 3 | 1 | 1 | 2 | 5 | 4 | 1 | 3 | 5 | 2 | 4 | 4 | 4 | 4 | 5 | 3 | 1 | 1 | 3 | 5 | 1 | 1 | 2 | 4 | 1 | 4 | 2 | 1 | 4 | 4 | 4 | 1 | 1 | 5 | 4 | 2 | 1 | 5 | 1 | 5 | 2 | 1
359 | 22 | 14 | 26 | 35 | 52 | 62 | 72 | 86 | 99 | 108 | 121 | 131 | 140 | 150 | 5 | 5 | 1 | 3 | 3 | 5 | 2 | 2 | 3 | 2 | 1 | 3 | 5 | 4 | 4 | 4 | 2 | 1 | 5 | 2 | 2 | 3 | 1 | 4 | 3 | 4 | 4 | 3 | 4 | 3 | 4 | 2 | 3 | 1 | 1 | 4 | 3 | 2 | 5 | 3 | 4 | 3 | 1 | 2 | 4 | 1 | 1 | 3 | 2 | 3 | 1 | 4
360 | 20 | 13 | 24 | 36 | 50 | 66 | 79 | 88 | 104 | 117 | 135 | 149 | 161 | 176 | 5 | 1 | 3 | 4 | 5 | 2 | 1 | 3 | 2 | 1 | 4 | 5 | 4 | 1 | 5 | 4 | 4 | 4 | 5 | 3 | 5 | 5 | 1 | 2 | 1 | 2 | 2 | 4 | 5 | 5 | 2 | 4 | 3 | 5 | 3 | 2 | 5 | 3 | 5 | 5 | 2 | 5 | 3 | 4 | 3 | 4 | 3 | 2 | 5 | 4 | 1 | 5
361 | 21 | 14 | 29 | 38 | 52 | 67 | 82 | 94 | 109 | 119 | 130 | 144 | 156 | 167 | 4 | 2 | 5 | 3 | 3 | 4 | 5 | 3 | 3 | 2 | 2 | 2 | 1 | 4 | 5 | 4 | 4 | 5 | 5 | 1 | 4 | 5 | 5 | 1 | 2 | 4 | 4 | 2 | 5 | 4 | 1 | 5 | 1 | 3 | 2 | 4 | 2 | 1 | 5 | 3 | 4 | 5 | 1 | 4 | 5 | 2 | 3 | 2 | 1 | 4 | 5 | 1
362 | 20 | 14 | 27 | 38 | 45 | 59 | 72 | 81 | 91 | 105 | 118 | 128 | 144 | 154 | 5 | 2 | 4 | 3 | 5 | 1 | 4 | 3 | 4 | 2 | 1 | 4 | 1 | 1 | 3 | 2 | 3 | 3 | 3 | 5 | 2 | 3 | 4 | 4 | 1 | 1 | 2 | 5 | 1 | 3 | 2 | 4 | 3 | 1 | 5 | 5 | 4 | 4 | 3 | 2 | 3 | 4 | 1 | 2 | 5 | 4 | 5 | 2 | 3 | 4 | 2 | 1
363 | 13 | 7 | 18 | 30 | 41 | 51 | 61 | 72 | 85 | 96 | 110 | 119 | 135 | 142 | 2 | 1 | 3 | 1 | 5 | 1 | 1 | 4 | 2 | 4 | 5 | 1 | 1 | 1 | 4 | 5 | 5 | 1 | 1 | 3 | 1 | 5 | 2 | 2 | 3 | 5 | 2 | 1 | 2 | 3 | 4 | 4 | 1 | 4 | 5 | 1 | 5 | 2 | 4 | 3 | 3 | 2 | 3 | 1 | 5 | 5 | 5 | 1 | 2 | 3 | 1 | 1
364 | 15 | 9 | 21 | 36 | 46 | 56 | 68 | 80 | 95 | 106 | 116 | 128 | 142 | 155 | 3 | 2 | 2 | 2 | 5 | 1 | 3 | 3 | 4 | 4 | 3 | 4 | 1 | 4 | 2 | 3 | 3 | 3 | 3 | 1 | 2 | 3 | 3 | 4 | 3 | 4 | 3 | 2 | 3 | 5 | 3 | 4 | 2 | 2 | 5 | 2 | 1 | 4 | 4 | 1 | 1 | 3 | 5 | 3 | 2 | 4 | 3 | 5 | 5 | 2 | 3 | 3
365 | 11 | 8 | 17 | 34 | 43 | 55 | 64 | 82 | 94 | 108 | 116 | 128 | 140 | 149 | 3 | 3 | 1 | 1 | 1 | 2 | 5 | 1 | 4 | 4 | 5 | 4 | 4 | 1 | 3 | 1 | 1 | 4 | 2 | 5 | 1 | 2 | 1 | 5 | 5 | 4 | 5 | 4 | 1 | 3 | 5 | 3 | 5 | 3 | 4 | 2 | 2 | 2 | 1 | 3 | 4 | 3 | 3 | 2 | 5 | 4 | 1 | 2 | 1 | 5 | 2 | 1
366 | 20 | 15 | 24 | 37 | 50 | 63 | 76 | 96 | 111 | 121 | 130 | 143 | 152 | 165 | 3 | 2 | 5 | 5 | 3 | 2 | 1 | 3 | 5 | 4 | 3 | 1 | 4 | 1 | 3 | 5 | 4 | 2 | 4 | 3 | 4 | 5 | 1 | 3 | 5 | 5 | 5 | 5 | 4 | 3 | 4 | 4 | 2 | 4 | 2 | 2 | 4 | 2 | 2 | 1 | 2 | 2 | 4 | 5 | 3 | 4 | 1 | 1 | 4 | 5 | 3 | 1
367 | 23 | 18 | 32 | 45 | 53 | 61 | 73 | 83 | 94 | 108 | 122 | 133 | 144 | 157 | 4 | 4 | 5 | 5 | 2 | 3 | 4 | 5 | 5 | 1 | 3 | 4 | 2 | 2 | 3 | 1 | 3 | 1 | 3 | 1 | 4 | 4 | 3 | 1 | 1 | 5 | 1 | 3 | 3 | 2 | 2 | 4 | 2 | 5 | 3 | 4 | 1 | 5 | 3 | 5 | 2 | 1 | 4 | 4 | 2 | 3 | 1 | 5 | 3 | 5 | 4 | 1
368 | 11 | 6 | 15 | 29 | 43 | 51 | 61 | 77 | 95 | 111 | 120 | 133 | 141 | 155 | 3 | 1 | 1 | 1 | 3 | 2 | 1 | 3 | 4 | 3 | 4 | 3 | 4 | 5 | 3 | 2 | 2 | 2 | 1 | 3 | 5 | 3 | 1 | 1 | 3 | 3 | 5 | 5 | 4 | 4 | 5 | 5 | 3 | 5 | 5 | 3 | 4 | 1 | 2 | 2 | 3 | 4 | 2 | 4 | 1 | 4 | 2 | 1 | 5 | 1 | 3 | 5
369 | 20 | 13 | 23 | 34 | 45 | 55 | 63 | 75 | 89 | 102 | 113 | 128 | 138 | 151 | 3 | 1 | 5 | 4 | 4 | 3 | 2 | 1 | 5 | 4 | 1 | 1 | 2 | 5 | 2 | 2 | 2 | 4 | 1 | 3 | 2 | 3 | 1 | 2 | 5 | 1 | 2 | 4 | 5 | 1 | 5 | 3 | 4 | 5 | 2 | 2 | 1 | 5 | 3 | 2 | 4 | 4 | 5 | 2 | 2 | 1 | 4 | 3 | 3 | 1 | 4 | 5
370 | 12 | 7 | 19 | 29 | 39 | 49 | 65 | 80 | 94 | 113 | 122 | 134 | 141 | 152 | 1 | 2 | 2 | 2 | 1 | 4 | 2 | 5 | 1 | 5 | 1 | 3 | 5 | 2 | 2 | 1 | 3 | 1 | 5 | 1 | 5 | 5 | 5 | 1 | 5 | 3 | 3 | 4 | 5 | 4 | 2 | 3 | 5 | 4 | 5 | 5 | 1 | 1 | 4 | 3 | 2 | 4 | 5 | 1 | 1 | 2 | 3 | 1 | 3 | 1 | 4 | 3
371 | 19 | 14 | 25 | 39 | 43 | 54 | 65 | 75 | 92 | 105 | 118 | 131 | 142 | 157 | 3 | 3 | 5 | 3 | 3 | 2 | 2 | 4 | 2 | 5 | 4 | 3 | 1 | 1 | 1 | 1 | 3 | 3 | 2 | 3 | 1 | 1 | 4 | 5 | 4 | 1 | 2 | 3 | 3 | 5 | 4 | 5 | 1 | 4 | 4 | 4 | 3 | 3 | 4 | 3 | 1 | 5 | 2 | 5 | 5 | 1 | 1 | 4 | 5 | 4 | 1 | 5
372 | 16 | 13 | 21 | 33 | 43 | 52 | 62 | 71 | 79 | 92 | 103 | 116 | 129 | 143 | 4 | 3 | 2 | 4 | 2 | 1 | 1 | 4 | 2 | 3 | 5 | 2 | 2 | 4 | 2 | 2 | 2 | 1 | 5 | 1 | 3 | 1 | 5 | 1 | 1 | 5 | 2 | 1 | 1 | 2 | 3 | 2 | 2 | 2 | 5 | 4 | 1 | 3 | 3 | 4 | 3 | 5 | 3 | 2 | 2 | 3 | 4 | 4 | 3 | 3 | 5 | 3
373 | 23 | 13 | 33 | 46 | 58 | 70 | 82 | 96 | 111 | 121 | 136 | 148 | 162 | 170 | 5 | 3 | 1 | 4 | 5 | 5 | 5 | 5 | 4 | 2 | 5 | 2 | 2 | 2 | 3 | 5 | 1 | 5 | 1 | 5 | 3 | 4 | 2 | 3 | 4 | 5 | 1 | 4 | 2 | 3 | 5 | 5 | 2 | 3 | 2 | 3 | 3 | 4 | 3 | 5 | 4 | 2 | 3 | 3 | 4 | 4 | 2 | 4 | 1 | 5 | 1 | 1
374 | 22 | 17 | 31 | 43 | 50 | 60 | 75 | 87 | 100 | 106 | 116 | 131 | 144 | 153 | 4 | 5 | 5 | 3 | 3 | 2 | 4 | 5 | 3 | 2 | 2 | 5 | 1 | 4 | 1 | 1 | 4 | 3 | 1 | 2 | 3 | 4 | 4 | 4 | 1 | 5 | 4 | 2 | 1 | 4 | 3 | 5 | 1 | 3 | 1 | 1 | 1 | 5 | 1 | 3 | 3 | 5 | 5 | 2 | 4 | 4 | 2 | 3 | 1 | 4 | 2 | 2
375 | 28 | 19 | 34 | 44 | 53 | 64 | 78 | 87 | 98 | 109 | 124 | 137 | 147 | 161 | 5 | 5 | 5 | 4 | 5 | 4 | 4 | 2 | 5 | 1 | 1 | 3 | 1 | 4 | 1 | 3 | 2 | 4 | 3 | 2 | 5 | 2 | 2 | 5 | 5 | 2 | 1 | 1 | 4 | 2 | 2 | 3 | 1 | 3 | 2 | 5 | 2 | 4 | 4 | 5 | 1 | 5 | 5 | 2 | 2 | 5 | 2 | 1 | 5 | 3 | 5 | 1
376 | 14 | 10 | 22 | 30 | 41 | 53 | 65 | 75 | 90 | 102 | 114 | 125 | 136 | 143 | 1 | 4 | 1 | 4 | 1 | 3 | 5 | 3 | 2 | 3 | 1 | 2 | 3 | 3 | 4 | 1 | 4 | 3 | 4 | 1 | 4 | 5 | 1 | 2 | 1 | 2 | 2 | 5 | 5 | 2 | 3 | 5 | 4 | 2 | 2 | 4 | 3 | 5 | 3 | 1 | 5 | 2 | 3 | 1 | 4 | 5 | 1 | 1 | 1 | 1 | 4 | 1
377 | 23 | 15 | 29 | 39 | 53 | 64 | 78 | 97 | 104 | 115 | 125 | 135 | 146 | 161 | 2 | 5 | 3 | 5 | 5 | 3 | 2 | 4 | 4 | 1 | 4 | 1 | 5 | 2 | 4 | 3 | 3 | 2 | 4 | 2 | 3 | 5 | 5 | 1 | 5 | 5 | 4 | 5 | 1 | 4 | 1 | 1 | 3 | 3 | 4 | 1 | 3 | 3 | 1 | 3 | 1 | 2 | 4 | 3 | 4 | 2 | 1 | 4 | 2 | 3 | 5 | 5
378 | 21 | 15 | 29 | 35 | 48 | 63 | 73 | 91 | 104 | 118 | 128 | 135 | 150 | 156 | 5 | 5 | 1 | 4 | 1 | 5 | 3 | 5 | 2 | 1 | 1 | 2 | 5 | 2 | 2 | 4 | 1 | 5 | 4 | 5 | 3 | 2 | 4 | 1 | 5 | 5 | 5 | 3 | 3 | 5 | 4 | 1 | 3 | 2 | 5 | 4 | 4 | 2 | 1 | 3 | 2 | 1 | 2 | 2 | 5 | 5 | 3 | 2 | 2 | 1 | 2 | 1
379 | 21 | 15 | 29 | 39 | 56 | 69 | 80 | 89 | 100 | 116 | 124 | 134 | 148 | 163 | 5 | 5 | 2 | 3 | 3 | 3 | 4 | 4 | 3 | 4 | 2 | 1 | 4 | 5 | 4 | 4 | 2 | 2 | 5 | 4 | 3 | 4 | 1 | 3 | 1 | 2 | 4 | 2 | 2 | 2 | 5 | 2 | 4 | 5 | 3 | 4 | 3 | 1 | 3 | 1 | 1 | 2 | 4 | 3 | 3 | 3 | 3 | 5 | 4 | 4 | 4 | 3
380 | 16 | 10 | 20 | 32 | 46 | 61 | 76 | 90 | 97 | 104 | 113 | 127 | 131 | 144 | 3 | 2 | 3 | 2 | 4 | 2 | 2 | 2 | 3 | 4 | 3 | 2 | 3 | 3 | 5 | 3 | 5 | 4 | 2 | 4 | 3 | 3 | 4 | 5 | 4 | 3 | 5 | 2 | 1 | 3 | 1 | 2 | 3 | 1 | 1 | 2 | 1 | 2 | 2 | 4 | 5 | 4 | 1 | 4 | 1 | 1 | 1 | 1 | 2 | 5 | 5 | 1
381 | 17 | 13 | 22 | 36 | 46 | 55 | 68 | 81 | 97 | 106 | 118 | 131 | 144 | 151 | 5 | 4 | 3 | 1 | 2 | 2 | 4 | 1 | 1 | 5 | 3 | 5 | 3 | 1 | 2 | 4 | 2 | 1 | 3 | 3 | 2 | 4 | 4 | 3 | 3 | 5 | 4 | 1 | 5 | 5 | 3 | 3 | 3 | 1 | 1 | 4 | 3 | 4 | 4 | 1 | 3 | 4 | 1 | 5 | 4 | 2 | 5 | 2 | 1 | 1 | 3 | 2
382 | 15 | 8 | 17 | 28 | 39 | 51 | 65 | 81 | 91 | 110 | 125 | 135 | 143 | 156 | 5 | 1 | 1 | 1 | 4 | 3 | 1 | 1 | 4 | 1 | 5 | 1 | 4 | 5 | 1 | 1 | 2 | 2 | 4 | 4 | 3 | 5 | 2 | 4 | 5 | 2 | 5 | 4 | 4 | 1 | 4 | 1 | 4 | 5 | 5 | 5 | 4 | 5 | 3 | 3 | 3 | 4 | 2 | 1 | 2 | 1 | 2 | 3 | 4 | 3 | 3 | 3
383 | 17 | 9 | 21 | 36 | 51 | 64 | 72 | 87 | 97 | 109 | 118 | 132 | 143 | 152 | 4 | 2 | 2 | 1 | 3 | 5 | 2 | 2 | 4 | 5 | 1 | 5 | 4 | 4 | 4 | 3 | 5 | 1 | 5 | 2 | 2 | 4 | 1 | 1 | 4 | 3 | 4 | 4 | 1 | 4 | 4 | 1 | 2 | 5 | 4 | 1 | 1 | 4 | 3 | 1 | 4 | 3 | 3 | 4 | 3 | 3 | 4 | 1 | 4 | 1 | 1 | 3
384 | 14 | 9 | 23 | 36 | 42 | 57 | 69 | 82 | 97 | 110 | 123 | 131 | 142 | 154 | 2 | 1 | 4 | 2 | 4 | 1 | 4 | 5 | 3 | 5 | 3 | 2 | 1 | 3 | 1 | 1 | 5 | 4 | 1 | 5 | 3 | 4 | 4 | 1 | 5 | 5 | 2 | 1 | 5 | 3 | 3 | 4 | 1 | 4 | 5 | 3 | 4 | 4 | 1 | 4 | 1 | 2 | 2 | 3 | 4 | 5 | 1 | 1 | 2 | 5 | 1 | 4
385 | 14 | 8 | 18 | 31 | 39 | 51 | 64 | 72 | 85 | 98 | 107 | 122 | 132 | 146 | 2 | 3 | 2 | 1 | 2 | 4 | 3 | 1 | 1 | 5 | 5 | 2 | 2 | 1 | 4 | 1 | 5 | 2 | 4 | 1 | 5 | 4 | 2 | 2 | 2 | 1 | 4 | 1 | 3 | 2 | 3 | 5 | 2 | 5 | 3 | 3 | 1 | 3 | 1 | 4 | 5 | 5 | 3 | 2 | 5 | 2 | 1 | 2 | 3 | 4 | 4 | 3
386 | 12 | 7 | 18 | 28 | 40 | 54 | 63 | 74 | 88 | 101 | 114 | 124 | 135 | 147 | 1 | 3 | 1 | 2 | 1 | 4 | 5 | 1 | 3 | 2 | 3 | 2 | 1 | 4 | 3 | 4 | 5 | 2 | 5 | 2 | 2 | 3 | 1 | 3 | 1 | 2 | 3 | 5 | 3 | 3 | 4 | 4 | 2 | 5 | 3 | 3 | 5 | 2 | 2 | 4 | 3 | 4 | 1 | 2 | 1 | 4 | 1 | 5 | 5 | 1 | 5 | 1
387 | 21 | 13 | 23 | 38 | 52 | 64 | 77 | 90 | 101 | 113 | 129 | 146 | 157 | 169 | 1 | 4 | 3 | 5 | 3 | 5 | 1 | 1 | 5 | 3 | 3 | 4 | 1 | 5 | 3 | 5 | 1 | 4 | 2 | 5 | 3 | 2 | 3 | 5 | 4 | 3 | 1 | 5 | 4 | 1 | 3 | 3 | 3 | 4 | 4 | 1 | 3 | 3 | 5 | 5 | 5 | 4 | 3 | 5 | 1 | 4 | 5 | 1 | 2 | 4 | 5 | 1
388 | 23 | 16 | 28 | 36 | 47 | 61 | 73 | 86 | 95 | 102 | 113 | 123 | 129 | 145 | 5 | 2 | 5 | 4 | 5 | 2 | 2 | 3 | 1 | 2 | 1 | 4 | 5 | 1 | 4 | 1 | 4 | 5 | 4 | 1 | 3 | 2 | 4 | 3 | 3 | 4 | 5 | 1 | 4 | 1 | 1 | 3 | 1 | 3 | 2 | 1 | 4 | 4 | 2 | 1 | 1 | 3 | 1 | 5 | 2 | 1 | 1 | 2 | 4 | 4 | 5 | 3
389 | 19 | 14 | 25 | 41 | 57 | 69 | 80 | 93 | 105 | 117 | 130 | 139 | 146 | 164 | 5 | 4 | 1 | 4 | 2 | 3 | 4 | 2 | 3 | 4 | 5 | 4 | 5 | 3 | 5 | 3 | 1 | 3 | 5 | 3 | 3 | 2 | 5 | 1 | 4 | 2 | 5 | 2 | 5 | 3 | 1 | 3 | 2 | 2 | 5 | 3 | 3 | 1 | 4 | 5 | 1 | 2 | 5 | 1 | 3 | 1 | 1 | 2 | 5 | 5 | 4 | 4
390 | 11 | 9 | 16 | 29 | 40 | 49 | 57 | 70 | 83 | 95 | 105 | 116 | 132 | 142 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 4 | 5 | 3 | 2 | 3 | 1 | 5 | 2 | 3 | 2 | 1 | 1 | 5 | 2 | 4 | 1 | 1 | 5 | 3 | 2 | 3 | 3 | 2 | 5 | 3 | 5 | 3 | 2 | 2 | 2 | 3 | 4 | 1 | 2 | 2 | 5 | 2 | 3 | 5 | 4 | 4 | 2 | 5 | 1 | 2
391 | 16 | 11 | 23 | 32 | 46 | 60 | 69 | 83 | 97 | 107 | 120 | 133 | 147 | 160 | 2 | 2 | 2 | 5 | 2 | 3 | 3 | 4 | 1 | 1 | 5 | 2 | 3 | 4 | 2 | 5 | 5 | 4 | 2 | 3 | 2 | 1 | 3 | 3 | 4 | 5 | 3 | 2 | 4 | 4 | 4 | 2 | 1 | 5 | 3 | 1 | 1 | 3 | 5 | 4 | 3 | 5 | 1 | 4 | 4 | 5 | 1 | 4 | 5 | 2 | 1 | 5
392 | 18 | 12 | 24 | 34 | 47 | 61 | 77 | 89 | 103 | 111 | 120 | 127 | 139 | 149 | 5 | 3 | 2 | 2 | 5 | 1 | 1 | 5 | 1 | 4 | 3 | 2 | 3 | 3 | 5 | 2 | 4 | 5 | 3 | 2 | 5 | 5 | 1 | 5 | 2 | 4 | 2 | 4 | 4 | 5 | 3 | 2 | 2 | 1 | 4 | 1 | 5 | 1 | 2 | 1 | 1 | 3 | 1 | 2 | 3 | 4 | 1 | 4 | 2 | 4 | 1 | 3
393 | 21 | 16 | 27 | 38 | 47 | 54 | 63 | 74 | 85 | 96 | 108 | 126 | 134 | 150 | 5 | 4 | 2 | 5 | 2 | 3 | 3 | 3 | 2 | 4 | 3 | 2 | 1 | 3 | 2 | 3 | 2 | 1 | 3 | 1 | 4 | 2 | 1 | 2 | 4 | 3 | 2 | 2 | 2 | 1 | 5 | 3 | 2 | 3 | 3 | 3 | 5 | 2 | 3 | 2 | 4 | 5 | 4 | 5 | 2 | 2 | 2 | 2 | 5 | 5 | 3 | 3
394 | 19 | 15 | 24 | 37 | 47 | 57 | 65 | 81 | 92 | 105 | 119 | 128 | 141 | 157 | 4 | 5 | 1 | 5 | 1 | 3 | 2 | 3 | 1 | 4 | 5 | 3 | 5 | 1 | 1 | 3 | 1 | 4 | 2 | 3 | 2 | 2 | 1 | 3 | 1 | 5 | 5 | 5 | 1 | 4 | 1 | 5 | 2 | 4 | 2 | 5 | 5 | 1 | 4 | 4 | 3 | 3 | 2 | 1 | 3 | 2 | 3 | 5 | 5 | 2 | 4 | 5
395 | 21 | 16 | 28 | 38 | 52 | 60 | 66 | 77 | 96 | 107 | 120 | 126 | 138 | 150 | 4 | 5 | 4 | 3 | 3 | 2 | 5 | 2 | 1 | 2 | 5 | 2 | 3 | 2 | 4 | 5 | 3 | 2 | 1 | 2 | 2 | 1 | 1 | 2 | 3 | 3 | 2 | 3 | 4 | 5 | 5 | 5 | 3 | 3 | 2 | 3 | 1 | 3 | 5 | 4 | 2 | 1 | 2 | 1 | 4 | 3 | 4 | 1 | 3 | 3 | 1 | 5
396 | 19 | 11 | 27 | 41 | 54 | 66 | 77 | 86 | 96 | 106 | 120 | 134 | 149 | 164 | 2 | 3 | 3 | 3 | 5 | 3 | 4 | 4 | 5 | 3 | 3 | 3 | 3 | 3 | 2 | 5 | 3 | 2 | 4 | 3 | 3 | 3 | 2 | 3 | 5 | 1 | 2 | 1 | 1 | 3 | 5 | 1 | 3 | 2 | 1 | 4 | 3 | 4 | 5 | 2 | 1 | 5 | 3 | 5 | 3 | 2 | 5 | 5 | 2 | 4 | 5 | 4
397 | 12 | 7 | 20 | 33 | 44 | 56 | 65 | 79 | 93 | 109 | 116 | 130 | 143 | 159 | 1 | 2 | 1 | 3 | 2 | 3 | 5 | 3 | 3 | 4 | 1 | 5 | 3 | 2 | 5 | 1 | 3 | 4 | 3 | 2 | 2 | 1 | 5 | 1 | 2 | 4 | 4 | 4 | 1 | 5 | 5 | 3 | 5 | 5 | 1 | 5 | 2 | 1 | 3 | 1 | 1 | 5 | 3 | 5 | 4 | 5 | 2 | 2 | 4 | 4 | 5 | 3
398 | 14 | 9 | 22 | 30 | 42 | 54 | 67 | 79 | 92 | 101 | 109 | 121 | 131 | 143 | 3 | 1 | 3 | 2 | 2 | 3 | 5 | 3 | 3 | 2 | 1 | 2 | 4 | 2 | 4 | 2 | 4 | 1 | 5 | 2 | 5 | 2 | 5 | 1 | 3 | 3 | 5 | 1 | 3 | 3 | 3 | 4 | 1 | 4 | 3 | 1 | 1 | 1 | 1 | 5 | 3 | 1 | 4 | 4 | 2 | 3 | 3 | 2 | 5 | 1 | 5 | 1
399 | 18 | 10 | 28 | 40 | 54 | 67 | 80 | 91 | 103 | 114 | 128 | 143 | 152 | 161 | 2 | 1 | 2 | 5 | 4 | 4 | 5 | 5 | 5 | 3 | 1 | 3 | 2 | 5 | 5 | 2 | 3 | 3 | 3 | 4 | 3 | 2 | 3 | 5 | 3 | 2 | 3 | 3 | 3 | 3 | 1 | 5 | 4 | 1 | 2 | 4 | 2 | 5 | 2 | 5 | 1 | 5 | 5 | 4 | 1 | 5 | 2 | 1 | 1 | 4 | 3 | 1
400 | 20 | 17 | 28 | 39 | 52 | 65 | 75 | 84 | 94 | 103 | 111 | 120 | 129 | 138 | 5 | 3 | 4 | 5 | 1 | 2 | 3 | 5 | 2 | 4 | 4 | 1 | 3 | 3 | 5 | 2 | 5 | 4 | 2 | 2 | 4 | 3 | 1 | 2 | 4 | 1 | 2 | 2 | 5 | 1 | 2 | 2 | 2 | 1 | 4 | 2 | 1 | 1 | 2 | 4 | 2 | 2 | 3 | 2 | 3 | 1 | 3 | 2 | 4 | 2 | 1 | 2
401 | 23 | 17 | 31 | 43 | 52 | 64 | 82 | 87 | 95 | 109 | 128 | 140 | 150 | 165 | 3 | 4 | 5 | 5 | 1 | 5 | 5 | 3 | 3 | 4 | 4 | 1 | 3 | 2 | 3 | 1 | 3 | 3 | 1 | 5 | 5 | 4 | 4 | 5 | 1 | 1 | 1 | 2 | 1 | 1 | 4 | 2 | 1 | 5 | 5 | 3 | 5 | 5 | 4 | 5 | 4 | 4 | 1 | 3 | 3 | 2 | 1 | 4 | 5 | 2 | 3 | 5
402 | 21 | 13 | 31 | 47 | 58 | 67 | 79 | 97 | 106 | 113 | 124 | 132 | 141 | 154 | 1 | 4 | 4 | 4 | 3 | 5 | 5 | 5 | 2 | 5 | 4 | 5 | 4 | 4 | 1 | 2 | 1 | 1 | 5 | 2 | 3 | 4 | 3 | 2 | 4 | 4 | 5 | 5 | 4 | 2 | 1 | 2 | 1 | 1 | 1 | 4 | 1 | 1 | 4 | 5 | 3 | 1 | 2 | 2 | 2 | 2 | 2 | 3 | 5 | 2 | 4 | 2
403 | 18 | 13 | 28 | 41 | 55 | 69 | 82 | 93 | 111 | 124 | 135 | 153 | 165 | 179 | 3 | 5 | 3 | 2 | 1 | 4 | 5 | 5 | 3 | 2 | 4 | 4 | 3 | 4 | 5 | 2 | 5 | 2 | 5 | 2 | 2 | 2 | 4 | 5 | 3 | 1 | 2 | 5 | 5 | 5 | 3 | 5 | 4 | 2 | 4 | 3 | 5 | 3 | 2 | 1 | 5 | 5 | 5 | 3 | 3 | 4 | 2 | 3 | 1 | 5 | 5 | 3
404 | 17 | 12 | 22 | 32 | 44 | 55 | 66 | 78 | 88 | 101 | 109 | 118 | 132 | 146 | 3 | 3 | 5 | 1 | 2 | 3 | 3 | 2 | 2 | 2 | 5 | 1 | 1 | 2 | 4 | 5 | 2 | 5 | 1 | 3 | 4 | 1 | 5 | 1 | 3 | 4 | 1 | 4 | 1 | 1 | 3 | 5 | 2 | 4 | 2 | 5 | 5 | 1 | 1 | 1 | 4 | 1 | 1 | 3 | 4 | 3 | 3 | 4 | 3 | 3 | 3 | 5
405 | 14 | 10 | 16 | 29 | 44 | 58 | 71 | 85 | 101 | 112 | 127 | 136 | 148 | 160 | 2 | 4 | 2 | 2 | 2 | 2 | 1 | 1 | 4 | 3 | 2 | 4 | 5 | 4 | 5 | 1 | 3 | 4 | 5 | 2 | 3 | 5 | 2 | 3 | 2 | 4 | 3 | 5 | 4 | 4 | 4 | 4 | 5 | 2 | 3 | 1 | 3 | 5 | 4 | 3 | 3 | 2 | 3 | 1 | 4 | 1 | 4 | 3 | 1 | 4 | 5 | 2
406 | 15 | 11 | 20 | 33 | 43 | 54 | 66 | 83 | 96 | 103 | 117 | 132 | 145 | 159 | 2 | 4 | 4 | 1 | 1 | 3 | 4 | 1 | 5 | 2 | 1 | 5 | 5 | 2 | 2 | 1 | 5 | 2 | 1 | 3 | 5 | 1 | 4 | 2 | 4 | 5 | 4 | 4 | 3 | 1 | 4 | 5 | 1 | 2 | 3 | 1 | 5 | 2 | 5 | 2 | 5 | 4 | 5 | 1 | 5 | 2 | 4 | 2 | 5 | 5 | 1 | 3
407 | 20 | 11 | 26 | 35 | 47 | 62 | 75 | 89 | 100 | 113 | 127 | 145 | 165 | 180 | 3 | 3 | 2 | 3 | 4 | 5 | 3 | 3 | 1 | 3 | 1 | 4 | 4 | 2 | 5 | 1 | 4 | 4 | 4 | 3 | 4 | 3 | 4 | 2 | 1 | 4 | 4 | 5 | 5 | 2 | 1 | 3 | 2 | 3 | 4 | 4 | 5 | 5 | 3 | 1 | 5 | 5 | 5 | 3 | 5 | 5 | 5 | 5 | 4 | 5 | 5 | 1
408 | 18 | 12 | 24 | 32 | 49 | 65 | 80 | 94 | 109 | 125 | 136 | 151 | 160 | 168 | 4 | 4 | 3 | 1 | 1 | 5 | 3 | 3 | 4 | 2 | 1 | 1 | 5 | 4 | 5 | 3 | 4 | 5 | 4 | 3 | 3 | 2 | 5 | 5 | 3 | 4 | 4 | 3 | 3 | 3 | 4 | 5 | 4 | 3 | 4 | 5 | 3 | 2 | 1 | 5 | 1 | 4 | 5 | 5 | 3 | 1 | 1 | 4 | 1 | 3 | 1 | 3
409 | 20 | 13 | 27 | 39 | 53 | 66 | 80 | 90 | 99 | 114 | 128 | 139 | 152 | 163 | 4 | 2 | 2 | 5 | 3 | 4 | 3 | 4 | 4 | 4 | 3 | 1 | 5 | 2 | 4 | 3 | 2 | 5 | 1 | 5 | 3 | 4 | 3 | 4 | 3 | 3 | 3 | 1 | 1 | 3 | 2 | 3 | 3 | 5 | 5 | 2 | 4 | 4 | 2 | 4 | 1 | 1 | 4 | 5 | 3 | 5 | 2 | 3 | 4 | 2 | 3 | 2
410 | 20 | 14 | 26 | 36 | 49 | 58 | 67 | 79 | 98 | 112 | 129 | 142 | 152 | 166 | 5 | 4 | 1 | 4 | 2 | 4 | 4 | 2 | 4 | 3 | 2 | 1 | 4 | 5 | 3 | 1 | 1 | 5 | 1 | 2 | 4 | 2 | 1 | 2 | 1 | 5 | 4 | 2 | 5 | 5 | 4 | 5 | 4 | 1 | 4 | 5 | 5 | 5 | 5 | 2 | 5 | 2 | 1 | 5 | 1 | 4 | 2 | 3 | 3 | 5 | 4 | 2
411 | 23 | 13 | 29 | 45 | 62 | 76 | 87 | 99 | 110 | 120 | 135 | 144 | 160 | 169 | 5 | 2 | 1 | 5 | 5 | 5 | 4 | 2 | 5 | 3 | 3 | 5 | 5 | 5 | 2 | 5 | 5 | 1 | 5 | 3 | 4 | 1 | 1 | 5 | 2 | 1 | 4 | 5 | 2 | 1 | 3 | 5 | 1 | 4 | 4 | 1 | 4 | 3 | 5 | 3 | 3 | 2 | 3 | 1 | 5 | 5 | 2 | 4 | 1 | 2 | 4 | 2
412 | 19 | 10 | 26 | 41 | 55 | 72 | 83 | 96 | 110 | 117 | 130 | 140 | 149 | 158 | 2 | 2 | 3 | 3 | 5 | 4 | 4 | 3 | 4 | 3 | 4 | 4 | 5 | 4 | 4 | 1 | 5 | 5 | 3 | 4 | 2 | 3 | 2 | 4 | 3 | 4 | 3 | 3 | 4 | 5 | 4 | 1 | 1 | 1 | 1 | 4 | 5 | 4 | 2 | 2 | 2 | 4 | 1 | 3 | 2 | 1 | 5 | 1 | 2 | 2 | 2 | 3
413 | 15 | 11 | 21 | 30 | 38 | 55 | 67 | 80 | 96 | 104 | 120 | 135 | 149 | 163 | 2 | 1 | 4 | 4 | 2 | 2 | 2 | 4 | 1 | 1 | 4 | 3 | 5 | 1 | 1 | 1 | 5 | 2 | 5 | 5 | 2 | 5 | 4 | 1 | 5 | 3 | 1 | 4 | 3 | 5 | 5 | 3 | 2 | 2 | 3 | 1 | 5 | 4 | 4 | 3 | 5 | 3 | 5 | 2 | 2 | 5 | 2 | 5 | 3 | 5 | 4 | 2
414 | 21 | 13 | 27 | 39 | 51 | 66 | 81 | 93 | 110 | 122 | 137 | 148 | 165 | 177 | 3 | 4 | 1 | 5 | 5 | 3 | 5 | 1 | 3 | 1 | 4 | 4 | 4 | 2 | 3 | 3 | 3 | 5 | 2 | 5 | 4 | 5 | 2 | 4 | 4 | 1 | 2 | 5 | 5 | 2 | 5 | 5 | 2 | 4 | 2 | 4 | 5 | 4 | 5 | 1 | 2 | 2 | 2 | 5 | 3 | 5 | 4 | 5 | 2 | 4 | 1 | 5
415 | 18 | 12 | 27 | 35 | 50 | 58 | 64 | 77 | 88 | 103 | 110 | 126 | 134 | 144 | 3 | 3 | 4 | 2 | 3 | 3 | 4 | 5 | 4 | 1 | 1 | 2 | 3 | 4 | 4 | 4 | 1 | 1 | 1 | 5 | 2 | 2 | 1 | 1 | 3 | 5 | 1 | 4 | 3 | 3 | 4 | 1 | 5 | 3 | 3 | 4 | 1 | 2 | 2 | 2 | 4 | 3 | 4 | 5 | 2 | 2 | 3 | 1 | 1 | 5 | 1 | 3
416 | 18 | 12 | 27 | 34 | 44 | 57 | 62 | 74 | 81 | 92 | 107 | 118 | 131 | 143 | 3 | 2 | 2 | 5 | 2 | 4 | 5 | 4 | 1 | 2 | 2 | 2 | 3 | 4 | 2 | 1 | 5 | 2 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 5 | 1 | 5 | 1 | 1 | 2 | 3 | 2 | 5 | 3 | 1 | 5 | 1 | 4 | 5 | 2 | 3 | 2 | 4 | 3 | 4 | 3 | 3 | 3 | 3 | 1 | 5
417 | 16 | 12 | 18 | 28 | 44 | 54 | 64 | 80 | 94 | 109 | 120 | 136 | 153 | 164 | 1 | 3 | 5 | 3 | 1 | 3 | 1 | 1 | 4 | 3 | 1 | 2 | 5 | 2 | 5 | 4 | 1 | 3 | 2 | 4 | 1 | 5 | 1 | 3 | 5 | 5 | 4 | 2 | 5 | 3 | 3 | 3 | 5 | 4 | 2 | 4 | 5 | 2 | 1 | 3 | 2 | 5 | 5 | 4 | 3 | 4 | 5 | 5 | 5 | 1 | 2 | 3
418 | 19 | 13 | 25 | 38 | 49 | 60 | 67 | 74 | 82 | 87 | 99 | 108 | 117 | 126 | 2 | 2 | 5 | 4 | 4 | 2 | 2 | 4 | 4 | 2 | 4 | 3 | 1 | 4 | 4 | 2 | 1 | 3 | 3 | 4 | 1 | 1 | 2 | 3 | 2 | 1 | 1 | 3 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 2 | 4 | 1 | 3 | 4 | 2 | 2 | 2 | 3 | 2 | 3 | 2 | 2 | 2 | 3 | 2 | 2
419 | 16 | 10 | 20 | 28 | 40 | 53 | 65 | 83 | 94 | 105 | 114 | 126 | 138 | 149 | 1 | 3 | 3 | 3 | 5 | 1 | 2 | 2 | 1 | 1 | 3 | 3 | 5 | 4 | 2 | 1 | 2 | 5 | 4 | 2 | 4 | 1 | 4 | 3 | 5 | 5 | 5 | 3 | 3 | 5 | 2 | 1 | 3 | 3 | 1 | 4 | 2 | 1 | 5 | 1 | 3 | 2 | 4 | 3 | 2 | 5 | 1 | 4 | 3 | 3 | 2 | 3
420 | 20 | 11 | 30 | 38 | 51 | 62 | 76 | 85 | 97 | 109 | 124 | 130 | 143 | 156 | 3 | 1 | 5 | 2 | 5 | 4 | 5 | 5 | 2 | 3 | 1 | 2 | 5 | 4 | 3 | 1 | 2 | 4 | 4 | 1 | 3 | 4 | 3 | 4 | 3 | 3 | 2 | 1 | 5 | 1 | 5 | 1 | 1 | 4 | 3 | 4 | 5 | 4 | 2 | 4 | 1 | 2 | 1 | 2 | 5 | 1 | 2 | 5 | 2 | 3 | 5 | 3
421 | 12 | 9 | 21 | 30 | 38 | 51 | 64 | 78 | 87 | 99 | 110 | 126 | 138 | 156 | 2 | 1 | 2 | 4 | 2 | 1 | 4 | 5 | 2 | 4 | 2 | 1 | 1 | 1 | 4 | 2 | 4 | 5 | 1 | 3 | 2 | 4 | 3 | 4 | 3 | 5 | 1 | 5 | 3 | 1 | 1 | 4 | 5 | 4 | 2 | 1 | 4 | 3 | 2 | 2 | 4 | 4 | 4 | 4 | 2 | 3 | 4 | 3 | 5 | 5 | 4 | 4
422 | 21 | 13 | 26 | 41 | 50 | 70 | 77 | 90 | 103 | 112 | 124 | 137 | 148 | 159 | 5 | 3 | 1 | 4 | 5 | 3 | 4 | 1 | 4 | 5 | 4 | 2 | 1 | 4 | 3 | 1 | 5 | 5 | 5 | 5 | 1 | 1 | 1 | 4 | 4 | 1 | 5 | 3 | 2 | 2 | 4 | 5 | 3 | 2 | 1 | 3 | 5 | 1 | 1 | 5 | 4 | 4 | 3 | 2 | 1 | 4 | 5 | 1 | 4 | 4 | 1 | 2
423 | 21 | 19 | 29 | 38 | 51 | 67 | 76 | 86 | 103 | 114 | 129 | 140 | 148 | 162 | 5 | 4 | 5 | 5 | 1 | 1 | 5 | 3 | 4 | 2 | 2 | 1 | 3 | 1 | 4 | 5 | 3 | 3 | 5 | 5 | 2 | 2 | 2 | 3 | 2 | 2 | 1 | 5 | 3 | 4 | 5 | 5 | 1 | 4 | 5 | 1 | 5 | 3 | 3 | 4 | 5 | 2 | 3 | 1 | 1 | 2 | 4 | 1 | 3 | 3 | 3 | 5
424 | 17 | 11 | 25 | 41 | 56 | 70 | 78 | 86 | 100 | 109 | 116 | 129 | 138 | 150 | 4 | 4 | 2 | 1 | 4 | 2 | 3 | 5 | 5 | 4 | 3 | 4 | 3 | 2 | 5 | 5 | 4 | 4 | 2 | 4 | 1 | 4 | 1 | 2 | 1 | 3 | 2 | 2 | 1 | 5 | 5 | 3 | 1 | 3 | 1 | 4 | 3 | 2 | 1 | 1 | 3 | 4 | 5 | 1 | 1 | 5 | 2 | 1 | 4 | 1 | 3 | 4
425 | 17 | 11 | 24 | 37 | 47 | 56 | 64 | 75 | 89 | 103 | 113 | 125 | 140 | 151 | 3 | 4 | 3 | 1 | 1 | 5 | 3 | 4 | 4 | 4 | 4 | 1 | 4 | 3 | 2 | 1 | 1 | 2 | 3 | 3 | 4 | 1 | 1 | 2 | 3 | 2 | 3 | 3 | 4 | 3 | 5 | 2 | 5 | 1 | 5 | 3 | 5 | 3 | 1 | 1 | 4 | 2 | 4 | 2 | 5 | 5 | 3 | 2 | 2 | 3 | 1 | 5
426 | 20 | 16 | 25 | 39 | 54 | 69 | 83 | 91 | 98 | 114 | 129 | 139 | 153 | 169 | 3 | 5 | 4 | 4 | 1 | 3 | 1 | 4 | 4 | 4 | 2 | 4 | 4 | 4 | 5 | 2 | 1 | 5 | 5 | 4 | 3 | 5 | 1 | 5 | 2 | 2 | 2 | 2 | 2 | 1 | 2 | 2 | 5 | 3 | 4 | 4 | 1 | 5 | 4 | 5 | 3 | 4 | 2 | 1 | 3 | 3 | 3 | 5 | 2 | 4 | 5 | 5
427 | 23 | 15 | 29 | 37 | 49 | 67 | 81 | 97 | 109 | 122 | 136 | 149 | 159 | 170 | 3 | 5 | 5 | 2 | 5 | 3 | 2 | 4 | 2 | 2 | 1 | 3 | 4 | 5 | 1 | 2 | 3 | 5 | 5 | 5 | 1 | 5 | 3 | 5 | 3 | 4 | 4 | 5 | 5 | 1 | 2 | 4 | 3 | 3 | 5 | 2 | 4 | 4 | 4 | 2 | 1 | 2 | 5 | 5 | 2 | 2 | 4 | 2 | 3 | 1 | 3 | 4
428 | 18 | 11 | 22 | 34 | 49 | 61 | 75 | 91 | 100 | 106 | 114 | 128 | 138 | 149 | 1 | 5 | 2 | 3 | 3 | 4 | 3 | 1 | 5 | 4 | 1 | 2 | 5 | 5 | 3 | 2 | 4 | 3 | 2 | 3 | 4 | 4 | 5 | 1 | 5 | 5 | 3 | 3 | 3 | 2 | 1 | 3 | 1 | 1 | 1 | 3 | 3 | 1 | 3 | 1 | 4 | 4 | 5 | 1 | 3 | 3 | 2 | 2 | 5 | 2 | 2 | 2
429 | 17 | 12 | 24 | 41 | 50 | 62 | 72 | 84 | 103 | 114 | 128 | 145 | 159 | 170 | 5 | 4 | 1 | 2 | 1 | 4 | 5 | 2 | 5 | 4 | 4 | 4 | 4 | 2 | 2 | 1 | 3 | 5 | 3 | 1 | 4 | 4 | 1 | 1 | 3 | 5 | 1 | 3 | 5 | 5 | 4 | 5 | 2 | 2 | 3 | 4 | 3 | 5 | 4 | 2 | 4 | 3 | 5 | 5 | 5 | 3 | 2 | 4 | 1 | 5 | 2 | 3
430 | 16 | 10 | 22 | 37 | 51 | 60 | 72 | 84 | 95 | 109 | 125 | 135 | 146 | 160 | 2 | 2 | 5 | 1 | 1 | 5 | 1 | 5 | 3 | 5 | 2 | 5 | 5 | 3 | 3 | 3 | 3 | 2 | 1 | 3 | 5 | 2 | 4 | 1 | 3 | 5 | 1 | 3 | 3 | 3 | 3 | 2 | 3 | 4 | 5 | 2 | 5 | 5 | 1 | 5 | 2 | 1 | 4 | 3 | 3 | 5 | 1 | 2 | 3 | 3 | 4 | 4
431 | 16 | 11 | 21 | 35 | 49 | 59 | 68 | 78 | 96 | 104 | 115 | 129 | 141 | 151 | 1 | 5 | 1 | 4 | 1 | 4 | 3 | 2 | 3 | 5 | 4 | 2 | 3 | 5 | 1 | 5 | 4 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 1 | 3 | 5 | 5 | 4 | 5 | 4 | 1 | 1 | 1 | 5 | 1 | 2 | 5 | 3 | 2 | 5 | 2 | 5 | 2 | 2 | 4 | 4 | 4 | 3 | 2 | 1
432 | 16 | 7 | 24 | 34 | 48 | 62 | 70 | 82 | 96 | 104 | 112 | 122 | 136 | 149 | 1 | 3 | 2 | 1 | 4 | 5 | 3 | 5 | 2 | 1 | 4 | 3 | 3 | 4 | 3 | 4 | 2 | 4 | 3 | 5 | 2 | 2 | 3 | 1 | 1 | 5 | 1 | 5 | 5 | 1 | 3 | 5 | 1 | 2 | 1 | 4 | 1 | 1 | 2 | 4 | 5 | 1 | 3 | 1 | 5 | 4 | 1 | 4 | 3 | 1 | 4 | 5
433 | 17 | 11 | 21 | 34 | 46 | 60 | 72 | 79 | 92 | 105 | 119 | 130 | 145 | 161 | 4 | 4 | 1 | 2 | 5 | 1 | 1 | 3 | 4 | 1 | 4 | 4 | 1 | 3 | 3 | 5 | 4 | 4 | 2 | 4 | 2 | 3 | 3 | 4 | 3 | 1 | 2 | 1 | 3 | 4 | 5 | 1 | 5 | 4 | 1 | 3 | 1 | 4 | 5 | 4 | 1 | 3 | 3 | 4 | 5 | 5 | 1 | 4 | 4 | 5 | 5 | 2
434 | 21 | 14 | 28 | 37 | 52 | 63 | 71 | 82 | 91 | 102 | 115 | 131 | 145 | 153 | 2 | 5 | 4 | 3 | 5 | 2 | 4 | 3 | 2 | 2 | 2 | 3 | 4 | 3 | 4 | 4 | 4 | 3 | 3 | 1 | 1 | 1 | 5 | 1 | 2 | 4 | 2 | 3 | 3 | 1 | 2 | 3 | 3 | 2 | 2 | 4 | 4 | 3 | 5 | 1 | 3 | 3 | 5 | 5 | 5 | 3 | 1 | 5 | 2 | 1 | 1 | 4
435 | 19 | 12 | 25 | 36 | 47 | 54 | 69 | 82 | 96 | 104 | 115 | 126 | 136 | 148 | 4 | 3 | 1 | 4 | 2 | 5 | 3 | 3 | 2 | 1 | 4 | 4 | 2 | 1 | 5 | 3 | 2 | 1 | 2 | 2 | 4 | 5 | 1 | 5 | 5 | 5 | 1 | 2 | 4 | 5 | 4 | 1 | 1 | 1 | 3 | 3 | 4 | 1 | 2 | 4 | 4 | 1 | 5 | 1 | 2 | 1 | 5 | 2 | 2 | 2 | 3 | 5
436 | 24 | 15 | 31 | 47 | 58 | 66 | 81 | 95 | 110 | 126 | 138 | 147 | 157 | 171 | 4 | 4 | 3 | 4 | 5 | 4 | 3 | 4 | 4 | 5 | 2 | 5 | 3 | 2 | 5 | 1 | 2 | 4 | 1 | 1 | 4 | 1 | 5 | 5 | 3 | 4 | 2 | 5 | 3 | 5 | 2 | 5 | 3 | 5 | 3 | 5 | 2 | 2 | 5 | 3 | 2 | 2 | 3 | 2 | 3 | 2 | 3 | 2 | 2 | 5 | 2 | 5
437 | 14 | 11 | 18 | 28 | 44 | 60 | 72 | 83 | 94 | 109 | 121 | 134 | 149 | 159 | 4 | 2 | 3 | 2 | 1 | 2 | 3 | 1 | 2 | 2 | 5 | 1 | 5 | 5 | 3 | 3 | 5 | 5 | 5 | 1 | 4 | 2 | 4 | 2 | 3 | 3 | 3 | 2 | 2 | 5 | 3 | 1 | 5 | 2 | 5 | 3 | 5 | 2 | 2 | 3 | 5 | 4 | 2 | 2 | 5 | 3 | 5 | 2 | 1 | 2 | 3 | 4
438 | 22 | 14 | 28 | 37 | 53 | 67 | 77 | 88 | 96 | 108 | 120 | 137 | 148 | 166 | 1 | 5 | 3 | 5 | 5 | 3 | 2 | 4 | 5 | 1 | 1 | 2 | 5 | 4 | 5 | 2 | 4 | 3 | 3 | 4 | 2 | 3 | 1 | 4 | 5 | 3 | 2 | 1 | 2 | 4 | 1 | 1 | 1 | 5 | 4 | 2 | 1 | 2 | 4 | 5 | 5 | 3 | 5 | 4 | 1 | 3 | 3 | 4 | 4 | 5 | 5 | 4
439 | 18 | 10 | 21 | 28 | 42 | 52 | 70 | 82 | 94 | 104 | 116 | 131 | 140 | 150 | 4 | 2 | 2 | 2 | 4 | 4 | 2 | 1 | 3 | 1 | 1 | 2 | 3 | 5 | 2 | 4 | 5 | 1 | 1 | 3 | 3 | 5 | 5 | 5 | 1 | 5 | 2 | 4 | 2 | 5 | 4 | 1 | 2 | 4 | 2 | 2 | 4 | 4 | 2 | 2 | 5 | 3 | 2 | 5 | 1 | 5 | 2 | 1 | 4 | 2 | 3 | 1
440 | 20 | 14 | 26 | 38 | 52 | 66 | 77 | 89 | 100 | 111 | 124 | 135 | 144 | 155 | 3 | 5 | 3 | 3 | 1 | 5 | 3 | 3 | 5 | 3 | 3 | 1 | 2 | 5 | 3 | 4 | 5 | 5 | 2 | 2 | 3 | 3 | 4 | 1 | 2 | 3 | 2 | 5 | 5 | 2 | 2 | 2 | 5 | 2 | 1 | 3 | 2 | 5 | 2 | 4 | 4 | 2 | 1 | 4 | 2 | 3 | 1 | 3 | 3 | 4 | 2 | 2
441 | 22 | 15 | 30 | 38 | 54 | 63 | 73 | 86 | 94 | 106 | 116 | 130 | 147 | 158 | 5 | 1 | 4 | 5 | 3 | 4 | 4 | 4 | 5 | 1 | 1 | 1 | 4 | 4 | 4 | 4 | 1 | 1 | 3 | 4 | 4 | 4 | 1 | 1 | 3 | 4 | 2 | 4 | 1 | 1 | 1 | 5 | 2 | 5 | 1 | 4 | 3 | 3 | 3 | 1 | 4 | 2 | 3 | 5 | 4 | 4 | 5 | 4 | 2 | 5 | 2 | 2
442 | 23 | 16 | 28 | 41 | 55 | 70 | 85 | 95 | 105 | 119 | 127 | 137 | 145 | 154 | 3 | 5 | 3 | 5 | 4 | 3 | 1 | 4 | 3 | 5 | 4 | 1 | 5 | 1 | 3 | 5 | 4 | 5 | 3 | 3 | 4 | 4 | 2 | 5 | 4 | 4 | 1 | 1 | 4 | 1 | 2 | 3 | 3 | 5 | 2 | 4 | 4 | 1 | 1 | 2 | 5 | 1 | 1 | 3 | 1 | 2 | 4 | 1 | 2 | 5 | 1 | 1
443 | 17 | 11 | 24 | 37 | 48 | 63 | 77 | 87 | 98 | 107 | 122 | 138 | 152 | 161 | 4 | 2 | 3 | 2 | 1 | 5 | 4 | 3 | 2 | 4 | 5 | 2 | 5 | 2 | 1 | 3 | 5 | 3 | 4 | 3 | 3 | 4 | 2 | 5 | 2 | 1 | 5 | 2 | 1 | 4 | 1 | 5 | 1 | 3 | 1 | 4 | 1 | 5 | 5 | 4 | 3 | 3 | 5 | 5 | 4 | 4 | 5 | 1 | 3 | 2 | 1 | 3
444 | 15 | 13 | 22 | 33 | 48 | 59 | 70 | 79 | 87 | 104 | 116 | 125 | 137 | 149 | 4 | 5 | 2 | 2 | 1 | 1 | 4 | 3 | 1 | 5 | 1 | 4 | 5 | 4 | 5 | 1 | 4 | 1 | 4 | 2 | 1 | 5 | 1 | 4 | 4 | 2 | 1 | 2 | 1 | 1 | 3 | 3 | 5 | 5 | 2 | 5 | 2 | 2 | 3 | 5 | 1 | 4 | 1 | 3 | 2 | 3 | 4 | 3 | 3 | 2 | 4 | 3
445 | 18 | 11 | 22 | 31 | 43 | 55 | 65 | 77 | 89 | 99 | 111 | 122 | 135 | 144 | 4 | 1 | 4 | 2 | 2 | 5 | 1 | 3 | 3 | 1 | 1 | 4 | 1 | 4 | 3 | 4 | 2 | 3 | 4 | 3 | 2 | 4 | 1 | 3 | 5 | 1 | 5 | 1 | 3 | 1 | 4 | 4 | 2 | 2 | 2 | 4 | 4 | 3 | 4 | 1 | 3 | 1 | 4 | 3 | 4 | 1 | 5 | 3 | 1 | 2 | 1 | 5
446 | 20 | 13 | 24 | 36 | 47 | 64 | 77 | 92 | 103 | 116 | 133 | 143 | 155 | 171 | 3 | 5 | 3 | 2 | 3 | 4 | 3 | 1 | 5 | 4 | 1 | 2 | 4 | 3 | 1 | 3 | 4 | 5 | 5 | 3 | 3 | 3 | 5 | 2 | 5 | 5 | 1 | 4 | 2 | 2 | 2 | 5 | 3 | 3 | 2 | 5 | 5 | 3 | 5 | 4 | 2 | 4 | 1 | 3 | 1 | 5 | 3 | 3 | 4 | 2 | 5 | 5
447 | 22 | 14 | 27 | 42 | 50 | 60 | 78 | 92 | 103 | 115 | 128 | 137 | 146 | 155 | 3 | 4 | 5 | 2 | 3 | 5 | 3 | 2 | 1 | 5 | 5 | 4 | 1 | 2 | 2 | 3 | 3 | 3 | 3 | 1 | 5 | 4 | 5 | 4 | 4 | 5 | 2 | 3 | 2 | 3 | 1 | 5 | 2 | 4 | 4 | 2 | 5 | 1 | 2 | 5 | 1 | 1 | 3 | 4 | 1 | 1 | 2 | 5 | 4 | 2 | 1 | 2
448 | 21 | 14 | 26 | 39 | 56 | 71 | 84 | 97 | 108 | 117 | 132 | 143 | 160 | 168 | 5 | 4 | 1 | 4 | 3 | 4 | 3 | 2 | 5 | 5 | 2 | 1 | 5 | 5 | 3 | 4 | 3 | 2 | 5 | 5 | 5 | 2 | 3 | 3 | 2 | 4 | 3 | 4 | 5 | 1 | 1 | 4 | 1 | 3 | 4 | 1 | 5 | 2 | 5 | 3 | 5 | 2 | 3 | 1 | 3 | 5 | 5 | 4 | 2 | 4 | 1 | 1
449 | 21 | 14 | 31 | 45 | 54 | 70 | 83 | 95 | 105 | 115 | 128 | 141 | 156 | 169 | 4 | 1 | 4 | 5 | 4 | 3 | 5 | 5 | 1 | 4 | 5 | 4 | 3 | 2 | 3 | 1 | 4 | 5 | 4 | 3 | 2 | 5 | 3 | 3 | 2 | 4 | 2 | 4 | 4 | 3 | 1 | 2 | 1 | 3 | 4 | 2 | 4 | 3 | 2 | 4 | 3 | 2 | 5 | 3 | 5 | 5 | 4 | 1 | 1 | 5 | 5 | 2
450 | 22 | 14 | 28 | 36 | 49 | 55 | 68 | 75 | 92 | 107 | 127 | 139 | 149 | 158 | 5 | 2 | 3 | 4 | 4 | 4 | 3 | 3 | 5 | 1 | 1 | 1 | 4 | 2 | 2 | 5 | 1 | 1 | 3 | 1 | 2 | 3 | 3 | 5 | 1 | 1 | 1 | 4 | 5 | 3 | 5 | 4 | 4 | 4 | 2 | 5 | 5 | 5 | 5 | 5 | 4 | 1 | 3 | 4 | 5 | 1 | 1 | 3 | 1 | 3 | 1 | 4
451 | 16 | 9 | 22 | 30 | 44 | 56 | 71 | 84 | 96 | 106 | 123 | 134 | 150 | 159 | 3 | 1 | 3 | 2 | 5 | 2 | 1 | 5 | 2 | 1 | 3 | 2 | 5 | 4 | 3 | 2 | 3 | 4 | 2 | 3 | 5 | 4 | 2 | 4 | 3 | 5 | 3 | 2 | 4 | 2 | 1 | 5 | 1 | 4 | 3 | 2 | 4 | 3 | 5 | 5 | 5 | 2 | 3 | 1 | 5 | 3 | 5 | 3 | 2 | 1 | 4 | 2
452 | 16 | 11 | 19 | 35 | 48 | 66 | 83 | 98 | 112 | 118 | 132 | 140 | 149 | 155 | 1 | 3 | 4 | 3 | 4 | 1 | 1 | 2 | 5 | 4 | 5 | 2 | 5 | 5 | 1 | 2 | 4 | 5 | 5 | 4 | 3 | 5 | 5 | 4 | 1 | 5 | 5 | 4 | 3 | 4 | 2 | 5 | 1 | 1 | 2 | 2 | 4 | 2 | 4 | 4 | 2 | 2 | 3 | 1 | 4 | 1 | 3 | 1 | 1 | 1 | 1 | 3
453 | 16 | 12 | 23 | 33 | 43 | 55 | 64 | 74 | 85 | 96 | 102 | 117 | 124 | 135 | 2 | 4 | 1 | 5 | 2 | 2 | 2 | 5 | 2 | 3 | 3 | 2 | 1 | 5 | 1 | 3 | 2 | 3 | 4 | 3 | 1 | 4 | 3 | 1 | 3 | 5 | 1 | 1 | 4 | 4 | 2 | 1 | 4 | 1 | 3 | 3 | 2 | 1 | 2 | 1 | 4 | 4 | 2 | 5 | 3 | 1 | 2 | 1 | 5 | 2 | 1 | 3
454 | 19 | 11 | 22 | 37 | 51 | 61 | 72 | 85 | 94 | 102 | 115 | 127 | 137 | 147 | 4 | 2 | 1 | 4 | 3 | 5 | 1 | 2 | 2 | 5 | 5 | 3 | 4 | 3 | 2 | 5 | 5 | 1 | 3 | 1 | 3 | 1 | 2 | 5 | 5 | 1 | 5 | 2 | 1 | 2 | 3 | 3 | 1 | 3 | 1 | 3 | 5 | 2 | 2 | 4 | 1 | 3 | 3 | 5 | 5 | 3 | 1 | 1 | 3 | 2 | 3 | 2
455 | 15 | 10 | 18 | 33 | 46 | 57 | 66 | 77 | 86 | 99 | 114 | 125 | 142 | 151 | 1 | 4 | 1 | 4 | 4 | 1 | 2 | 1 | 2 | 5 | 4 | 4 | 2 | 4 | 3 | 4 | 1 | 4 | 3 | 3 | 3 | 3 | 1 | 2 | 4 | 2 | 3 | 2 | 1 | 2 | 3 | 3 | 5 | 3 | 4 | 1 | 4 | 5 | 4 | 2 | 1 | 2 | 3 | 5 | 5 | 5 | 2 | 5 | 1 | 5 | 2 | 1
456 | 15 | 11 | 22 | 33 | 46 | 62 | 75 | 86 | 99 | 116 | 129 | 138 | 153 | 161 | 4 | 2 | 2 | 3 | 1 | 3 | 2 | 5 | 3 | 5 | 2 | 1 | 4 | 2 | 5 | 2 | 4 | 4 | 5 | 3 | 4 | 5 | 3 | 1 | 2 | 3 | 3 | 3 | 3 | 4 | 1 | 5 | 5 | 5 | 5 | 2 | 1 | 3 | 5 | 4 | 1 | 5 | 1 | 2 | 4 | 1 | 5 | 5 | 3 | 2 | 1 | 2
457 | 15 | 8 | 22 | 31 | 44 | 57 | 64 | 72 | 83 | 98 | 104 | 114 | 126 | 135 | 2 | 3 | 2 | 1 | 2 | 5 | 3 | 4 | 4 | 1 | 2 | 2 | 5 | 2 | 2 | 4 | 1 | 4 | 5 | 3 | 1 | 3 | 2 | 1 | 2 | 2 | 3 | 1 | 1 | 3 | 4 | 3 | 5 | 3 | 2 | 5 | 1 | 1 | 3 | 1 | 3 | 2 | 3 | 2 | 3 | 2 | 2 | 5 | 3 | 2 | 3 | 1
458 | 22 | 12 | 29 | 35 | 45 | 58 | 68 | 81 | 94 | 103 | 110 | 117 | 126 | 141 | 3 | 3 | 1 | 5 | 5 | 5 | 3 | 4 | 2 | 1 | 1 | 2 | 1 | 3 | 2 | 4 | 5 | 1 | 3 | 4 | 1 | 2 | 2 | 5 | 1 | 5 | 4 | 3 | 5 | 2 | 5 | 1 | 1 | 4 | 3 | 1 | 1 | 2 | 3 | 1 | 2 | 1 | 3 | 1 | 1 | 3 | 2 | 3 | 3 | 3 | 4 | 5
459 | 18 | 10 | 21 | 36 | 49 | 63 | 79 | 87 | 98 | 105 | 120 | 133 | 148 | 161 | 3 | 1 | 1 | 5 | 3 | 5 | 1 | 2 | 3 | 5 | 3 | 4 | 3 | 4 | 2 | 4 | 4 | 2 | 4 | 4 | 5 | 5 | 2 | 4 | 3 | 1 | 1 | 3 | 3 | 2 | 4 | 2 | 1 | 2 | 1 | 3 | 3 | 4 | 5 | 3 | 4 | 2 | 2 | 5 | 1 | 5 | 4 | 5 | 4 | 3 | 3 | 3
460 | 21 | 12 | 25 | 42 | 54 | 69 | 81 | 92 | 102 | 120 | 135 | 145 | 160 | 175 | 2 | 2 | 4 | 4 | 5 | 4 | 3 | 1 | 5 | 3 | 4 | 5 | 5 | 1 | 3 | 3 | 4 | 3 | 4 | 4 | 2 | 3 | 5 | 2 | 5 | 1 | 3 | 2 | 3 | 5 | 1 | 1 | 5 | 5 | 4 | 4 | 3 | 2 | 5 | 5 | 3 | 4 | 2 | 1 | 4 | 4 | 2 | 5 | 5 | 3 | 5 | 2
461 | 15 | 8 | 18 | 28 | 41 | 51 | 62 | 71 | 81 | 96 | 106 | 124 | 139 | 148 | 3 | 1 | 2 | 2 | 4 | 3 | 2 | 1 | 1 | 3 | 1 | 5 | 3 | 4 | 1 | 5 | 2 | 2 | 5 | 1 | 1 | 5 | 2 | 3 | 4 | 1 | 3 | 1 | 1 | 3 | 2 | 4 | 4 | 5 | 4 | 2 | 2 | 2 | 2 | 4 | 4 | 5 | 4 | 5 | 3 | 3 | 5 | 4 | 2 | 3 | 3 | 1
462 | 18 | 12 | 27 | 44 | 56 | 67 | 83 | 95 | 101 | 116 | 132 | 143 | 154 | 164 | 4 | 4 | 3 | 1 | 4 | 2 | 5 | 4 | 4 | 3 | 5 | 5 | 4 | 2 | 1 | 5 | 3 | 1 | 5 | 2 | 3 | 4 | 4 | 5 | 4 | 4 | 3 | 1 | 2 | 1 | 2 | 1 | 5 | 3 | 4 | 3 | 5 | 4 | 4 | 3 | 5 | 2 | 3 | 1 | 2 | 4 | 2 | 3 | 2 | 2 | 4 | 2
463 | 13 | 7 | 20 | 30 | 38 | 57 | 68 | 81 | 100 | 116 | 129 | 139 | 148 | 153 | 1 | 3 | 1 | 2 | 3 | 3 | 3 | 4 | 3 | 2 | 3 | 2 | 1 | 3 | 2 | 2 | 5 | 5 | 4 | 5 | 1 | 5 | 4 | 1 | 4 | 5 | 2 | 2 | 4 | 5 | 5 | 5 | 3 | 5 | 5 | 3 | 3 | 4 | 5 | 1 | 2 | 1 | 5 | 2 | 1 | 1 | 4 | 3 | 1 | 1 | 1 | 2
464 | 16 | 9 | 22 | 37 | 47 | 60 | 69 | 82 | 93 | 100 | 110 | 119 | 133 | 149 | 3 | 1 | 3 | 2 | 3 | 4 | 1 | 5 | 4 | 4 | 3 | 4 | 4 | 1 | 2 | 3 | 5 | 1 | 2 | 5 | 4 | 1 | 1 | 3 | 5 | 4 | 3 | 1 | 2 | 5 | 1 | 3 | 1 | 4 | 1 | 1 | 1 | 5 | 2 | 2 | 1 | 1 | 3 | 4 | 3 | 4 | 4 | 3 | 4 | 3 | 5 | 4
465 | 18 | 11 | 25 | 41 | 54 | 67 | 81 | 96 | 107 | 117 | 129 | 139 | 154 | 170 | 4 | 3 | 3 | 1 | 5 | 2 | 4 | 3 | 5 | 2 | 4 | 5 | 4 | 4 | 2 | 3 | 2 | 3 | 3 | 5 | 5 | 5 | 2 | 2 | 5 | 5 | 4 | 1 | 2 | 4 | 4 | 1 | 4 | 2 | 1 | 3 | 1 | 4 | 3 | 4 | 3 | 3 | 3 | 1 | 5 | 3 | 3 | 4 | 5 | 2 | 5 | 4
466 | 18 | 13 | 20 | 34 | 48 | 59 | 72 | 85 | 93 | 109 | 116 | 125 | 136 | 148 | 2 | 3 | 3 | 5 | 3 | 2 | 1 | 1 | 4 | 4 | 3 | 3 | 2 | 4 | 3 | 5 | 3 | 3 | 1 | 4 | 4 | 2 | 3 | 4 | 5 | 1 | 2 | 5 | 4 | 1 | 2 | 1 | 5 | 2 | 5 | 4 | 1 | 3 | 1 | 2 | 2 | 3 | 1 | 3 | 1 | 3 | 2 | 5 | 5 | 1 | 1 | 5
467 | 16 | 11 | 23 | 36 | 47 | 55 | 67 | 79 | 88 | 101 | 118 | 132 | 145 | 154 | 3 | 5 | 1 | 2 | 2 | 3 | 3 | 4 | 3 | 3 | 4 | 3 | 1 | 5 | 4 | 1 | 3 | 3 | 1 | 1 | 2 | 5 | 3 | 2 | 3 | 3 | 5 | 1 | 2 | 1 | 3 | 3 | 5 | 2 | 2 | 4 | 2 | 5 | 5 | 5 | 2 | 4 | 5 | 3 | 4 | 2 | 3 | 4 | 2 | 3 | 2 | 2
468 | 19 | 13 | 26 | 38 | 53 | 60 | 71 | 83 | 99 | 110 | 117 | 130 | 140 | 155 | 5 | 4 | 2 | 2 | 5 | 1 | 2 | 5 | 3 | 3 | 2 | 4 | 4 | 4 | 2 | 5 | 1 | 4 | 1 | 1 | 4 | 3 | 1 | 3 | 5 | 1 | 5 | 1 | 4 | 3 | 4 | 5 | 1 | 4 | 4 | 2 | 1 | 3 | 1 | 2 | 5 | 1 | 2 | 5 | 2 | 2 | 5 | 1 | 4 | 1 | 5 | 5
469 | 23 | 16 | 27 | 42 | 53 | 62 | 72 | 84 | 96 | 106 | 120 | 137 | 145 | 160 | 5 | 4 | 3 | 4 | 4 | 3 | 1 | 3 | 4 | 2 | 4 | 5 | 2 | 3 | 2 | 4 | 2 | 3 | 1 | 3 | 4 | 1 | 2 | 3 | 2 | 2 | 5 | 3 | 2 | 4 | 3 | 3 | 2 | 1 | 5 | 2 | 5 | 4 | 2 | 3 | 3 | 4 | 5 | 5 | 2 | 2 | 1 | 3 | 5 | 2 | 5 | 3
470 | 14 | 7 | 17 | 26 | 35 | 48 | 61 | 77 | 86 | 94 | 111 | 124 | 136 | 151 | 1 | 2 | 3 | 1 | 2 | 5 | 2 | 1 | 5 | 2 | 1 | 1 | 4 | 2 | 1 | 2 | 2 | 5 | 1 | 5 | 1 | 4 | 5 | 3 | 4 | 5 | 2 | 5 | 5 | 1 | 2 | 1 | 1 | 2 | 2 | 3 | 5 | 3 | 4 | 5 | 4 | 3 | 4 | 2 | 1 | 3 | 3 | 5 | 4 | 5 | 5 | 1
471 | 17 | 11 | 23 | 34 | 49 | 60 | 72 | 79 | 96 | 104 | 115 | 131 | 147 | 163 | 1 | 1 | 4 | 5 | 5 | 1 | 5 | 1 | 1 | 5 | 2 | 3 | 3 | 3 | 5 | 4 | 4 | 3 | 1 | 3 | 3 | 1 | 5 | 3 | 4 | 1 | 1 | 1 | 5 | 5 | 4 | 3 | 1 | 1 | 3 | 3 | 2 | 2 | 2 | 5 | 5 | 3 | 3 | 5 | 3 | 5 | 3 | 5 | 1 | 5 | 5 | 5
472 | 17 | 13 | 23 | 36 | 52 | 60 | 69 | 81 | 97 | 109 | 126 | 134 | 149 | 163 | 2 | 2 | 5 | 4 | 1 | 3 | 5 | 1 | 5 | 2 | 2 | 4 | 3 | 5 | 5 | 3 | 2 | 1 | 1 | 4 | 3 | 2 | 2 | 2 | 4 | 2 | 4 | 2 | 5 | 1 | 5 | 5 | 4 | 2 | 5 | 1 | 3 | 4 | 5 | 5 | 1 | 3 | 2 | 2 | 2 | 5 | 5 | 3 | 5 | 4 | 2 | 3
473 | 19 | 14 | 27 | 46 | 61 | 74 | 81 | 97 | 109 | 121 | 133 | 143 | 154 | 164 | 3 | 5 | 5 | 1 | 4 | 1 | 3 | 5 | 5 | 4 | 5 | 5 | 5 | 3 | 4 | 3 | 4 | 2 | 3 | 4 | 1 | 1 | 1 | 4 | 5 | 2 | 4 | 5 | 2 | 4 | 1 | 5 | 3 | 2 | 4 | 3 | 2 | 4 | 4 | 2 | 2 | 1 | 2 | 5 | 3 | 3 | 3 | 2 | 1 | 3 | 4 | 2
474 | 16 | 9 | 22 | 27 | 36 | 48 | 64 | 75 | 85 | 94 | 104 | 120 | 132 | 148 | 4 | 1 | 1 | 3 | 3 | 4 | 3 | 3 | 2 | 1 | 1 | 1 | 2 | 1 | 5 | 1 | 2 | 5 | 4 | 1 | 5 | 4 | 3 | 4 | 2 | 3 | 2 | 4 | 4 | 2 | 1 | 3 | 2 | 1 | 3 | 3 | 2 | 2 | 5 | 1 | 4 | 5 | 2 | 5 | 1 | 2 | 5 | 4 | 5 | 3 | 4 | 4
475 | 16 | 13 | 22 | 35 | 46 | 62 | 74 | 91 | 101 | 114 | 125 | 135 | 149 | 164 | 5 | 2 | 2 | 4 | 2 | 1 | 3 | 3 | 1 | 5 | 5 | 2 | 3 | 3 | 4 | 1 | 5 | 4 | 2 | 5 | 3 | 3 | 3 | 3 | 5 | 4 | 5 | 3 | 2 | 3 | 4 | 1 | 3 | 3 | 5 | 2 | 3 | 2 | 1 | 5 | 4 | 2 | 2 | 2 | 5 | 4 | 1 | 4 | 5 | 5 | 3 | 2
476 | 20 | 14 | 29 | 41 | 54 | 69 | 83 | 89 | 100 | 114 | 126 | 140 | 155 | 168 | 4 | 3 | 3 | 4 | 3 | 3 | 5 | 4 | 3 | 4 | 2 | 3 | 2 | 5 | 1 | 5 | 5 | 4 | 2 | 4 | 2 | 2 | 5 | 5 | 1 | 2 | 1 | 2 | 5 | 3 | 2 | 1 | 3 | 5 | 4 | 2 | 1 | 5 | 3 | 3 | 3 | 4 | 4 | 3 | 5 | 2 | 5 | 3 | 4 | 4 | 1 | 4
477 | 16 | 11 | 20 | 34 | 39 | 52 | 60 | 73 | 86 | 97 | 110 | 120 | 127 | 137 | 5 | 2 | 1 | 3 | 3 | 2 | 1 | 3 | 5 | 5 | 1 | 3 | 1 | 2 | 1 | 1 | 5 | 2 | 2 | 4 | 1 | 2 | 2 | 3 | 5 | 3 | 3 | 2 | 3 | 1 | 4 | 5 | 2 | 3 | 2 | 4 | 5 | 1 | 2 | 5 | 2 | 4 | 2 | 2 | 2 | 1 | 1 | 3 | 3 | 3 | 1 | 3
478 | 17 | 12 | 22 | 36 | 48 | 64 | 73 | 86 | 94 | 103 | 116 | 131 | 147 | 155 | 3 | 4 | 4 | 1 | 2 | 3 | 1 | 4 | 3 | 5 | 3 | 3 | 4 | 4 | 1 | 3 | 5 | 4 | 3 | 4 | 1 | 1 | 2 | 5 | 3 | 2 | 5 | 3 | 2 | 2 | 1 | 3 | 2 | 1 | 1 | 5 | 4 | 4 | 3 | 2 | 5 | 2 | 3 | 5 | 5 | 4 | 2 | 5 | 1 | 4 | 1 | 2
479 | 14 | 12 | 22 | 39 | 48 | 56 | 69 | 82 | 93 | 104 | 118 | 129 | 137 | 151 | 3 | 4 | 1 | 4 | 1 | 1 | 3 | 5 | 5 | 5 | 2 | 5 | 2 | 3 | 1 | 3 | 2 | 2 | 1 | 3 | 4 | 1 | 4 | 4 | 4 | 4 | 4 | 1 | 3 | 2 | 4 | 2 | 2 | 1 | 3 | 5 | 5 | 4 | 3 | 2 | 4 | 1 | 3 | 3 | 4 | 1 | 2 | 1 | 1 | 5 | 5 | 3
480 | 17 | 11 | 26 | 38 | 46 | 57 | 69 | 81 | 91 | 101 | 114 | 129 | 143 | 154 | 5 | 1 | 2 | 3 | 5 | 1 | 5 | 4 | 5 | 3 | 2 | 2 | 4 | 1 | 2 | 1 | 4 | 3 | 3 | 1 | 5 | 3 | 2 | 2 | 5 | 2 | 4 | 1 | 2 | 5 | 1 | 2 | 2 | 1 | 5 | 2 | 5 | 3 | 2 | 3 | 4 | 5 | 4 | 2 | 5 | 4 | 1 | 4 | 3 | 2 | 3 | 3
481 | 19 | 15 | 27 | 37 | 53 | 64 | 77 | 94 | 103 | 111 | 123 | 135 | 142 | 156 | 5 | 2 | 4 | 4 | 1 | 3 | 4 | 4 | 1 | 5 | 2 | 2 | 5 | 4 | 2 | 5 | 5 | 1 | 1 | 4 | 2 | 2 | 5 | 4 | 5 | 3 | 4 | 5 | 2 | 1 | 3 | 3 | 1 | 3 | 3 | 1 | 5 | 2 | 4 | 1 | 4 | 1 | 5 | 2 | 3 | 1 | 1 | 2 | 1 | 4 | 5 | 4
482 | 21 | 16 | 29 | 37 | 47 | 58 | 65 | 75 | 82 | 98 | 105 | 117 | 131 | 145 | 4 | 5 | 5 | 2 | 2 | 3 | 3 | 5 | 1 | 5 | 1 | 1 | 3 | 3 | 1 | 3 | 4 | 1 | 3 | 3 | 1 | 2 | 2 | 2 | 1 | 2 | 3 | 4 | 1 | 2 | 2 | 2 | 2 | 5 | 5 | 4 | 1 | 3 | 1 | 2 | 3 | 1 | 4 | 4 | 5 | 3 | 5 | 1 | 2 | 5 | 4 | 3
483 | 14 | 9 | 20 | 34 | 45 | 60 | 76 | 86 | 96 | 104 | 116 | 127 | 136 | 147 | 1 | 4 | 1 | 3 | 4 | 1 | 1 | 5 | 4 | 4 | 2 | 4 | 4 | 3 | 1 | 3 | 3 | 5 | 2 | 5 | 5 | 1 | 5 | 5 | 4 | 1 | 4 | 1 | 4 | 2 | 2 | 2 | 2 | 1 | 2 | 3 | 4 | 1 | 3 | 4 | 2 | 1 | 5 | 3 | 4 | 1 | 3 | 1 | 1 | 1 | 5 | 4
484 | 23 | 15 | 29 | 41 | 54 | 64 | 73 | 86 | 100 | 107 | 121 | 131 | 147 | 161 | 5 | 4 | 5 | 1 | 5 | 3 | 4 | 2 | 3 | 4 | 4 | 1 | 2 | 4 | 2 | 5 | 5 | 3 | 1 | 1 | 2 | 1 | 5 | 1 | 3 | 5 | 3 | 2 | 4 | 3 | 4 | 3 | 2 | 2 | 1 | 2 | 3 | 2 | 5 | 4 | 1 | 2 | 2 | 5 | 5 | 5 | 3 | 3 | 3 | 5 | 3 | 3
485 | 27 | 18 | 37 | 48 | 55 | 63 | 77 | 90 | 104 | 118 | 132 | 151 | 161 | 175 | 5 | 3 | 5 | 5 | 4 | 5 | 5 | 5 | 3 | 4 | 2 | 2 | 2 | 3 | 1 | 1 | 3 | 2 | 2 | 1 | 5 | 2 | 5 | 2 | 4 | 5 | 2 | 2 | 5 | 3 | 4 | 2 | 4 | 2 | 3 | 5 | 2 | 4 | 5 | 3 | 5 | 4 | 5 | 5 | 2 | 3 | 4 | 1 | 2 | 4 | 3 | 5
486 | 12 | 8 | 21 | 30 | 43 | 60 | 73 | 81 | 89 | 100 | 111 | 127 | 139 | 154 | 3 | 2 | 2 | 1 | 2 | 2 | 4 | 5 | 2 | 5 | 1 | 1 | 1 | 3 | 4 | 5 | 5 | 4 | 5 | 3 | 2 | 2 | 5 | 4 | 2 | 3 | 2 | 1 | 1 | 5 | 1 | 1 | 4 | 3 | 2 | 2 | 3 | 1 | 2 | 5 | 4 | 5 | 2 | 5 | 2 | 3 | 3 | 4 | 5 | 4 | 4 | 2
487 | 19 | 16 | 25 | 32 | 42 | 52 | 66 | 75 | 91 | 105 | 118 | 131 | 142 | 153 | 3 | 5 | 5 | 3 | 2 | 1 | 4 | 2 | 2 | 2 | 2 | 1 | 3 | 1 | 4 | 2 | 3 | 2 | 4 | 1 | 2 | 5 | 5 | 2 | 2 | 4 | 2 | 1 | 4 | 5 | 4 | 3 | 4 | 4 | 4 | 2 | 3 | 5 | 3 | 2 | 3 | 3 | 2 | 5 | 1 | 3 | 5 | 2 | 4 | 4 | 1 | 2
488 | 18 | 15 | 24 | 36 | 46 | 54 | 68 | 82 | 92 | 100 | 115 | 132 | 141 | 154 | 3 | 5 | 5 | 2 | 2 | 1 | 3 | 3 | 2 | 4 | 4 | 2 | 4 | 1 | 1 | 4 | 2 | 4 | 1 | 1 | 3 | 4 | 3 | 4 | 4 | 4 | 2 | 4 | 4 | 1 | 2 | 3 | 1 | 1 | 2 | 4 | 4 | 4 | 3 | 4 | 4 | 5 | 5 | 3 | 3 | 1 | 4 | 1 | 4 | 4 | 3 | 2
489 | 20 | 10 | 28 | 39 | 51 | 58 | 69 | 81 | 88 | 99 | 118 | 133 | 148 | 165 | 2 | 4 | 1 | 3 | 5 | 5 | 4 | 4 | 5 | 1 | 2 | 3 | 3 | 4 | 1 | 4 | 1 | 1 | 4 | 1 | 3 | 2 | 5 | 1 | 5 | 4 | 2 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 4 | 5 | 4 | 5 | 5 | 5 | 3 | 3 | 5 | 4 | 4 | 4 | 5 | 2 | 5 | 4 | 4 | 4
490 | 17 | 13 | 24 | 41 | 48 | 62 | 75 | 91 | 101 | 114 | 124 | 138 | 154 | 166 | 5 | 3 | 3 | 2 | 1 | 3 | 2 | 5 | 5 | 5 | 3 | 4 | 2 | 3 | 1 | 1 | 3 | 5 | 3 | 3 | 1 | 3 | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 1 | 3 | 3 | 4 | 5 | 1 | 1 | 1 | 3 | 5 | 5 | 3 | 3 | 3 | 5 | 5 | 5 | 1 | 1 | 3 | 3 | 5
491 | 16 | 10 | 23 | 32 | 42 | 54 | 68 | 82 | 98 | 107 | 115 | 126 | 133 | 146 | 2 | 2 | 5 | 1 | 4 | 2 | 2 | 5 | 3 | 2 | 3 | 1 | 1 | 2 | 2 | 5 | 2 | 2 | 5 | 3 | 5 | 2 | 5 | 2 | 3 | 5 | 5 | 1 | 5 | 5 | 4 | 2 | 2 | 1 | 4 | 2 | 1 | 3 | 2 | 2 | 2 | 3 | 1 | 5 | 2 | 1 | 1 | 3 | 4 | 1 | 5 | 3
492 | 14 | 9 | 23 | 36 | 46 | 61 | 74 | 80 | 93 | 104 | 119 | 130 | 144 | 157 | 2 | 1 | 4 | 2 | 4 | 1 | 5 | 4 | 1 | 3 | 5 | 4 | 3 | 3 | 3 | 1 | 3 | 5 | 3 | 4 | 3 | 4 | 3 | 3 | 1 | 1 | 2 | 2 | 1 | 5 | 4 | 3 | 4 | 1 | 3 | 3 | 3 | 5 | 2 | 5 | 4 | 1 | 5 | 1 | 3 | 4 | 2 | 5 | 5 | 3 | 2 | 3
493 | 20 | 15 | 25 | 39 | 51 | 58 | 67 | 79 | 91 | 103 | 118 | 127 | 145 | 153 | 5 | 2 | 5 | 3 | 3 | 2 | 1 | 4 | 5 | 5 | 1 | 3 | 5 | 1 | 3 | 3 | 4 | 1 | 1 | 1 | 1 | 3 | 1 | 4 | 3 | 1 | 5 | 3 | 3 | 3 | 5 | 1 | 3 | 4 | 4 | 1 | 5 | 4 | 1 | 5 | 4 | 1 | 2 | 2 | 5 | 4 | 4 | 5 | 1 | 1 | 2 | 4
494 | 20 | 12 | 23 | 35 | 44 | 58 | 72 | 86 | 97 | 112 | 125 | 137 | 146 | 156 | 4 | 3 | 4 | 1 | 5 | 3 | 2 | 1 | 2 | 2 | 5 | 3 | 1 | 5 | 2 | 1 | 2 | 5 | 3 | 4 | 2 | 5 | 4 | 3 | 5 | 4 | 3 | 2 | 2 | 1 | 4 | 4 | 5 | 3 | 2 | 5 | 5 | 3 | 1 | 4 | 3 | 1 | 5 | 3 | 1 | 4 | 2 | 2 | 1 | 2 | 5 | 2
495 | 22 | 14 | 31 | 45 | 59 | 69 | 78 | 85 | 92 | 102 | 119 | 136 | 146 | 159 | 3 | 4 | 2 | 5 | 5 | 3 | 5 | 4 | 4 | 4 | 5 | 1 | 3 | 4 | 2 | 5 | 5 | 2 | 2 | 1 | 5 | 1 | 2 | 1 | 4 | 1 | 1 | 1 | 1 | 3 | 1 | 2 | 3 | 2 | 2 | 3 | 5 | 4 | 4 | 4 | 4 | 5 | 3 | 5 | 1 | 3 | 3 | 3 | 5 | 4 | 3 | 1
496 | 17 | 11 | 26 | 40 | 52 | 69 | 85 | 97 | 111 | 127 | 141 | 150 | 162 | 176 | 4 | 2 | 1 | 4 | 5 | 1 | 4 | 5 | 4 | 2 | 5 | 3 | 2 | 3 | 2 | 5 | 4 | 4 | 5 | 4 | 4 | 5 | 4 | 3 | 5 | 2 | 2 | 3 | 1 | 5 | 3 | 5 | 4 | 4 | 4 | 4 | 2 | 5 | 3 | 4 | 4 | 3 | 1 | 1 | 4 | 3 | 1 | 4 | 4 | 2 | 5 | 3
497 | 21 | 15 | 28 | 40 | 49 | 63 | 73 | 83 | 91 | 100 | 112 | 124 | 136 | 148 | 1 | 4 | 5 | 5 | 3 | 3 | 5 | 2 | 4 | 5 | 2 | 1 | 1 | 1 | 5 | 2 | 3 | 5 | 2 | 4 | 3 | 5 | 1 | 1 | 5 | 2 | 1 | 2 | 2 | 1 | 3 | 2 | 1 | 2 | 3 | 3 | 4 | 1 | 3 | 4 | 2 | 1 | 4 | 5 | 4 | 1 | 3 | 4 | 1 | 3 | 3 | 5
498 | 14 | 8 | 22 | 32 | 42 | 52 | 61 | 74 | 83 | 98 | 107 | 123 | 135 | 149 | 1 | 1 | 5 | 1 | 1 | 5 | 4 | 4 | 1 | 1 | 3 | 5 | 3 | 1 | 3 | 3 | 2 | 5 | 2 | 1 | 2 | 1 | 3 | 3 | 1 | 4 | 4 | 4 | 3 | 2 | 3 | 1 | 4 | 5 | 2 | 4 | 3 | 4 | 1 | 1 | 5 | 4 | 3 | 4 | 3 | 3 | 2 | 4 | 4 | 3 | 3 | 4
499 | 18 | 9 | 23 | 36 | 48 | 61 | 78 | 93 | 105 | 116 | 128 | 143 | 156 | 167 | 2 | 4 | 1 | 2 | 4 | 5 | 4 | 1 | 5 | 3 | 2 | 3 | 2 | 2 | 3 | 5 | 4 | 1 | 3 | 5 | 5 | 3 | 4 | 5 | 3 | 5 | 2 | 5 | 2 | 5 | 1 | 4 | 4 | 2 | 2 | 3 | 1 | 5 | 2 | 4 | 5 | 3 | 4 | 3 | 2 | 5 | 5 | 1 | 1 | 5 | 4 | 1
500 | 25 | 15 | 34 | 50 | 63 | 71 | 86 | 100 | 117 | 123 | 134 | 147 | 162 | 176 | 5 | 3 | 4 | 3 | 5 | 5 | 5 | 4 | 2 | 5 | 4 | 5 | 4 | 2 | 5 | 2 | 1 | 1 | 4 | 2 | 4 | 3 | 3 | 5 | 4 | 2 | 3 | 5 | 5 | 4 | 5 | 3 | 2 | 2 | 1 | 1 | 2 | 1 | 5 | 3 | 2 | 5 | 2 | 4 | 4 | 1 | 5 | 5 | 1 | 5 | 5 | 3
| 6 | Sum4: 4; Sum8: 8; Sum12: 12; Sum16: 16; Sum20: 20; Sum24: 24; Sum28: 28; Sum32: 32; Sum36: 36; Sum40: 40; Sum44: 44; Sum48: 48; Sum52: 52
1% | 10 | Sum4: 5; Sum8: 15; Sum12: 25; Sum16: 35.99; Sum20: 46.99; Sum24: 57; Sum28: 67.99; Sum32: 79.99; Sum36: 89.99; Sum40: 101.98; Sum44: 112.99; Sum48: 124.99; Sum52: 135
2% | 11 | Sum4: 6; Sum8: 16; Sum12: 26.98; Sum16: 37; Sum20: 48; Sum24: 59; Sum28: 70; Sum32: 81; Sum36: 92; Sum40: 103.98; Sum44: 114; Sum48: 126; Sum52: 137
3% | 11 | Sum4: 6.97; Sum8: 16.97; Sum12: 27; Sum16: 38; Sum20: 49; Sum24: 60; Sum28: 71; Sum32: 82; Sum36: 94; Sum40: 104; Sum44: 115.97; Sum48: 127; Sum52: 138
4% | 12 | Sum4: 7; Sum8: 17; Sum12: 27.96; Sum16: 39; Sum20: 50; Sum24: 61; Sum28: 72; Sum32: 82; Sum36: 94; Sum40: 105; Sum44: 117; Sum48: 128; Sum52: 139.96
5% | 12 | Sum4: 7; Sum8: 17; Sum12: 28; Sum16: 39; Sum20: 50; Sum24: 61; Sum28: 72; Sum32: 83; Sum36: 96; Sum40: 106; Sum44: 117; Sum48: 129; Sum52: 140.95
6% | 12 | Sum4: 7; Sum8: 18; Sum12: 28; Sum16: 39.94; Sum20: 51; Sum24: 62; Sum28: 73; Sum32: 84; Sum36: 96; Sum40: 106; Sum44: 117; Sum48: 130; Sum52: 141
7% | 12.93 | Sum4: 7; Sum8: 18; Sum12: 28; Sum16: 40; Sum20: 51; Sum24: 62; Sum28: 73; Sum32: 84.93; Sum36: 96; Sum40: 106; Sum44: 118; Sum48: 130; Sum52: 142
8% | 13 | Sum4: 8; Sum8: 18; Sum12: 29; Sum16: 40; Sum20: 51; Sum24: 62; Sum28: 74; Sum32: 85; Sum36: 97; Sum40: 107; Sum44: 118.92; Sum48: 131; Sum52: 142
9% | 13 | Sum4: 8; Sum8: 19; Sum12: 29; Sum16: 40; Sum20: 52; Sum24: 63; Sum28: 74; Sum32: 85.91; Sum36: 97; Sum40: 108; Sum44: 119; Sum48: 131; Sum52: 143
10% | 13 | Sum4: 8; Sum8: 19; Sum12: 29.9; Sum16: 41; Sum20: 52; Sum24: 63; Sum28: 75; Sum32: 86; Sum36: 97; Sum40: 109; Sum44: 120; Sum48: 132; Sum52: 143.9
11% | 14 | Sum4: 8; Sum8: 19; Sum12: 30; Sum16: 41; Sum20: 52; Sum24: 63; Sum28: 75; Sum32: 86; Sum36: 98; Sum40: 109; Sum44: 121; Sum48: 132; Sum52: 144
12% | 14 | Sum4: 8; Sum8: 19; Sum12: 30; Sum16: 41; Sum20: 53; Sum24: 64; Sum28: 75; Sum32: 87; Sum36: 98; Sum40: 110; Sum44: 121; Sum48: 132.88; Sum52: 144
13% | 14 | Sum4: 8; Sum8: 19; Sum12: 30; Sum16: 42; Sum20: 53; Sum24: 64; Sum28: 76; Sum32: 87; Sum36: 98; Sum40: 110; Sum44: 122; Sum48: 133; Sum52: 145
14% | 14 | Sum4: 8; Sum8: 20; Sum12: 30.86; Sum16: 42; Sum20: 53; Sum24: 64; Sum28: 76; Sum32: 87; Sum36: 99; Sum40: 110; Sum44: 122; Sum48: 133.86; Sum52: 145.86
15% | 14 | Sum4: 9; Sum8: 20; Sum12: 31; Sum16: 42; Sum20: 54; Sum24: 65; Sum28: 76; Sum32: 88; Sum36: 99; Sum40: 111; Sum44: 123; Sum48: 134; Sum52: 146
16% | 14 | Sum4: 9; Sum8: 20; Sum12: 31; Sum16: 43; Sum20: 54; Sum24: 65; Sum28: 77; Sum32: 88; Sum36: 100; Sum40: 111; Sum44: 123; Sum48: 135; Sum52: 146
17% | 15 | Sum4: 9; Sum8: 20; Sum12: 31; Sum16: 43; Sum20: 54; Sum24: 65; Sum28: 77; Sum32: 88; Sum36: 100; Sum40: 112; Sum44: 123; Sum48: 135; Sum52: 147
18% | 15 | Sum4: 9; Sum8: 20; Sum12: 32; Sum16: 43; Sum20: 54; Sum24: 65; Sum28: 77; Sum32: 89; Sum36: 100; Sum40: 112; Sum44: 124; Sum48: 135; Sum52: 147
19% | 15 | Sum4: 9; Sum8: 20; Sum12: 32; Sum16: 43; Sum20: 54; Sum24: 65.81; Sum28: 77; Sum32: 89; Sum36: 101; Sum40: 112; Sum44: 124; Sum48: 136; Sum52: 147.81
20% | 15 | Sum4: 9; Sum8: 21; Sum12: 32; Sum16: 43; Sum20: 54; Sum24: 66; Sum28: 77.8; Sum32: 89.8; Sum36: 101; Sum40: 113; Sum44: 124.8; Sum48: 136; Sum52: 148
21% | 15 | Sum4: 9; Sum8: 21; Sum12: 32; Sum16: 43.79; Sum20: 54; Sum24: 66; Sum28: 78; Sum32: 90; Sum36: 101; Sum40: 113; Sum44: 125; Sum48: 136; Sum52: 148
22% | 15 | Sum4: 10; Sum8: 21; Sum12: 32; Sum16: 44; Sum20: 55; Sum24: 66; Sum28: 78; Sum32: 90; Sum36: 102; Sum40: 113; Sum44: 125; Sum48: 137; Sum52: 148
23% | 15 | Sum4: 10; Sum8: 21; Sum12: 32.77; Sum16: 44; Sum20: 55; Sum24: 66; Sum28: 78; Sum32: 90; Sum36: 102; Sum40: 114; Sum44: 126; Sum48: 137; Sum52: 148.77
24% | 15 | Sum4: 10; Sum8: 21; Sum12: 33; Sum16: 44; Sum20: 55; Sum24: 66; Sum28: 79; Sum32: 91; Sum36: 102; Sum40: 114; Sum44: 126; Sum48: 137; Sum52: 149
25% | 16 | Sum4: 10; Sum8: 21; Sum12: 33; Sum16: 44; Sum20: 55; Sum24: 67; Sum28: 79; Sum32: 91; Sum36: 103; Sum40: 114; Sum44: 126; Sum48: 138; Sum52: 149
26% | 16 | Sum4: 10; Sum8: 22; Sum12: 33; Sum16: 44; Sum20: 56; Sum24: 67; Sum28: 79; Sum32: 91; Sum36: 103; Sum40: 114; Sum44: 126; Sum48: 138; Sum52: 150
27% | 16 | Sum4: 10; Sum8: 22; Sum12: 33; Sum16: 45; Sum20: 56; Sum24: 67.73; Sum28: 79; Sum32: 91; Sum36: 103; Sum40: 114; Sum44: 127; Sum48: 138; Sum52: 150
28% | 16 | Sum4: 10; Sum8: 22; Sum12: 33; Sum16: 45; Sum20: 56; Sum24: 68; Sum28: 80; Sum32: 92; Sum36: 103; Sum40: 115; Sum44: 127; Sum48: 139; Sum52: 150
29% | 16 | Sum4: 10; Sum8: 22; Sum12: 33; Sum16: 45; Sum20: 56; Sum24: 68; Sum28: 80; Sum32: 92; Sum36: 104; Sum40: 115; Sum44: 127; Sum48: 139; Sum52: 151
30% | 16 | Sum4: 10; Sum8: 22; Sum12: 33; Sum16: 45; Sum20: 57; Sum24: 68; Sum28: 80; Sum32: 92; Sum36: 104; Sum40: 115.7; Sum44: 127; Sum48: 139; Sum52: 151
31% | 16 | Sum4: 10; Sum8: 22; Sum12: 33; Sum16: 45; Sum20: 57; Sum24: 68; Sum28: 80; Sum32: 92; Sum36: 104; Sum40: 116; Sum44: 127; Sum48: 140; Sum52: 151
32% | 16 | Sum4: 10; Sum8: 22; Sum12: 34; Sum16: 46; Sum20: 57; Sum24: 69; Sum28: 81; Sum32: 92; Sum36: 104; Sum40: 116; Sum44: 128; Sum48: 140; Sum52: 151
33% | 16 | Sum4: 11; Sum8: 22; Sum12: 34; Sum16: 46; Sum20: 57; Sum24: 69; Sum28: 81; Sum32: 93; Sum36: 104; Sum40: 116; Sum44: 128; Sum48: 140; Sum52: 151
34% | 16 | Sum4: 11; Sum8: 22; Sum12: 34; Sum16: 46; Sum20: 57; Sum24: 69; Sum28: 81; Sum32: 93; Sum36: 104; Sum40: 116; Sum44: 128; Sum48: 140; Sum52: 152
35% | 16 | Sum4: 11; Sum8: 22; Sum12: 34; Sum16: 46; Sum20: 57.65; Sum24: 69; Sum28: 81; Sum32: 93; Sum36: 105; Sum40: 116; Sum44: 128; Sum48: 141; Sum52: 152
36% | 16 | Sum4: 11; Sum8: 22; Sum12: 34; Sum16: 46; Sum20: 58; Sum24: 69; Sum28: 81; Sum32: 93; Sum36: 105; Sum40: 117; Sum44: 128.64; Sum48: 141; Sum52: 152
37% | 17 | 11 | 22 | 34 | 46 | 58 | 70 | 81 | 93 | 105 | 117 | 129 | 141 | 153
38% | 17 | 11 | 23 | 34 | 46 | 58 | 70 | 82 | 94 | 105 | 117 | 129 | 141 | 153
39% | 17 | 11 | 23 | 35 | 47 | 58 | 70 | 82 | 94 | 106 | 117 | 129 | 141 | 153
40% | 17 | 11 | 23 | 35 | 47 | 58 | 70 | 82 | 94 | 106 | 117.6 | 129 | 142 | 154
41% | 17 | 11 | 23 | 35 | 47 | 58 | 71 | 82 | 94 | 106 | 118 | 130 | 142 | 154
42% | 17 | 11 | 23 | 35 | 47 | 59 | 71 | 82 | 94 | 106 | 118 | 130 | 142 | 154
43% | 17 | 11 | 23 | 35 | 47 | 59 | 71 | 82 | 95 | 106 | 118 | 130 | 142 | 154
44% | 17 | 11 | 23 | 35 | 47 | 59 | 71 | 83 | 95 | 106 | 118 | 131 | 142 | 154
45% | 17 | 12 | 23 | 35 | 47 | 59 | 71 | 83 | 95 | 107 | 118 | 131 | 142.55 | 155
46% | 17.54 | 12 | 23 | 36 | 47 | 59 | 72 | 83 | 95 | 107 | 118 | 131 | 143 | 155
47% | 18 | 12 | 24 | 36 | 48 | 60 | 72 | 83 | 95 | 107 | 119 | 131 | 143 | 155
48% | 18 | 12 | 24 | 36 | 48 | 60 | 72 | 83 | 95 | 107 | 119 | 131 | 144 | 155
49% | 18 | 12 | 24 | 36 | 48 | 60 | 72 | 83.51 | 95 | 107 | 119 | 132 | 144 | 155
50% | 18 | 12 | 24 | 36 | 48 | 60 | 72 | 84 | 96 | 108 | 119 | 132 | 144 | 156
51% | 18 | 12 | 24 | 36 | 48 | 60 | 72 | 84 | 96 | 108 | 120 | 132 | 144 | 156
52% | 18 | 12 | 24 | 36 | 48 | 60 | 72 | 84 | 96 | 108 | 120 | 132 | 144 | 156
53% | 18 | 12 | 24 | 36 | 49 | 60 | 73 | 84 | 96 | 108 | 120 | 132 | 144 | 156
54% | 18 | 12 | 24 | 36 | 49 | 60 | 73 | 84 | 96 | 108 | 120 | 133 | 145 | 157
55% | 18 | 12 | 24 | 36 | 49 | 61 | 73 | 85 | 96 | 109 | 121 | 133 | 145 | 157
56% | 18 | 12 | 24 | 37 | 49 | 61 | 73 | 85 | 97 | 109 | 121 | 133 | 145 | 157
57% | 19 | 12 | 25 | 37 | 49 | 61 | 73 | 85 | 97 | 109 | 121 | 133 | 145 | 157
58% | 19 | 13 | 25 | 37 | 49 | 61 | 73 | 85 | 97 | 109 | 122 | 133.42 | 146 | 158
59% | 19 | 13 | 25 | 37 | 49 | 62 | 73 | 86 | 97 | 109 | 122 | 134 | 146 | 158
60% | 19 | 13 | 25 | 37 | 49 | 62 | 73.4 | 86 | 97 | 110 | 122.4 | 134 | 146 | 158
61% | 19 | 13 | 25 | 37 | 49.39 | 62 | 74 | 86 | 97 | 110 | 123 | 134 | 146 | 158.39
62% | 19 | 13 | 25 | 37 | 50 | 62 | 74 | 86 | 98 | 110 | 123 | 135 | 146.38 | 159
63% | 19 | 13 | 25 | 37 | 50 | 62 | 74 | 86 | 98 | 110 | 123 | 135 | 147 | 159
64% | 19 | 13 | 25 | 38 | 50 | 62 | 75 | 86 | 98 | 111 | 124 | 135 | 147 | 159
65% | 19 | 13 | 25 | 38 | 50 | 62 | 75 | 86 | 99 | 111 | 124 | 135 | 148 | 159.35
66% | 19 | 13 | 25 | 38 | 50 | 63 | 75 | 87 | 99 | 111 | 124 | 136 | 148 | 160
67% | 19 | 13 | 26 | 38 | 50 | 63 | 75 | 87 | 99 | 112 | 124 | 136 | 148 | 160
68% | 20 | 13 | 26 | 38 | 51 | 63 | 75 | 87 | 99 | 112 | 124 | 136 | 148 | 160.32
69% | 20 | 13 | 26 | 38 | 51 | 63 | 75 | 88 | 99 | 112 | 125 | 137 | 148 | 161
70% | 20 | 13 | 26 | 38.3 | 51 | 63 | 76 | 88 | 100 | 112 | 125 | 137 | 149 | 161
71% | 20 | 14 | 26 | 39 | 51 | 63 | 76 | 88 | 100 | 112 | 125 | 137 | 149 | 161
72% | 20 | 14 | 26 | 39 | 51 | 64 | 76 | 88.28 | 100 | 112.28 | 125 | 138 | 149 | 162
73% | 20 | 14 | 26.27 | 39 | 51 | 64 | 76 | 89 | 100 | 113 | 125 | 138 | 149 | 162
74% | 20 | 14 | 27 | 39 | 51 | 64 | 76 | 89 | 101 | 113 | 126 | 138 | 150 | 163
75% | 20 | 14 | 27 | 39 | 52 | 64 | 77 | 89 | 101 | 113 | 126 | 138 | 150 | 163
76% | 20 | 14 | 27 | 39 | 52 | 64 | 77 | 89 | 101 | 114 | 126 | 139 | 150.24 | 163
77% | 20 | 14 | 27 | 39 | 52 | 64 | 77 | 89 | 101 | 114 | 127 | 139 | 151 | 164
78% | 21 | 14 | 27 | 40 | 52 | 65 | 77 | 90 | 102 | 114 | 127 | 139 | 152 | 164
79% | 21 | 14 | 27 | 40 | 52 | 65 | 77 | 90 | 102 | 114 | 127 | 139 | 152 | 164.21
80% | 21 | 14 | 27 | 40 | 52 | 65 | 78 | 90 | 102 | 115 | 127.2 | 139 | 152 | 165
81% | 21 | 14 | 28 | 40 | 52.19 | 65 | 78 | 90 | 103 | 115 | 128 | 140 | 152 | 165
82% | 21 | 14 | 28 | 40.18 | 53 | 66 | 78 | 90 | 103 | 115 | 128 | 140 | 153 | 166
83% | 21 | 15 | 28 | 41 | 53 | 66 | 79 | 91 | 103 | 115.17 | 128 | 140 | 153 | 166
84% | 21 | 15 | 28 | 41 | 53 | 66 | 79 | 91 | 104 | 116 | 129 | 141 | 154 | 167
85% | 21.15 | 15 | 28.15 | 41 | 53 | 66 | 79 | 91 | 104 | 116 | 129 | 141 | 155 | 167
86% | 22 | 15 | 29 | 41 | 54 | 67 | 80 | 92 | 104 | 116.14 | 129 | 142 | 155 | 168
87% | 22 | 15 | 29 | 41 | 54 | 67 | 80 | 92 | 105 | 117 | 130 | 143 | 155 | 168
88% | 22 | 15 | 29 | 41 | 54 | 67 | 80 | 92.12 | 105 | 117 | 131 | 143 | 156 | 169
89% | 22 | 15 | 29 | 42 | 54 | 67 | 80 | 93 | 105 | 117.11 | 131 | 143 | 156 | 169
90% | 22 | 15 | 29 | 42 | 54.1 | 67.1 | 81 | 94 | 106 | 118 | 132 | 144 | 157 | 170
91% | 23 | 16 | 29 | 42 | 55 | 68 | 81 | 94 | 106.09 | 118 | 132 | 145 | 157.09 | 170
92% | 23 | 16 | 30 | 43 | 55 | 68 | 81 | 95 | 107 | 119 | 133 | 145 | 158.08 | 171
93% | 23 | 16 | 30 | 43 | 55 | 69 | 82 | 95.07 | 108 | 119.07 | 134 | 146 | 159 | 172
94% | 23 | 16 | 30 | 43 | 56 | 69 | 82 | 96 | 109 | 120.06 | 135 | 147 | 160 | 172
95% | 23 | 16 | 31 | 44 | 56 | 69 | 83 | 96 | 109 | 121 | 135 | 148.05 | 160 | 173
96% | 23 | 17 | 31 | 45 | 57 | 70 | 83 | 97 | 110 | 122 | 136 | 149 | 161 | 175
97% | 24 | 17 | 31 | 45 | 58 | 70 | 83.03 | 97 | 111 | 123.03 | 136 | 150 | 162 | 176
98% | 24 | 17 | 32 | 46 | 58 | 71 | 84.02 | 98.02 | 111 | 125.02 | 137 | 151 | 164.02 | 177
99% | 25 | 18.01 | 33 | 47 | 61 | 73.01 | 86 | 100 | 114 | 127 | 141 | 152 | 165 | 179
100% | 28 | 20 | 37 | 50 | 63 | 76 | 89 | 104 | 119 | 131 | 145 | 156 | 170 | 184