## Instructions
Single Feature Forecaster
Always get the latest version of this spreadsheet here.
Version history:
| 1 | 2015-04-07 | Initial beta release for feedback.
| 1.01 | 2015-05-22 | Fixed validation usability errors.
| 1.1 | 2015-05-26 | Added risks and charts.
| 1.2 | 2015-06-01 | Updated instructions and charts.
| 1.3 | 2016-02-12 | Added split rate inputs.
| 1.4 | 2016-06-01 | Added actual plot.
| 1.5 | 2016-06-02 | Added story count forecast by period.
| 1.6 | 2017-06-09 | Added risk impact scores and increased risks to 10 entries
What is this: This spreadsheet helps to probabilistically forecast how long it will take to complete features and stories based on range estimates.
How does it work? Given your estimates, this spreadsheet hypothetically completes all work 500 times. It calculates likelihood result as the number of simulated trials that finished on or before a given date.
Why is this better than burndowns and traditional Agile forecasting? Most forecasting techniques give a single date result and hide the likelihood of that date. Most often the date given as the result is 50% because work is divided by an average (or median). Thats the odds of a toin-coss. This method allows the reader to choose the amount of schedule risk they wish to sign-up for. 85% is a common middle ground used in the industry.
Is it reliable? It has no mathematical errors (that we know of!), and all we guarentee is its better than intuition alone and better than simple regression models. But, help us improve it by letting us know when it misses the actual results you are seeing.
How to: Fill in the orange boxes in the Forecast worksheet and read off the dates in the results table adjacent to the likelihood/certainty you think is appropriate. 85% is a common industry level of certainty used.
What is throughput? Where do I get that data? Throughput is the number of DONE stories completed by a team per week or per sprint (you choose in this spreadsheet, default is per week). We will be providing a viz that gathers this data for your team. Stay tuned.
What is this: This spreadsheet helps to probabilistically forecast how long it will take to complete features based on story count range estimates and either estimated team throughput or historical team throughput samples.
How does it work? Given your estimates, this spreadsheet hypothetically completes all work 500 times. It calculates likelihood result as the number of simulated trials that finished on or before a given date. Given your desired scenario order, features are completed in order and the dates computed based on specified likelihood.
Why is this better than burndowns and traditional Agile forecasting? Most forecasting techniques give a single date result and hide the likelihood of that date. Most often the date given as the result is 50% because work is divided by an average (or median). Thats the odds of a toin-coss. This method allows the reader to choose the amount of schedule risk they wish to sign-up for. 85% is a common middle ground used in the industry.
Is it reliable? It has no mathematical errors (that we know of!), and all we guarantee is its better than intuition alone and better than simple regression models. But, help us improve it by letting us know when it misses the actual results you are seeing.
How to: Fill in the orange boxes in the Forecast worksheet and read off the dates in the results table adjacent to the likelihood/certainty you think is appropriate. 85% is a common industry level of certainty used - a good balance of better than average but not susceptible to extreme outliers.
What is throughput? Where do I get that data? Throughput is the number of DONE stories completed by a team per week or per sprint (you choose in this spreadsheet, default is per week). Also see our Throughput and Cycle Time Calculator spreadsheet for convertinf story/item data to throughput values. Also see our tutorials on how to use Excel to calculate throughput rates.
Ideas, errors, requests? Email: troy.magennis@focusedobjective.com
Work licensed under a Creative Commons Attribution-NonCommercial-ShareAlike 4.0 International License.
Get more tools like this from: http://bit.ly/SimResources
About us: Focused Objective LLC offers tools, training and expert advice on metrics, risk and forecasting. We have more advanced tools to model Agile teams and projects that help analyze staffing options and risk, and a proven track record of positive results. We are always happy to discuss next steps and training opportunities should this tool prove useful. See our website: http://www.focusedobjective.com or email me at troy.magennis@focusedobjective.com.

## Forecast
Forecast Completion Date | [7 empty] | Results
Duration in
1. Start Date |  |  | 2017-06-09 |  |  |  |  | Likelihood | 1 week's | Date
[8 empty] | 100% | 15 | 2017-09-22
2. How many stories are remaining to be completed? | [7 empty] | 95% | 12 | 2017-09-01
(enter the range estimate of stories. Tip: start wide and narrow as certainty increases) | [7 empty] | 90% | 11 | 2017-08-25
| Low guess |  | 20 |  | Highest guess |  | 30 | 85% | 11 | 2017-08-25
[8 empty] | 80% | 10 | 2017-08-18
3. Stories are often split before and whilst being worked on. Estimate the split rate low and high bounds. | [7 empty] | 75% | 10 | 2017-08-18
(often the throughput in the backlog is pre-split, but captured throughput post-split. Adjust for this here) | [7 empty] | 70% | 10 | 2017-08-18
| Low guess |  | 1 |  | Highest guess |  | 1 | 65% | 9 | 2017-08-11
[8 empty] | 60% | 9 | 2017-08-11
4. Throughput. How many completed stories per week or sprint do you estimate low and high bounds? | [7 empty] | 55% | 9 | 2017-08-11
[8 empty] | 50% | 9 | 2017-08-11
Throughput/velocity data or estimate is for |  |  |  | 1 week | 7 | days |  | 45% | 8 | 2017-08-04
(choose a time interval that throughput of velocity is measured in weeks from the list in the orange cell above) | [7 empty] | 40% | 8 | 2017-08-04
Use historical throughput data OR enter a low and high estimate below. Use: | [6 empty] | Estimate | 35% | 8 | 2017-08-04
[8 empty] | 30% | 8 | 2017-08-04
[8 empty] | 25% | 7 | 2017-07-28
| Low guess |  | 1 |  | Highest guess |  | 5 | 20% | 7 | 2017-07-28
[8 empty] | 15% | 7 | 2017-07-28
[8 empty] | 10% | 7 | 2017-07-28
[8 empty] | 5% | 6 | 2017-07-21
[8 empty] | 0% | 5 | 2017-07-14
Forecast Story Count Completion by Time Period
5. How long? |  | 6 | 1 weeks |  | Result: Total Pre-split Stories in 6 1 weeks
(To forecast story counts, enter the how long. |  |  |  |  | (Pre-split means, splitting IS accounted for)
To change unit, change input 4. above.) |  |  |  |  | 95% | 13
[5 empty] | 85% | 15 | <--- Tip: This is your forecasted # storiess for this period at 85% confidence
[5 empty] | 5% | 24
Almost certain
Somewhat certain
Less than coin-toss odds. But if you are game?
Can I use velocity rather than throughput?
Yes. If you do have estimates in story points, then you can sume all of the estimates and use that for input 2 and estimate or use historical team velocity for input 4. The benefit of using throughput (count of completed stories per week/sprint) is that the individual stories don't require estimation in story points.
Enter data in Orange cells
Please Remember: This forecast is only as good as the estimates you enter into it. Always look for multiple ways to forecast your project and compare the outcomes, especially if making a financially critical decision. In the end - any decision to proceed with a project is YOURS.
How do I use this story count forecast?
This forecast aims to show how many stories might be completed given the team data or estimates entered above. Enter all data for inputs 3. and 4. above. This forecast simulates 500 times to determine what number of stories will be completed for the period you entered for input 5. It also creates a chart view of this forecast in the charts tab. This forecast ignores risk data, and un-necessary inputs 1 and 2 from above.
Note on I16: Troy Magennis: This is the measure of how two random groups of your sample data would align when forecasting. Anything below 25% is good, but lower is better. It grows if there is too little data, and ALSO if the process changes over time and you use too much data.

## Risks
Likelihood | Impact Low | Impact High | Description | Combined Impact (higher is worse) | Impact Rank (fix lowest first)
Likelihood | Impact Low | Impact High | Description
30% | 10 | 15 | Server performance issues
15% | 5 | 10 | Layout issues when text localized
20% | 5 | 15 | Layout in Safari issues
Why would I use risks?
Risks allow you to put a probability on work being expanded because of something more than plan. For eample, there might be a chance that more work is needed to improve performance characteristics. If you think there is a 20% chance, put 20 in the likelihood column. Have the team estimate the low and high story count to rectify and add these to the low and high impact columns.
Risk impact analysis
It can be hard to determine what risks are most impactful when they have different likelihoods and impacts. The risks are ranked here from most impactful (Rank = 1) to least impactful.
This is a simple ranking. It helps quickly see what is the most important to decrease likelihood or impact.

## Charts
[14 empty] | Week | Frequency
[14 empty] | 2017-07-14 | 6
[14 empty] | 2017-07-21 | 41
[14 empty] | 2017-07-28 | 89
[14 empty] | 2017-08-04 | 99
[14 empty] | 2017-08-11 | 101
[14 empty] | 2017-08-18 | 89
[14 empty] | 2017-08-25 | 42
[14 empty] | 2017-09-01 | 20
[14 empty] | 2017-09-08 | 8
[14 empty] | 2017-09-15 | 5
[14 empty] | 2017-09-22 | 1
0
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
Story count results in table form. For the probabilities entered, how many stories for each period?
| 4 1 weeks | 8 1 weeks | 12 1 weeks | 16 1 weeks | 20 1 weeks | 24 1 weeks | 28 1 weeks | 32 1 weeks | 36 1 weeks | 40 1 weeks | 44 1 weeks | 48 1 weeks | 52 1 weeks
95% | 7 | 18 | 28 | 38 | 49 | 60 | 71.95 | 82 | 93 | 105 | 116 | 127 | 139
85% | 9 | 20 | 31 | 42 | 54 | 64 | 76 | 87 | 99 | 110 | 121 | 132 | 144
5% | 17 | 31 | 44 | 58 | 70.05 | 83 | 97 | 109 | 124 | 135 | 148 | 161 | 174
What is this chart?
This chart shows how many simulated trials completed on or before the x-axis date. The higher the bar, the more likely that outcome.
What is this chart?
This chart shows the simulated burn-down trends. It shows the first 50 trials and visually shows the general hotspots and outlier dates. Enter actual stories remaining in the Reamining Stories Actual worksheet to see progress.
What is this chart?
This chart shows the number of completed (pre-split) stories for a given period. Select the time period on the forecast worksheet. The forecast is shown at three confidence intervals specified on the forecast worksheet.

## Throughput Samples
Enter Samples Below | Group | Unique Rank
3 | 1 | 3
5 | 1 | 5
2 | 2 | 2
1 | 1 | 1
5 | 2 | 6
3 | 2 | 4
Stability Between Two Random Groups of the Samples
|  |  | Group | All | 1 | 2 | Diff
|  |  | count | 6 | 3 | 3 | 0
|  |  | min | 1 | 1 | 2
|  |  | max | 5 | 5 | 5
|  |  | avg | 3.1667 | 3 | 3.3333 | -0.33333
|  |  | median | 3 | 3 | 3 | 0
|  |  | avg error |  |  |  | 0.33333 | I also tried average of the mean and median error….but think average will do.
|  |  | error/range |  |  |  | 8.333% | Aim to keep this below 25%. By adding more sample data. You will see where to stop.
Transportable data formats
|  |  | Total Count |  | 6 |  |  |  |  | CSV | 3,5,2,1,5,3
|  |  | Data |  | 3 | 3 | 3 | 5 | 1 | SIP 2.0 | <sip name="dist" type="CSV" ver="1.0" count="6" average="3.16666666666667" median="3">3,5,2,1,5,3</sip>
|  |  | Estimate |  | 1 | 1 | 4 | 2 | 3 | Distribution | <distribution name="dist" shape="fromSamples">3,5,2,1,5,3</distribution>
|  |  | Samples Or Data |  | 3 | 3 | 2 | 3 | 5
Instructions.
If you have team historic throughput samples, you can use them when forecasting forward. If not, estimate the range in the forecast sheet. When actual data becomes available, add it here and your forecast will become more indicative.
Add seven (7) minimum, and twenty five (25) maximum recent throughput samples for your team. These samples will be used as throughput values picked at random. By using your teams data, the forecast will follow the patterns your teams throughput historically follows.
Remember to set the unit of throughput measure.
No blank rows within sample range, leave rows after the last sample blank.
Data beyond 24 weeks is most likely out of date. When adding, add most recent samples to the top and remove older samples from the bottom.
These are for testing the formulas that return random ssamples from data or between the estimates. They are included here for education and reference.
These formats are to help share throughput samples with others or teams should the need arise.
CSV = simple comma separated value list
SIP 2.0 = ProbabilityManagement.org's SIP standard for sharing data
Distribution = FocusedObjective.com's distribution format for sharing and creating random data from samples in their simulation software
What is throughput? Where do I get that data? Throughput is the number of DONE stories completed by a team per week or per sprint (you choose in this spreadsheet, default is per week). Also see our Throughput and Cycle Time Calculator spreadsheet for convertinf story/item data to throughput values. Also see our tutorials on how to use Excel to calculate throughput rates.
How many amples?
You could make this spreadsheet use more historical data, but its not statistically necessary. My advice: use the most recent 15 samples if you have them to avoid using "old" data that was cptured when the team was performing differently than it is now. You should use the most recent data where the error percentage is less than 10%

## Remaining Stories Actuals
Date (week ending) | Number of Incompleted (but in scope) stories | Notes
2017-06-09 | 27
2017-06-16 | 25
2017-06-23 | 20
2017-06-30 | 19
2017-07-07
2017-07-14
2017-07-21
2017-07-28
2017-08-04
2017-08-11
2017-08-18
2017-08-25
2017-09-01
2017-09-08
2017-09-15
2017-09-22
2017-09-29
2017-10-06
2017-10-13
2017-10-20
2017-10-27
2017-11-03
2017-11-10
2017-11-17
2017-11-24
2017-12-01
2017-12-08
2017-12-15
2017-12-22
2017-12-29
2018-01-05
2018-01-12
2018-01-19
2018-01-26
2018-02-02
2018-02-09
2018-02-16
2018-02-23
2018-03-02
2018-03-09
2018-03-16
2018-03-23
2018-03-30
2018-04-06
2018-04-13
2018-04-20
2018-04-27
2018-05-04
2018-05-11
2018-05-18
2018-05-25
Instructions.
Enter the actual number of IN-COMPLETE items in the backlog in column B for the dates shown in column A. This line will be charted on the burndown chart.

## Settings
Duration name | days
1 week | 7
2 weeks | 14
3 weeks | 21
4 weeks | 28
This table converts throughput duration name to number of days. Add more or edit these here. The days is used to increment forecasting periods. Resolution of forecast will also be in increments of this value.

## Monte Carlo (hidden)
Trial | Weeks to Zero | End of Zero Week | TotalStories | End period 1 | End period 2 | End period 3 | End period 4 | End period 5 | End period 6 | End period 7 | End period 8 | End period 9 | End period 10 | End period 11 | End period 12 | End period 13 | End period 14 | End period 15 | End period 16 | End period 17 | End period 18 | End period 19 | End period 20 | End period 21 | End period 22 | End period 23 | End period 24 | End period 25 | End period 26 | End period 27 | End period 28 | End period 29 | End period 30 | End period 31 | End period 32 | End period 33 | End period 34 | End period 35 | End period 36 | End period 37 | End period 38 | End period 39 | End period 40 | End period 41 | End period 42 | End period 43 | End period 44 | End period 45 | End period 46 | End period 47 | End period 48 | End period 49 | End period 50 | End period 51 | End period 52
 | time axis 2017-06-09 to 2018-06-08
1 | 8 | 2017-08-04 | 26 | 22 | 17 | 16 | 12 | 7 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 11 | 2017-08-25 | 27 | 25 | 20 | 18 | 16 | 13 | 11 | 9 | 8 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 7 | 2017-07-28 | 22 | 17 | 14 | 12 | 9 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 9 | 2017-08-11 | 21 | 20 | 17 | 16 | 12 | 8 | 5 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 7 | 2017-07-28 | 24 | 21 | 17 | 12 | 9 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 7 | 2017-07-28 | 24 | 21 | 17 | 13 | 9 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 10 | 2017-08-18 | 26 | 21 | 19 | 18 | 16 | 11 | 10 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 12 | 2017-09-01 | 30 | 27 | 24 | 23 | 20 | 16 | 12 | 10 | 9 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 8 | 2017-08-04 | 20 | 17 | 14 | 12 | 11 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | 8 | 2017-08-04 | 23 | 22 | 21 | 16 | 13 | 12 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | 11 | 2017-08-25 | 30 | 29 | 27 | 22 | 18 | 15 | 12 | 9 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 10 | 2017-08-18 | 24 | 23 | 21 | 19 | 18 | 13 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | 10 | 2017-08-18 | 26 | 21 | 20 | 17 | 13 | 11 | 9 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 12 | 2017-09-01 | 28 | 25 | 23 | 21 | 19 | 15 | 13 | 10 | 6 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | 8 | 2017-08-04 | 25 | 23 | 20 | 19 | 17 | 15 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | 8 | 2017-08-04 | 28 | 27 | 23 | 19 | 14 | 12 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 11 | 2017-08-25 | 30 | 29 | 28 | 26 | 22 | 21 | 17 | 15 | 10 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 6 | 2017-07-21 | 22 | 17 | 16 | 11 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | 7 | 2017-07-28 | 27 | 23 | 18 | 14 | 9 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | 12 | 2017-09-01 | 29 | 25 | 23 | 22 | 17 | 16 | 14 | 13 | 11 | 7 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 6 | 2017-07-21 | 21 | 20 | 16 | 11 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | 10 | 2017-08-18 | 23 | 20 | 19 | 15 | 14 | 12 | 9 | 8 | 7 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | 9 | 2017-08-11 | 27 | 25 | 21 | 18 | 13 | 11 | 8 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 7 | 2017-07-28 | 20 | 17 | 13 | 11 | 10 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | 11 | 2017-08-25 | 30 | 28 | 25 | 21 | 18 | 17 | 15 | 14 | 10 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | 8 | 2017-08-04 | 28 | 23 | 18 | 16 | 13 | 8 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | 9 | 2017-08-11 | 21 | 19 | 16 | 12 | 11 | 8 | 7 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | 8 | 2017-08-04 | 22 | 21 | 17 | 14 | 12 | 7 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | 12 | 2017-09-01 | 30 | 29 | 28 | 26 | 22 | 18 | 16 | 11 | 10 | 8 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | 10 | 2017-08-18 | 27 | 23 | 21 | 17 | 13 | 11 | 10 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | 9 | 2017-08-11 | 23 | 20 | 18 | 16 | 14 | 10 | 7 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | 9 | 2017-08-11 | 29 | 25 | 21 | 17 | 14 | 11 | 9 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | 7 | 2017-07-28 | 22 | 18 | 15 | 11 | 6 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | 9 | 2017-08-11 | 24 | 22 | 19 | 15 | 12 | 10 | 7 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | 8 | 2017-08-04 | 20 | 19 | 15 | 11 | 10 | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | 10 | 2017-08-18 | 25 | 22 | 20 | 19 | 16 | 15 | 12 | 7 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | 11 | 2017-08-25 | 27 | 26 | 25 | 20 | 17 | 13 | 10 | 7 | 5 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | 6 | 2017-07-21 | 21 | 17 | 14 | 9 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | 11 | 2017-08-25 | 28 | 27 | 24 | 23 | 19 | 15 | 10 | 9 | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | 8 | 2017-08-04 | 22 | 20 | 19 | 17 | 15 | 11 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | 7 | 2017-07-28 | 22 | 20 | 15 | 11 | 10 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | 9 | 2017-08-11 | 29 | 28 | 26 | 24 | 20 | 15 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | 8 | 2017-08-04 | 27 | 23 | 19 | 18 | 13 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | 8 | 2017-08-04 | 23 | 20 | 18 | 16 | 12 | 7 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | 10 | 2017-08-18 | 29 | 27 | 24 | 19 | 16 | 14 | 13 | 8 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | 11 | 2017-08-25 | 25 | 24 | 21 | 20 | 19 | 15 | 11 | 9 | 8 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | 8 | 2017-08-04 | 24 | 22 | 21 | 19 | 15 | 12 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 7 | 2017-07-28 | 24 | 21 | 16 | 15 | 10 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | 7 | 2017-07-28 | 26 | 24 | 19 | 14 | 13 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | 8 | 2017-08-04 | 20 | 15 | 13 | 12 | 8 | 7 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | 8 | 2017-08-04 | 27 | 22 | 17 | 14 | 9 | 6 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 | 6 | 2017-07-21 | 21 | 20 | 16 | 12 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | 11 | 2017-08-25 | 23 | 21 | 19 | 17 | 14 | 13 | 10 | 9 | 5 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | 7 | 2017-07-28 | 21 | 19 | 14 | 10 | 9 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 | 6 | 2017-07-21 | 21 | 17 | 16 | 11 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56 | 8 | 2017-08-04 | 23 | 18 | 17 | 16 | 15 | 11 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57 | 10 | 2017-08-18 | 25 | 21 | 19 | 17 | 15 | 14 | 11 | 8 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58 | 6 | 2017-07-21 | 26 | 21 | 18 | 13 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
59 | 6 | 2017-07-21 | 20 | 15 | 12 | 7 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 | 6 | 2017-07-21 | 23 | 19 | 15 | 13 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
61 | 9 | 2017-08-11 | 23 | 18 | 16 | 14 | 11 | 8 | 6 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
62 | 8 | 2017-08-04 | 30 | 29 | 24 | 19 | 15 | 10 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | 8 | 2017-08-04 | 28 | 24 | 19 | 14 | 12 | 8 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
64 | 8 | 2017-08-04 | 20 | 17 | 15 | 12 | 8 | 7 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
65 | 10 | 2017-08-18 | 27 | 26 | 25 | 22 | 19 | 15 | 12 | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
66 | 7 | 2017-07-28 | 25 | 22 | 17 | 12 | 7 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
67 | 10 | 2017-08-18 | 25 | 21 | 19 | 14 | 11 | 9 | 8 | 7 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
68 | 10 | 2017-08-18 | 26 | 24 | 21 | 16 | 12 | 8 | 7 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
69 | 10 | 2017-08-18 | 30 | 25 | 22 | 17 | 16 | 12 | 8 | 7 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 | 7 | 2017-07-28 | 21 | 20 | 16 | 11 | 7 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
71 | 10 | 2017-08-18 | 24 | 20 | 17 | 14 | 13 | 8 | 6 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 11 | 2017-08-25 | 26 | 25 | 24 | 19 | 15 | 13 | 8 | 6 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
73 | 8 | 2017-08-04 | 24 | 19 | 17 | 15 | 12 | 9 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
74 | 7 | 2017-07-28 | 25 | 20 | 16 | 13 | 9 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
75 | 9 | 2017-08-11 | 23 | 20 | 18 | 16 | 12 | 8 | 7 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
76 | 6 | 2017-07-21 | 22 | 19 | 14 | 10 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
77 | 8 | 2017-08-04 | 21 | 20 | 17 | 12 | 11 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
78 | 10 | 2017-08-18 | 24 | 22 | 21 | 18 | 14 | 10 | 9 | 6 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
79 | 8 | 2017-08-04 | 25 | 20 | 19 | 14 | 9 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | 9 | 2017-08-11 | 22 | 17 | 16 | 13 | 12 | 11 | 6 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 | 9 | 2017-08-11 | 22 | 17 | 14 | 12 | 11 | 8 | 6 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
82 | 10 | 2017-08-18 | 28 | 26 | 23 | 19 | 18 | 17 | 12 | 8 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | 9 | 2017-08-11 | 29 | 26 | 22 | 21 | 17 | 16 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | 8 | 2017-08-04 | 23 | 21 | 19 | 14 | 11 | 10 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
85 | 10 | 2017-08-18 | 30 | 25 | 24 | 21 | 17 | 12 | 8 | 5 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 | 7 | 2017-07-28 | 22 | 20 | 16 | 13 | 10 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | 6 | 2017-07-21 | 20 | 16 | 13 | 9 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 | 10 | 2017-08-18 | 29 | 28 | 26 | 23 | 19 | 16 | 11 | 8 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
89 | 6 | 2017-07-21 | 22 | 18 | 14 | 9 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | 7 | 2017-07-28 | 20 | 18 | 16 | 15 | 10 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 | 12 | 2017-09-01 | 30 | 26 | 25 | 24 | 22 | 19 | 17 | 15 | 13 | 11 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 | 9 | 2017-08-11 | 23 | 19 | 18 | 16 | 14 | 12 | 10 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 | 7 | 2017-07-28 | 22 | 21 | 18 | 14 | 9 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 | 15 | 2017-09-22 | 30 | 29 | 28 | 26 | 25 | 23 | 22 | 20 | 15 | 14 | 13 | 12 | 9 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 | 10 | 2017-08-18 | 27 | 23 | 20 | 16 | 14 | 13 | 9 | 7 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 | 7 | 2017-07-28 | 23 | 21 | 16 | 13 | 10 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
97 | 10 | 2017-08-18 | 30 | 26 | 24 | 19 | 18 | 17 | 13 | 10 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 | 11 | 2017-08-25 | 30 | 26 | 25 | 24 | 23 | 19 | 17 | 13 | 11 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | 7 | 2017-07-28 | 22 | 18 | 16 | 13 | 11 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100 | 7 | 2017-07-28 | 25 | 20 | 15 | 12 | 8 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
101 | 10 | 2017-08-18 | 30 | 27 | 26 | 25 | 20 | 19 | 14 | 10 | 7 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
102 | 13 | 2017-09-08 | 26 | 25 | 24 | 22 | 18 | 15 | 14 | 13 | 10 | 7 | 5 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
103 | 10 | 2017-08-18 | 26 | 23 | 21 | 16 | 14 | 12 | 9 | 7 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
104 | 8 | 2017-08-04 | 21 | 19 | 18 | 15 | 13 | 8 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
105 | 14 | 2017-09-15 | 30 | 26 | 25 | 22 | 20 | 19 | 15 | 12 | 10 | 9 | 8 | 5 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
106 | 9 | 2017-08-11 | 26 | 22 | 21 | 20 | 18 | 17 | 14 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
107 | 10 | 2017-08-18 | 29 | 28 | 27 | 23 | 21 | 17 | 16 | 11 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
108 | 8 | 2017-08-04 | 23 | 18 | 15 | 10 | 9 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
109 | 10 | 2017-08-18 | 27 | 22 | 20 | 18 | 16 | 15 | 14 | 9 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
110 | 10 | 2017-08-18 | 29 | 27 | 26 | 21 | 18 | 16 | 14 | 10 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
111 | 9 | 2017-08-11 | 25 | 23 | 22 | 18 | 15 | 10 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
112 | 6 | 2017-07-21 | 22 | 17 | 12 | 11 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
113 | 12 | 2017-09-01 | 30 | 29 | 26 | 22 | 17 | 14 | 12 | 11 | 9 | 5 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
114 | 6 | 2017-07-21 | 20 | 15 | 14 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
115 | 11 | 2017-08-25 | 28 | 25 | 22 | 18 | 17 | 14 | 12 | 11 | 9 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
116 | 9 | 2017-08-11 | 25 | 22 | 21 | 17 | 13 | 9 | 8 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
117 | 9 | 2017-08-11 | 30 | 26 | 22 | 20 | 15 | 13 | 9 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
118 | 6 | 2017-07-21 | 26 | 21 | 16 | 11 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
119 | 8 | 2017-08-04 | 29 | 25 | 20 | 16 | 11 | 8 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
120 | 7 | 2017-07-28 | 22 | 20 | 15 | 11 | 10 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
121 | 8 | 2017-08-04 | 21 | 20 | 15 | 14 | 12 | 7 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
122 | 6 | 2017-07-21 | 21 | 18 | 16 | 14 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
123 | 8 | 2017-08-04 | 24 | 23 | 20 | 17 | 14 | 9 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
124 | 8 | 2017-08-04 | 25 | 22 | 18 | 15 | 12 | 7 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
125 | 10 | 2017-08-18 | 28 | 25 | 20 | 16 | 12 | 11 | 10 | 7 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
126 | 10 | 2017-08-18 | 30 | 28 | 26 | 22 | 19 | 14 | 13 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
127 | 11 | 2017-08-25 | 30 | 29 | 24 | 23 | 22 | 17 | 14 | 10 | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
128 | 6 | 2017-07-21 | 20 | 16 | 11 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
129 | 6 | 2017-07-21 | 21 | 17 | 13 | 10 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
130 | 9 | 2017-08-11 | 25 | 20 | 18 | 13 | 12 | 11 | 10 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
131 | 11 | 2017-08-25 | 29 | 28 | 24 | 23 | 19 | 16 | 11 | 8 | 6 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
132 | 9 | 2017-08-11 | 28 | 26 | 21 | 18 | 17 | 14 | 11 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
133 | 7 | 2017-07-28 | 23 | 18 | 16 | 15 | 12 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
134 | 6 | 2017-07-21 | 25 | 21 | 17 | 14 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
135 | 7 | 2017-07-28 | 25 | 23 | 19 | 14 | 9 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
136 | 10 | 2017-08-18 | 29 | 25 | 23 | 19 | 17 | 13 | 10 | 9 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
137 | 7 | 2017-07-28 | 27 | 22 | 20 | 15 | 10 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
138 | 9 | 2017-08-11 | 24 | 23 | 22 | 17 | 15 | 10 | 9 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
139 | 8 | 2017-08-04 | 25 | 20 | 18 | 15 | 13 | 9 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
140 | 9 | 2017-08-11 | 30 | 28 | 24 | 19 | 15 | 10 | 6 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
141 | 9 | 2017-08-11 | 29 | 26 | 24 | 19 | 15 | 10 | 9 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
142 | 7 | 2017-07-28 | 20 | 16 | 14 | 10 | 5 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
143 | 6 | 2017-07-21 | 21 | 17 | 15 | 10 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
144 | 7 | 2017-07-28 | 22 | 17 | 14 | 10 | 8 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
145 | 8 | 2017-08-04 | 21 | 17 | 14 | 12 | 11 | 9 | 7 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
146 | 12 | 2017-09-01 | 28 | 27 | 24 | 23 | 22 | 20 | 18 | 16 | 14 | 13 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
147 | 6 | 2017-07-21 | 22 | 21 | 16 | 12 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
148 | 8 | 2017-08-04 | 22 | 18 | 15 | 13 | 9 | 8 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
149 | 10 | 2017-08-18 | 29 | 26 | 24 | 21 | 16 | 13 | 11 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
150 | 6 | 2017-07-21 | 25 | 20 | 16 | 11 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
151 | 14 | 2017-09-15 | 30 | 28 | 27 | 23 | 20 | 16 | 15 | 12 | 11 | 7 | 6 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
152 | 7 | 2017-07-28 | 21 | 17 | 15 | 13 | 10 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
153 | 14 | 2017-09-15 | 27 | 26 | 24 | 21 | 20 | 19 | 17 | 14 | 12 | 10 | 8 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
154 | 8 | 2017-08-04 | 23 | 19 | 16 | 15 | 14 | 9 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
155 | 10 | 2017-08-18 | 21 | 20 | 18 | 17 | 15 | 13 | 12 | 9 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
156 | 10 | 2017-08-18 | 29 | 24 | 23 | 19 | 17 | 14 | 10 | 9 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
157 | 6 | 2017-07-21 | 21 | 17 | 15 | 10 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
158 | 8 | 2017-08-04 | 25 | 23 | 21 | 19 | 14 | 10 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
159 | 5 | 2017-07-14 | 20 | 18 | 13 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
160 | 8 | 2017-08-04 | 21 | 20 | 19 | 14 | 11 | 7 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
161 | 9 | 2017-08-11 | 25 | 24 | 19 | 18 | 13 | 8 | 7 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
162 | 8 | 2017-08-04 | 27 | 23 | 20 | 16 | 14 | 9 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
163 | 10 | 2017-08-18 | 27 | 26 | 25 | 22 | 18 | 17 | 12 | 8 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
164 | 9 | 2017-08-11 | 26 | 21 | 17 | 15 | 12 | 7 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
165 | 7 | 2017-07-28 | 21 | 18 | 17 | 16 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
166 | 8 | 2017-08-04 | 23 | 21 | 19 | 17 | 13 | 9 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
167 | 9 | 2017-08-11 | 29 | 26 | 25 | 23 | 18 | 16 | 11 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
168 | 8 | 2017-08-04 | 26 | 23 | 22 | 17 | 12 | 8 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
169 | 7 | 2017-07-28 | 24 | 22 | 17 | 14 | 9 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
170 | 10 | 2017-08-18 | 23 | 21 | 20 | 17 | 14 | 11 | 9 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
171 | 7 | 2017-07-28 | 23 | 19 | 15 | 14 | 9 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
172 | 9 | 2017-08-11 | 22 | 21 | 20 | 16 | 12 | 11 | 10 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
173 | 10 | 2017-08-18 | 24 | 22 | 19 | 17 | 14 | 12 | 9 | 7 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
174 | 10 | 2017-08-18 | 29 | 26 | 23 | 19 | 16 | 14 | 12 | 7 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
175 | 9 | 2017-08-11 | 25 | 24 | 22 | 17 | 14 | 13 | 9 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
176 | 8 | 2017-08-04 | 26 | 23 | 20 | 15 | 11 | 6 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
177 | 8 | 2017-08-04 | 20 | 17 | 15 | 11 | 6 | 5 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
178 | 8 | 2017-08-04 | 22 | 17 | 16 | 15 | 12 | 7 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
179 | 13 | 2017-09-08 | 29 | 25 | 22 | 19 | 15 | 14 | 12 | 11 | 10 | 7 | 5 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
180 | 9 | 2017-08-11 | 27 | 22 | 21 | 17 | 14 | 10 | 7 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
181 | 9 | 2017-08-11 | 22 | 17 | 16 | 14 | 10 | 8 | 6 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
182 | 9 | 2017-08-11 | 24 | 20 | 15 | 13 | 9 | 8 | 7 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
183 | 10 | 2017-08-18 | 26 | 24 | 20 | 15 | 14 | 12 | 9 | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
184 | 6 | 2017-07-21 | 21 | 17 | 12 | 7 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
185 | 7 | 2017-07-28 | 20 | 17 | 13 | 11 | 10 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
186 | 6 | 2017-07-21 | 24 | 20 | 19 | 15 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
187 | 10 | 2017-08-18 | 25 | 24 | 19 | 15 | 14 | 13 | 12 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
188 | 7 | 2017-07-28 | 22 | 18 | 16 | 13 | 11 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
189 | 7 | 2017-07-28 | 23 | 19 | 18 | 15 | 13 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
190 | 9 | 2017-08-11 | 24 | 20 | 19 | 17 | 16 | 12 | 7 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
191 | 9 | 2017-08-11 | 29 | 27 | 24 | 19 | 14 | 13 | 9 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
192 | 9 | 2017-08-11 | 27 | 23 | 22 | 21 | 18 | 16 | 12 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
193 | 11 | 2017-08-25 | 26 | 24 | 20 | 15 | 11 | 10 | 8 | 5 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
194 | 10 | 2017-08-18 | 29 | 25 | 23 | 19 | 15 | 11 | 7 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
195 | 11 | 2017-08-25 | 28 | 26 | 23 | 20 | 17 | 14 | 11 | 7 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
196 | 9 | 2017-08-11 | 29 | 25 | 22 | 19 | 15 | 13 | 9 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
197 | 10 | 2017-08-18 | 27 | 25 | 20 | 16 | 15 | 14 | 12 | 10 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
198 | 9 | 2017-08-11 | 26 | 24 | 23 | 19 | 16 | 12 | 9 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
199 | 7 | 2017-07-28 | 20 | 17 | 16 | 11 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
200 | 14 | 2017-09-15 | 29 | 26 | 22 | 20 | 17 | 16 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
201 | 8 | 2017-08-04 | 25 | 21 | 17 | 15 | 11 | 10 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
202 | 8 | 2017-08-04 | 22 | 21 | 20 | 17 | 14 | 10 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
203 | 7 | 2017-07-28 | 29 | 26 | 21 | 17 | 13 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
204 | 6 | 2017-07-21 | 21 | 16 | 11 | 6 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
205 | 8 | 2017-08-04 | 24 | 20 | 17 | 16 | 15 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
206 | 7 | 2017-07-28 | 22 | 18 | 15 | 12 | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
207 | 7 | 2017-07-28 | 20 | 16 | 13 | 11 | 9 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
208 | 8 | 2017-08-04 | 26 | 25 | 21 | 16 | 11 | 8 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
209 | 7 | 2017-07-28 | 20 | 17 | 13 | 10 | 9 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
210 | 12 | 2017-09-01 | 28 | 27 | 24 | 22 | 21 | 19 | 15 | 14 | 12 | 9 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
211 | 11 | 2017-08-25 | 27 | 23 | 20 | 15 | 12 | 11 | 9 | 5 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
212 | 11 | 2017-08-25 | 24 | 22 | 20 | 19 | 16 | 15 | 12 | 11 | 9 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
213 | 10 | 2017-08-18 | 25 | 21 | 20 | 19 | 16 | 14 | 11 | 9 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
214 | 9 | 2017-08-11 | 22 | 18 | 17 | 14 | 13 | 9 | 6 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
215 | 9 | 2017-08-11 | 24 | 23 | 21 | 20 | 16 | 14 | 9 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
216 | 11 | 2017-08-25 | 30 | 28 | 25 | 21 | 18 | 13 | 11 | 10 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
217 | 7 | 2017-07-28 | 27 | 22 | 17 | 16 | 11 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
218 | 9 | 2017-08-11 | 29 | 24 | 20 | 18 | 15 | 10 | 9 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
219 | 10 | 2017-08-18 | 24 | 20 | 19 | 15 | 13 | 12 | 9 | 7 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
220 | 9 | 2017-08-11 | 29 | 27 | 26 | 23 | 20 | 15 | 12 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
221 | 6 | 2017-07-21 | 20 | 18 | 13 | 11 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
222 | 7 | 2017-07-28 | 20 | 17 | 13 | 9 | 8 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
223 | 9 | 2017-08-11 | 24 | 22 | 17 | 15 | 13 | 8 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
224 | 9 | 2017-08-11 | 24 | 22 | 19 | 18 | 17 | 13 | 9 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
225 | 7 | 2017-07-28 | 24 | 19 | 16 | 13 | 10 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
226 | 11 | 2017-08-25 | 27 | 23 | 20 | 19 | 15 | 14 | 12 | 9 | 8 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
227 | 13 | 2017-09-08 | 30 | 26 | 23 | 19 | 17 | 16 | 14 | 12 | 11 | 10 | 7 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
228 | 10 | 2017-08-18 | 23 | 21 | 18 | 14 | 12 | 7 | 6 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
229 | 10 | 2017-08-18 | 23 | 19 | 14 | 12 | 10 | 8 | 5 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
230 | 9 | 2017-08-11 | 28 | 27 | 26 | 22 | 20 | 17 | 12 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
231 | 7 | 2017-07-28 | 20 | 16 | 15 | 14 | 9 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
232 | 9 | 2017-08-11 | 25 | 24 | 19 | 17 | 15 | 12 | 9 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
233 | 11 | 2017-08-25 | 25 | 23 | 21 | 18 | 17 | 15 | 10 | 5 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
234 | 8 | 2017-08-04 | 21 | 20 | 18 | 15 | 11 | 9 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
235 | 10 | 2017-08-18 | 30 | 26 | 25 | 22 | 20 | 16 | 15 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
236 | 11 | 2017-08-25 | 29 | 26 | 23 | 22 | 20 | 16 | 11 | 10 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
237 | 13 | 2017-09-08 | 26 | 23 | 18 | 17 | 15 | 13 | 12 | 11 | 7 | 6 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
238 | 9 | 2017-08-11 | 26 | 24 | 23 | 18 | 14 | 11 | 10 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
239 | 11 | 2017-08-25 | 26 | 22 | 18 | 14 | 11 | 10 | 8 | 5 | 4 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
240 | 7 | 2017-07-28 | 26 | 21 | 17 | 13 | 8 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
241 | 7 | 2017-07-28 | 20 | 18 | 14 | 11 | 10 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
242 | 8 | 2017-08-04 | 27 | 23 | 18 | 17 | 12 | 8 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
243 | 11 | 2017-08-25 | 28 | 23 | 20 | 17 | 16 | 15 | 11 | 10 | 7 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
244 | 13 | 2017-09-08 | 27 | 26 | 23 | 19 | 17 | 14 | 11 | 10 | 9 | 7 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
245 | 8 | 2017-08-04 | 22 | 21 | 18 | 14 | 9 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
246 | 6 | 2017-07-21 | 22 | 17 | 12 | 11 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
247 | 9 | 2017-08-11 | 25 | 21 | 20 | 19 | 16 | 13 | 11 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
248 | 11 | 2017-08-25 | 24 | 23 | 20 | 19 | 18 | 13 | 11 | 10 | 9 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
249 | 10 | 2017-08-18 | 28 | 26 | 25 | 21 | 17 | 13 | 8 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
250 | 7 | 2017-07-28 | 20 | 16 | 13 | 11 | 10 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
251 | 8 | 2017-08-04 | 21 | 20 | 18 | 14 | 12 | 9 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
252 | 9 | 2017-08-11 | 25 | 20 | 16 | 12 | 9 | 7 | 6 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
253 | 8 | 2017-08-04 | 22 | 18 | 14 | 12 | 8 | 5 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
254 | 10 | 2017-08-18 | 30 | 28 | 26 | 21 | 18 | 16 | 14 | 13 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
255 | 11 | 2017-08-25 | 26 | 22 | 21 | 20 | 19 | 16 | 15 | 14 | 10 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
256 | 10 | 2017-08-18 | 25 | 23 | 18 | 17 | 16 | 12 | 7 | 6 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
257 | 9 | 2017-08-11 | 22 | 21 | 20 | 15 | 14 | 11 | 10 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
258 | 10 | 2017-08-18 | 29 | 27 | 23 | 19 | 16 | 13 | 11 | 7 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
259 | 8 | 2017-08-04 | 25 | 22 | 17 | 14 | 9 | 8 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
260 | 8 | 2017-08-04 | 24 | 21 | 16 | 13 | 11 | 7 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
261 | 7 | 2017-07-28 | 23 | 19 | 16 | 11 | 7 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
262 | 6 | 2017-07-21 | 20 | 16 | 14 | 10 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
263 | 7 | 2017-07-28 | 20 | 18 | 14 | 12 | 11 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
264 | 9 | 2017-08-11 | 27 | 24 | 21 | 17 | 13 | 8 | 7 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
265 | 8 | 2017-08-04 | 21 | 20 | 16 | 12 | 9 | 8 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
266 | 7 | 2017-07-28 | 21 | 16 | 11 | 8 | 7 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
267 | 7 | 2017-07-28 | 21 | 19 | 15 | 13 | 8 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
268 | 8 | 2017-08-04 | 27 | 22 | 18 | 15 | 12 | 7 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
269 | 7 | 2017-07-28 | 20 | 19 | 16 | 12 | 7 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
270 | 9 | 2017-08-11 | 25 | 21 | 20 | 17 | 16 | 11 | 9 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
271 | 10 | 2017-08-18 | 28 | 26 | 25 | 21 | 18 | 17 | 14 | 11 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
272 | 10 | 2017-08-18 | 28 | 23 | 21 | 18 | 14 | 12 | 9 | 8 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
273 | 10 | 2017-08-18 | 28 | 24 | 21 | 18 | 16 | 15 | 12 | 8 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
274 | 7 | 2017-07-28 | 22 | 19 | 14 | 13 | 10 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
275 | 10 | 2017-08-18 | 30 | 27 | 25 | 22 | 17 | 13 | 12 | 7 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
276 | 10 | 2017-08-18 | 27 | 24 | 23 | 18 | 14 | 9 | 8 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
277 | 8 | 2017-08-04 | 21 | 19 | 18 | 14 | 12 | 8 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
278 | 7 | 2017-07-28 | 25 | 20 | 17 | 16 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
279 | 9 | 2017-08-11 | 20 | 16 | 13 | 10 | 9 | 8 | 5 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
280 | 9 | 2017-08-11 | 24 | 23 | 18 | 17 | 12 | 9 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
281 | 10 | 2017-08-18 | 29 | 27 | 24 | 21 | 18 | 13 | 11 | 10 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
282 | 12 | 2017-09-01 | 30 | 29 | 26 | 24 | 21 | 18 | 15 | 10 | 8 | 7 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
283 | 7 | 2017-07-28 | 27 | 23 | 19 | 15 | 10 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
284 | 9 | 2017-08-11 | 21 | 18 | 14 | 10 | 8 | 7 | 5 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
285 | 9 | 2017-08-11 | 30 | 25 | 21 | 16 | 13 | 11 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
286 | 11 | 2017-08-25 | 29 | 26 | 25 | 21 | 19 | 18 | 17 | 14 | 12 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
287 | 7 | 2017-07-28 | 20 | 19 | 14 | 9 | 6 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
288 | 9 | 2017-08-11 | 21 | 19 | 18 | 16 | 13 | 10 | 9 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
289 | 6 | 2017-07-21 | 20 | 16 | 14 | 12 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
290 | 9 | 2017-08-11 | 29 | 28 | 26 | 21 | 19 | 16 | 11 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
291 | 11 | 2017-08-25 | 26 | 23 | 21 | 17 | 16 | 14 | 11 | 10 | 9 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
292 | 10 | 2017-08-18 | 26 | 25 | 22 | 18 | 17 | 14 | 10 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
293 | 9 | 2017-08-11 | 29 | 25 | 24 | 21 | 17 | 13 | 11 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
294 | 9 | 2017-08-11 | 27 | 24 | 20 | 16 | 12 | 9 | 7 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
295 | 7 | 2017-07-28 | 22 | 21 | 17 | 14 | 9 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
296 | 7 | 2017-07-28 | 21 | 17 | 12 | 11 | 7 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
297 | 10 | 2017-08-18 | 23 | 20 | 16 | 14 | 13 | 12 | 8 | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
298 | 5 | 2017-07-14 | 20 | 18 | 14 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
299 | 8 | 2017-08-04 | 20 | 15 | 10 | 9 | 7 | 6 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
300 | 7 | 2017-07-28 | 27 | 25 | 20 | 15 | 12 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
301 | 8 | 2017-08-04 | 23 | 21 | 17 | 13 | 11 | 9 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
302 | 12 | 2017-09-01 | 26 | 24 | 21 | 18 | 14 | 13 | 11 | 7 | 5 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
303 | 8 | 2017-08-04 | 20 | 19 | 14 | 10 | 6 | 5 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
304 | 8 | 2017-08-04 | 25 | 22 | 17 | 14 | 12 | 9 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
305 | 11 | 2017-08-25 | 23 | 22 | 19 | 16 | 13 | 10 | 8 | 7 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
306 | 9 | 2017-08-11 | 26 | 25 | 20 | 19 | 16 | 11 | 8 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
307 | 9 | 2017-08-11 | 26 | 21 | 20 | 18 | 15 | 10 | 8 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
308 | 8 | 2017-08-04 | 22 | 19 | 16 | 14 | 10 | 9 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
309 | 9 | 2017-08-11 | 30 | 25 | 22 | 19 | 18 | 16 | 12 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
310 | 9 | 2017-08-11 | 27 | 23 | 21 | 18 | 15 | 13 | 10 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
311 | 5 | 2017-07-14 | 22 | 18 | 13 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
312 | 10 | 2017-08-18 | 24 | 23 | 21 | 20 | 15 | 14 | 12 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
313 | 6 | 2017-07-21 | 22 | 18 | 14 | 9 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
314 | 7 | 2017-07-28 | 21 | 18 | 14 | 11 | 9 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
315 | 7 | 2017-07-28 | 21 | 18 | 16 | 13 | 11 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
316 | 8 | 2017-08-04 | 25 | 21 | 16 | 14 | 12 | 11 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
317 | 8 | 2017-08-04 | 23 | 22 | 17 | 15 | 14 | 12 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
318 | 8 | 2017-08-04 | 22 | 19 | 14 | 9 | 8 | 7 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
319 | 7 | 2017-07-28 | 22 | 18 | 17 | 12 | 7 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
320 | 6 | 2017-07-21 | 21 | 16 | 12 | 8 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
321 | 9 | 2017-08-11 | 30 | 27 | 26 | 25 | 21 | 17 | 12 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
322 | 10 | 2017-08-18 | 29 | 28 | 26 | 21 | 19 | 17 | 15 | 10 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
323 | 8 | 2017-08-04 | 20 | 19 | 15 | 11 | 10 | 7 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
324 | 9 | 2017-08-11 | 22 | 19 | 14 | 11 | 10 | 6 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
325 | 8 | 2017-08-04 | 23 | 20 | 15 | 11 | 10 | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
326 | 9 | 2017-08-11 | 27 | 22 | 18 | 13 | 8 | 6 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
327 | 9 | 2017-08-11 | 25 | 24 | 19 | 16 | 11 | 10 | 7 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
328 | 10 | 2017-08-18 | 30 | 25 | 21 | 20 | 15 | 14 | 12 | 9 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
329 | 10 | 2017-08-18 | 29 | 25 | 21 | 19 | 16 | 12 | 11 | 7 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
330 | 13 | 2017-09-08 | 30 | 28 | 23 | 21 | 20 | 19 | 17 | 15 | 10 | 7 | 6 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
331 | 11 | 2017-08-25 | 27 | 24 | 20 | 16 | 15 | 10 | 8 | 7 | 6 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
332 | 8 | 2017-08-04 | 24 | 20 | 16 | 14 | 10 | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
333 | 6 | 2017-07-21 | 25 | 20 | 15 | 12 | 7 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
334 | 9 | 2017-08-11 | 23 | 18 | 15 | 14 | 13 | 11 | 7 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
335 | 5 | 2017-07-14 | 21 | 17 | 14 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
336 | 10 | 2017-08-18 | 20 | 18 | 16 | 14 | 9 | 8 | 7 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
337 | 8 | 2017-08-04 | 24 | 19 | 16 | 14 | 10 | 8 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
338 | 8 | 2017-08-04 | 23 | 20 | 16 | 12 | 8 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
339 | 6 | 2017-07-21 | 22 | 18 | 13 | 10 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
340 | 9 | 2017-08-11 | 29 | 27 | 24 | 19 | 14 | 11 | 7 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
341 | 10 | 2017-08-18 | 23 | 18 | 16 | 15 | 14 | 13 | 12 | 9 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
342 | 10 | 2017-08-18 | 27 | 26 | 25 | 24 | 22 | 18 | 13 | 8 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
343 | 7 | 2017-07-28 | 24 | 20 | 16 | 15 | 11 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
344 | 8 | 2017-08-04 | 29 | 24 | 23 | 20 | 15 | 10 | 7 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
345 | 8 | 2017-08-04 | 30 | 28 | 23 | 18 | 14 | 9 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
346 | 11 | 2017-08-25 | 25 | 22 | 20 | 18 | 16 | 15 | 13 | 11 | 6 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
347 | 11 | 2017-08-25 | 27 | 25 | 21 | 19 | 15 | 13 | 8 | 7 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
348 | 8 | 2017-08-04 | 21 | 18 | 17 | 15 | 12 | 9 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
349 | 13 | 2017-09-08 | 30 | 27 | 22 | 21 | 17 | 16 | 15 | 14 | 12 | 11 | 7 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
350 | 9 | 2017-08-11 | 21 | 20 | 19 | 14 | 13 | 11 | 10 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
351 | 7 | 2017-07-28 | 23 | 21 | 18 | 15 | 10 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
352 | 9 | 2017-08-11 | 28 | 26 | 23 | 18 | 16 | 13 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
353 | 11 | 2017-08-25 | 27 | 24 | 22 | 20 | 19 | 18 | 16 | 12 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
354 | 9 | 2017-08-11 | 26 | 24 | 19 | 18 | 14 | 12 | 9 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
355 | 8 | 2017-08-04 | 22 | 17 | 15 | 11 | 8 | 7 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
356 | 9 | 2017-08-11 | 28 | 27 | 26 | 21 | 16 | 12 | 8 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
357 | 8 | 2017-08-04 | 22 | 19 | 18 | 14 | 9 | 8 | 7 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
358 | 7 | 2017-07-28 | 25 | 20 | 17 | 14 | 10 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
359 | 12 | 2017-09-01 | 30 | 28 | 27 | 26 | 22 | 19 | 17 | 13 | 9 | 8 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
360 | 13 | 2017-09-08 | 25 | 24 | 22 | 21 | 19 | 15 | 13 | 9 | 7 | 5 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
361 | 12 | 2017-09-01 | 29 | 27 | 24 | 23 | 20 | 18 | 16 | 13 | 9 | 6 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
362 | 9 | 2017-08-11 | 29 | 27 | 25 | 23 | 20 | 15 | 10 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
363 | 6 | 2017-07-21 | 24 | 20 | 15 | 10 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
364 | 9 | 2017-08-11 | 23 | 21 | 17 | 14 | 12 | 9 | 5 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
365 | 9 | 2017-08-11 | 24 | 21 | 20 | 18 | 16 | 11 | 9 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
366 | 8 | 2017-08-04 | 22 | 17 | 13 | 11 | 8 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
367 | 8 | 2017-08-04 | 25 | 20 | 18 | 16 | 11 | 9 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
368 | 7 | 2017-07-28 | 20 | 19 | 18 | 15 | 10 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
369 | 8 | 2017-08-04 | 22 | 21 | 18 | 17 | 15 | 10 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
370 | 8 | 2017-08-04 | 23 | 20 | 16 | 11 | 10 | 5 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
371 | 8 | 2017-08-04 | 20 | 15 | 13 | 12 | 7 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
372 | 8 | 2017-08-04 | 22 | 17 | 16 | 15 | 12 | 8 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
373 | 8 | 2017-08-04 | 25 | 21 | 17 | 15 | 10 | 5 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
374 | 6 | 2017-07-21 | 20 | 18 | 14 | 10 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
375 | 9 | 2017-08-11 | 26 | 25 | 21 | 16 | 11 | 6 | 5 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
376 | 12 | 2017-09-01 | 29 | 25 | 24 | 21 | 20 | 19 | 18 | 17 | 16 | 12 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
377 | 8 | 2017-08-04 | 20 | 18 | 15 | 11 | 9 | 7 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
378 | 7 | 2017-07-28 | 20 | 16 | 13 | 10 | 9 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
379 | 10 | 2017-08-18 | 27 | 22 | 18 | 16 | 13 | 8 | 6 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
380 | 12 | 2017-09-01 | 24 | 21 | 20 | 15 | 13 | 10 | 9 | 7 | 5 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
381 | 7 | 2017-07-28 | 21 | 17 | 13 | 11 | 9 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
382 | 10 | 2017-08-18 | 30 | 26 | 25 | 23 | 18 | 17 | 13 | 11 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
383 | 9 | 2017-08-11 | 22 | 21 | 18 | 14 | 12 | 8 | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
384 | 11 | 2017-08-25 | 28 | 27 | 26 | 23 | 19 | 16 | 14 | 13 | 8 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
385 | 9 | 2017-08-11 | 29 | 26 | 22 | 18 | 16 | 14 | 10 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
386 | 8 | 2017-08-04 | 24 | 21 | 19 | 16 | 11 | 7 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
387 | 7 | 2017-07-28 | 21 | 20 | 15 | 13 | 8 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
388 | 12 | 2017-09-01 | 30 | 26 | 25 | 21 | 20 | 18 | 14 | 10 | 7 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
389 | 10 | 2017-08-18 | 26 | 22 | 20 | 15 | 14 | 11 | 10 | 6 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
390 | 8 | 2017-08-04 | 21 | 20 | 16 | 13 | 12 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
391 | 7 | 2017-07-28 | 24 | 20 | 16 | 12 | 10 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
392 | 8 | 2017-08-04 | 26 | 24 | 23 | 20 | 15 | 13 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
393 | 10 | 2017-08-18 | 28 | 26 | 25 | 24 | 19 | 17 | 13 | 10 | 7 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
394 | 11 | 2017-08-25 | 25 | 22 | 20 | 19 | 18 | 16 | 15 | 13 | 12 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
395 | 10 | 2017-08-18 | 25 | 21 | 18 | 14 | 12 | 11 | 10 | 7 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
396 | 11 | 2017-08-25 | 30 | 25 | 22 | 21 | 19 | 16 | 14 | 9 | 7 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
397 | 10 | 2017-08-18 | 25 | 23 | 19 | 17 | 13 | 10 | 9 | 7 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
398 | 12 | 2017-09-01 | 30 | 29 | 24 | 20 | 18 | 17 | 16 | 15 | 13 | 8 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
399 | 7 | 2017-07-28 | 23 | 20 | 18 | 14 | 13 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
400 | 9 | 2017-08-11 | 23 | 22 | 18 | 14 | 13 | 9 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
401 | 8 | 2017-08-04 | 26 | 24 | 21 | 17 | 14 | 11 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
402 | 8 | 2017-08-04 | 26 | 21 | 20 | 16 | 13 | 11 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
403 | 10 | 2017-08-18 | 29 | 26 | 23 | 21 | 18 | 14 | 12 | 9 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
404 | 8 | 2017-08-04 | 27 | 22 | 21 | 16 | 11 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
405 | 7 | 2017-07-28 | 22 | 19 | 16 | 11 | 6 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
406 | 7 | 2017-07-28 | 24 | 23 | 18 | 13 | 9 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
407 | 8 | 2017-08-04 | 27 | 24 | 23 | 18 | 16 | 11 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
408 | 12 | 2017-09-01 | 29 | 28 | 25 | 21 | 16 | 11 | 9 | 8 | 6 | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
409 | 8 | 2017-08-04 | 29 | 24 | 19 | 14 | 11 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
410 | 10 | 2017-08-18 | 27 | 25 | 22 | 20 | 18 | 13 | 10 | 6 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
411 | 10 | 2017-08-18 | 26 | 24 | 22 | 17 | 12 | 8 | 7 | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
412 | 7 | 2017-07-28 | 23 | 22 | 19 | 16 | 11 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
413 | 9 | 2017-08-11 | 22 | 20 | 15 | 14 | 11 | 8 | 5 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
414 | 11 | 2017-08-25 | 28 | 26 | 24 | 22 | 20 | 16 | 12 | 9 | 6 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
415 | 9 | 2017-08-11 | 25 | 20 | 19 | 17 | 14 | 9 | 7 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
416 | 10 | 2017-08-18 | 26 | 25 | 20 | 19 | 16 | 11 | 6 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
417 | 10 | 2017-08-18 | 26 | 21 | 17 | 13 | 11 | 9 | 8 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
418 | 9 | 2017-08-11 | 30 | 27 | 26 | 21 | 17 | 13 | 9 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
419 | 11 | 2017-08-25 | 30 | 27 | 22 | 19 | 14 | 11 | 10 | 5 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
420 | 11 | 2017-08-25 | 28 | 27 | 22 | 20 | 17 | 16 | 12 | 9 | 6 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
421 | 7 | 2017-07-28 | 20 | 16 | 15 | 14 | 10 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
422 | 7 | 2017-07-28 | 21 | 16 | 11 | 8 | 6 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
423 | 9 | 2017-08-11 | 30 | 25 | 20 | 19 | 15 | 14 | 13 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
424 | 9 | 2017-08-11 | 27 | 23 | 22 | 21 | 19 | 15 | 10 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
425 | 9 | 2017-08-11 | 27 | 25 | 22 | 19 | 15 | 11 | 10 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
426 | 9 | 2017-08-11 | 29 | 25 | 22 | 20 | 17 | 13 | 12 | 7 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
427 | 10 | 2017-08-18 | 27 | 22 | 19 | 17 | 16 | 12 | 9 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
428 | 12 | 2017-09-01 | 25 | 21 | 20 | 17 | 14 | 13 | 11 | 8 | 7 | 6 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
429 | 7 | 2017-07-28 | 24 | 19 | 15 | 14 | 9 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
430 | 8 | 2017-08-04 | 23 | 19 | 18 | 14 | 12 | 9 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
431 | 10 | 2017-08-18 | 29 | 24 | 20 | 19 | 18 | 14 | 10 | 9 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
432 | 10 | 2017-08-18 | 30 | 28 | 23 | 22 | 18 | 17 | 13 | 10 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
433 | 10 | 2017-08-18 | 21 | 20 | 18 | 15 | 14 | 11 | 8 | 5 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
434 | 8 | 2017-08-04 | 28 | 25 | 23 | 19 | 14 | 9 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
435 | 8 | 2017-08-04 | 23 | 22 | 21 | 16 | 14 | 9 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
436 | 8 | 2017-08-04 | 24 | 20 | 18 | 16 | 14 | 10 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
437 | 11 | 2017-08-25 | 30 | 28 | 23 | 22 | 19 | 17 | 12 | 10 | 9 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
438 | 9 | 2017-08-11 | 26 | 25 | 23 | 19 | 14 | 11 | 8 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
439 | 9 | 2017-08-11 | 21 | 18 | 16 | 15 | 10 | 9 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
440 | 9 | 2017-08-11 | 22 | 21 | 18 | 17 | 16 | 11 | 10 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
441 | 7 | 2017-07-28 | 22 | 19 | 18 | 14 | 9 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
442 | 6 | 2017-07-21 | 23 | 20 | 18 | 13 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
443 | 14 | 2017-09-15 | 26 | 25 | 24 | 22 | 21 | 20 | 16 | 15 | 14 | 12 | 11 | 6 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
444 | 7 | 2017-07-28 | 24 | 21 | 17 | 12 | 10 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
445 | 5 | 2017-07-14 | 20 | 15 | 10 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
446 | 9 | 2017-08-11 | 28 | 23 | 19 | 18 | 15 | 12 | 11 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
447 | 9 | 2017-08-11 | 27 | 23 | 19 | 17 | 12 | 9 | 7 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
448 | 10 | 2017-08-18 | 25 | 24 | 19 | 16 | 12 | 10 | 8 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
449 | 10 | 2017-08-18 | 27 | 25 | 22 | 19 | 16 | 14 | 10 | 8 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
450 | 9 | 2017-08-11 | 24 | 23 | 21 | 17 | 13 | 11 | 10 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
451 | 12 | 2017-09-01 | 29 | 28 | 25 | 23 | 19 | 17 | 15 | 14 | 13 | 8 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
452 | 7 | 2017-07-28 | 27 | 23 | 19 | 16 | 11 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
453 | 10 | 2017-08-18 | 24 | 21 | 20 | 15 | 13 | 12 | 10 | 9 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
454 | 6 | 2017-07-21 | 20 | 18 | 13 | 8 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
455 | 10 | 2017-08-18 | 21 | 19 | 16 | 12 | 10 | 9 | 6 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
456 | 6 | 2017-07-21 | 20 | 15 | 11 | 6 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
457 | 10 | 2017-08-18 | 24 | 23 | 19 | 16 | 15 | 13 | 11 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
458 | 9 | 2017-08-11 | 25 | 24 | 22 | 19 | 16 | 14 | 13 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
459 | 7 | 2017-07-28 | 21 | 16 | 13 | 9 | 8 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
460 | 10 | 2017-08-18 | 26 | 21 | 19 | 18 | 13 | 11 | 10 | 8 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
461 | 9 | 2017-08-11 | 29 | 26 | 22 | 21 | 16 | 11 | 9 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
462 | 8 | 2017-08-04 | 21 | 16 | 15 | 11 | 10 | 9 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
463 | 7 | 2017-07-28 | 26 | 22 | 17 | 14 | 10 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
464 | 12 | 2017-09-01 | 29 | 26 | 22 | 19 | 17 | 15 | 12 | 7 | 5 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
465 | 7 | 2017-07-28 | 24 | 19 | 17 | 12 | 7 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
466 | 5 | 2017-07-14 | 20 | 15 | 11 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
467 | 7 | 2017-07-28 | 24 | 19 | 14 | 13 | 9 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
468 | 7 | 2017-07-28 | 21 | 20 | 19 | 14 | 9 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
469 | 6 | 2017-07-21 | 20 | 15 | 13 | 8 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
470 | 10 | 2017-08-18 | 25 | 22 | 21 | 16 | 11 | 9 | 7 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
471 | 7 | 2017-07-28 | 24 | 22 | 19 | 16 | 12 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
472 | 9 | 2017-08-11 | 30 | 27 | 23 | 19 | 16 | 14 | 10 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
473 | 8 | 2017-08-04 | 27 | 25 | 21 | 17 | 12 | 9 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
474 | 6 | 2017-07-21 | 23 | 19 | 14 | 10 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
475 | 9 | 2017-08-11 | 21 | 19 | 18 | 15 | 13 | 12 | 8 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
476 | 8 | 2017-08-04 | 25 | 20 | 19 | 16 | 11 | 10 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
477 | 11 | 2017-08-25 | 29 | 26 | 21 | 16 | 14 | 13 | 10 | 6 | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
478 | 9 | 2017-08-11 | 28 | 27 | 22 | 21 | 20 | 17 | 12 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
479 | 11 | 2017-08-25 | 29 | 28 | 27 | 24 | 20 | 17 | 13 | 10 | 7 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
480 | 7 | 2017-07-28 | 26 | 24 | 21 | 18 | 14 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
481 | 7 | 2017-07-28 | 22 | 17 | 14 | 11 | 10 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
482 | 8 | 2017-08-04 | 24 | 19 | 18 | 13 | 11 | 9 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
483 | 9 | 2017-08-11 | 24 | 19 | 14 | 12 | 11 | 6 | 5 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
484 | 9 | 2017-08-11 | 28 | 26 | 24 | 21 | 17 | 12 | 7 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
485 | 8 | 2017-08-04 | 22 | 19 | 14 | 11 | 9 | 7 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
486 | 9 | 2017-08-11 | 28 | 25 | 20 | 18 | 16 | 12 | 10 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
487 | 6 | 2017-07-21 | 24 | 19 | 16 | 13 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
488 | 8 | 2017-08-04 | 27 | 24 | 20 | 16 | 11 | 7 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
489 | 7 | 2017-07-28 | 20 | 16 | 13 | 11 | 9 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
490 | 10 | 2017-08-18 | 28 | 24 | 19 | 16 | 15 | 14 | 12 | 9 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
491 | 10 | 2017-08-18 | 30 | 28 | 24 | 20 | 19 | 18 | 14 | 12 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
492 | 7 | 2017-07-28 | 24 | 22 | 20 | 15 | 10 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
493 | 9 | 2017-08-11 | 26 | 25 | 21 | 17 | 16 | 14 | 9 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
494 | 10 | 2017-08-18 | 26 | 21 | 20 | 17 | 16 | 13 | 8 | 7 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
495 | 11 | 2017-08-25 | 28 | 25 | 22 | 20 | 15 | 13 | 12 | 9 | 8 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
496 | 10 | 2017-08-18 | 24 | 23 | 21 | 18 | 14 | 13 | 10 | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
497 | 7 | 2017-07-28 | 21 | 19 | 15 | 10 | 8 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
498 | 10 | 2017-08-18 | 28 | 24 | 20 | 15 | 14 | 13 | 9 | 7 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
499 | 7 | 2017-07-28 | 21 | 17 | 16 | 12 | 9 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
500 | 8 | 2017-08-04 | 28 | 27 | 23 | 20 | 15 | 11 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
501 | 9 | 2017-08-11 | 30 | 27 | 22 | 18 | 14 | 12 | 10 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Formulas:
End of Zero Week = IF([Weeks to Zero]<>"",INDEX(D2:BD2,1,[Weeks to Zero]+1),"")

## Risk Impact Monte Carlo (hidden)
 | time axis 2017-06-09 to 2018-06-08
Risk 1 - Reduce Probability
Trial | Weeks to Zero | End of Zero Week | TotalStories | End period 1 | End period 2 | End period 3 | End period 4 | End period 5 | End period 6 | End period 7 | End period 8 | End period 9 | End period 10 | End period 11 | End period 12 | End period 13 | End period 14 | End period 15 | End period 16 | End period 17 | End period 18 | End period 19 | End period 20 | End period 21 | End period 22 | End period 23 | End period 24 | End period 25 | End period 26 | End period 27 | End period 28 | End period 29 | End period 30 | End period 31 | End period 32 | End period 33 | End period 34 | End period 35 | End period 36 | End period 37 | End period 38 | End period 39 | End period 40 | End period 41 | End period 42 | End period 43 | End period 44 | End period 45 | End period 46 | End period 47 | End period 48 | End period 49 | End period 50 | End period 51 | End period 52
1 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
4 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
6 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
8 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
9 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
10 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
11 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
12 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
13 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
14 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
15 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
16 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
17 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
18 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
19 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
20 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
21 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
22 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
23 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
24 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
25 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
26 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
27 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
28 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
29 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
30 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
31 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
32 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
33 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
34 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
35 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
36 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
37 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
38 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
39 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
40 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
41 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
42 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
43 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
44 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
45 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
46 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
47 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
48 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
49 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
50 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
51 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
52 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
53 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
54 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
55 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
56 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
57 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
58 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
59 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
60 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
61 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
62 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
63 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
64 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
65 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
66 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
67 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
68 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
69 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
70 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
71 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
72 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
73 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
74 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
75 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
76 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
77 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
78 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
79 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
80 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
81 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
82 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
83 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
84 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
85 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
86 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
87 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
88 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
89 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
90 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
91 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
92 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
93 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
94 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
95 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
96 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
97 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
98 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
99 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
100 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Risk 1 - Reduce Impact
Trial | Weeks to Zero | End of Zero Week | TotalStories | End period 1 | End period 2 | End period 3 | End period 4 | End period 5 | End period 6 | End period 7 | End period 8 | End period 9 | End period 10 | End period 11 | End period 12 | End period 13 | End period 14 | End period 15 | End period 16 | End period 17 | End period 18 | End period 19 | End period 20 | End period 21 | End period 22 | End period 23 | End period 24 | End period 25 | End period 26 | End period 27 | End period 28 | End period 29 | End period 30 | End period 31 | End period 32 | End period 33 | End period 34 | End period 35 | End period 36 | End period 37 | End period 38 | End period 39 | End period 40 | End period 41 | End period 42 | End period 43 | End period 44 | End period 45 | End period 46 | End period 47 | End period 48 | End period 49 | End period 50 | End period 51 | End period 52
1 | 11 | 2017-08-25 | 29 | 27 | 22 | 17 | 16 | 13 | 11 | 8 | 7 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 10 | 2017-08-18 | 27 | 25 | 20 | 19 | 16 | 13 | 12 | 7 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 9 | 2017-08-11 | 26 | 23 | 22 | 17 | 13 | 12 | 7 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 7 | 2017-07-28 | 20 | 17 | 12 | 11 | 6 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 9 | 2017-08-11 | 25 | 23 | 19 | 15 | 13 | 8 | 7 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 7 | 2017-07-28 | 22 | 20 | 19 | 17 | 12 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 7 | 2017-07-28 | 28 | 25 | 20 | 16 | 12 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 10 | 2017-08-18 | 27 | 26 | 22 | 17 | 16 | 14 | 10 | 7 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 8 | 2017-08-04 | 28 | 24 | 21 | 17 | 13 | 11 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | 10 | 2017-08-18 | 27 | 24 | 23 | 19 | 17 | 16 | 11 | 9 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | 9 | 2017-08-11 | 23 | 22 | 20 | 17 | 16 | 12 | 7 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 9 | 2017-08-11 | 26 | 25 | 20 | 16 | 12 | 7 | 6 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | 6 | 2017-07-21 | 21 | 19 | 15 | 13 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 8 | 2017-08-04 | 25 | 21 | 16 | 11 | 10 | 7 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | 10 | 2017-08-18 | 26 | 23 | 22 | 17 | 15 | 10 | 9 | 6 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | 9 | 2017-08-11 | 28 | 24 | 21 | 19 | 17 | 14 | 10 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 8 | 2017-08-04 | 22 | 17 | 16 | 14 | 12 | 11 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 8 | 2017-08-04 | 27 | 22 | 17 | 16 | 12 | 9 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | 12 | 2017-09-01 | 29 | 27 | 26 | 21 | 20 | 19 | 15 | 13 | 8 | 6 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | 11 | 2017-08-25 | 29 | 24 | 21 | 18 | 16 | 13 | 9 | 8 | 4 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 11 | 2017-08-25 | 25 | 24 | 21 | 20 | 18 | 13 | 12 | 11 | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | 10 | 2017-08-18 | 28 | 23 | 22 | 19 | 16 | 13 | 11 | 7 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | 11 | 2017-08-25 | 29 | 27 | 26 | 22 | 21 | 16 | 12 | 7 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 8 | 2017-08-04 | 23 | 18 | 14 | 12 | 11 | 7 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | 8 | 2017-08-04 | 28 | 24 | 22 | 17 | 13 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | 9 | 2017-08-11 | 20 | 16 | 13 | 12 | 8 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | 9 | 2017-08-11 | 29 | 24 | 19 | 14 | 10 | 9 | 7 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | 7 | 2017-07-28 | 22 | 18 | 16 | 11 | 8 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | 10 | 2017-08-18 | 29 | 24 | 23 | 21 | 16 | 15 | 13 | 10 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | 9 | 2017-08-11 | 22 | 20 | 18 | 15 | 13 | 12 | 7 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | 8 | 2017-08-04 | 20 | 18 | 15 | 14 | 10 | 9 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | 11 | 2017-08-25 | 30 | 29 | 25 | 22 | 21 | 18 | 14 | 13 | 9 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | 9 | 2017-08-11 | 25 | 23 | 21 | 19 | 18 | 15 | 10 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | 12 | 2017-09-01 | 27 | 23 | 22 | 21 | 20 | 19 | 17 | 14 | 12 | 10 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | 8 | 2017-08-04 | 27 | 26 | 21 | 18 | 14 | 11 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | 8 | 2017-08-04 | 22 | 20 | 16 | 14 | 13 | 9 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | 11 | 2017-08-25 | 22 | 18 | 17 | 15 | 14 | 13 | 11 | 10 | 8 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | 6 | 2017-07-21 | 20 | 18 | 16 | 11 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | 10 | 2017-08-18 | 27 | 22 | 20 | 19 | 15 | 11 | 8 | 4 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | 11 | 2017-08-25 | 26 | 25 | 23 | 19 | 18 | 15 | 13 | 11 | 6 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | 9 | 2017-08-11 | 21 | 19 | 16 | 12 | 7 | 5 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | 8 | 2017-08-04 | 21 | 20 | 16 | 12 | 11 | 7 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | 10 | 2017-08-18 | 29 | 27 | 25 | 20 | 17 | 15 | 13 | 11 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | 9 | 2017-08-11 | 29 | 26 | 23 | 19 | 15 | 11 | 8 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | 9 | 2017-08-11 | 26 | 25 | 22 | 17 | 12 | 7 | 6 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | 8 | 2017-08-04 | 22 | 17 | 14 | 13 | 9 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | 9 | 2017-08-11 | 24 | 23 | 18 | 16 | 14 | 13 | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 7 | 2017-07-28 | 22 | 17 | 16 | 11 | 9 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | 13 | 2017-09-08 | 30 | 29 | 28 | 24 | 23 | 21 | 19 | 18 | 16 | 13 | 9 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | 10 | 2017-08-18 | 26 | 24 | 20 | 15 | 14 | 12 | 11 | 7 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | 12 | 2017-09-01 | 30 | 29 | 28 | 26 | 23 | 22 | 17 | 14 | 9 | 8 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 | 10 | 2017-08-18 | 29 | 26 | 23 | 21 | 19 | 15 | 11 | 9 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | 8 | 2017-08-04 | 22 | 21 | 20 | 19 | 14 | 9 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | 9 | 2017-08-11 | 30 | 27 | 23 | 22 | 19 | 14 | 10 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 | 8 | 2017-08-04 | 29 | 24 | 21 | 17 | 14 | 13 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56 | 10 | 2017-08-18 | 25 | 24 | 22 | 17 | 15 | 12 | 11 | 7 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57 | 7 | 2017-07-28 | 20 | 15 | 14 | 11 | 10 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58 | 7 | 2017-07-28 | 24 | 20 | 15 | 14 | 11 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
59 | 7 | 2017-07-28 | 20 | 18 | 14 | 10 | 9 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 | 10 | 2017-08-18 | 28 | 27 | 24 | 22 | 18 | 17 | 15 | 10 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
61 | 9 | 2017-08-11 | 25 | 20 | 16 | 13 | 12 | 10 | 8 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
62 | 9 | 2017-08-11 | 22 | 19 | 15 | 13 | 12 | 8 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | 6 | 2017-07-21 | 25 | 22 | 17 | 12 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
64 | 8 | 2017-08-04 | 22 | 20 | 15 | 11 | 10 | 8 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
65 | 10 | 2017-08-18 | 21 | 17 | 16 | 15 | 12 | 11 | 10 | 8 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
66 | 7 | 2017-07-28 | 21 | 18 | 17 | 13 | 11 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
67 | 8 | 2017-08-04 | 29 | 25 | 20 | 15 | 14 | 11 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
68 | 11 | 2017-08-25 | 29 | 28 | 26 | 24 | 20 | 16 | 13 | 10 | 7 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
69 | 12 | 2017-09-01 | 25 | 23 | 22 | 19 | 17 | 16 | 15 | 13 | 12 | 11 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 | 7 | 2017-07-28 | 21 | 17 | 16 | 11 | 9 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
71 | 11 | 2017-08-25 | 27 | 23 | 22 | 19 | 17 | 16 | 15 | 13 | 9 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 7 | 2017-07-28 | 25 | 20 | 19 | 15 | 12 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
73 | 12 | 2017-09-01 | 30 | 28 | 27 | 22 | 17 | 16 | 14 | 13 | 10 | 9 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
74 | 7 | 2017-07-28 | 21 | 19 | 15 | 13 | 10 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
75 | 7 | 2017-07-28 | 21 | 17 | 13 | 10 | 9 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
76 | 11 | 2017-08-25 | 29 | 25 | 22 | 17 | 14 | 13 | 10 | 8 | 7 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
77 | 9 | 2017-08-11 | 25 | 24 | 21 | 17 | 15 | 12 | 10 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
78 | 8 | 2017-08-04 | 24 | 19 | 17 | 13 | 12 | 9 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
79 | 7 | 2017-07-28 | 21 | 19 | 18 | 17 | 12 | 7 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | 8 | 2017-08-04 | 30 | 28 | 24 | 20 | 17 | 14 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 | 8 | 2017-08-04 | 22 | 21 | 17 | 12 | 11 | 10 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
82 | 10 | 2017-08-18 | 22 | 21 | 20 | 15 | 13 | 11 | 7 | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | 8 | 2017-08-04 | 27 | 23 | 20 | 17 | 15 | 11 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | 10 | 2017-08-18 | 24 | 22 | 18 | 16 | 12 | 11 | 10 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
85 | 10 | 2017-08-18 | 28 | 26 | 22 | 18 | 17 | 16 | 12 | 11 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 | 6 | 2017-07-21 | 21 | 17 | 12 | 11 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | 9 | 2017-08-11 | 30 | 27 | 24 | 21 | 16 | 11 | 9 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 | 8 | 2017-08-04 | 29 | 27 | 22 | 20 | 15 | 12 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
89 | 8 | 2017-08-04 | 20 | 17 | 16 | 11 | 10 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | 6 | 2017-07-21 | 23 | 19 | 15 | 13 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 | 11 | 2017-08-25 | 27 | 25 | 20 | 19 | 16 | 15 | 10 | 6 | 5 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 | 10 | 2017-08-18 | 25 | 22 | 21 | 19 | 18 | 16 | 12 | 8 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 | 12 | 2017-09-01 | 29 | 26 | 23 | 21 | 18 | 15 | 13 | 11 | 10 | 8 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 | 8 | 2017-08-04 | 24 | 20 | 18 | 13 | 12 | 10 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 | 10 | 2017-08-18 | 28 | 23 | 18 | 17 | 15 | 11 | 8 | 7 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 | 9 | 2017-08-11 | 23 | 21 | 18 | 16 | 12 | 11 | 9 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
97 | 10 | 2017-08-18 | 26 | 25 | 24 | 19 | 14 | 13 | 8 | 7 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 | 8 | 2017-08-04 | 23 | 21 | 16 | 14 | 13 | 9 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | 10 | 2017-08-18 | 27 | 24 | 23 | 18 | 17 | 13 | 11 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100 | 6 | 2017-07-21 | 23 | 18 | 13 | 9 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Formulas:
End of Zero Week = IF([Weeks to Zero]<>"",INDEX(D1:BD1,1,[Weeks to Zero]+1),"")

## Throughput Monte Carlo Weeks (hidden)
Trial # | Sumx | Sum4 | Sum8 | Sum12 | Sum16 | Sum20 | Sum24 | Sum28 | Sum32 | Sum36 | Sum40 | Sum44 | Sum48 | Sum52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
1 | 15 | 9 | 23 | 37 | 48 | 60 | 71 | 83 | 94 | 103 | 118 | 130 | 143 | 158 | 3 | 2 | 3 | 1 | 5 | 1 | 3 | 5 | 5 | 3 | 2 | 4 | 4 | 3 | 2 | 2 | 4 | 2 | 4 | 2 | 5 | 1 | 4 | 1 | 5 | 1 | 4 | 2 | 4 | 3 | 2 | 2 | 1 | 3 | 3 | 2 | 4 | 4 | 4 | 3 | 2 | 4 | 2 | 4 | 5 | 1 | 5 | 2 | 5 | 5 | 2 | 3
2 | 23 | 16 | 28 | 40 | 53 | 67 | 82 | 96 | 114 | 126 | 139 | 153 | 167 | 179 | 4 | 5 | 3 | 4 | 4 | 3 | 1 | 4 | 5 | 2 | 2 | 3 | 1 | 4 | 4 | 4 | 5 | 2 | 4 | 3 | 2 | 4 | 4 | 5 | 4 | 4 | 1 | 5 | 5 | 5 | 4 | 4 | 4 | 2 | 2 | 4 | 4 | 4 | 3 | 2 | 2 | 4 | 5 | 3 | 2 | 4 | 5 | 3 | 4 | 4 | 2 | 2
3 | 25 | 17 | 34 | 48 | 62 | 74 | 83 | 99 | 112 | 125 | 139 | 154 | 164 | 180 | 5 | 5 | 4 | 3 | 3 | 5 | 4 | 5 | 5 | 2 | 3 | 4 | 3 | 1 | 5 | 5 | 5 | 1 | 3 | 3 | 3 | 2 | 1 | 3 | 4 | 5 | 5 | 2 | 3 | 4 | 4 | 2 | 3 | 2 | 3 | 5 | 2 | 4 | 3 | 5 | 5 | 4 | 2 | 4 | 2 | 5 | 1 | 2 | 4 | 5 | 2 | 5
4 | 19 | 13 | 26 | 37 | 47 | 65 | 75 | 88 | 101 | 116 | 127 | 144 | 155 | 165 | 2 | 5 | 2 | 4 | 1 | 5 | 3 | 4 | 1 | 5 | 1 | 4 | 4 | 3 | 1 | 2 | 5 | 3 | 5 | 5 | 2 | 3 | 3 | 2 | 4 | 2 | 5 | 2 | 4 | 1 | 5 | 3 | 4 | 4 | 5 | 2 | 1 | 3 | 4 | 3 | 5 | 5 | 4 | 3 | 1 | 4 | 4 | 2 | 4 | 1 | 1 | 4
5 | 19 | 13 | 25 | 33 | 44 | 54 | 70 | 84 | 95 | 109 | 123 | 136 | 151 | 167 | 5 | 3 | 3 | 2 | 4 | 2 | 5 | 1 | 1 | 4 | 2 | 1 | 4 | 1 | 5 | 1 | 4 | 1 | 1 | 4 | 2 | 4 | 5 | 5 | 3 | 1 | 5 | 5 | 5 | 2 | 2 | 2 | 4 | 4 | 2 | 4 | 1 | 5 | 3 | 5 | 2 | 4 | 4 | 3 | 3 | 3 | 5 | 4 | 4 | 3 | 5 | 4
6 | 20 | 11 | 29 | 39 | 46 | 63 | 76 | 88 | 103 | 114 | 128 | 143 | 153 | 166 | 4 | 1 | 3 | 3 | 4 | 5 | 4 | 5 | 3 | 5 | 1 | 1 | 3 | 1 | 1 | 2 | 4 | 5 | 4 | 4 | 2 | 5 | 1 | 5 | 4 | 2 | 4 | 2 | 4 | 4 | 5 | 2 | 2 | 5 | 2 | 2 | 1 | 4 | 5 | 4 | 4 | 1 | 5 | 5 | 1 | 3 | 1 | 5 | 4 | 3 | 5 | 1
7 | 17 | 9 | 24 | 36 | 44 | 60 | 71 | 82 | 90 | 104 | 118 | 129 | 142 | 149 | 2 | 3 | 1 | 3 | 4 | 4 | 2 | 5 | 5 | 2 | 2 | 3 | 4 | 2 | 1 | 1 | 4 | 4 | 3 | 5 | 3 | 2 | 4 | 2 | 5 | 2 | 3 | 1 | 1 | 1 | 5 | 1 | 3 | 2 | 4 | 5 | 5 | 3 | 5 | 1 | 2 | 2 | 4 | 3 | 2 | 5 | 5 | 1 | 2 | 2 | 1 | 2
8 | 18 | 12 | 23 | 30 | 44 | 51 | 65 | 76 | 90 | 110 | 119 | 130 | 143 | 156 | 1 | 4 | 2 | 5 | 4 | 2 | 4 | 1 | 2 | 2 | 1 | 2 | 4 | 4 | 3 | 3 | 1 | 4 | 1 | 1 | 5 | 1 | 5 | 3 | 3 | 2 | 2 | 4 | 2 | 5 | 2 | 5 | 5 | 5 | 5 | 5 | 5 | 1 | 1 | 2 | 1 | 4 | 3 | 3 | 4 | 3 | 3 | 3 | 2 | 4 | 3 | 4
9 | 24 | 15 | 30 | 43 | 58 | 66 | 77 | 90 | 97 | 111 | 127 | 140 | 153 | 163 | 2 | 4 | 5 | 4 | 4 | 5 | 1 | 5 | 3 | 5 | 1 | 4 | 5 | 1 | 4 | 5 | 3 | 2 | 1 | 2 | 3 | 2 | 5 | 1 | 4 | 3 | 2 | 4 | 1 | 2 | 1 | 3 | 3 | 3 | 4 | 4 | 5 | 5 | 5 | 1 | 3 | 2 | 3 | 5 | 3 | 4 | 3 | 3 | 1 | 4 | 1 | 4
10 | 22 | 15 | 29 | 41 | 51 | 65 | 75 | 86 | 104 | 120 | 136 | 149 | 162 | 170 | 5 | 3 | 5 | 2 | 2 | 5 | 5 | 2 | 4 | 2 | 2 | 4 | 3 | 1 | 5 | 1 | 3 | 3 | 3 | 5 | 1 | 1 | 4 | 4 | 2 | 1 | 5 | 3 | 5 | 5 | 3 | 5 | 5 | 5 | 2 | 4 | 4 | 4 | 5 | 3 | 3 | 4 | 4 | 2 | 4 | 1 | 3 | 5 | 2 | 4 | 1 | 1
11 | 17 | 11 | 27 | 35 | 50 | 63 | 72 | 84 | 93 | 108 | 115 | 129 | 145 | 158 | 2 | 4 | 2 | 3 | 5 | 1 | 5 | 5 | 5 | 1 | 1 | 1 | 3 | 5 | 2 | 5 | 5 | 5 | 2 | 1 | 4 | 1 | 3 | 1 | 1 | 4 | 5 | 2 | 2 | 1 | 2 | 4 | 4 | 3 | 3 | 5 | 3 | 2 | 1 | 1 | 4 | 5 | 4 | 1 | 5 | 4 | 5 | 2 | 2 | 3 | 5 | 3
12 | 15 | 13 | 19 | 28 | 37 | 55 | 68 | 76 | 89 | 99 | 114 | 130 | 140 | 156 | 3 | 4 | 3 | 3 | 1 | 1 | 3 | 1 | 2 | 3 | 3 | 1 | 1 | 5 | 2 | 1 | 4 | 4 | 5 | 5 | 5 | 3 | 4 | 1 | 1 | 1 | 2 | 4 | 5 | 2 | 4 | 2 | 2 | 4 | 3 | 1 | 4 | 4 | 3 | 4 | 5 | 5 | 4 | 2 | 5 | 2 | 1 | 2 | 4 | 5 | 4 | 3
13 | 13 | 7 | 18 | 22 | 32 | 45 | 60 | 69 | 77 | 89 | 103 | 115 | 125 | 138 | 4 | 1 | 1 | 1 | 2 | 4 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 5 | 3 | 1 | 2 | 3 | 4 | 4 | 5 | 5 | 4 | 1 | 1 | 4 | 1 | 3 | 2 | 2 | 1 | 3 | 3 | 1 | 3 | 5 | 4 | 5 | 1 | 4 | 2 | 1 | 4 | 5 | 2 | 4 | 1 | 3 | 4 | 3 | 5 | 1
14 | 18 | 11 | 27 | 37 | 48 | 57 | 68 | 79 | 86 | 102 | 114 | 125 | 143 | 149 | 5 | 4 | 1 | 1 | 3 | 4 | 4 | 5 | 5 | 2 | 2 | 1 | 1 | 5 | 1 | 4 | 5 | 1 | 2 | 1 | 4 | 3 | 1 | 3 | 1 | 1 | 5 | 4 | 2 | 2 | 1 | 2 | 5 | 5 | 4 | 2 | 4 | 3 | 1 | 4 | 3 | 1 | 2 | 5 | 5 | 5 | 3 | 5 | 2 | 2 | 1 | 1
15 | 16 | 10 | 23 | 30 | 43 | 51 | 63 | 76 | 89 | 99 | 114 | 126 | 135 | 153 | 3 | 2 | 2 | 3 | 3 | 3 | 4 | 3 | 4 | 1 | 1 | 1 | 2 | 3 | 5 | 3 | 1 | 2 | 3 | 2 | 2 | 2 | 4 | 4 | 3 | 4 | 4 | 2 | 5 | 4 | 1 | 3 | 2 | 3 | 3 | 2 | 1 | 4 | 5 | 5 | 2 | 2 | 3 | 5 | 2 | 2 | 3 | 2 | 5 | 4 | 4 | 5
16 | 20 | 13 | 23 | 38 | 53 | 62 | 74 | 92 | 104 | 115 | 129 | 141 | 154 | 169 | 5 | 1 | 5 | 2 | 5 | 2 | 1 | 2 | 4 | 1 | 5 | 5 | 5 | 1 | 4 | 5 | 3 | 1 | 1 | 4 | 3 | 1 | 3 | 5 | 4 | 4 | 5 | 5 | 4 | 1 | 4 | 3 | 4 | 1 | 2 | 4 | 5 | 2 | 4 | 3 | 2 | 5 | 1 | 4 | 4 | 2 | 2 | 5 | 5 | 2 | 4 | 4
17 | 16 | 10 | 25 | 35 | 43 | 53 | 64 | 72 | 82 | 97 | 109 | 123 | 138 | 150 | 1 | 4 | 4 | 1 | 5 | 1 | 5 | 4 | 1 | 4 | 3 | 2 | 1 | 1 | 4 | 2 | 1 | 1 | 4 | 4 | 3 | 4 | 1 | 3 | 1 | 4 | 2 | 1 | 2 | 1 | 4 | 3 | 4 | 5 | 2 | 4 | 2 | 3 | 5 | 2 | 3 | 5 | 1 | 5 | 3 | 4 | 5 | 3 | 4 | 4 | 3 | 1
18 | 20 | 15 | 25 | 37 | 56 | 67 | 78 | 92 | 102 | 112 | 127 | 139 | 155 | 167 | 3 | 4 | 3 | 5 | 2 | 3 | 3 | 2 | 1 | 5 | 4 | 2 | 5 | 5 | 4 | 5 | 3 | 1 | 5 | 2 | 1 | 4 | 5 | 1 | 5 | 1 | 4 | 4 | 2 | 1 | 3 | 4 | 4 | 2 | 2 | 2 | 4 | 3 | 4 | 4 | 5 | 2 | 1 | 4 | 5 | 2 | 5 | 4 | 2 | 5 | 2 | 3
19 | 18 | 12 | 23 | 38 | 52 | 59 | 74 | 82 | 96 | 110 | 123 | 133 | 141 | 157 | 2 | 5 | 2 | 3 | 5 | 1 | 1 | 4 | 1 | 5 | 5 | 4 | 4 | 1 | 5 | 4 | 1 | 1 | 2 | 3 | 2 | 4 | 5 | 4 | 2 | 3 | 1 | 2 | 4 | 5 | 1 | 4 | 2 | 5 | 2 | 5 | 3 | 5 | 3 | 2 | 2 | 2 | 5 | 1 | 1 | 5 | 1 | 1 | 4 | 2 | 5 | 5
20 | 16 | 8 | 23 | 37 | 48 | 58 | 68 | 83 | 96 | 107 | 121 | 132 | 143 | 154 | 3 | 2 | 2 | 1 | 4 | 4 | 5 | 2 | 1 | 5 | 5 | 3 | 2 | 4 | 2 | 3 | 5 | 1 | 2 | 2 | 3 | 2 | 1 | 4 | 5 | 1 | 5 | 4 | 5 | 4 | 2 | 2 | 3 | 1 | 3 | 4 | 5 | 3 | 2 | 4 | 2 | 4 | 2 | 3 | 2 | 4 | 2 | 3 | 1 | 4 | 1 | 5
21 | 24 | 14 | 34 | 45 | 55 | 66 | 78 | 84 | 96 | 110 | 125 | 136 | 147 | 155 | 3 | 5 | 5 | 1 | 5 | 5 | 5 | 5 | 4 | 2 | 1 | 4 | 3 | 3 | 1 | 3 | 1 | 4 | 5 | 1 | 1 | 5 | 4 | 2 | 2 | 1 | 2 | 1 | 5 | 1 | 1 | 5 | 5 | 4 | 1 | 4 | 4 | 3 | 4 | 4 | 1 | 5 | 2 | 3 | 2 | 4 | 3 | 2 | 3 | 3 | 1 | 1
22 | 20 | 12 | 27 | 37 | 45 | 59 | 74 | 88 | 102 | 113 | 125 | 133 | 140 | 153 | 5 | 2 | 3 | 2 | 5 | 3 | 4 | 3 | 4 | 4 | 1 | 1 | 1 | 2 | 3 | 2 | 3 | 3 | 4 | 4 | 3 | 2 | 5 | 5 | 2 | 5 | 2 | 5 | 3 | 2 | 5 | 4 | 2 | 2 | 5 | 2 | 4 | 1 | 5 | 2 | 1 | 3 | 3 | 1 | 1 | 1 | 3 | 2 | 1 | 4 | 5 | 3
23 | 22 | 16 | 32 | 42 | 54 | 67 | 79 | 90 | 97 | 109 | 124 | 136 | 148 | 161 | 3 | 5 | 3 | 5 | 1 | 5 | 5 | 5 | 1 | 5 | 1 | 3 | 2 | 2 | 4 | 4 | 3 | 4 | 2 | 4 | 2 | 1 | 4 | 5 | 2 | 4 | 2 | 3 | 1 | 3 | 1 | 2 | 1 | 1 | 5 | 5 | 5 | 5 | 4 | 1 | 1 | 3 | 4 | 4 | 3 | 4 | 2 | 3 | 1 | 2 | 5 | 5
24 | 19 | 14 | 28 | 40 | 53 | 61 | 74 | 88 | 98 | 104 | 116 | 131 | 145 | 156 | 5 | 4 | 3 | 2 | 2 | 3 | 5 | 4 | 5 | 1 | 2 | 4 | 5 | 1 | 2 | 5 | 4 | 2 | 1 | 1 | 1 | 5 | 4 | 3 | 4 | 5 | 3 | 2 | 2 | 4 | 2 | 2 | 1 | 1 | 3 | 1 | 5 | 4 | 1 | 2 | 3 | 3 | 5 | 4 | 1 | 5 | 5 | 3 | 2 | 3 | 5 | 1
25 | 21 | 13 | 26 | 33 | 49 | 62 | 78 | 90 | 104 | 115 | 122 | 135 | 147 | 161 | 2 | 5 | 2 | 4 | 3 | 5 | 1 | 4 | 4 | 1 | 1 | 1 | 5 | 5 | 3 | 3 | 1 | 5 | 4 | 3 | 4 | 3 | 4 | 5 | 1 | 5 | 5 | 1 | 3 | 5 | 3 | 3 | 4 | 3 | 1 | 3 | 1 | 2 | 1 | 3 | 4 | 3 | 5 | 1 | 3 | 5 | 1 | 3 | 1 | 4 | 5 | 4
26 | 23 | 16 | 30 | 42 | 51 | 65 | 79 | 99 | 112 | 125 | 137 | 148 | 161 | 170 | 5 | 5 | 1 | 5 | 5 | 2 | 4 | 3 | 4 | 5 | 1 | 2 | 1 | 3 | 1 | 4 | 4 | 2 | 3 | 5 | 1 | 5 | 3 | 5 | 5 | 5 | 5 | 5 | 3 | 4 | 5 | 1 | 3 | 3 | 2 | 5 | 3 | 4 | 3 | 2 | 3 | 1 | 4 | 3 | 3 | 3 | 2 | 5 | 2 | 1 | 3 | 3
27 | 16 | 11 | 21 | 32 | 50 | 66 | 80 | 94 | 110 | 125 | 135 | 151 | 163 | 176 | 5 | 3 | 1 | 2 | 1 | 4 | 2 | 3 | 3 | 4 | 1 | 3 | 5 | 5 | 3 | 5 | 3 | 4 | 5 | 4 | 3 | 4 | 5 | 2 | 4 | 3 | 4 | 3 | 4 | 5 | 5 | 2 | 3 | 3 | 5 | 4 | 3 | 1 | 4 | 2 | 5 | 5 | 5 | 1 | 4 | 2 | 4 | 2 | 4 | 1 | 3 | 5
28 | 15 | 9 | 19 | 30 | 37 | 45 | 55 | 71 | 87 | 98 | 111 | 127 | 139 | 147 | 1 | 3 | 3 | 2 | 1 | 5 | 2 | 2 | 1 | 3 | 2 | 5 | 2 | 1 | 1 | 3 | 2 | 3 | 2 | 1 | 1 | 4 | 3 | 2 | 2 | 5 | 4 | 5 | 4 | 3 | 5 | 4 | 3 | 2 | 2 | 4 | 4 | 4 | 3 | 2 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 2 | 2 | 3 | 1
29 | 18 | 12 | 25 | 36 | 48 | 65 | 76 | 81 | 93 | 106 | 118 | 128 | 140 | 153 | 5 | 3 | 1 | 3 | 5 | 1 | 4 | 3 | 2 | 3 | 1 | 5 | 2 | 2 | 5 | 3 | 5 | 2 | 5 | 5 | 1 | 3 | 3 | 4 | 2 | 1 | 1 | 1 | 2 | 4 | 4 | 2 | 5 | 2 | 4 | 2 | 4 | 2 | 3 | 3 | 3 | 1 | 2 | 4 | 3 | 2 | 3 | 4 | 5 | 1 | 2 | 5
30 | 23 | 17 | 28 | 40 | 52 | 62 | 71 | 84 | 96 | 105 | 116 | 124 | 137 | 147 | 5 | 4 | 3 | 5 | 4 | 2 | 4 | 1 | 5 | 4 | 2 | 1 | 4 | 3 | 3 | 2 | 3 | 2 | 1 | 4 | 3 | 2 | 3 | 1 | 5 | 2 | 4 | 2 | 2 | 3 | 4 | 3 | 1 | 2 | 2 | 4 | 4 | 2 | 1 | 4 | 1 | 2 | 1 | 4 | 2 | 3 | 4 | 4 | 1 | 5 | 1 | 3
31 | 15 | 11 | 19 | 29 | 43 | 57 | 68 | 78 | 91 | 107 | 117 | 132 | 144 | 160 | 1 | 2 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 1 | 3 | 4 | 1 | 5 | 5 | 3 | 2 | 3 | 4 | 5 | 2 | 3 | 4 | 2 | 2 | 5 | 1 | 2 | 2 | 4 | 2 | 5 | 5 | 5 | 2 | 4 | 5 | 2 | 1 | 2 | 5 | 4 | 1 | 5 | 3 | 3 | 5 | 1 | 5 | 5 | 2 | 4
32 | 9 | 6 | 17 | 31 | 47 | 59 | 69 | 86 | 101 | 108 | 115 | 128 | 140 | 155 | 1 | 1 | 1 | 3 | 1 | 2 | 3 | 5 | 4 | 5 | 1 | 4 | 5 | 5 | 1 | 5 | 3 | 3 | 4 | 2 | 4 | 2 | 1 | 3 | 4 | 3 | 5 | 5 | 4 | 3 | 5 | 3 | 1 | 1 | 1 | 4 | 2 | 2 | 1 | 2 | 4 | 2 | 4 | 3 | 5 | 3 | 2 | 2 | 4 | 5 | 1 | 5
33 | 23 | 15 | 27 | 41 | 52 | 63 | 77 | 87 | 100 | 112 | 123 | 133 | 150 | 163 | 2 | 3 | 5 | 5 | 3 | 5 | 3 | 1 | 4 | 1 | 5 | 4 | 1 | 1 | 5 | 4 | 1 | 5 | 2 | 3 | 4 | 2 | 5 | 3 | 4 | 1 | 3 | 2 | 1 | 5 | 4 | 3 | 2 | 3 | 3 | 4 | 3 | 4 | 2 | 2 | 2 | 4 | 3 | 1 | 5 | 2 | 5 | 5 | 4 | 2 | 4 | 3
34 | 14 | 9 | 20 | 32 | 44 | 55 | 65 | 75 | 83 | 102 | 110 | 119 | 134 | 148 | 4 | 2 | 1 | 2 | 2 | 3 | 4 | 2 | 2 | 4 | 4 | 2 | 2 | 3 | 4 | 3 | 3 | 2 | 3 | 3 | 2 | 2 | 5 | 1 | 3 | 1 | 1 | 5 | 4 | 1 | 1 | 2 | 5 | 5 | 4 | 5 | 1 | 1 | 4 | 2 | 1 | 2 | 2 | 4 | 5 | 3 | 4 | 3 | 4 | 2 | 4 | 4
35 | 17 | 13 | 22 | 36 | 46 | 57 | 71 | 86 | 102 | 113 | 129 | 141 | 154 | 169 | 3 | 5 | 2 | 3 | 3 | 1 | 3 | 2 | 2 | 3 | 5 | 4 | 1 | 1 | 3 | 5 | 1 | 4 | 3 | 3 | 5 | 2 | 5 | 2 | 1 | 5 | 5 | 4 | 4 | 4 | 3 | 5 | 5 | 3 | 1 | 2 | 5 | 1 | 5 | 5 | 4 | 2 | 4 | 2 | 3 | 1 | 4 | 5 | 3 | 4 | 4 | 4
36 | 18 | 13 | 21 | 32 | 45 | 56 | 69 | 84 | 93 | 106 | 113 | 124 | 140 | 151 | 3 | 4 | 5 | 1 | 3 | 2 | 2 | 1 | 4 | 1 | 3 | 3 | 5 | 2 | 2 | 4 | 1 | 5 | 1 | 4 | 3 | 5 | 4 | 1 | 3 | 5 | 3 | 4 | 3 | 3 | 1 | 2 | 5 | 4 | 3 | 1 | 3 | 1 | 2 | 1 | 2 | 5 | 3 | 1 | 3 | 5 | 5 | 3 | 1 | 3 | 5 | 2
37 | 15 | 12 | 18 | 33 | 47 | 53 | 63 | 76 | 89 | 104 | 115 | 134 | 146 | 160 | 4 | 3 | 4 | 1 | 1 | 2 | 2 | 1 | 5 | 4 | 4 | 2 | 5 | 3 | 4 | 2 | 1 | 1 | 1 | 3 | 4 | 1 | 2 | 3 | 4 | 3 | 2 | 4 | 5 | 1 | 3 | 4 | 4 | 2 | 4 | 5 | 2 | 1 | 3 | 5 | 5 | 4 | 5 | 5 | 3 | 1 | 3 | 5 | 3 | 1 | 5 | 5
38 | 17 | 11 | 24 | 35 | 49 | 58 | 68 | 77 | 86 | 101 | 108 | 120 | 131 | 142 | 2 | 1 | 3 | 5 | 1 | 5 | 4 | 3 | 4 | 2 | 1 | 4 | 1 | 4 | 5 | 4 | 3 | 4 | 1 | 1 | 2 | 2 | 2 | 4 | 2 | 4 | 1 | 2 | 2 | 3 | 2 | 2 | 4 | 2 | 4 | 5 | 1 | 1 | 4 | 1 | 2 | 4 | 4 | 2 | 5 | 1 | 3 | 2 | 5 | 4 | 1 | 1
39 | 21 | 15 | 27 | 40 | 52 | 61 | 69 | 79 | 91 | 105 | 120 | 130 | 144 | 156 | 3 | 5 | 3 | 4 | 3 | 3 | 3 | 3 | 5 | 2 | 2 | 4 | 2 | 4 | 1 | 5 | 5 | 1 | 2 | 1 | 1 | 2 | 3 | 2 | 1 | 3 | 3 | 3 | 2 | 4 | 5 | 1 | 3 | 5 | 5 | 1 | 5 | 2 | 4 | 4 | 1 | 4 | 2 | 3 | 5 | 2 | 4 | 3 | 3 | 3 | 2 | 4
40 | 21 | 13 | 27 | 38 | 50 | 62 | 77 | 89 | 103 | 112 | 121 | 134 | 143 | 156 | 3 | 2 | 5 | 3 | 4 | 4 | 2 | 4 | 2 | 5 | 1 | 3 | 4 | 2 | 2 | 4 | 3 | 4 | 2 | 3 | 5 | 3 | 2 | 5 | 4 | 3 | 1 | 4 | 3 | 5 | 1 | 5 | 3 | 1 | 4 | 1 | 2 | 3 | 2 | 2 | 1 | 5 | 4 | 3 | 3 | 2 | 1 | 3 | 4 | 5 | 3 | 1
41 | 20 | 14 | 28 | 42 | 52 | 64 | 74 | 84 | 98 | 111 | 121 | 132 | 146 | 158 | 4 | 4 | 3 | 3 | 1 | 5 | 5 | 3 | 4 | 1 | 4 | 5 | 2 | 3 | 4 | 1 | 3 | 4 | 4 | 1 | 1 | 4 | 4 | 1 | 3 | 3 | 2 | 2 | 5 | 4 | 4 | 1 | 4 | 1 | 4 | 4 | 2 | 1 | 3 | 4 | 1 | 2 | 4 | 4 | 3 | 4 | 2 | 5 | 4 | 1 | 3 | 4
42 | 19 | 11 | 28 | 41 | 51 | 66 | 81 | 90 | 105 | 118 | 131 | 144 | 156 | 169 | 4 | 1 | 5 | 1 | 5 | 3 | 4 | 5 | 2 | 4 | 3 | 4 | 3 | 3 | 3 | 1 | 5 | 2 | 5 | 3 | 3 | 5 | 4 | 3 | 1 | 1 | 5 | 2 | 4 | 5 | 3 | 3 | 4 | 2 | 4 | 3 | 2 | 1 | 5 | 5 | 5 | 1 | 3 | 4 | 4 | 3 | 1 | 4 | 2 | 5 | 5 | 1
43 | 15 | 12 | 18 | 31 | 46 | 56 | 70 | 80 | 94 | 103 | 113 | 128 | 143 | 157 | 3 | 1 | 3 | 5 | 1 | 2 | 2 | 1 | 3 | 4 | 2 | 4 | 4 | 5 | 4 | 2 | 1 | 3 | 5 | 1 | 3 | 4 | 3 | 4 | 1 | 5 | 2 | 2 | 4 | 2 | 3 | 5 | 4 | 2 | 1 | 2 | 3 | 4 | 2 | 1 | 3 | 5 | 3 | 4 | 3 | 4 | 4 | 4 | 3 | 4 | 2 | 5
44 | 17 | 13 | 21 | 34 | 50 | 63 | 77 | 85 | 95 | 107 | 117 | 130 | 144 | 154 | 4 | 4 | 1 | 4 | 3 | 1 | 3 | 1 | 4 | 2 | 4 | 3 | 5 | 5 | 4 | 2 | 4 | 2 | 4 | 3 | 2 | 3 | 5 | 4 | 1 | 3 | 1 | 3 | 2 | 3 | 2 | 3 | 4 | 1 | 3 | 4 | 1 | 5 | 2 | 2 | 2 | 5 | 3 | 3 | 5 | 2 | 4 | 3 | 1 | 1 | 5 | 3
45 | 23 | 13 | 32 | 46 | 52 | 64 | 73 | 83 | 99 | 114 | 123 | 132 | 143 | 155 | 5 | 2 | 4 | 2 | 5 | 5 | 5 | 4 | 2 | 5 | 2 | 5 | 1 | 1 | 1 | 3 | 5 | 3 | 1 | 3 | 1 | 3 | 1 | 4 | 4 | 2 | 3 | 1 | 5 | 3 | 5 | 3 | 2 | 5 | 5 | 3 | 2 | 1 | 3 | 3 | 1 | 1 | 5 | 2 | 2 | 3 | 2 | 4 | 4 | 4 | 3 | 1
46 | 16 | 11 | 21 | 34 | 45 | 55 | 63 | 78 | 86 | 101 | 115 | 124 | 134 | 147 | 2 | 5 | 3 | 1 | 4 | 1 | 2 | 3 | 4 | 3 | 3 | 3 | 4 | 4 | 1 | 2 | 1 | 5 | 3 | 1 | 2 | 1 | 3 | 2 | 2 | 5 | 3 | 5 | 3 | 1 | 1 | 3 | 5 | 2 | 5 | 3 | 3 | 5 | 5 | 1 | 2 | 1 | 1 | 5 | 1 | 2 | 2 | 5 | 5 | 3 | 4 | 1
47 | 15 | 11 | 21 | 32 | 45 | 59 | 70 | 82 | 91 | 104 | 122 | 136 | 147 | 162 | 3 | 2 | 2 | 4 | 2 | 2 | 3 | 3 | 1 | 3 | 2 | 5 | 5 | 2 | 4 | 2 | 2 | 5 | 3 | 4 | 4 | 1 | 5 | 1 | 3 | 1 | 4 | 4 | 1 | 1 | 2 | 5 | 4 | 2 | 3 | 4 | 5 | 4 | 5 | 4 | 4 | 4 | 1 | 5 | 1 | 1 | 4 | 5 | 3 | 4 | 3 | 5
48 | 19 | 11 | 25 | 34 | 47 | 59 | 65 | 73 | 84 | 97 | 111 | 127 | 137 | 147 | 3 | 1 | 2 | 5 | 5 | 3 | 3 | 3 | 5 | 1 | 2 | 1 | 3 | 4 | 3 | 3 | 1 | 2 | 5 | 4 | 1 | 2 | 1 | 2 | 4 | 1 | 2 | 1 | 2 | 2 | 5 | 2 | 1 | 2 | 5 | 5 | 5 | 4 | 2 | 3 | 3 | 4 | 5 | 4 | 5 | 1 | 1 | 3 | 3 | 1 | 4 | 2
49 | 16 | 12 | 24 | 37 | 46 | 58 | 73 | 91 | 108 | 119 | 130 | 148 | 157 | 169 | 2 | 3 | 3 | 4 | 1 | 3 | 4 | 4 | 5 | 1 | 5 | 2 | 1 | 3 | 2 | 3 | 2 | 5 | 1 | 4 | 4 | 3 | 3 | 5 | 4 | 4 | 5 | 5 | 5 | 3 | 4 | 5 | 5 | 1 | 1 | 4 | 5 | 1 | 3 | 2 | 5 | 4 | 5 | 4 | 3 | 1 | 3 | 2 | 1 | 4 | 2 | 5
50 | 21 | 15 | 24 | 41 | 49 | 62 | 73 | 85 | 96 | 109 | 121 | 135 | 148 | 166 | 5 | 5 | 1 | 4 | 4 | 2 | 2 | 1 | 4 | 3 | 5 | 5 | 3 | 1 | 2 | 2 | 5 | 4 | 1 | 3 | 3 | 1 | 5 | 2 | 3 | 4 | 4 | 1 | 5 | 2 | 3 | 1 | 4 | 4 | 2 | 3 | 1 | 1 | 5 | 5 | 3 | 3 | 3 | 5 | 4 | 1 | 4 | 4 | 4 | 5 | 4 | 5
51 | 11 | 8 | 16 | 23 | 37 | 49 | 62 | 71 | 82 | 89 | 105 | 119 | 132 | 147 | 4 | 1 | 1 | 2 | 1 | 2 | 1 | 4 | 2 | 2 | 2 | 1 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 4 | 3 | 1 | 1 | 4 | 1 | 3 | 1 | 3 | 2 | 5 | 1 | 2 | 1 | 3 | 4 | 4 | 5 | 3 | 1 | 5 | 3 | 5 | 2 | 4 | 5 | 2 | 2 | 5 | 4 | 4
52 | 15 | 11 | 19 | 26 | 36 | 45 | 53 | 64 | 75 | 84 | 97 | 114 | 123 | 138 | 5 | 1 | 2 | 3 | 2 | 2 | 1 | 3 | 4 | 1 | 1 | 1 | 3 | 4 | 2 | 1 | 1 | 3 | 4 | 1 | 3 | 2 | 2 | 1 | 2 | 2 | 3 | 4 | 2 | 3 | 3 | 3 | 2 | 1 | 2 | 4 | 5 | 4 | 2 | 2 | 5 | 5 | 4 | 3 | 4 | 1 | 2 | 2 | 5 | 4 | 2 | 4
53 | 17 | 12 | 25 | 38 | 49 | 63 | 74 | 84 | 94 | 103 | 111 | 125 | 138 | 148 | 3 | 1 | 5 | 3 | 3 | 2 | 4 | 4 | 2 | 5 | 4 | 2 | 3 | 2 | 2 | 4 | 4 | 4 | 5 | 1 | 3 | 3 | 1 | 4 | 1 | 3 | 5 | 1 | 1 | 3 | 4 | 2 | 3 | 1 | 4 | 1 | 2 | 1 | 4 | 1 | 5 | 5 | 3 | 1 | 5 | 4 | 1 | 3 | 2 | 1 | 4 | 3
54 | 13 | 11 | 17 | 31 | 40 | 53 | 62 | 75 | 89 | 100 | 107 | 114 | 126 | 135 | 1 | 1 | 4 | 5 | 1 | 1 | 1 | 3 | 4 | 5 | 1 | 4 | 5 | 1 | 2 | 1 | 5 | 2 | 3 | 3 | 2 | 2 | 1 | 4 | 1 | 3 | 4 | 5 | 1 | 3 | 5 | 5 | 3 | 2 | 4 | 2 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 3 | 3 | 5 | 1 | 1 | 2 | 5 | 1
55 | 19 | 15 | 25 | 36 | 50 | 68 | 80 | 92 | 104 | 115 | 131 | 143 | 150 | 159 | 5 | 3 | 3 | 4 | 3 | 1 | 5 | 1 | 3 | 2 | 2 | 4 | 1 | 4 | 4 | 5 | 5 | 4 | 5 | 4 | 1 | 4 | 3 | 4 | 5 | 1 | 1 | 5 | 2 | 1 | 4 | 5 | 4 | 5 | 1 | 1 | 5 | 2 | 4 | 5 | 5 | 1 | 2 | 4 | 2 | 2 | 2 | 1 | 4 | 1 | 1 | 3
56 | 17 | 10 | 25 | 41 | 54 | 63 | 73 | 80 | 98 | 113 | 127 | 137 | 155 | 167 | 1 | 5 | 3 | 1 | 2 | 5 | 4 | 4 | 3 | 4 | 4 | 5 | 2 | 1 | 5 | 5 | 3 | 1 | 1 | 4 | 4 | 3 | 2 | 1 | 2 | 1 | 2 | 2 | 4 | 5 | 5 | 4 | 4 | 5 | 1 | 5 | 5 | 4 | 3 | 2 | 2 | 4 | 1 | 3 | 4 | 4 | 5 | 5 | 2 | 3 | 2 | 5
57 | 9 | 7 | 15 | 27 | 33 | 46 | 52 | 64 | 73 | 83 | 95 | 109 | 121 | 129 | 2 | 3 | 1 | 1 | 1 | 1 | 4 | 2 | 2 | 4 | 3 | 3 | 1 | 1 | 3 | 1 | 3 | 3 | 5 | 2 | 1 | 1 | 1 | 3 | 5 | 4 | 1 | 2 | 4 | 3 | 1 | 1 | 3 | 4 | 1 | 2 | 1 | 2 | 5 | 4 | 4 | 4 | 1 | 5 | 2 | 3 | 2 | 5 | 4 | 1 | 1 | 2
58 | 15 | 10 | 21 | 38 | 47 | 58 | 71 | 83 | 96 | 112 | 124 | 138 | 150 | 165 | 1 | 5 | 2 | 2 | 4 | 1 | 3 | 3 | 4 | 5 | 3 | 5 | 2 | 1 | 4 | 2 | 4 | 1 | 2 | 4 | 2 | 5 | 4 | 2 | 3 | 1 | 4 | 4 | 4 | 2 | 2 | 5 | 4 | 3 | 5 | 4 | 2 | 4 | 2 | 4 | 3 | 4 | 3 | 4 | 2 | 3 | 2 | 5 | 5 | 4 | 3 | 3
59 | 13 | 10 | 17 | 26 | 36 | 46 | 61 | 72 | 80 | 97 | 107 | 118 | 127 | 138 | 3 | 1 | 1 | 5 | 1 | 2 | 1 | 3 | 3 | 2 | 2 | 2 | 1 | 2 | 5 | 2 | 2 | 2 | 5 | 1 | 4 | 3 | 5 | 3 | 3 | 3 | 3 | 2 | 4 | 1 | 2 | 1 | 5 | 2 | 5 | 5 | 1 | 3 | 5 | 1 | 3 | 1 | 2 | 5 | 4 | 1 | 2 | 2 | 3 | 5 | 2 | 1
60 | 23 | 16 | 27 | 33 | 45 | 58 | 68 | 73 | 86 | 101 | 111 | 121 | 130 | 140 | 3 | 3 | 5 | 5 | 4 | 3 | 3 | 1 | 1 | 2 | 1 | 2 | 5 | 1 | 4 | 2 | 5 | 4 | 1 | 3 | 1 | 3 | 5 | 1 | 1 | 1 | 2 | 1 | 5 | 4 | 2 | 2 | 2 | 5 | 4 | 4 | 1 | 3 | 2 | 4 | 1 | 1 | 3 | 5 | 2 | 3 | 2 | 2 | 1 | 3 | 4 | 2
61 | 17 | 13 | 23 | 35 | 50 | 59 | 73 | 88 | 103 | 108 | 117 | 129 | 143 | 151 | 3 | 3 | 5 | 2 | 3 | 1 | 1 | 5 | 5 | 5 | 1 | 1 | 1 | 5 | 5 | 4 | 2 | 5 | 1 | 1 | 2 | 2 | 5 | 5 | 3 | 4 | 5 | 3 | 5 | 3 | 4 | 3 | 1 | 1 | 2 | 1 | 3 | 2 | 1 | 3 | 5 | 2 | 4 | 1 | 4 | 2 | 3 | 5 | 3 | 1 | 1 | 3
62 | 19 | 14 | 22 | 37 | 56 | 68 | 82 | 98 | 115 | 131 | 142 | 160 | 172 | 182 | 4 | 4 | 3 | 3 | 1 | 4 | 2 | 1 | 4 | 2 | 5 | 4 | 5 | 5 | 4 | 5 | 3 | 2 | 5 | 2 | 2 | 5 | 4 | 3 | 4 | 2 | 5 | 5 | 5 | 2 | 5 | 5 | 5 | 3 | 4 | 4 | 1 | 4 | 2 | 4 | 4 | 5 | 5 | 4 | 3 | 2 | 3 | 4 | 1 | 3 | 1 | 5
63 | 16 | 13 | 23 | 33 | 46 | 58 | 71 | 84 | 96 | 106 | 114 | 126 | 139 | 153 | 5 | 1 | 4 | 3 | 2 | 1 | 3 | 4 | 4 | 4 | 1 | 1 | 4 | 4 | 4 | 1 | 3 | 4 | 2 | 3 | 5 | 1 | 2 | 5 | 5 | 3 | 2 | 3 | 4 | 1 | 5 | 2 | 4 | 1 | 1 | 4 | 4 | 2 | 1 | 1 | 3 | 4 | 2 | 3 | 5 | 1 | 4 | 3 | 4 | 4 | 2 | 4
64 | 21 | 16 | 27 | 39 | 54 | 71 | 84 | 92 | 100 | 110 | 121 | 130 | 143 | 152 | 5 | 1 | 5 | 5 | 4 | 1 | 2 | 4 | 5 | 3 | 3 | 1 | 4 | 3 | 5 | 3 | 3 | 5 | 4 | 5 | 5 | 1 | 5 | 2 | 2 | 4 | 1 | 1 | 1 | 1 | 4 | 2 | 1 | 5 | 3 | 1 | 4 | 1 | 4 | 2 | 3 | 4 | 1 | 1 | 2 | 5 | 5 | 1 | 2 | 1 | 3 | 3
65 | 26 | 16 | 30 | 42 | 59 | 70 | 83 | 94 | 109 | 116 | 124 | 141 | 153 | 169 | 4 | 3 | 5 | 4 | 5 | 5 | 1 | 3 | 4 | 3 | 1 | 4 | 5 | 3 | 5 | 4 | 1 | 1 | 4 | 5 | 2 | 3 | 4 | 4 | 3 | 4 | 1 | 3 | 2 | 5 | 5 | 3 | 4 | 1 | 1 | 1 | 1 | 1 | 5 | 1 | 4 | 4 | 4 | 5 | 2 | 4 | 1 | 5 | 4 | 5 | 4 | 3
66 | 26 | 17 | 32 | 47 | 58 | 71 | 83 | 99 | 112 | 129 | 136 | 152 | 164 | 180 | 4 | 4 | 4 | 5 | 5 | 4 | 4 | 2 | 4 | 5 | 3 | 3 | 4 | 3 | 1 | 3 | 2 | 5 | 3 | 3 | 3 | 5 | 2 | 2 | 3 | 5 | 3 | 5 | 1 | 2 | 5 | 5 | 5 | 5 | 5 | 2 | 1 | 1 | 3 | 2 | 4 | 5 | 4 | 3 | 3 | 2 | 3 | 4 | 2 | 5 | 5 | 4
67 | 16 | 14 | 20 | 31 | 42 | 55 | 66 | 79 | 87 | 103 | 113 | 123 | 134 | 141 | 2 | 4 | 5 | 3 | 1 | 1 | 2 | 2 | 1 | 4 | 2 | 4 | 3 | 2 | 1 | 5 | 4 | 4 | 3 | 2 | 3 | 1 | 4 | 3 | 4 | 2 | 3 | 4 | 1 | 3 | 1 | 3 | 5 | 1 | 5 | 5 | 2 | 1 | 5 | 2 | 5 | 1 | 1 | 3 | 1 | 4 | 3 | 3 | 2 | 1 | 1 | 3
68 | 21 | 13 | 25 | 37 | 55 | 64 | 72 | 84 | 99 | 110 | 119 | 124 | 141 | 149 | 1 | 5 | 5 | 2 | 4 | 4 | 1 | 3 | 3 | 3 | 3 | 3 | 4 | 5 | 4 | 5 | 2 | 1 | 2 | 4 | 1 | 4 | 2 | 1 | 5 | 4 | 1 | 2 | 5 | 4 | 5 | 1 | 3 | 2 | 4 | 2 | 1 | 3 | 4 | 1 | 2 | 1 | 1 | 1 | 5 | 4 | 3 | 5 | 2 | 4 | 1 | 1
69 | 19 | 11 | 27 | 42 | 54 | 68 | 78 | 94 | 105 | 120 | 133 | 143 | 158 | 175 | 4 | 1 | 1 | 5 | 4 | 4 | 4 | 4 | 5 | 3 | 3 | 4 | 5 | 5 | 1 | 1 | 3 | 5 | 4 | 2 | 1 | 1 | 3 | 5 | 4 | 2 | 5 | 5 | 2 | 5 | 1 | 3 | 5 | 5 | 1 | 4 | 4 | 1 | 5 | 3 | 1 | 1 | 3 | 5 | 5 | 4 | 1 | 5 | 2 | 5 | 5 | 5
70 | 18 | 8 | 25 | 34 | 42 | 59 | 71 | 86 | 98 | 111 | 123 | 135 | 147 | 156 | 2 | 2 | 1 | 3 | 5 | 5 | 5 | 2 | 2 | 1 | 2 | 4 | 4 | 2 | 1 | 1 | 5 | 4 | 3 | 5 | 3 | 5 | 1 | 3 | 3 | 2 | 5 | 5 | 3 | 3 | 3 | 3 | 1 | 5 | 4 | 3 | 2 | 5 | 2 | 3 | 3 | 3 | 4 | 2 | 4 | 1 | 5 | 2 | 2 | 5 | 1 | 1
71 | 17 | 12 | 21 | 39 | 51 | 67 | 80 | 88 | 96 | 109 | 122 | 133 | 147 | 164 | 1 | 3 | 3 | 5 | 4 | 1 | 3 | 1 | 5 | 5 | 5 | 3 | 5 | 1 | 1 | 5 | 3 | 5 | 5 | 3 | 2 | 4 | 5 | 2 | 3 | 1 | 3 | 1 | 1 | 2 | 2 | 3 | 2 | 4 | 3 | 4 | 4 | 2 | 4 | 3 | 1 | 4 | 2 | 4 | 5 | 3 | 2 | 4 | 5 | 4 | 4 | 4
72 | 16 | 10 | 23 | 36 | 51 | 66 | 76 | 92 | 108 | 124 | 137 | 148 | 156 | 166 | 4 | 1 | 2 | 3 | 2 | 4 | 2 | 5 | 4 | 5 | 2 | 2 | 2 | 4 | 4 | 5 | 3 | 4 | 3 | 5 | 1 | 1 | 3 | 5 | 5 | 2 | 5 | 4 | 5 | 3 | 4 | 4 | 5 | 3 | 3 | 5 | 5 | 4 | 1 | 3 | 3 | 3 | 1 | 4 | 3 | 1 | 1 | 3 | 1 | 2 | 3 | 4
73 | 15 | 8 | 21 | 31 | 45 | 59 | 68 | 78 | 90 | 103 | 118 | 127 | 139 | 147 | 2 | 3 | 1 | 2 | 2 | 5 | 3 | 3 | 1 | 3 | 4 | 2 | 4 | 4 | 5 | 1 | 3 | 2 | 4 | 5 | 2 | 2 | 2 | 3 | 2 | 2 | 2 | 4 | 2 | 2 | 4 | 4 | 3 | 1 | 5 | 4 | 5 | 5 | 4 | 1 | 1 | 2 | 1 | 5 | 3 | 3 | 3 | 3 | 2 | 1 | 3 | 2
74 | 16 | 10 | 18 | 34 | 41 | 49 | 60 | 69 | 80 | 86 | 100 | 117 | 128 | 141 | 2 | 2 | 5 | 1 | 4 | 2 | 1 | 1 | 4 | 5 | 3 | 4 | 1 | 2 | 1 | 3 | 4 | 1 | 2 | 1 | 3 | 2 | 5 | 1 | 1 | 5 | 2 | 1 | 1 | 4 | 1 | 5 | 3 | 1 | 1 | 1 | 5 | 2 | 4 | 3 | 4 | 5 | 4 | 4 | 5 | 1 | 2 | 3 | 3 | 2 | 3 | 5
75 | 16 | 9 | 23 | 36 | 46 | 61 | 75 | 83 | 96 | 111 | 123 | 135 | 148 | 159 | 3 | 1 | 3 | 2 | 4 | 3 | 3 | 4 | 4 | 3 | 5 | 1 | 2 | 5 | 2 | 1 | 1 | 4 | 5 | 5 | 1 | 5 | 4 | 4 | 1 | 3 | 3 | 1 | 5 | 2 | 5 | 1 | 4 | 5 | 2 | 4 | 3 | 4 | 3 | 2 | 3 | 1 | 3 | 5 | 4 | 2 | 4 | 3 | 1 | 4 | 5 | 1
76 | 16 | 9 | 20 | 33 | 43 | 56 | 72 | 82 | 96 | 109 | 121 | 131 | 141 | 151 | 2 | 5 | 1 | 1 | 4 | 3 | 1 | 3 | 3 | 3 | 2 | 5 | 3 | 5 | 1 | 1 | 2 | 4 | 4 | 3 | 4 | 5 | 4 | 3 | 3 | 1 | 5 | 1 | 5 | 5 | 2 | 2 | 4 | 2 | 5 | 2 | 4 | 2 | 5 | 1 | 4 | 2 | 3 | 1 | 5 | 1 | 2 | 2 | 2 | 5 | 1 | 2
77 | 19 | 13 | 23 | 40 | 54 | 69 | 81 | 95 | 107 | 121 | 131 | 143 | 158 | 165 | 5 | 1 | 2 | 5 | 2 | 4 | 3 | 1 | 5 | 3 | 4 | 5 | 5 | 5 | 3 | 1 | 4 | 4 | 3 | 4 | 3 | 1 | 4 | 4 | 3 | 1 | 5 | 5 | 3 | 1 | 3 | 5 | 5 | 3 | 3 | 3 | 3 | 1 | 2 | 4 | 4 | 2 | 2 | 4 | 5 | 3 | 3 | 4 | 3 | 1 | 2 | 1
78 | 23 | 13 | 31 | 39 | 49 | 56 | 68 | 78 | 91 | 105 | 116 | 124 | 135 | 143 | 4 | 3 | 4 | 2 | 5 | 5 | 5 | 3 | 1 | 3 | 2 | 2 | 2 | 2 | 2 | 4 | 2 | 3 | 1 | 1 | 3 | 5 | 3 | 1 | 2 | 4 | 2 | 2 | 4 | 2 | 5 | 2 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 5 | 1 | 2 | 3 | 2 | 2 | 3 | 4 | 2 | 4 | 1 | 2 | 1
79 | 24 | 14 | 32 | 47 | 59 | 66 | 78 | 87 | 102 | 112 | 125 | 136 | 142 | 152 | 2 | 5 | 4 | 3 | 5 | 5 | 5 | 3 | 5 | 3 | 5 | 2 | 5 | 3 | 3 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 1 | 5 | 1 | 2 | 5 | 1 | 3 | 4 | 4 | 4 | 1 | 3 | 3 | 3 | 4 | 2 | 3 | 4 | 4 | 1 | 2 | 4 | 2 | 2 | 1 | 1 | 2 | 1 | 4 | 3
80 | 14 | 10 | 16 | 28 | 38 | 53 | 63 | 75 | 82 | 93 | 102 | 112 | 121 | 138 | 1 | 4 | 4 | 1 | 3 | 1 | 1 | 1 | 4 | 1 | 4 | 3 | 3 | 3 | 2 | 2 | 3 | 4 | 3 | 5 | 2 | 2 | 2 | 4 | 4 | 1 | 3 | 4 | 4 | 1 | 1 | 1 | 4 | 2 | 3 | 2 | 3 | 3 | 2 | 1 | 2 | 4 | 3 | 1 | 1 | 3 | 1 | 4 | 2 | 5 | 5 | 5
81 | 19 | 10 | 25 | 39 | 50 | 62 | 70 | 77 | 85 | 97 | 108 | 120 | 131 | 142 | 4 | 2 | 2 | 2 | 5 | 4 | 4 | 2 | 5 | 4 | 4 | 1 | 4 | 1 | 1 | 5 | 1 | 5 | 1 | 5 | 1 | 4 | 1 | 2 | 1 | 1 | 3 | 2 | 1 | 1 | 4 | 2 | 2 | 3 | 3 | 4 | 1 | 1 | 4 | 5 | 3 | 3 | 4 | 2 | 3 | 1 | 2 | 5 | 2 | 1 | 5 | 3
82 | 21 | 14 | 24 | 37 | 48 | 56 | 66 | 77 | 88 | 99 | 105 | 122 | 135 | 145 | 5 | 2 | 5 | 2 | 4 | 3 | 2 | 1 | 3 | 5 | 3 | 2 | 4 | 3 | 3 | 1 | 1 | 1 | 5 | 1 | 1 | 2 | 3 | 4 | 4 | 2 | 4 | 1 | 3 | 1 | 5 | 2 | 1 | 5 | 4 | 1 | 2 | 1 | 1 | 2 | 5 | 5 | 2 | 5 | 2 | 3 | 5 | 3 | 1 | 5 | 1 | 3
83 | 19 | 12 | 27 | 43 | 50 | 60 | 71 | 83 | 90 | 98 | 110 | 122 | 130 | 141 | 5 | 2 | 1 | 4 | 3 | 4 | 4 | 4 | 5 | 5 | 4 | 2 | 1 | 2 | 2 | 2 | 1 | 5 | 3 | 1 | 1 | 5 | 1 | 4 | 5 | 4 | 1 | 2 | 2 | 1 | 1 | 3 | 3 | 1 | 3 | 1 | 2 | 5 | 3 | 2 | 4 | 1 | 4 | 3 | 2 | 2 | 2 | 2 | 2 | 1 | 4 | 4
84 | 11 | 8 | 15 | 25 | 36 | 46 | 57 | 71 | 86 | 99 | 110 | 119 | 126 | 135 | 3 | 1 | 1 | 3 | 2 | 1 | 2 | 2 | 2 | 3 | 2 | 3 | 2 | 5 | 1 | 3 | 1 | 3 | 3 | 3 | 3 | 1 | 4 | 3 | 3 | 4 | 3 | 4 | 4 | 4 | 2 | 5 | 3 | 3 | 4 | 3 | 3 | 3 | 3 | 2 | 1 | 3 | 1 | 4 | 1 | 3 | 1 | 2 | 3 | 3 | 1 | 2
85 | 21 | 13 | 26 | 42 | 54 | 70 | 83 | 96 | 107 | 119 | 126 | 137 | 148 | 160 | 2 | 5 | 3 | 3 | 5 | 3 | 3 | 2 | 5 | 3 | 4 | 4 | 1 | 5 | 1 | 5 | 5 | 4 | 2 | 5 | 4 | 5 | 3 | 1 | 2 | 5 | 4 | 2 | 5 | 3 | 2 | 1 | 4 | 3 | 2 | 3 | 2 | 1 | 1 | 3 | 1 | 2 | 5 | 3 | 4 | 4 | 2 | 1 | 3 | 5 | 2 | 2
86 | 18 | 11 | 22 | 33 | 42 | 57 | 70 | 80 | 90 | 98 | 111 | 120 | 133 | 148 | 4 | 1 | 5 | 1 | 4 | 3 | 1 | 3 | 1 | 1 | 5 | 4 | 2 | 1 | 4 | 2 | 3 | 5 | 4 | 3 | 2 | 3 | 5 | 3 | 3 | 1 | 2 | 4 | 1 | 4 | 4 | 1 | 3 | 1 | 2 | 2 | 4 | 5 | 1 | 3 | 1 | 1 | 2 | 5 | 3 | 5 | 3 | 2 | 1 | 5 | 5 | 4
87 | 18 | 11 | 22 | 33 | 45 | 54 | 67 | 80 | 85 | 99 | 111 | 124 | 138 | 147 | 5 | 1 | 3 | 2 | 3 | 4 | 1 | 3 | 1 | 3 | 3 | 4 | 2 | 3 | 3 | 4 | 3 | 2 | 3 | 1 | 3 | 3 | 4 | 3 | 5 | 1 | 2 | 5 | 1 | 1 | 1 | 2 | 3 | 5 | 5 | 1 | 1 | 4 | 5 | 2 | 4 | 1 | 4 | 4 | 3 | 5 | 5 | 1 | 3 | 2 | 1 | 3
88 | 17 | 10 | 24 | 41 | 59 | 70 | 82 | 91 | 102 | 115 | 131 | 143 | 152 | 161 | 5 | 2 | 2 | 1 | 5 | 2 | 2 | 5 | 4 | 4 | 5 | 4 | 5 | 3 | 5 | 5 | 3 | 1 | 2 | 5 | 2 | 4 | 3 | 3 | 1 | 1 | 5 | 2 | 5 | 3 | 1 | 2 | 3 | 5 | 2 | 3 | 4 | 5 | 3 | 4 | 4 | 2 | 2 | 4 | 4 | 1 | 1 | 3 | 1 | 1 | 3 | 4
89 | 10 | 7 | 20 | 27 | 37 | 52 | 62 | 76 | 88 | 96 | 111 | 123 | 136 | 142 | 3 | 1 | 2 | 1 | 1 | 2 | 5 | 5 | 3 | 2 | 1 | 1 | 3 | 1 | 3 | 3 | 4 | 1 | 5 | 5 | 4 | 1 | 1 | 4 | 3 | 4 | 3 | 4 | 4 | 1 | 4 | 3 | 1 | 1 | 4 | 2 | 1 | 5 | 4 | 5 | 2 | 4 | 2 | 4 | 2 | 5 | 1 | 5 | 1 | 1 | 1 | 3
90 | 17 | 12 | 24 | 36 | 47 | 57 | 71 | 82 | 95 | 102 | 110 | 121 | 130 | 138 | 1 | 5 | 5 | 1 | 3 | 2 | 4 | 3 | 3 | 3 | 5 | 1 | 4 | 2 | 4 | 1 | 2 | 1 | 5 | 2 | 4 | 4 | 3 | 3 | 1 | 4 | 5 | 1 | 1 | 5 | 5 | 2 | 2 | 2 | 1 | 2 | 3 | 3 | 1 | 1 | 1 | 4 | 5 | 1 | 1 | 2 | 2 | 4 | 1 | 4 | 2 | 1
91 | 23 | 13 | 28 | 40 | 49 | 59 | 66 | 77 | 85 | 101 | 116 | 127 | 138 | 149 | 3 | 3 | 5 | 2 | 5 | 5 | 4 | 1 | 4 | 2 | 5 | 1 | 1 | 1 | 3 | 4 | 5 | 3 | 1 | 1 | 2 | 2 | 1 | 2 | 1 | 4 | 1 | 5 | 1 | 2 | 2 | 3 | 5 | 4 | 4 | 3 | 3 | 2 | 5 | 5 | 1 | 5 | 2 | 3 | 1 | 4 | 5 | 1 | 4 | 4 | 1 | 2
92 | 20 | 13 | 29 | 43 | 52 | 67 | 76 | 88 | 104 | 115 | 125 | 134 | 147 | 167 | 2 | 5 | 3 | 3 | 2 | 5 | 4 | 5 | 4 | 1 | 4 | 5 | 4 | 1 | 3 | 1 | 4 | 5 | 3 | 3 | 2 | 3 | 1 | 3 | 2 | 3 | 5 | 2 | 4 | 3 | 5 | 4 | 3 | 5 | 1 | 2 | 2 | 1 | 3 | 4 | 1 | 3 | 2 | 3 | 4 | 3 | 2 | 4 | 5 | 5 | 5 | 5
93 | 18 | 12 | 25 | 37 | 45 | 56 | 66 | 74 | 86 | 93 | 107 | 123 | 129 | 136 | 4 | 2 | 4 | 2 | 2 | 4 | 4 | 3 | 2 | 2 | 4 | 4 | 2 | 1 | 3 | 2 | 1 | 4 | 1 | 5 | 1 | 4 | 4 | 1 | 1 | 4 | 2 | 1 | 4 | 4 | 3 | 1 | 1 | 4 | 1 | 1 | 3 | 2 | 4 | 5 | 4 | 4 | 5 | 3 | 2 | 1 | 1 | 2 | 1 | 3 | 2 | 1
94 | 16 | 12 | 24 | 39 | 51 | 62 | 74 | 90 | 104 | 120 | 133 | 145 | 158 | 172 | 1 | 4 | 2 | 5 | 3 | 1 | 4 | 4 | 4 | 4 | 3 | 4 | 5 | 2 | 4 | 1 | 5 | 1 | 3 | 2 | 4 | 4 | 1 | 3 | 4 | 5 | 5 | 2 | 4 | 2 | 4 | 4 | 3 | 4 | 5 | 4 | 3 | 3 | 4 | 3 | 5 | 1 | 4 | 2 | 3 | 3 | 5 | 2 | 5 | 1 | 5 | 3
95 | 17 | 12 | 22 | 38 | 44 | 53 | 64 | 73 | 82 | 97 | 111 | 126 | 145 | 154 | 1 | 2 | 4 | 5 | 3 | 2 | 4 | 1 | 4 | 3 | 5 | 4 | 1 | 1 | 3 | 1 | 2 | 4 | 1 | 2 | 2 | 5 | 1 | 3 | 4 | 3 | 1 | 1 | 2 | 1 | 3 | 3 | 5 | 4 | 2 | 4 | 5 | 1 | 5 | 3 | 3 | 5 | 5 | 2 | 4 | 5 | 5 | 5 | 2 | 1 | 5 | 1
96 | 27 | 17 | 33 | 46 | 57 | 71 | 80 | 92 | 106 | 116 | 126 | 139 | 149 | 162 | 3 | 4 | 5 | 5 | 5 | 5 | 2 | 4 | 5 | 1 | 4 | 3 | 5 | 2 | 2 | 2 | 3 | 2 | 5 | 4 | 1 | 4 | 1 | 3 | 3 | 3 | 1 | 5 | 5 | 2 | 5 | 2 | 2 | 2 | 1 | 5 | 2 | 2 | 5 | 1 | 5 | 2 | 4 | 2 | 5 | 3 | 1 | 1 | 5 | 2 | 2 | 4
97 | 24 | 14 | 31 | 44 | 56 | 67 | 81 | 93 | 106 | 117 | 128 | 142 | 152 | 165 | 3 | 2 | 5 | 4 | 5 | 5 | 3 | 4 | 2 | 2 | 5 | 4 | 1 | 3 | 4 | 4 | 2 | 2 | 3 | 4 | 4 | 1 | 5 | 4 | 2 | 3 | 3 | 4 | 4 | 3 | 4 | 2 | 2 | 4 | 3 | 2 | 3 | 4 | 2 | 2 | 3 | 5 | 5 | 1 | 4 | 2 | 2 | 2 | 3 | 4 | 3 | 3
98 | 19 | 10 | 25 | 31 | 45 | 55 | 66 | 86 | 105 | 121 | 135 | 143 | 153 | 161 | 5 | 1 | 3 | 1 | 4 | 5 | 2 | 4 | 1 | 2 | 2 | 1 | 2 | 5 | 3 | 4 | 3 | 4 | 1 | 2 | 5 | 3 | 1 | 2 | 5 | 5 | 5 | 5 | 4 | 5 | 5 | 5 | 5 | 5 | 1 | 5 | 2 | 5 | 3 | 4 | 2 | 1 | 2 | 3 | 4 | 1 | 4 | 1 | 1 | 5 | 1 | 1
99 | 14 | 10 | 18 | 27 | 42 | 54 | 64 | 75 | 79 | 87 | 100 | 109 | 125 | 136 | 3 | 3 | 3 | 1 | 3 | 1 | 1 | 3 | 3 | 2 | 3 | 1 | 3 | 5 | 4 | 3 | 3 | 4 | 2 | 3 | 2 | 4 | 1 | 3 | 5 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 3 | 2 | 5 | 3 | 1 | 2 | 3 | 3 | 5 | 5 | 3 | 3 | 5 | 2 | 3 | 1
100 | 17 | 13 | 20 | 32 | 45 | 56 | 69 | 78 | 91 | 100 | 117 | 125 | 132 | 143 | 3 | 3 | 2 | 5 | 2 | 2 | 2 | 1 | 3 | 4 | 1 | 4 | 1 | 4 | 5 | 3 | 1 | 4 | 4 | 2 | 2 | 5 | 3 | 3 | 2 | 2 | 1 | 4 | 5 | 5 | 1 | 2 | 1 | 2 | 5 | 1 | 4 | 5 | 5 | 3 | 1 | 1 | 1 | 5 | 2 | 2 | 1 | 2 | 1 | 4 | 1 | 5
101 | 20 | 16 | 23 | 32 | 46 | 58 | 69 | 79 | 91 | 101 | 114 | 131 | 141 | 153 | 5 | 3 | 5 | 3 | 2 | 2 | 2 | 1 | 3 | 2 | 1 | 3 | 5 | 4 | 3 | 2 | 4 | 1 | 4 | 3 | 1 | 4 | 5 | 1 | 4 | 2 | 3 | 1 | 3 | 2 | 4 | 3 | 3 | 4 | 1 | 2 | 5 | 5 | 2 | 1 | 5 | 4 | 4 | 4 | 3 | 3 | 2 | 2 | 4 | 4 | 1 | 3
102 | 24 | 14 | 30 | 44 | 59 | 72 | 78 | 90 | 102 | 113 | 122 | 131 | 147 | 160 | 3 | 5 | 1 | 5 | 5 | 5 | 2 | 4 | 2 | 5 | 4 | 3 | 5 | 3 | 2 | 5 | 1 | 5 | 4 | 3 | 2 | 1 | 2 | 1 | 5 | 4 | 2 | 1 | 2 | 3 | 4 | 3 | 2 | 2 | 4 | 3 | 2 | 3 | 3 | 1 | 2 | 1 | 4 | 2 | 4 | 4 | 3 | 5 | 3 | 3 | 3 | 4
103 | 20 | 13 | 25 | 40 | 56 | 69 | 79 | 96 | 108 | 124 | 137 | 153 | 162 | 175 | 4 | 5 | 3 | 1 | 5 | 2 | 3 | 2 | 4 | 4 | 4 | 3 | 1 | 5 | 5 | 5 | 3 | 5 | 3 | 2 | 3 | 4 | 2 | 1 | 4 | 4 | 5 | 4 | 4 | 1 | 5 | 2 | 5 | 1 | 5 | 5 | 2 | 5 | 4 | 2 | 5 | 2 | 4 | 5 | 2 | 1 | 3 | 3 | 3 | 5 | 4 | 1
104 | 18 | 11 | 26 | 35 | 44 | 54 | 63 | 69 | 81 | 95 | 108 | 117 | 131 | 147 | 3 | 5 | 1 | 2 | 3 | 4 | 4 | 4 | 2 | 2 | 2 | 3 | 2 | 2 | 4 | 1 | 1 | 1 | 4 | 4 | 4 | 3 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 4 | 2 | 3 | 2 | 5 | 4 | 3 | 5 | 3 | 4 | 1 | 2 | 2 | 1 | 4 | 4 | 3 | 5 | 2 | 3 | 3 | 5 | 5
105 | 22 | 15 | 27 | 39 | 58 | 72 | 88 | 100 | 105 | 120 | 134 | 150 | 160 | 172 | 4 | 5 | 2 | 4 | 3 | 4 | 3 | 2 | 5 | 2 | 2 | 3 | 4 | 5 | 5 | 5 | 1 | 5 | 3 | 5 | 5 | 5 | 2 | 4 | 3 | 2 | 3 | 4 | 1 | 2 | 1 | 1 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 5 | 4 | 4 | 3 | 5 | 1 | 2 | 2 | 5 | 3 | 2 | 2 | 5
106 | 18 | 11 | 23 | 35 | 47 | 57 | 69 | 81 | 95 | 108 | 117 | 129 | 142 | 153 | 5 | 4 | 1 | 1 | 4 | 3 | 4 | 1 | 2 | 4 | 2 | 4 | 2 | 3 | 3 | 4 | 4 | 3 | 2 | 1 | 5 | 4 | 1 | 2 | 2 | 4 | 3 | 3 | 4 | 3 | 2 | 5 | 3 | 4 | 5 | 1 | 2 | 2 | 1 | 4 | 1 | 1 | 5 | 5 | 2 | 4 | 4 | 3 | 5 | 4 | 1 | 1
107 | 14 | 7 | 23 | 33 | 48 | 57 | 74 | 87 | 101 | 117 | 130 | 139 | 149 | 163 | 1 | 1 | 1 | 4 | 4 | 3 | 4 | 5 | 2 | 2 | 2 | 4 | 5 | 3 | 2 | 5 | 2 | 1 | 4 | 2 | 4 | 5 | 4 | 4 | 1 | 5 | 3 | 4 | 4 | 3 | 4 | 3 | 3 | 3 | 5 | 5 | 4 | 5 | 1 | 3 | 4 | 1 | 3 | 1 | 2 | 2 | 3 | 3 | 4 | 2 | 4 | 4
108 | 19 | 15 | 26 | 36 | 48 | 67 | 79 | 94 | 108 | 121 | 133 | 147 | 160 | 171 | 2 | 3 | 5 | 5 | 1 | 3 | 4 | 3 | 3 | 1 | 4 | 2 | 5 | 1 | 3 | 3 | 4 | 5 | 5 | 5 | 4 | 4 | 2 | 2 | 4 | 4 | 2 | 5 | 4 | 3 | 5 | 2 | 2 | 5 | 1 | 5 | 4 | 4 | 3 | 1 | 4 | 2 | 4 | 4 | 2 | 3 | 3 | 5 | 3 | 2 | 2 | 4
109 | 13 | 9 | 22 | 31 | 42 | 52 | 60 | 74 | 84 | 97 | 110 | 123 | 137 | 152 | 5 | 1 | 1 | 2 | 3 | 1 | 4 | 5 | 1 | 1 | 4 | 3 | 4 | 4 | 2 | 1 | 2 | 4 | 3 | 1 | 1 | 5 | 1 | 1 | 2 | 4 | 3 | 5 | 3 | 2 | 4 | 1 | 3 | 1 | 5 | 4 | 4 | 2 | 3 | 4 | 2 | 5 | 3 | 3 | 1 | 5 | 4 | 4 | 4 | 1 | 5 | 5
110 | 13 | 10 | 15 | 27 | 37 | 47 | 56 | 68 | 81 | 87 | 101 | 115 | 128 | 142 | 4 | 4 | 1 | 1 | 2 | 1 | 1 | 1 | 5 | 5 | 1 | 1 | 4 | 1 | 1 | 4 | 2 | 1 | 4 | 3 | 2 | 1 | 5 | 1 | 3 | 2 | 4 | 3 | 4 | 1 | 3 | 5 | 1 | 1 | 1 | 3 | 3 | 2 | 4 | 5 | 4 | 5 | 2 | 3 | 4 | 2 | 5 | 2 | 2 | 3 | 5 | 4
111 | 17 | 15 | 22 | 35 | 46 | 55 | 65 | 74 | 83 | 97 | 110 | 123 | 132 | 144 | 2 | 3 | 5 | 5 | 1 | 1 | 4 | 1 | 5 | 2 | 5 | 1 | 3 | 2 | 5 | 1 | 1 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 1 | 3 | 5 | 1 | 2 | 1 | 5 | 5 | 2 | 2 | 4 | 3 | 5 | 1 | 5 | 5 | 2 | 1 | 1 | 2 | 2 | 4 | 1 | 2 | 5 | 4
112 | 24 | 17 | 31 | 40 | 49 | 57 | 67 | 79 | 91 | 108 | 119 | 129 | 139 | 152 | 3 | 5 | 5 | 4 | 3 | 4 | 2 | 5 | 1 | 5 | 1 | 2 | 1 | 4 | 1 | 3 | 2 | 1 | 1 | 4 | 1 | 5 | 1 | 3 | 1 | 1 | 5 | 5 | 2 | 4 | 2 | 4 | 4 | 4 | 4 | 5 | 4 | 2 | 4 | 1 | 2 | 3 | 3 | 2 | 1 | 3 | 5 | 1 | 3 | 3 | 4 | 3
113 | 19 | 11 | 24 | 38 | 51 | 66 | 80 | 89 | 96 | 110 | 129 | 144 | 155 | 166 | 3 | 4 | 1 | 3 | 4 | 4 | 4 | 1 | 4 | 5 | 1 | 4 | 3 | 5 | 3 | 2 | 1 | 5 | 4 | 5 | 4 | 4 | 1 | 5 | 2 | 2 | 4 | 1 | 4 | 1 | 1 | 1 | 5 | 3 | 2 | 4 | 5 | 4 | 5 | 5 | 1 | 4 | 5 | 5 | 1 | 4 | 1 | 5 | 3 | 2 | 3 | 3
114 | 16 | 10 | 20 | 33 | 45 | 58 | 69 | 84 | 98 | 106 | 121 | 136 | 151 | 162 | 2 | 1 | 4 | 3 | 3 | 3 | 2 | 2 | 5 | 2 | 3 | 3 | 2 | 3 | 2 | 5 | 4 | 4 | 3 | 2 | 4 | 1 | 3 | 3 | 2 | 4 | 5 | 4 | 4 | 5 | 1 | 4 | 1 | 3 | 3 | 1 | 2 | 5 | 4 | 4 | 5 | 4 | 2 | 4 | 3 | 3 | 4 | 5 | 1 | 4 | 1 | 5
115 | 19 | 13 | 27 | 38 | 49 | 61 | 77 | 92 | 104 | 119 | 133 | 146 | 160 | 173 | 4 | 5 | 2 | 2 | 5 | 1 | 4 | 4 | 3 | 3 | 4 | 1 | 1 | 5 | 3 | 2 | 2 | 4 | 2 | 4 | 3 | 5 | 5 | 3 | 5 | 3 | 5 | 2 | 3 | 2 | 2 | 5 | 4 | 2 | 4 | 5 | 4 | 4 | 3 | 3 | 1 | 2 | 5 | 5 | 4 | 3 | 2 | 5 | 3 | 2 | 3 | 5
116 | 18 | 12 | 23 | 33 | 49 | 58 | 69 | 85 | 102 | 112 | 124 | 138 | 153 | 166 | 1 | 5 | 2 | 4 | 5 | 1 | 2 | 3 | 1 | 5 | 2 | 2 | 5 | 1 | 5 | 5 | 4 | 2 | 1 | 2 | 1 | 4 | 5 | 1 | 3 | 4 | 4 | 5 | 5 | 5 | 3 | 4 | 3 | 1 | 4 | 2 | 4 | 4 | 1 | 3 | 5 | 3 | 5 | 1 | 3 | 3 | 5 | 4 | 2 | 3 | 3 | 5
117 | 20 | 13 | 24 | 31 | 41 | 55 | 62 | 80 | 92 | 101 | 117 | 128 | 137 | 150 | 5 | 4 | 3 | 1 | 3 | 4 | 2 | 2 | 1 | 1 | 3 | 2 | 4 | 3 | 2 | 1 | 4 | 3 | 5 | 2 | 1 | 1 | 3 | 2 | 4 | 4 | 5 | 5 | 4 | 3 | 1 | 4 | 2 | 1 | 5 | 1 | 4 | 3 | 5 | 4 | 3 | 5 | 2 | 1 | 5 | 2 | 1 | 1 | 4 | 4 | 4 | 1
118 | 21 | 13 | 28 | 37 | 47 | 60 | 75 | 84 | 97 | 112 | 122 | 135 | 144 | 160 | 2 | 5 | 3 | 3 | 5 | 3 | 2 | 5 | 5 | 1 | 1 | 2 | 3 | 1 | 5 | 1 | 5 | 3 | 3 | 2 | 5 | 2 | 5 | 3 | 3 | 2 | 3 | 1 | 4 | 3 | 3 | 3 | 4 | 3 | 4 | 4 | 1 | 2 | 5 | 2 | 2 | 2 | 5 | 4 | 1 | 3 | 3 | 2 | 5 | 4 | 4 | 3
119 | 20 | 11 | 28 | 37 | 50 | 65 | 78 | 88 | 94 | 103 | 111 | 121 | 131 | 140 | 1 | 3 | 4 | 3 | 5 | 4 | 5 | 3 | 3 | 2 | 2 | 2 | 1 | 4 | 5 | 3 | 5 | 4 | 5 | 1 | 4 | 1 | 4 | 4 | 5 | 2 | 2 | 1 | 1 | 1 | 3 | 1 | 5 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 1 | 4 | 3 | 2 | 4 | 1 | 1 | 4 | 2 | 2 | 4 | 1
120 | 11 | 8 | 16 | 28 | 35 | 49 | 60 | 71 | 84 | 95 | 108 | 118 | 130 | 146 | 1 | 3 | 3 | 1 | 1 | 2 | 1 | 4 | 4 | 1 | 4 | 3 | 3 | 1 | 2 | 1 | 5 | 4 | 4 | 1 | 1 | 2 | 3 | 5 | 1 | 5 | 3 | 2 | 3 | 4 | 5 | 1 | 4 | 1 | 5 | 1 | 4 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 1 | 3 | 4 | 4 | 4 | 5 | 5 | 2
121 | 23 | 15 | 29 | 37 | 51 | 65 | 83 | 94 | 107 | 119 | 129 | 144 | 155 | 172 | 5 | 5 | 4 | 1 | 4 | 4 | 1 | 5 | 1 | 1 | 3 | 3 | 2 | 4 | 3 | 5 | 3 | 5 | 5 | 1 | 5 | 3 | 5 | 5 | 2 | 5 | 3 | 1 | 5 | 5 | 2 | 1 | 3 | 2 | 5 | 2 | 2 | 5 | 1 | 2 | 5 | 1 | 4 | 5 | 2 | 1 | 3 | 5 | 4 | 5 | 5 | 3
122 | 22 | 12 | 28 | 40 | 50 | 61 | 72 | 85 | 99 | 111 | 122 | 133 | 142 | 153 | 5 | 2 | 2 | 3 | 5 | 5 | 2 | 4 | 2 | 4 | 5 | 1 | 4 | 3 | 2 | 1 | 1 | 2 | 5 | 3 | 3 | 3 | 4 | 1 | 2 | 5 | 5 | 1 | 5 | 3 | 2 | 4 | 2 | 3 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 3 | 1 | 3 | 1 | 5 | 1 | 2 | 3 | 4 | 3 | 1
123 | 19 | 10 | 25 | 37 | 47 | 58 | 71 | 86 | 99 | 117 | 130 | 142 | 151 | 161 | 3 | 1 | 2 | 4 | 4 | 5 | 2 | 4 | 2 | 4 | 4 | 2 | 1 | 1 | 4 | 4 | 3 | 2 | 5 | 1 | 3 | 5 | 1 | 4 | 3 | 5 | 5 | 2 | 4 | 4 | 1 | 4 | 5 | 4 | 5 | 4 | 3 | 3 | 4 | 3 | 2 | 2 | 5 | 3 | 1 | 3 | 3 | 2 | 4 | 1 | 3 | 2
124 | 22 | 15 | 31 | 40 | 51 | 62 | 72 | 89 | 99 | 106 | 112 | 126 | 142 | 151 | 2 | 5 | 3 | 5 | 3 | 4 | 4 | 5 | 1 | 3 | 4 | 1 | 4 | 5 | 1 | 1 | 1 | 4 | 2 | 4 | 5 | 1 | 2 | 2 | 5 | 4 | 4 | 4 | 4 | 1 | 1 | 4 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 2 | 5 | 3 | 4 | 4 | 5 | 3 | 4 | 2 | 1 | 3 | 3
125 | 19 | 11 | 27 | 37 | 46 | 56 | 67 | 86 | 100 | 115 | 128 | 140 | 157 | 172 | 3 | 2 | 1 | 5 | 4 | 4 | 3 | 5 | 4 | 1 | 1 | 4 | 1 | 1 | 2 | 5 | 2 | 4 | 2 | 2 | 5 | 2 | 3 | 1 | 5 | 5 | 5 | 4 | 3 | 5 | 2 | 4 | 1 | 5 | 4 | 5 | 5 | 5 | 1 | 2 | 2 | 5 | 4 | 1 | 4 | 3 | 5 | 5 | 4 | 5 | 5 | 1
126 | 14 | 10 | 20 | 30 | 40 | 49 | 59 | 73 | 84 | 93 | 108 | 119 | 132 | 142 | 4 | 1 | 3 | 2 | 3 | 1 | 3 | 3 | 1 | 4 | 4 | 1 | 2 | 3 | 2 | 3 | 1 | 2 | 5 | 1 | 1 | 2 | 3 | 4 | 3 | 2 | 4 | 5 | 3 | 3 | 4 | 1 | 5 | 2 | 1 | 1 | 5 | 4 | 2 | 4 | 4 | 2 | 4 | 1 | 1 | 4 | 4 | 4 | 5 | 1 | 2 | 2
127 | 17 | 10 | 21 | 32 | 48 | 61 | 76 | 88 | 94 | 107 | 116 | 128 | 141 | 153 | 5 | 1 | 2 | 2 | 2 | 5 | 3 | 1 | 3 | 1 | 5 | 2 | 5 | 5 | 2 | 4 | 4 | 5 | 2 | 2 | 5 | 3 | 2 | 5 | 3 | 2 | 5 | 2 | 1 | 2 | 1 | 2 | 4 | 2 | 4 | 3 | 1 | 3 | 4 | 1 | 2 | 5 | 4 | 1 | 5 | 2 | 5 | 1 | 1 | 5 | 2 | 4
128 | 18 | 13 | 25 | 42 | 55 | 61 | 71 | 83 | 96 | 109 | 121 | 134 | 145 | 160 | 4 | 4 | 4 | 1 | 3 | 2 | 3 | 4 | 4 | 5 | 5 | 3 | 2 | 3 | 5 | 3 | 2 | 1 | 1 | 2 | 1 | 3 | 5 | 1 | 1 | 4 | 4 | 3 | 4 | 1 | 4 | 4 | 2 | 3 | 3 | 5 | 1 | 5 | 2 | 4 | 4 | 4 | 4 | 1 | 4 | 1 | 3 | 3 | 3 | 5 | 2 | 5
129 | 17 | 10 | 27 | 38 | 50 | 61 | 70 | 79 | 92 | 105 | 121 | 133 | 143 | 155 | 5 | 1 | 1 | 3 | 5 | 2 | 5 | 5 | 2 | 3 | 5 | 1 | 5 | 1 | 5 | 1 | 3 | 4 | 2 | 2 | 5 | 2 | 1 | 1 | 1 | 2 | 4 | 2 | 3 | 5 | 3 | 2 | 5 | 2 | 2 | 4 | 4 | 5 | 2 | 5 | 1 | 1 | 5 | 5 | 4 | 2 | 1 | 3 | 5 | 1 | 3 | 3
130 | 16 | 8 | 25 | 37 | 48 | 62 | 76 | 89 | 104 | 119 | 131 | 148 | 162 | 174 | 3 | 2 | 1 | 2 | 4 | 4 | 4 | 5 | 4 | 2 | 1 | 5 | 3 | 3 | 1 | 4 | 2 | 4 | 4 | 4 | 5 | 2 | 3 | 4 | 2 | 3 | 4 | 4 | 2 | 4 | 4 | 5 | 5 | 2 | 4 | 4 | 2 | 1 | 4 | 5 | 4 | 4 | 4 | 5 | 1 | 5 | 4 | 4 | 4 | 3 | 2 | 3
131 | 17 | 9 | 23 | 32 | 46 | 55 | 68 | 78 | 90 | 106 | 116 | 127 | 137 | 149 | 5 | 1 | 1 | 2 | 3 | 5 | 5 | 1 | 2 | 1 | 3 | 3 | 5 | 3 | 4 | 2 | 3 | 2 | 1 | 3 | 4 | 1 | 4 | 4 | 1 | 3 | 4 | 2 | 4 | 5 | 1 | 2 | 5 | 5 | 1 | 5 | 3 | 2 | 1 | 4 | 2 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 1 | 2 | 5 | 4
132 | 19 | 11 | 22 | 34 | 46 | 56 | 70 | 81 | 97 | 107 | 124 | 136 | 147 | 161 | 3 | 1 | 5 | 2 | 4 | 4 | 1 | 2 | 3 | 4 | 1 | 4 | 4 | 4 | 1 | 3 | 4 | 3 | 1 | 2 | 4 | 5 | 2 | 3 | 5 | 3 | 2 | 1 | 5 | 3 | 3 | 5 | 2 | 1 | 4 | 3 | 5 | 5 | 3 | 4 | 1 | 2 | 4 | 5 | 3 | 1 | 2 | 5 | 5 | 3 | 1 | 5
133 | 18 | 10 | 21 | 33 | 46 | 57 | 68 | 81 | 93 | 102 | 109 | 120 | 131 | 142 | 2 | 5 | 2 | 1 | 3 | 5 | 2 | 1 | 1 | 2 | 5 | 4 | 2 | 4 | 3 | 4 | 5 | 2 | 1 | 3 | 3 | 4 | 1 | 3 | 1 | 5 | 5 | 2 | 4 | 1 | 3 | 4 | 2 | 1 | 5 | 1 | 4 | 1 | 1 | 1 | 5 | 1 | 1 | 4 | 1 | 4 | 1 | 5 | 5 | 2 | 3 | 1
134 | 20 | 12 | 27 | 37 | 50 | 63 | 77 | 85 | 92 | 105 | 118 | 130 | 147 | 159 | 1 | 5 | 2 | 4 | 4 | 4 | 3 | 4 | 4 | 1 | 1 | 4 | 5 | 2 | 2 | 4 | 3 | 5 | 2 | 3 | 4 | 5 | 4 | 1 | 5 | 1 | 1 | 1 | 2 | 1 | 3 | 1 | 2 | 5 | 3 | 3 | 3 | 1 | 5 | 4 | 3 | 3 | 1 | 5 | 3 | 5 | 5 | 4 | 4 | 1 | 4 | 3
135 | 16 | 12 | 21 | 29 | 39 | 49 | 60 | 71 | 87 | 96 | 104 | 116 | 127 | 135 | 1 | 4 | 5 | 2 | 3 | 1 | 4 | 1 | 2 | 1 | 4 | 1 | 1 | 2 | 4 | 3 | 3 | 3 | 3 | 1 | 4 | 1 | 2 | 4 | 2 | 4 | 1 | 4 | 4 | 4 | 5 | 3 | 1 | 5 | 1 | 2 | 2 | 2 | 3 | 1 | 3 | 5 | 1 | 3 | 1 | 1 | 4 | 5 | 1 | 3 | 3 | 1
136 | 24 | 15 | 31 | 44 | 56 | 67 | 83 | 97 | 111 | 123 | 135 | 148 | 159 | 173 | 4 | 1 | 5 | 5 | 4 | 5 | 2 | 5 | 2 | 5 | 2 | 4 | 4 | 1 | 3 | 4 | 1 | 2 | 3 | 5 | 5 | 4 | 5 | 2 | 4 | 4 | 5 | 1 | 5 | 4 | 1 | 4 | 4 | 2 | 3 | 3 | 3 | 3 | 4 | 2 | 4 | 3 | 2 | 4 | 4 | 2 | 2 | 3 | 4 | 3 | 4 | 3
137 | 18 | 12 | 21 | 36 | 52 | 67 | 84 | 92 | 107 | 122 | 133 | 145 | 161 | 170 | 3 | 4 | 3 | 2 | 5 | 1 | 1 | 2 | 5 | 1 | 4 | 5 | 1 | 5 | 5 | 5 | 3 | 4 | 3 | 5 | 5 | 5 | 4 | 3 | 2 | 2 | 1 | 3 | 5 | 2 | 4 | 4 | 4 | 2 | 5 | 4 | 3 | 1 | 2 | 5 | 4 | 2 | 5 | 1 | 4 | 4 | 3 | 5 | 3 | 2 | 2 | 2
138 | 19 | 15 | 29 | 41 | 53 | 67 | 83 | 96 | 109 | 120 | 133 | 143 | 156 | 167 | 5 | 4 | 3 | 3 | 1 | 3 | 5 | 5 | 4 | 2 | 1 | 5 | 3 | 3 | 4 | 2 | 4 | 4 | 4 | 2 | 2 | 5 | 4 | 5 | 3 | 2 | 4 | 4 | 1 | 5 | 4 | 3 | 4 | 1 | 5 | 1 | 2 | 5 | 1 | 5 | 5 | 1 | 3 | 1 | 4 | 1 | 5 | 3 | 3 | 3 | 2 | 3
139 | 20 | 15 | 29 | 38 | 48 | 60 | 70 | 83 | 97 | 107 | 115 | 124 | 137 | 148 | 5 | 5 | 2 | 3 | 3 | 2 | 5 | 4 | 1 | 3 | 4 | 1 | 2 | 2 | 4 | 2 | 5 | 2 | 4 | 1 | 2 | 4 | 1 | 3 | 2 | 5 | 2 | 4 | 5 | 1 | 5 | 3 | 4 | 2 | 2 | 2 | 1 | 5 | 1 | 1 | 1 | 4 | 1 | 3 | 5 | 3 | 1 | 4 | 1 | 4 | 2 | 4
140 | 20 | 13 | 25 | 35 | 48 | 59 | 70 | 86 | 97 | 105 | 117 | 131 | 146 | 160 | 5 | 3 | 2 | 3 | 5 | 2 | 4 | 1 | 4 | 1 | 4 | 1 | 1 | 4 | 4 | 4 | 5 | 1 | 4 | 1 | 1 | 5 | 4 | 1 | 5 | 2 | 4 | 5 | 2 | 3 | 5 | 1 | 2 | 3 | 2 | 1 | 2 | 5 | 4 | 1 | 5 | 1 | 5 | 3 | 4 | 5 | 3 | 3 | 3 | 4 | 2 | 5
141 | 22 | 17 | 28 | 39 | 52 | 62 | 72 | 84 | 94 | 103 | 112 | 120 | 132 | 143 | 2 | 5 | 5 | 5 | 1 | 4 | 4 | 2 | 1 | 4 | 5 | 1 | 2 | 2 | 5 | 4 | 3 | 3 | 1 | 3 | 2 | 2 | 3 | 3 | 2 | 5 | 1 | 4 | 1 | 1 | 5 | 3 | 3 | 1 | 1 | 4 | 4 | 2 | 2 | 1 | 2 | 3 | 2 | 1 | 1 | 3 | 4 | 4 | 2 | 3 | 5 | 1
142 | 10 | 5 | 17 | 31 | 41 | 51 | 62 | 71 | 86 | 93 | 106 | 116 | 125 | 138 | 1 | 2 | 1 | 1 | 3 | 2 | 2 | 5 | 1 | 5 | 5 | 3 | 2 | 3 | 1 | 4 | 2 | 1 | 5 | 2 | 2 | 2 | 5 | 2 | 4 | 1 | 1 | 3 | 5 | 2 | 3 | 5 | 3 | 1 | 1 | 2 | 5 | 5 | 1 | 2 | 1 | 4 | 2 | 3 | 2 | 1 | 2 | 4 | 3 | 5 | 3 | 2
143 | 21 | 14 | 27 | 42 | 52 | 59 | 71 | 84 | 98 | 107 | 116 | 129 | 140 | 149 | 4 | 4 | 5 | 1 | 3 | 4 | 4 | 2 | 3 | 4 | 3 | 5 | 4 | 1 | 2 | 3 | 1 | 4 | 1 | 1 | 1 | 4 | 2 | 5 | 5 | 5 | 2 | 1 | 2 | 3 | 5 | 4 | 1 | 5 | 1 | 2 | 2 | 1 | 4 | 2 | 4 | 2 | 3 | 4 | 3 | 2 | 4 | 2 | 3 | 3 | 2 | 1
144 | 21 | 15 | 27 | 41 | 47 | 63 | 80 | 93 | 103 | 108 | 122 | 132 | 143 | 155 | 5 | 3 | 5 | 2 | 3 | 3 | 1 | 5 | 5 | 4 | 1 | 4 | 1 | 2 | 2 | 1 | 3 | 4 | 5 | 4 | 3 | 5 | 5 | 4 | 5 | 4 | 1 | 3 | 1 | 1 | 3 | 5 | 1 | 1 | 2 | 1 | 4 | 3 | 2 | 5 | 1 | 1 | 3 | 5 | 1 | 3 | 5 | 2 | 4 | 2 | 3 | 3
145 | 15 | 10 | 22 | 37 | 53 | 64 | 78 | 86 | 96 | 108 | 115 | 132 | 141 | 157 | 5 | 3 | 1 | 1 | 1 | 4 | 5 | 2 | 5 | 5 | 1 | 4 | 5 | 3 | 3 | 5 | 3 | 2 | 4 | 2 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 3 | 2 | 3 | 2 | 1 | 4 | 4 | 3 | 3 | 2 | 1 | 1 | 4 | 4 | 5 | 4 | 2 | 2 | 4 | 1 | 3 | 4 | 4 | 5
146 | 15 | 13 | 23 | 32 | 45 | 53 | 63 | 80 | 95 | 110 | 126 | 138 | 150 | 159 | 4 | 4 | 2 | 3 | 1 | 1 | 4 | 4 | 1 | 2 | 1 | 5 | 3 | 5 | 4 | 1 | 1 | 3 | 3 | 1 | 5 | 2 | 1 | 2 | 4 | 5 | 3 | 5 | 2 | 5 | 5 | 3 | 5 | 1 | 5 | 4 | 5 | 1 | 5 | 5 | 2 | 5 | 2 | 3 | 4 | 1 | 4 | 3 | 2 | 5 | 1 | 1
147 | 21 | 15 | 27 | 40 | 45 | 54 | 64 | 74 | 89 | 99 | 107 | 121 | 132 | 144 | 2 | 5 | 4 | 4 | 5 | 1 | 2 | 4 | 1 | 5 | 5 | 2 | 1 | 1 | 1 | 2 | 1 | 2 | 2 | 4 | 5 | 1 | 3 | 1 | 1 | 3 | 5 | 1 | 2 | 5 | 3 | 5 | 4 | 2 | 3 | 1 | 1 | 2 | 2 | 3 | 2 | 4 | 4 | 4 | 5 | 1 | 4 | 1 | 3 | 5 | 3 | 1
148 | 17 | 9 | 23 | 36 | 52 | 65 | 82 | 92 | 107 | 124 | 139 | 152 | 166 | 178 | 4 | 1 | 3 | 1 | 5 | 3 | 5 | 1 | 4 | 5 | 2 | 2 | 4 | 5 | 3 | 4 | 5 | 4 | 3 | 1 | 2 | 5 | 5 | 5 | 3 | 1 | 4 | 2 | 5 | 4 | 4 | 2 | 5 | 4 | 4 | 4 | 4 | 2 | 4 | 5 | 3 | 5 | 3 | 2 | 2 | 4 | 4 | 4 | 1 | 2 | 5 | 4
149 | 14 | 10 | 20 | 37 | 50 | 65 | 79 | 92 | 100 | 109 | 122 | 134 | 143 | 157 | 1 | 3 | 2 | 4 | 1 | 3 | 4 | 2 | 5 | 4 | 5 | 3 | 1 | 5 | 2 | 5 | 5 | 5 | 3 | 2 | 1 | 4 | 4 | 5 | 5 | 4 | 1 | 3 | 1 | 1 | 5 | 1 | 1 | 3 | 4 | 1 | 3 | 4 | 1 | 5 | 2 | 4 | 3 | 3 | 2 | 1 | 4 | 2 | 3 | 4 | 4 | 3
150 | 28 | 18 | 34 | 47 | 58 | 69 | 81 | 96 | 107 | 120 | 130 | 144 | 161 | 174 | 5 | 4 | 5 | 4 | 5 | 5 | 3 | 3 | 3 | 2 | 3 | 5 | 2 | 1 | 5 | 3 | 2 | 3 | 2 | 4 | 2 | 3 | 5 | 2 | 5 | 3 | 3 | 4 | 4 | 4 | 1 | 2 | 3 | 2 | 3 | 5 | 1 | 1 | 4 | 4 | 5 | 2 | 3 | 4 | 5 | 5 | 5 | 2 | 3 | 4 | 1 | 5
151 | 19 | 15 | 26 | 38 | 50 | 65 | 78 | 92 | 103 | 116 | 126 | 136 | 156 | 170 | 5 | 3 | 2 | 5 | 3 | 1 | 5 | 2 | 4 | 5 | 2 | 1 | 2 | 4 | 1 | 5 | 4 | 2 | 5 | 4 | 2 | 4 | 4 | 3 | 5 | 4 | 3 | 2 | 2 | 2 | 2 | 5 | 5 | 1 | 3 | 4 | 1 | 2 | 2 | 5 | 3 | 3 | 3 | 1 | 5 | 5 | 5 | 5 | 5 | 3 | 4 | 2
152 | 16 | 6 | 22 | 33 | 44 | 55 | 69 | 82 | 90 | 100 | 114 | 123 | 135 | 145 | 1 | 2 | 1 | 2 | 5 | 5 | 4 | 2 | 5 | 1 | 3 | 2 | 4 | 1 | 4 | 2 | 3 | 2 | 5 | 1 | 3 | 2 | 5 | 4 | 5 | 5 | 2 | 1 | 1 | 1 | 3 | 3 | 1 | 2 | 5 | 2 | 4 | 4 | 1 | 5 | 1 | 4 | 2 | 2 | 3 | 4 | 2 | 3 | 1 | 5 | 1 | 3
153 | 24 | 16 | 32 | 40 | 47 | 57 | 72 | 88 | 100 | 109 | 118 | 132 | 150 | 163 | 4 | 5 | 3 | 4 | 4 | 4 | 5 | 3 | 1 | 2 | 4 | 1 | 1 | 2 | 1 | 3 | 1 | 2 | 2 | 5 | 4 | 4 | 4 | 3 | 4 | 5 | 2 | 5 | 2 | 3 | 4 | 3 | 4 | 2 | 2 | 1 | 1 | 3 | 1 | 4 | 4 | 3 | 5 | 2 | 5 | 5 | 3 | 5 | 4 | 2 | 4 | 3
154 | 17 | 15 | 24 | 37 | 50 | 66 | 73 | 85 | 96 | 110 | 120 | 135 | 151 | 158 | 5 | 2 | 3 | 5 | 1 | 1 | 5 | 2 | 3 | 3 | 3 | 4 | 3 | 1 | 5 | 4 | 4 | 5 | 5 | 2 | 3 | 2 | 1 | 1 | 4 | 3 | 1 | 4 | 1 | 3 | 3 | 4 | 5 | 2 | 5 | 2 | 2 | 1 | 2 | 5 | 4 | 3 | 3 | 5 | 1 | 5 | 5 | 5 | 2 | 1 | 2 | 2
155 | 18 | 13 | 21 | 29 | 39 | 54 | 65 | 74 | 87 | 96 | 113 | 122 | 134 | 145 | 1 | 5 | 2 | 5 | 3 | 2 | 2 | 1 | 3 | 2 | 1 | 2 | 2 | 1 | 3 | 4 | 4 | 3 | 4 | 4 | 2 | 1 | 4 | 4 | 1 | 2 | 4 | 2 | 1 | 3 | 4 | 5 | 1 | 3 | 3 | 2 | 3 | 4 | 5 | 5 | 5 | 2 | 1 | 1 | 1 | 5 | 4 | 2 | 1 | 4 | 5 | 1
156 | 16 | 11 | 22 | 31 | 46 | 59 | 70 | 81 | 93 | 107 | 117 | 130 | 138 | 154 | 3 | 4 | 3 | 1 | 1 | 4 | 3 | 3 | 5 | 1 | 2 | 1 | 5 | 1 | 5 | 4 | 3 | 2 | 4 | 4 | 5 | 1 | 2 | 3 | 4 | 1 | 4 | 2 | 5 | 1 | 2 | 4 | 4 | 5 | 1 | 4 | 2 | 2 | 1 | 5 | 3 | 3 | 5 | 2 | 1 | 3 | 2 | 2 | 5 | 5 | 4 | 2
157 | 21 | 11 | 27 | 45 | 62 | 80 | 85 | 97 | 109 | 121 | 133 | 146 | 154 | 174 | 3 | 2 | 2 | 4 | 5 | 5 | 3 | 3 | 5 | 5 | 5 | 3 | 2 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 1 | 2 | 1 | 1 | 3 | 2 | 5 | 2 | 4 | 4 | 1 | 3 | 4 | 3 | 3 | 2 | 3 | 3 | 2 | 4 | 3 | 3 | 2 | 5 | 1 | 3 | 1 | 3 | 5 | 5 | 5 | 5
158 | 19 | 12 | 22 | 30 | 44 | 57 | 66 | 83 | 90 | 100 | 108 | 120 | 133 | 141 | 2 | 4 | 2 | 4 | 4 | 3 | 1 | 2 | 4 | 2 | 1 | 1 | 5 | 1 | 5 | 3 | 1 | 5 | 2 | 5 | 1 | 2 | 2 | 4 | 5 | 2 | 5 | 5 | 1 | 3 | 2 | 1 | 3 | 1 | 2 | 4 | 1 | 1 | 5 | 1 | 5 | 2 | 2 | 3 | 3 | 2 | 5 | 3 | 1 | 3 | 3 | 1
159 | 14 | 10 | 18 | 28 | 43 | 55 | 64 | 71 | 80 | 89 | 100 | 114 | 126 | 141 | 5 | 1 | 1 | 3 | 1 | 3 | 3 | 1 | 3 | 2 | 1 | 4 | 5 | 2 | 3 | 5 | 5 | 3 | 3 | 1 | 1 | 1 | 5 | 2 | 3 | 1 | 2 | 1 | 2 | 5 | 1 | 1 | 2 | 2 | 4 | 1 | 1 | 5 | 2 | 3 | 2 | 4 | 4 | 4 | 2 | 2 | 4 | 4 | 5 | 3 | 2 | 5
160 | 13 | 10 | 18 | 26 | 35 | 48 | 62 | 77 | 89 | 104 | 118 | 130 | 145 | 154 | 3 | 3 | 3 | 1 | 1 | 2 | 2 | 3 | 3 | 2 | 1 | 2 | 2 | 2 | 1 | 4 | 5 | 3 | 3 | 2 | 3 | 5 | 2 | 4 | 5 | 4 | 4 | 2 | 4 | 4 | 3 | 1 | 5 | 4 | 5 | 1 | 3 | 5 | 1 | 5 | 5 | 1 | 3 | 3 | 5 | 5 | 3 | 2 | 2 | 3 | 1 | 3
161 | 14 | 7 | 20 | 25 | 36 | 48 | 60 | 72 | 80 | 89 | 101 | 111 | 127 | 139 | 2 | 2 | 2 | 1 | 2 | 5 | 2 | 4 | 1 | 1 | 2 | 1 | 3 | 2 | 4 | 2 | 3 | 2 | 4 | 3 | 5 | 3 | 3 | 1 | 2 | 4 | 3 | 3 | 4 | 1 | 1 | 2 | 1 | 2 | 3 | 3 | 3 | 3 | 5 | 1 | 4 | 1 | 1 | 4 | 4 | 5 | 3 | 4 | 5 | 2 | 4 | 1
162 | 16 | 10 | 22 | 30 | 41 | 52 | 66 | 76 | 90 | 102 | 108 | 121 | 130 | 140 | 3 | 2 | 1 | 4 | 2 | 4 | 3 | 3 | 3 | 2 | 1 | 2 | 1 | 3 | 5 | 2 | 2 | 1 | 3 | 5 | 5 | 3 | 1 | 5 | 1 | 5 | 1 | 3 | 1 | 3 | 5 | 5 | 5 | 2 | 2 | 3 | 1 | 2 | 2 | 1 | 4 | 3 | 2 | 4 | 1 | 2 | 1 | 5 | 3 | 2 | 1 | 4
163 | 14 | 10 | 21 | 41 | 57 | 66 | 81 | 96 | 109 | 121 | 132 | 142 | 154 | 165 | 2 | 4 | 2 | 2 | 1 | 3 | 2 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 1 | 2 | 4 | 1 | 2 | 1 | 5 | 5 | 4 | 3 | 5 | 2 | 5 | 4 | 5 | 2 | 2 | 4 | 1 | 5 | 2 | 2 | 3 | 2 | 4 | 2 | 3 | 2 | 3 | 3 | 3 | 2 | 4 | 4 | 4 | 2 | 1
164 | 18 | 12 | 26 | 40 | 49 | 57 | 67 | 79 | 87 | 102 | 107 | 116 | 127 | 141 | 3 | 5 | 3 | 1 | 5 | 1 | 3 | 5 | 1 | 5 | 4 | 4 | 2 | 5 | 1 | 1 | 1 | 2 | 4 | 1 | 2 | 2 | 3 | 3 | 3 | 5 | 1 | 3 | 1 | 1 | 4 | 2 | 4 | 5 | 4 | 2 | 1 | 2 | 1 | 1 | 1 | 2 | 4 | 2 | 3 | 2 | 2 | 4 | 4 | 5 | 4 | 1
165 | 24 | 17 | 27 | 38 | 50 | 63 | 71 | 82 | 94 | 108 | 121 | 134 | 146 | 158 | 3 | 5 | 4 | 5 | 5 | 2 | 2 | 1 | 5 | 1 | 3 | 2 | 1 | 2 | 5 | 4 | 4 | 3 | 4 | 2 | 1 | 1 | 1 | 5 | 3 | 2 | 5 | 1 | 3 | 3 | 1 | 5 | 5 | 4 | 1 | 4 | 2 | 5 | 3 | 3 | 4 | 1 | 3 | 5 | 3 | 4 | 4 | 1 | 4 | 2 | 3 | 3
166 | 22 | 12 | 28 | 41 | 53 | 58 | 69 | 75 | 87 | 98 | 108 | 120 | 130 | 141 | 1 | 3 | 3 | 5 | 5 | 5 | 1 | 5 | 3 | 3 | 5 | 2 | 3 | 2 | 3 | 4 | 1 | 1 | 1 | 2 | 2 | 5 | 3 | 1 | 1 | 2 | 2 | 1 | 4 | 2 | 5 | 1 | 4 | 2 | 1 | 4 | 4 | 1 | 3 | 2 | 4 | 2 | 2 | 4 | 1 | 5 | 1 | 3 | 1 | 3 | 5 | 2
167 | 21 | 15 | 28 | 38 | 46 | 61 | 75 | 85 | 103 | 114 | 127 | 137 | 152 | 165 | 5 | 3 | 3 | 4 | 1 | 5 | 4 | 3 | 1 | 3 | 3 | 3 | 4 | 1 | 2 | 1 | 3 | 3 | 4 | 5 | 5 | 1 | 3 | 5 | 2 | 4 | 3 | 1 | 5 | 3 | 5 | 5 | 5 | 4 | 1 | 1 | 5 | 5 | 1 | 2 | 1 | 3 | 5 | 1 | 5 | 2 | 5 | 3 | 5 | 1 | 3 | 4
168 | 19 | 14 | 25 | 38 | 52 | 61 | 70 | 84 | 92 | 102 | 116 | 127 | 137 | 150 | 5 | 4 | 2 | 3 | 4 | 1 | 3 | 3 | 3 | 2 | 5 | 3 | 3 | 5 | 1 | 5 | 2 | 3 | 2 | 2 | 3 | 4 | 1 | 1 | 4 | 4 | 1 | 5 | 1 | 5 | 1 | 1 | 2 | 2 | 4 | 2 | 5 | 3 | 3 | 3 | 3 | 1 | 5 | 2 | 1 | 2 | 5 | 2 | 5 | 3 | 2 | 3
169 | 17 | 12 | 27 | 44 | 61 | 73 | 86 | 96 | 110 | 121 | 128 | 143 | 155 | 171 | 5 | 5 | 1 | 1 | 3 | 2 | 5 | 5 | 4 | 3 | 5 | 5 | 3 | 5 | 4 | 5 | 1 | 4 | 2 | 5 | 3 | 3 | 3 | 4 | 2 | 1 | 2 | 5 | 5 | 5 | 3 | 1 | 3 | 3 | 4 | 1 | 2 | 1 | 1 | 3 | 2 | 4 | 5 | 4 | 4 | 3 | 2 | 3 | 4 | 2 | 5 | 5
170 | 23 | 17 | 28 | 38 | 50 | 58 | 65 | 76 | 86 | 99 | 110 | 122 | 131 | 144 | 5 | 5 | 3 | 4 | 3 | 3 | 2 | 3 | 2 | 5 | 2 | 1 | 4 | 4 | 1 | 3 | 2 | 2 | 3 | 1 | 2 | 2 | 2 | 1 | 4 | 2 | 3 | 2 | 3 | 4 | 1 | 2 | 5 | 3 | 1 | 4 | 5 | 2 | 2 | 2 | 2 | 4 | 4 | 2 | 1 | 3 | 1 | 4 | 5 | 2 | 5 | 1
171 | 22 | 16 | 28 | 42 | 54 | 63 | 74 | 90 | 101 | 113 | 128 | 140 | 151 | 166 | 3 | 5 | 5 | 3 | 1 | 5 | 4 | 2 | 1 | 5 | 4 | 4 | 2 | 4 | 5 | 1 | 1 | 4 | 1 | 3 | 4 | 2 | 1 | 4 | 5 | 5 | 5 | 1 | 1 | 1 | 4 | 5 | 2 | 3 | 3 | 4 | 5 | 4 | 1 | 5 | 1 | 4 | 4 | 3 | 4 | 5 | 1 | 1 | 5 | 4 | 2 | 4
172 | 14 | 10 | 18 | 30 | 44 | 51 | 64 | 78 | 88 | 102 | 113 | 123 | 135 | 147 | 4 | 1 | 3 | 2 | 3 | 1 | 3 | 1 | 4 | 3 | 1 | 4 | 1 | 3 | 5 | 5 | 3 | 1 | 1 | 2 | 1 | 4 | 3 | 5 | 3 | 1 | 5 | 5 | 1 | 3 | 2 | 4 | 5 | 1 | 5 | 3 | 3 | 4 | 2 | 2 | 1 | 4 | 2 | 3 | 1 | 1 | 5 | 5 | 3 | 3 | 5 | 1
173 | 16 | 11 | 23 | 42 | 52 | 63 | 79 | 92 | 103 | 116 | 127 | 136 | 149 | 160 | 5 | 2 | 3 | 1 | 4 | 1 | 4 | 3 | 5 | 5 | 5 | 4 | 3 | 4 | 2 | 1 | 3 | 3 | 3 | 2 | 4 | 4 | 4 | 4 | 5 | 3 | 1 | 4 | 1 | 4 | 4 | 2 | 2 | 3 | 3 | 5 | 3 | 1 | 5 | 2 | 1 | 1 | 2 | 5 | 2 | 5 | 3 | 3 | 4 | 1 | 3 | 3
174 | 13 | 8 | 19 | 31 | 48 | 55 | 66 | 74 | 90 | 100 | 113 | 128 | 142 | 156 | 1 | 1 | 1 | 5 | 4 | 1 | 2 | 4 | 3 | 2 | 4 | 3 | 4 | 5 | 3 | 5 | 2 | 1 | 1 | 3 | 3 | 4 | 3 | 1 | 4 | 1 | 2 | 1 | 4 | 5 | 2 | 5 | 1 | 3 | 4 | 2 | 1 | 3 | 4 | 5 | 4 | 5 | 4 | 2 | 2 | 5 | 5 | 2 | 3 | 5 | 3 | 3
175 | 21 | 15 | 23 | 31 | 48 | 56 | 67 | 77 | 91 | 107 | 113 | 125 | 132 | 141 | 5 | 1 | 5 | 4 | 2 | 4 | 1 | 1 | 2 | 2 | 3 | 1 | 3 | 5 | 4 | 5 | 1 | 3 | 3 | 1 | 1 | 4 | 1 | 5 | 2 | 3 | 4 | 1 | 3 | 1 | 5 | 5 | 5 | 3 | 3 | 5 | 1 | 1 | 2 | 2 | 3 | 5 | 3 | 1 | 1 | 3 | 2 | 1 | 3 | 1 | 2 | 3
176 | 14 | 8 | 20 | 30 | 40 | 52 | 65 | 74 | 84 | 97 | 113 | 122 | 134 | 146 | 3 | 1 | 1 | 3 | 2 | 4 | 5 | 1 | 1 | 1 | 3 | 5 | 2 | 4 | 2 | 2 | 2 | 3 | 2 | 5 | 3 | 4 | 4 | 2 | 3 | 1 | 1 | 4 | 4 | 3 | 2 | 1 | 3 | 3 | 5 | 2 | 5 | 5 | 5 | 1 | 2 | 1 | 2 | 4 | 1 | 1 | 5 | 5 | 4 | 2 | 4 | 2
177 | 17 | 11 | 21 | 38 | 49 | 57 | 71 | 87 | 103 | 114 | 128 | 143 | 150 | 165 | 5 | 2 | 2 | 2 | 3 | 3 | 1 | 3 | 5 | 4 | 4 | 4 | 2 | 3 | 2 | 4 | 1 | 1 | 1 | 5 | 5 | 4 | 2 | 3 | 2 | 4 | 5 | 5 | 5 | 4 | 5 | 2 | 4 | 1 | 4 | 2 | 4 | 3 | 2 | 5 | 1 | 4 | 5 | 5 | 2 | 2 | 1 | 2 | 3 | 4 | 3 | 5
178 | 23 | 14 | 32 | 47 | 55 | 70 | 84 | 96 | 108 | 124 | 137 | 147 | 161 | 174 | 1 | 4 | 4 | 5 | 4 | 5 | 4 | 5 | 4 | 3 | 3 | 5 | 3 | 2 | 1 | 2 | 5 | 1 | 5 | 4 | 3 | 3 | 3 | 5 | 5 | 1 | 2 | 4 | 2 | 4 | 2 | 4 | 3 | 5 | 5 | 3 | 5 | 2 | 2 | 4 | 4 | 2 | 3 | 1 | 4 | 5 | 4 | 1 | 1 | 2 | 5 | 5
179 | 12 | 9 | 18 | 31 | 46 | 59 | 72 | 81 | 93 | 103 | 111 | 120 | 134 | 148 | 1 | 2 | 3 | 3 | 2 | 1 | 3 | 3 | 5 | 1 | 5 | 2 | 4 | 5 | 3 | 3 | 3 | 1 | 5 | 4 | 1 | 4 | 3 | 5 | 3 | 2 | 2 | 2 | 5 | 3 | 3 | 1 | 1 | 3 | 5 | 1 | 2 | 2 | 1 | 3 | 1 | 1 | 2 | 5 | 5 | 4 | 4 | 1 | 2 | 5 | 5 | 2
180 | 14 | 12 | 24 | 35 | 45 | 53 | 68 | 79 | 93 | 109 | 116 | 129 | 143 | 154 | 3 | 3 | 1 | 5 | 1 | 1 | 5 | 5 | 4 | 4 | 1 | 2 | 1 | 4 | 4 | 1 | 1 | 1 | 3 | 3 | 5 | 4 | 3 | 3 | 3 | 2 | 1 | 5 | 3 | 2 | 4 | 5 | 3 | 5 | 5 | 3 | 1 | 4 | 1 | 1 | 1 | 3 | 4 | 5 | 4 | 2 | 3 | 5 | 1 | 4 | 2 | 4
181 | 14 | 11 | 21 | 34 | 43 | 60 | 72 | 84 | 95 | 106 | 119 | 128 | 141 | 154 | 4 | 1 | 5 | 1 | 1 | 2 | 3 | 4 | 4 | 4 | 1 | 4 | 5 | 2 | 1 | 1 | 5 | 5 | 5 | 2 | 2 | 2 | 4 | 4 | 2 | 5 | 1 | 4 | 2 | 5 | 2 | 2 | 3 | 2 | 1 | 5 | 2 | 5 | 1 | 5 | 3 | 1 | 3 | 2 | 3 | 3 | 5 | 2 | 4 | 3 | 3 | 3
182 | 19 | 13 | 25 | 44 | 51 | 67 | 80 | 94 | 104 | 114 | 127 | 138 | 152 | 169 | 1 | 4 | 5 | 3 | 5 | 1 | 4 | 2 | 5 | 5 | 5 | 4 | 1 | 3 | 1 | 2 | 4 | 5 | 3 | 4 | 3 | 3 | 2 | 5 | 4 | 2 | 5 | 3 | 1 | 3 | 2 | 4 | 3 | 4 | 1 | 2 | 1 | 3 | 4 | 5 | 4 | 5 | 1 | 1 | 3 | 5 | 5 | 1 | 3 | 4 | 5 | 5
183 | 20 | 12 | 28 | 42 | 61 | 74 | 81 | 99 | 111 | 124 | 134 | 147 | 161 | 177 | 4 | 1 | 5 | 2 | 4 | 4 | 5 | 3 | 5 | 3 | 3 | 3 | 5 | 5 | 4 | 5 | 4 | 3 | 2 | 4 | 2 | 1 | 2 | 2 | 5 | 4 | 4 | 5 | 4 | 5 | 2 | 1 | 1 | 4 | 3 | 5 | 5 | 1 | 2 | 2 | 4 | 2 | 4 | 3 | 5 | 2 | 2 | 5 | 4 | 2 | 5 | 5
184 | 15 | 8 | 21 | 34 | 43 | 53 | 67 | 83 | 91 | 103 | 118 | 127 | 139 | 152 | 2 | 2 | 1 | 3 | 5 | 2 | 5 | 1 | 2 | 1 | 5 | 5 | 2 | 4 | 1 | 2 | 1 | 5 | 1 | 3 | 4 | 5 | 4 | 1 | 3 | 5 | 3 | 5 | 1 | 1 | 3 | 3 | 5 | 1 | 2 | 4 | 3 | 5 | 5 | 2 | 1 | 3 | 4 | 1 | 2 | 5 | 3 | 2 | 3 | 1 | 5 | 4
185 | 23 | 13 | 26 | 37 | 48 | 62 | 74 | 83 | 93 | 100 | 115 | 129 | 146 | 158 | 4 | 4 | 3 | 2 | 5 | 5 | 2 | 1 | 3 | 2 | 1 | 5 | 3 | 1 | 2 | 5 | 5 | 3 | 4 | 2 | 5 | 2 | 2 | 3 | 4 | 2 | 2 | 1 | 4 | 2 | 2 | 2 | 2 | 1 | 3 | 1 | 1 | 5 | 5 | 4 | 2 | 4 | 5 | 3 | 3 | 4 | 5 | 5 | 2 | 3 | 2 | 5
186 | 18 | 12 | 20 | 37 | 45 | 59 | 75 | 84 | 98 | 108 | 120 | 133 | 144 | 154 | 5 | 2 | 3 | 2 | 5 | 1 | 1 | 1 | 4 | 5 | 5 | 3 | 5 | 1 | 1 | 1 | 2 | 5 | 3 | 4 | 4 | 5 | 5 | 2 | 1 | 2 | 2 | 4 | 4 | 1 | 5 | 4 | 2 | 2 | 5 | 1 | 1 | 5 | 5 | 1 | 3 | 2 | 5 | 3 | 1 | 4 | 5 | 1 | 4 | 2 | 2 | 2
187 | 17 | 10 | 23 | 40 | 53 | 63 | 78 | 88 | 100 | 109 | 123 | 135 | 149 | 160 | 3 | 2 | 2 | 3 | 5 | 2 | 4 | 2 | 4 | 4 | 4 | 5 | 2 | 3 | 4 | 4 | 5 | 1 | 2 | 2 | 2 | 3 | 5 | 5 | 4 | 1 | 2 | 3 | 2 | 1 | 5 | 4 | 2 | 3 | 3 | 1 | 5 | 3 | 4 | 2 | 2 | 3 | 5 | 2 | 3 | 2 | 5 | 4 | 5 | 2 | 1 | 3
188 | 17 | 11 | 22 | 32 | 42 | 58 | 64 | 77 | 86 | 96 | 108 | 120 | 131 | 146 | 3 | 1 | 2 | 5 | 5 | 1 | 4 | 1 | 3 | 3 | 1 | 3 | 5 | 2 | 2 | 1 | 5 | 3 | 5 | 3 | 2 | 2 | 1 | 1 | 2 | 3 | 4 | 4 | 2 | 3 | 3 | 1 | 1 | 4 | 2 | 3 | 5 | 5 | 1 | 1 | 5 | 1 | 4 | 2 | 3 | 5 | 2 | 1 | 5 | 2 | 5 | 3
189 | 13 | 10 | 17 | 22 | 39 | 53 | 70 | 84 | 97 | 110 | 118 | 131 | 144 | 153 | 2 | 3 | 2 | 3 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 2 | 3 | 5 | 4 | 5 | 1 | 4 | 4 | 5 | 3 | 5 | 5 | 4 | 3 | 5 | 5 | 1 | 4 | 4 | 2 | 3 | 4 | 4 | 1 | 4 | 2 | 2 | 1 | 3 | 1 | 5 | 3 | 4 | 4 | 3 | 4 | 2 | 2 | 1 | 1 | 5
190 | 12 | 8 | 18 | 32 | 40 | 49 | 62 | 73 | 84 | 90 | 102 | 108 | 120 | 130 | 3 | 3 | 1 | 1 | 2 | 2 | 1 | 5 | 5 | 1 | 3 | 5 | 1 | 2 | 2 | 3 | 2 | 1 | 5 | 1 | 1 | 5 | 2 | 5 | 4 | 5 | 1 | 1 | 1 | 2 | 4 | 4 | 2 | 1 | 2 | 1 | 5 | 5 | 1 | 1 | 1 | 1 | 3 | 1 | 4 | 4 | 2 | 2 | 3 | 2 | 3 | 2
191 | 17 | 13 | 24 | 39 | 51 | 59 | 77 | 89 | 101 | 113 | 123 | 135 | 149 | 157 | 2 | 3 | 5 | 3 | 3 | 1 | 2 | 5 | 5 | 5 | 3 | 2 | 3 | 3 | 1 | 5 | 3 | 2 | 2 | 1 | 5 | 5 | 3 | 5 | 2 | 4 | 3 | 3 | 4 | 4 | 2 | 2 | 4 | 2 | 2 | 4 | 1 | 4 | 3 | 2 | 2 | 4 | 5 | 1 | 4 | 5 | 3 | 2 | 3 | 2 | 2 | 1
192 | 18 | 13 | 27 | 36 | 45 | 53 | 62 | 79 | 88 | 100 | 109 | 120 | 131 | 139 | 1 | 3 | 5 | 4 | 3 | 2 | 4 | 5 | 2 | 1 | 1 | 5 | 1 | 5 | 2 | 1 | 1 | 2 | 4 | 1 | 3 | 1 | 2 | 3 | 5 | 5 | 3 | 4 | 2 | 1 | 5 | 1 | 4 | 2 | 3 | 3 | 2 | 2 | 1 | 4 | 2 | 2 | 2 | 5 | 1 | 4 | 3 | 3 | 1 | 1 | 5 | 1
193 | 16 | 12 | 21 | 30 | 35 | 47 | 59 | 76 | 92 | 109 | 128 | 139 | 151 | 162 | 2 | 3 | 5 | 2 | 1 | 3 | 1 | 4 | 4 | 2 | 2 | 1 | 1 | 1 | 2 | 1 | 3 | 2 | 3 | 4 | 1 | 5 | 2 | 4 | 4 | 5 | 3 | 5 | 5 | 5 | 5 | 1 | 3 | 5 | 4 | 5 | 4 | 5 | 5 | 5 | 2 | 1 | 3 | 5 | 1 | 3 | 4 | 4 | 3 | 3 | 4 | 1
194 | 24 | 15 | 29 | 42 | 50 | 63 | 72 | 85 | 96 | 110 | 125 | 140 | 152 | 169 | 5 | 4 | 5 | 1 | 5 | 4 | 4 | 1 | 2 | 4 | 2 | 5 | 1 | 5 | 1 | 1 | 3 | 4 | 2 | 4 | 1 | 1 | 4 | 3 | 3 | 3 | 3 | 4 | 5 | 4 | 1 | 1 | 2 | 2 | 5 | 5 | 5 | 3 | 2 | 5 | 4 | 4 | 5 | 2 | 5 | 4 | 1 | 2 | 5 | 4 | 5 | 3
195 | 18 | 12 | 24 | 38 | 47 | 61 | 71 | 81 | 89 | 101 | 110 | 125 | 133 | 144 | 2 | 2 | 4 | 4 | 2 | 4 | 1 | 5 | 5 | 4 | 4 | 1 | 2 | 2 | 4 | 1 | 4 | 4 | 3 | 3 | 4 | 3 | 2 | 1 | 4 | 3 | 1 | 2 | 2 | 3 | 1 | 2 | 1 | 5 | 4 | 2 | 4 | 2 | 1 | 2 | 3 | 5 | 2 | 5 | 3 | 3 | 1 | 1 | 2 | 3 | 2 | 4
196 | 17 | 12 | 25 | 42 | 49 | 61 | 74 | 83 | 98 | 111 | 119 | 131 | 144 | 154 | 3 | 1 | 5 | 3 | 3 | 2 | 4 | 4 | 5 | 5 | 5 | 2 | 1 | 1 | 1 | 4 | 5 | 1 | 2 | 4 | 4 | 4 | 2 | 3 | 1 | 2 | 3 | 3 | 3 | 2 | 5 | 5 | 4 | 2 | 5 | 2 | 2 | 1 | 2 | 3 | 3 | 2 | 3 | 4 | 1 | 5 | 5 | 2 | 4 | 3 | 1 | 2
197 | 22 | 15 | 29 | 39 | 49 | 59 | 71 | 82 | 96 | 108 | 118 | 131 | 148 | 160 | 5 | 4 | 3 | 3 | 3 | 4 | 2 | 5 | 2 | 2 | 1 | 5 | 5 | 1 | 1 | 3 | 3 | 1 | 4 | 2 | 2 | 3 | 5 | 2 | 5 | 2 | 3 | 1 | 1 | 5 | 4 | 4 | 4 | 3 | 4 | 1 | 3 | 3 | 2 | 2 | 3 | 3 | 2 | 5 | 5 | 5 | 2 | 5 | 1 | 2 | 4 | 5
198 | 23 | 15 | 27 | 37 | 53 | 64 | 76 | 84 | 96 | 105 | 116 | 129 | 145 | 155 | 5 | 1 | 4 | 5 | 3 | 5 | 2 | 2 | 4 | 4 | 1 | 1 | 5 | 3 | 4 | 4 | 5 | 4 | 1 | 1 | 2 | 1 | 4 | 5 | 2 | 3 | 2 | 1 | 3 | 1 | 4 | 4 | 1 | 3 | 3 | 2 | 2 | 5 | 1 | 3 | 4 | 5 | 3 | 1 | 2 | 5 | 4 | 5 | 5 | 1 | 1 | 3
199 | 21 | 12 | 26 | 42 | 54 | 71 | 85 | 98 | 113 | 127 | 138 | 153 | 166 | 180 | 2 | 4 | 1 | 5 | 5 | 4 | 4 | 1 | 4 | 3 | 4 | 5 | 1 | 5 | 1 | 5 | 5 | 2 | 5 | 5 | 5 | 3 | 3 | 3 | 5 | 2 | 4 | 2 | 4 | 5 | 5 | 1 | 3 | 4 | 3 | 4 | 1 | 5 | 4 | 1 | 3 | 4 | 3 | 5 | 2 | 5 | 3 | 3 | 1 | 3 | 5 | 5
200 | 19 | 11 | 24 | 38 | 48 | 55 | 66 | 76 | 85 | 100 | 110 | 122 | 135 | 151 | 4 | 3 | 2 | 2 | 5 | 3 | 3 | 2 | 2 | 5 | 4 | 3 | 3 | 2 | 4 | 1 | 1 | 1 | 2 | 3 | 5 | 1 | 3 | 2 | 2 | 1 | 3 | 4 | 1 | 3 | 2 | 3 | 3 | 3 | 5 | 4 | 2 | 3 | 1 | 4 | 4 | 4 | 3 | 1 | 5 | 4 | 2 | 2 | 2 | 5 | 5 | 4
201 | 23 | 13 | 26 | 36 | 55 | 69 | 79 | 93 | 107 | 120 | 132 | 143 | 155 | 167 | 4 | 3 | 5 | 1 | 5 | 5 | 1 | 2 | 3 | 3 | 2 | 2 | 5 | 5 | 4 | 5 | 1 | 4 | 5 | 4 | 4 | 2 | 1 | 3 | 3 | 5 | 1 | 5 | 4 | 2 | 5 | 3 | 1 | 4 | 5 | 3 | 2 | 4 | 1 | 5 | 4 | 5 | 1 | 1 | 1 | 5 | 5 | 1 | 4 | 1 | 3 | 4
202 | 17 | 9 | 21 | 31 | 41 | 55 | 65 | 78 | 88 | 102 | 110 | 126 | 136 | 147 | 2 | 2 | 2 | 3 | 5 | 3 | 1 | 3 | 4 | 1 | 3 | 2 | 1 | 3 | 4 | 2 | 2 | 4 | 3 | 5 | 4 | 1 | 1 | 4 | 3 | 4 | 5 | 1 | 2 | 2 | 3 | 3 | 3 | 2 | 5 | 4 | 1 | 1 | 4 | 2 | 2 | 5 | 5 | 4 | 3 | 1 | 1 | 5 | 5 | 2 | 3 | 1
203 | 22 | 14 | 26 | 39 | 50 | 60 | 73 | 88 | 98 | 110 | 122 | 137 | 147 | 155 | 3 | 4 | 4 | 3 | 3 | 5 | 2 | 2 | 4 | 4 | 4 | 1 | 3 | 4 | 1 | 3 | 4 | 1 | 1 | 4 | 2 | 4 | 5 | 2 | 4 | 4 | 2 | 5 | 4 | 2 | 3 | 1 | 2 | 5 | 2 | 3 | 5 | 5 | 1 | 1 | 2 | 3 | 5 | 5 | 5 | 3 | 1 | 1 | 4 | 1 | 1 | 2
204 | 16 | 7 | 21 | 33 | 46 | 59 | 76 | 85 | 97 | 109 | 124 | 141 | 155 | 166 | 1 | 2 | 2 | 2 | 4 | 5 | 2 | 3 | 4 | 2 | 5 | 1 | 2 | 3 | 4 | 4 | 3 | 5 | 4 | 1 | 5 | 5 | 2 | 5 | 1 | 4 | 3 | 1 | 4 | 2 | 2 | 4 | 3 | 4 | 2 | 3 | 2 | 4 | 5 | 4 | 5 | 4 | 5 | 3 | 4 | 5 | 3 | 2 | 4 | 2 | 1 | 4
205 | 23 | 13 | 30 | 43 | 54 | 69 | 83 | 94 | 109 | 120 | 134 | 148 | 158 | 171 | 4 | 1 | 4 | 4 | 5 | 5 | 3 | 4 | 3 | 5 | 2 | 3 | 4 | 3 | 1 | 3 | 4 | 3 | 4 | 4 | 4 | 1 | 4 | 5 | 3 | 2 | 2 | 4 | 4 | 5 | 3 | 3 | 3 | 1 | 3 | 4 | 4 | 4 | 5 | 1 | 1 | 4 | 4 | 5 | 2 | 2 | 5 | 1 | 2 | 5 | 5 | 1
206 | 19 | 12 | 27 | 41 | 51 | 58 | 70 | 78 | 89 | 104 | 117 | 133 | 147 | 162 | 2 | 1 | 5 | 4 | 3 | 4 | 4 | 4 | 4 | 4 | 2 | 4 | 4 | 1 | 3 | 2 | 2 | 1 | 2 | 2 | 1 | 5 | 4 | 2 | 3 | 1 | 2 | 2 | 4 | 1 | 4 | 2 | 5 | 5 | 3 | 2 | 3 | 2 | 3 | 5 | 5 | 5 | 1 | 5 | 1 | 4 | 4 | 5 | 3 | 3 | 5 | 4
207 | 12 | 8 | 14 | 29 | 40 | 53 | 63 | 78 | 89 | 98 | 110 | 124 | 132 | 141 | 1 | 1 | 1 | 5 | 1 | 3 | 1 | 1 | 5 | 5 | 2 | 3 | 5 | 3 | 2 | 1 | 3 | 4 | 1 | 5 | 1 | 3 | 3 | 3 | 4 | 2 | 5 | 4 | 1 | 4 | 1 | 5 | 4 | 3 | 1 | 1 | 2 | 5 | 4 | 1 | 5 | 5 | 2 | 2 | 2 | 1 | 4 | 1 | 2 | 1 | 2 | 4
208 | 18 | 13 | 27 | 41 | 53 | 59 | 72 | 82 | 91 | 105 | 114 | 130 | 144 | 155 | 5 | 2 | 5 | 1 | 4 | 1 | 4 | 5 | 5 | 3 | 2 | 4 | 2 | 2 | 4 | 4 | 1 | 2 | 2 | 1 | 3 | 4 | 1 | 5 | 2 | 2 | 1 | 5 | 3 | 4 | 1 | 1 | 4 | 4 | 5 | 1 | 2 | 1 | 4 | 2 | 3 | 5 | 3 | 5 | 5 | 4 | 1 | 4 | 3 | 1 | 3 | 4
209 | 15 | 7 | 19 | 31 | 40 | 55 | 62 | 77 | 87 | 99 | 111 | 118 | 132 | 145 | 1 | 3 | 1 | 2 | 4 | 4 | 1 | 3 | 3 | 1 | 3 | 5 | 4 | 1 | 3 | 1 | 3 | 2 | 5 | 5 | 2 | 2 | 2 | 1 | 1 | 5 | 4 | 5 | 3 | 2 | 2 | 3 | 1 | 3 | 3 | 5 | 1 | 4 | 4 | 3 | 2 | 1 | 1 | 3 | 4 | 4 | 2 | 4 | 3 | 2 | 3 | 5
210 | 15 | 12 | 24 | 39 | 52 | 62 | 74 | 83 | 90 | 101 | 110 | 124 | 136 | 145 | 1 | 5 | 1 | 5 | 1 | 2 | 5 | 4 | 4 | 4 | 3 | 4 | 5 | 2 | 4 | 2 | 3 | 1 | 2 | 4 | 5 | 1 | 4 | 2 | 2 | 2 | 4 | 1 | 2 | 3 | 1 | 1 | 2 | 2 | 2 | 5 | 2 | 2 | 1 | 4 | 5 | 4 | 3 | 2 | 2 | 4 | 5 | 1 | 1 | 3 | 4 | 1
211 | 14 | 12 | 22 | 35 | 48 | 57 | 75 | 85 | 101 | 113 | 124 | 137 | 156 | 169 | 1 | 4 | 4 | 3 | 1 | 1 | 3 | 5 | 5 | 5 | 2 | 1 | 3 | 3 | 2 | 5 | 1 | 2 | 2 | 4 | 3 | 5 | 5 | 5 | 3 | 2 | 2 | 3 | 5 | 4 | 5 | 2 | 2 | 4 | 2 | 4 | 4 | 2 | 4 | 1 | 5 | 1 | 3 | 4 | 4 | 5 | 5 | 5 | 4 | 3 | 1 | 5
212 | 15 | 7 | 22 | 30 | 44 | 61 | 70 | 79 | 91 | 103 | 114 | 125 | 135 | 145 | 3 | 2 | 1 | 1 | 3 | 5 | 2 | 5 | 2 | 1 | 3 | 2 | 3 | 4 | 4 | 3 | 4 | 5 | 3 | 5 | 2 | 2 | 4 | 1 | 1 | 4 | 3 | 1 | 4 | 2 | 2 | 4 | 3 | 2 | 2 | 5 | 2 | 3 | 4 | 2 | 5 | 1 | 4 | 1 | 3 | 1 | 2 | 4 | 1 | 5 | 2 | 2
213 | 21 | 12 | 25 | 36 | 51 | 62 | 80 | 88 | 102 | 108 | 118 | 129 | 136 | 153 | 4 | 3 | 4 | 1 | 4 | 5 | 2 | 2 | 4 | 3 | 1 | 3 | 4 | 5 | 5 | 1 | 4 | 4 | 1 | 2 | 5 | 5 | 3 | 5 | 2 | 3 | 1 | 2 | 3 | 4 | 4 | 3 | 1 | 2 | 2 | 1 | 4 | 4 | 1 | 1 | 4 | 2 | 3 | 2 | 1 | 3 | 2 | 1 | 5 | 2 | 5 | 5
214 | 15 | 8 | 21 | 30 | 43 | 59 | 69 | 85 | 94 | 104 | 119 | 131 | 144 | 155 | 2 | 1 | 2 | 3 | 4 | 3 | 4 | 2 | 1 | 5 | 2 | 1 | 4 | 2 | 4 | 3 | 4 | 5 | 3 | 4 | 3 | 1 | 3 | 3 | 4 | 2 | 5 | 5 | 1 | 2 | 4 | 2 | 5 | 3 | 1 | 1 | 5 | 4 | 5 | 1 | 2 | 5 | 3 | 2 | 2 | 2 | 5 | 4 | 1 | 4 | 1 | 5
215 | 14 | 10 | 19 | 35 | 47 | 62 | 74 | 86 | 98 | 113 | 121 | 134 | 148 | 159 | 4 | 1 | 1 | 4 | 2 | 2 | 4 | 1 | 3 | 4 | 5 | 4 | 1 | 3 | 3 | 5 | 2 | 5 | 5 | 3 | 3 | 4 | 4 | 1 | 3 | 4 | 1 | 4 | 2 | 4 | 4 | 2 | 3 | 5 | 2 | 5 | 1 | 1 | 2 | 4 | 5 | 1 | 4 | 3 | 2 | 5 | 4 | 3 | 2 | 5 | 2 | 2
216 | 18 | 11 | 20 | 28 | 36 | 48 | 59 | 76 | 85 | 96 | 112 | 125 | 135 | 146 | 1 | 2 | 5 | 3 | 2 | 5 | 1 | 1 | 4 | 2 | 1 | 1 | 1 | 2 | 4 | 1 | 1 | 3 | 3 | 5 | 1 | 3 | 3 | 4 | 5 | 3 | 4 | 5 | 1 | 3 | 1 | 4 | 3 | 5 | 2 | 1 | 4 | 5 | 5 | 2 | 4 | 4 | 3 | 2 | 2 | 3 | 4 | 1 | 5 | 2 | 3 | 1
217 | 22 | 15 | 27 | 43 | 53 | 62 | 70 | 83 | 95 | 108 | 119 | 133 | 147 | 156 | 4 | 3 | 5 | 3 | 3 | 4 | 3 | 2 | 4 | 5 | 5 | 2 | 4 | 3 | 2 | 1 | 1 | 1 | 2 | 5 | 5 | 1 | 1 | 1 | 2 | 5 | 5 | 1 | 5 | 2 | 3 | 2 | 5 | 1 | 3 | 4 | 3 | 2 | 4 | 2 | 2 | 5 | 4 | 3 | 3 | 5 | 3 | 3 | 3 | 4 | 1 | 1
218 | 20 | 10 | 28 | 43 | 55 | 70 | 82 | 97 | 106 | 115 | 132 | 143 | 155 | 165 | 4 | 1 | 2 | 3 | 5 | 5 | 3 | 5 | 4 | 4 | 4 | 3 | 2 | 3 | 4 | 3 | 3 | 4 | 4 | 4 | 5 | 2 | 1 | 4 | 4 | 4 | 3 | 4 | 2 | 2 | 4 | 1 | 3 | 4 | 1 | 1 | 2 | 5 | 5 | 5 | 3 | 1 | 5 | 2 | 2 | 3 | 5 | 2 | 1 | 3 | 1 | 5
219 | 14 | 8 | 21 | 34 | 51 | 64 | 72 | 79 | 93 | 110 | 121 | 134 | 150 | 166 | 2 | 1 | 1 | 4 | 5 | 1 | 2 | 5 | 5 | 1 | 5 | 2 | 2 | 5 | 5 | 5 | 2 | 2 | 4 | 5 | 4 | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 4 | 1 | 5 | 4 | 4 | 5 | 3 | 5 | 3 | 3 | 4 | 1 | 2 | 5 | 1 | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
220 | 16 | 9 | 21 | 30 | 42 | 50 | 60 | 73 | 86 | 99 | 112 | 127 | 145 | 155 | 1 | 4 | 3 | 1 | 3 | 4 | 2 | 3 | 2 | 5 | 1 | 1 | 3 | 4 | 3 | 2 | 2 | 3 | 1 | 2 | 4 | 2 | 2 | 2 | 4 | 1 | 4 | 4 | 5 | 2 | 5 | 1 | 2 | 2 | 5 | 4 | 3 | 2 | 3 | 5 | 5 | 1 | 5 | 4 | 5 | 5 | 5 | 3 | 4 | 2 | 2 | 2
221 | 20 | 14 | 28 | 39 | 50 | 64 | 76 | 94 | 101 | 109 | 120 | 129 | 137 | 144 | 5 | 4 | 4 | 1 | 2 | 4 | 5 | 3 | 2 | 2 | 4 | 3 | 5 | 3 | 1 | 2 | 4 | 5 | 3 | 2 | 1 | 5 | 3 | 3 | 5 | 4 | 4 | 5 | 1 | 3 | 2 | 1 | 1 | 1 | 3 | 3 | 1 | 5 | 3 | 2 | 5 | 2 | 1 | 1 | 4 | 1 | 2 | 1 | 2 | 3 | 1 | 1
222 | 18 | 12 | 25 | 33 | 42 | 54 | 65 | 75 | 89 | 102 | 112 | 121 | 131 | 139 | 4 | 1 | 5 | 2 | 3 | 3 | 3 | 4 | 1 | 2 | 1 | 4 | 5 | 2 | 1 | 1 | 1 | 5 | 3 | 3 | 1 | 1 | 5 | 4 | 5 | 1 | 2 | 2 | 4 | 4 | 3 | 3 | 4 | 4 | 3 | 2 | 1 | 2 | 3 | 4 | 4 | 1 | 1 | 3 | 4 | 2 | 1 | 3 | 2 | 1 | 1 | 4
223 | 21 | 16 | 28 | 38 | 49 | 59 | 69 | 83 | 91 | 105 | 119 | 135 | 148 | 162 | 3 | 5 | 3 | 5 | 1 | 4 | 2 | 5 | 2 | 2 | 5 | 1 | 3 | 1 | 3 | 4 | 2 | 2 | 5 | 1 | 4 | 1 | 4 | 1 | 2 | 5 | 4 | 3 | 2 | 2 | 1 | 3 | 5 | 1 | 5 | 3 | 4 | 3 | 4 | 3 | 5 | 2 | 4 | 5 | 2 | 4 | 4 | 3 | 3 | 4 | 3 | 4
224 | 26 | 17 | 32 | 45 | 58 | 74 | 84 | 91 | 103 | 117 | 131 | 147 | 155 | 167 | 5 | 2 | 5 | 5 | 4 | 5 | 1 | 5 | 2 | 2 | 5 | 4 | 3 | 3 | 2 | 5 | 4 | 3 | 5 | 4 | 4 | 1 | 3 | 2 | 2 | 1 | 1 | 3 | 3 | 5 | 1 | 3 | 3 | 5 | 1 | 5 | 4 | 5 | 2 | 3 | 3 | 5 | 4 | 4 | 2 | 1 | 3 | 2 | 3 | 4 | 2 | 3
225 | 18 | 14 | 25 | 35 | 47 | 62 | 74 | 82 | 93 | 106 | 114 | 131 | 145 | 157 | 5 | 3 | 3 | 3 | 3 | 1 | 2 | 5 | 3 | 2 | 3 | 2 | 1 | 2 | 5 | 4 | 4 | 2 | 5 | 4 | 1 | 1 | 5 | 5 | 4 | 1 | 1 | 2 | 3 | 1 | 5 | 2 | 3 | 3 | 2 | 5 | 2 | 2 | 2 | 2 | 5 | 5 | 2 | 5 | 3 | 3 | 5 | 3 | 5 | 5 | 1 | 1
226 | 16 | 11 | 18 | 35 | 48 | 62 | 73 | 89 | 102 | 118 | 133 | 140 | 150 | 158 | 2 | 5 | 2 | 2 | 1 | 4 | 1 | 1 | 5 | 3 | 5 | 4 | 1 | 4 | 4 | 4 | 1 | 5 | 4 | 4 | 5 | 4 | 1 | 1 | 4 | 4 | 4 | 4 | 1 | 3 | 5 | 4 | 3 | 4 | 5 | 4 | 4 | 5 | 2 | 4 | 1 | 3 | 1 | 2 | 3 | 3 | 2 | 2 | 3 | 1 | 2 | 2
227 | 13 | 6 | 23 | 33 | 46 | 62 | 75 | 85 | 95 | 101 | 112 | 119 | 134 | 146 | 1 | 1 | 2 | 2 | 3 | 4 | 5 | 5 | 1 | 3 | 3 | 3 | 4 | 3 | 1 | 5 | 5 | 4 | 5 | 2 | 2 | 5 | 4 | 2 | 1 | 2 | 5 | 2 | 1 | 2 | 2 | 5 | 2 | 2 | 1 | 1 | 5 | 3 | 2 | 1 | 2 | 1 | 2 | 2 | 5 | 4 | 1 | 5 | 3 | 3 | 1 | 5
228 | 13 | 9 | 20 | 31 | 46 | 58 | 67 | 77 | 94 | 103 | 113 | 124 | 138 | 153 | 1 | 4 | 2 | 2 | 3 | 1 | 3 | 4 | 5 | 1 | 1 | 4 | 5 | 4 | 5 | 1 | 5 | 1 | 5 | 1 | 3 | 2 | 1 | 3 | 2 | 2 | 5 | 1 | 5 | 4 | 5 | 3 | 3 | 2 | 2 | 2 | 1 | 1 | 3 | 5 | 2 | 4 | 3 | 2 | 4 | 4 | 1 | 5 | 4 | 5 | 4 | 2
229 | 17 | 14 | 26 | 36 | 44 | 54 | 68 | 80 | 97 | 110 | 119 | 125 | 137 | 152 | 5 | 3 | 2 | 4 | 1 | 2 | 5 | 4 | 2 | 2 | 2 | 4 | 1 | 1 | 5 | 1 | 1 | 1 | 5 | 3 | 1 | 4 | 4 | 5 | 5 | 5 | 1 | 1 | 5 | 2 | 5 | 5 | 5 | 4 | 2 | 2 | 2 | 1 | 2 | 4 | 1 | 1 | 1 | 3 | 3 | 1 | 3 | 5 | 5 | 4 | 3 | 3
230 | 22 | 16 | 28 | 44 | 54 | 66 | 76 | 91 | 99 | 110 | 117 | 131 | 141 | 155 | 4 | 3 | 5 | 4 | 2 | 4 | 3 | 3 | 4 | 5 | 2 | 5 | 4 | 1 | 3 | 2 | 1 | 5 | 1 | 5 | 3 | 4 | 2 | 1 | 3 | 3 | 5 | 4 | 1 | 2 | 4 | 1 | 2 | 1 | 3 | 5 | 1 | 2 | 2 | 2 | 4 | 2 | 4 | 4 | 3 | 1 | 1 | 5 | 1 | 5 | 3 | 5
231 | 16 | 10 | 22 | 34 | 49 | 59 | 70 | 83 | 92 | 106 | 113 | 131 | 143 | 156 | 3 | 1 | 4 | 2 | 3 | 3 | 2 | 4 | 3 | 2 | 4 | 3 | 5 | 1 | 5 | 4 | 1 | 3 | 3 | 3 | 3 | 1 | 4 | 3 | 2 | 3 | 4 | 4 | 5 | 2 | 1 | 1 | 5 | 1 | 5 | 3 | 1 | 3 | 2 | 1 | 5 | 5 | 3 | 5 | 2 | 3 | 4 | 3 | 1 | 2 | 5 | 5
232 | 21 | 14 | 23 | 36 | 50 | 59 | 73 | 86 | 97 | 109 | 121 | 133 | 145 | 158 | 1 | 5 | 4 | 4 | 2 | 5 | 1 | 1 | 3 | 3 | 5 | 2 | 5 | 5 | 1 | 3 | 1 | 2 | 4 | 2 | 4 | 2 | 3 | 5 | 4 | 4 | 4 | 1 | 2 | 1 | 4 | 4 | 3 | 1 | 5 | 3 | 2 | 1 | 5 | 4 | 3 | 3 | 2 | 4 | 2 | 4 | 3 | 3 | 2 | 4 | 4 | 3
233 | 15 | 10 | 19 | 31 | 45 | 54 | 69 | 80 | 95 | 108 | 119 | 133 | 147 | 162 | 3 | 1 | 3 | 3 | 4 | 1 | 3 | 1 | 5 | 2 | 2 | 3 | 5 | 4 | 4 | 1 | 1 | 3 | 1 | 4 | 2 | 3 | 5 | 5 | 1 | 2 | 4 | 4 | 5 | 3 | 5 | 2 | 3 | 5 | 1 | 4 | 5 | 1 | 3 | 2 | 5 | 2 | 3 | 4 | 2 | 3 | 4 | 5 | 5 | 2 | 4 | 4
234 | 25 | 17 | 32 | 44 | 56 | 65 | 78 | 92 | 104 | 110 | 122 | 134 | 146 | 160 | 5 | 5 | 2 | 5 | 5 | 3 | 4 | 3 | 3 | 3 | 5 | 1 | 4 | 2 | 4 | 2 | 1 | 1 | 2 | 5 | 1 | 5 | 2 | 5 | 4 | 5 | 3 | 2 | 2 | 5 | 4 | 1 | 1 | 2 | 1 | 2 | 1 | 3 | 3 | 5 | 1 | 2 | 5 | 4 | 2 | 4 | 5 | 1 | 4 | 5 | 4 | 1
235 | 23 | 17 | 31 | 42 | 53 | 66 | 76 | 91 | 102 | 116 | 128 | 142 | 155 | 167 | 5 | 3 | 5 | 4 | 4 | 2 | 5 | 3 | 2 | 1 | 3 | 5 | 1 | 2 | 5 | 3 | 3 | 4 | 5 | 1 | 4 | 1 | 3 | 2 | 5 | 5 | 4 | 1 | 4 | 3 | 2 | 2 | 1 | 5 | 5 | 3 | 2 | 4 | 5 | 1 | 5 | 5 | 1 | 3 | 1 | 3 | 4 | 5 | 5 | 2 | 1 | 4
236 | 15 | 8 | 22 | 33 | 38 | 49 | 59 | 73 | 82 | 93 | 105 | 117 | 130 | 144 | 1 | 5 | 1 | 1 | 2 | 5 | 4 | 3 | 5 | 3 | 2 | 1 | 1 | 2 | 1 | 1 | 2 | 2 | 3 | 4 | 4 | 4 | 1 | 1 | 4 | 3 | 4 | 3 | 1 | 3 | 2 | 3 | 3 | 3 | 1 | 4 | 3 | 3 | 3 | 3 | 3 | 5 | 1 | 3 | 5 | 2 | 2 | 4 | 3 | 5 | 4 | 2
237 | 17 | 11 | 26 | 42 | 50 | 62 | 72 | 80 | 93 | 109 | 119 | 129 | 138 | 154 | 4 | 1 | 3 | 3 | 3 | 3 | 4 | 5 | 4 | 5 | 3 | 4 | 1 | 1 | 3 | 3 | 2 | 1 | 4 | 5 | 3 | 2 | 4 | 1 | 1 | 1 | 2 | 4 | 2 | 4 | 5 | 2 | 4 | 5 | 5 | 2 | 1 | 5 | 1 | 3 | 3 | 1 | 3 | 3 | 4 | 1 | 1 | 3 | 5 | 4 | 2 | 5
238 | 21 | 11 | 29 | 45 | 62 | 69 | 81 | 92 | 102 | 114 | 125 | 139 | 153 | 166 | 3 | 4 | 1 | 3 | 5 | 5 | 5 | 3 | 4 | 5 | 2 | 5 | 4 | 3 | 5 | 5 | 1 | 3 | 1 | 2 | 4 | 2 | 2 | 4 | 1 | 1 | 4 | 5 | 1 | 3 | 3 | 3 | 4 | 5 | 2 | 1 | 2 | 5 | 2 | 2 | 3 | 5 | 1 | 5 | 4 | 4 | 3 | 3 | 5 | 2 | 3 | 3
239 | 19 | 13 | 25 | 32 | 47 | 62 | 73 | 88 | 100 | 115 | 125 | 134 | 142 | 155 | 1 | 4 | 3 | 5 | 1 | 5 | 3 | 3 | 2 | 1 | 1 | 3 | 2 | 3 | 5 | 5 | 5 | 1 | 4 | 5 | 5 | 2 | 2 | 2 | 2 | 3 | 5 | 5 | 5 | 3 | 3 | 1 | 2 | 4 | 4 | 5 | 3 | 4 | 1 | 2 | 1 | 2 | 3 | 3 | 1 | 2 | 3 | 2 | 3 | 4 | 1 | 5
240 | 23 | 17 | 31 | 40 | 58 | 73 | 89 | 99 | 107 | 117 | 124 | 135 | 146 | 159 | 4 | 5 | 5 | 3 | 1 | 5 | 5 | 3 | 1 | 1 | 4 | 3 | 4 | 5 | 4 | 5 | 5 | 5 | 1 | 4 | 3 | 3 | 5 | 5 | 5 | 2 | 1 | 2 | 3 | 1 | 1 | 3 | 2 | 5 | 1 | 2 | 2 | 2 | 2 | 1 | 2 | 5 | 2 | 2 | 2 | 2 | 4 | 3 | 2 | 2 | 4 | 5
241 | 17 | 12 | 24 | 41 | 55 | 67 | 78 | 89 | 104 | 119 | 134 | 152 | 161 | 170 | 1 | 4 | 3 | 4 | 3 | 2 | 3 | 4 | 3 | 5 | 4 | 5 | 4 | 3 | 3 | 4 | 3 | 3 | 2 | 4 | 4 | 1 | 4 | 2 | 1 | 3 | 5 | 2 | 5 | 1 | 5 | 4 | 4 | 5 | 5 | 1 | 5 | 3 | 2 | 5 | 5 | 4 | 4 | 5 | 3 | 3 | 1 | 2 | 3 | 2 | 1 | 3
242 | 15 | 9 | 21 | 37 | 46 | 61 | 65 | 80 | 96 | 102 | 114 | 126 | 138 | 155 | 1 | 2 | 5 | 1 | 2 | 4 | 5 | 1 | 5 | 5 | 3 | 3 | 3 | 1 | 2 | 3 | 3 | 4 | 5 | 3 | 1 | 1 | 1 | 1 | 5 | 5 | 1 | 4 | 2 | 5 | 5 | 4 | 2 | 2 | 1 | 1 | 2 | 5 | 3 | 2 | 3 | 4 | 1 | 4 | 3 | 4 | 3 | 2 | 4 | 4 | 5 | 4
243 | 22 | 14 | 27 | 45 | 56 | 70 | 82 | 101 | 114 | 133 | 149 | 164 | 176 | 185 | 2 | 4 | 4 | 4 | 5 | 3 | 1 | 4 | 4 | 4 | 5 | 5 | 2 | 1 | 5 | 3 | 2 | 5 | 5 | 2 | 2 | 2 | 4 | 4 | 4 | 5 | 5 | 5 | 1 | 4 | 5 | 3 | 5 | 4 | 5 | 5 | 4 | 5 | 5 | 2 | 1 | 5 | 4 | 5 | 3 | 2 | 4 | 3 | 3 | 3 | 2 | 1
244 | 18 | 16 | 27 | 38 | 58 | 69 | 82 | 96 | 113 | 125 | 139 | 157 | 167 | 179 | 3 | 4 | 4 | 5 | 1 | 1 | 4 | 5 | 1 | 4 | 4 | 2 | 5 | 5 | 5 | 5 | 1 | 3 | 3 | 4 | 2 | 5 | 4 | 2 | 2 | 4 | 3 | 5 | 5 | 3 | 5 | 4 | 2 | 5 | 2 | 3 | 5 | 1 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 3 | 1 | 1 | 5 | 2 | 2 | 3
245 | 18 | 11 | 26 | 45 | 58 | 70 | 83 | 95 | 107 | 122 | 133 | 144 | 163 | 171 | 2 | 3 | 3 | 3 | 2 | 5 | 3 | 5 | 4 | 5 | 5 | 5 | 2 | 2 | 5 | 4 | 4 | 5 | 1 | 2 | 2 | 2 | 4 | 5 | 2 | 4 | 2 | 4 | 4 | 1 | 4 | 3 | 1 | 5 | 5 | 4 | 1 | 2 | 3 | 5 | 5 | 1 | 4 | 1 | 5 | 4 | 5 | 5 | 1 | 3 | 2 | 2
246 | 18 | 13 | 26 | 32 | 49 | 62 | 77 | 92 | 103 | 113 | 121 | 135 | 147 | 159 | 2 | 5 | 3 | 3 | 2 | 3 | 5 | 3 | 2 | 1 | 1 | 2 | 4 | 5 | 3 | 5 | 2 | 5 | 2 | 4 | 4 | 4 | 3 | 4 | 5 | 1 | 4 | 5 | 2 | 1 | 3 | 5 | 5 | 2 | 1 | 2 | 3 | 1 | 1 | 3 | 3 | 4 | 3 | 4 | 5 | 1 | 2 | 4 | 2 | 1 | 4 | 5
247 | 12 | 7 | 17 | 32 | 42 | 60 | 74 | 87 | 98 | 105 | 118 | 126 | 139 | 155 | 1 | 1 | 4 | 1 | 4 | 1 | 2 | 3 | 3 | 4 | 5 | 3 | 3 | 4 | 1 | 2 | 5 | 5 | 3 | 5 | 4 | 3 | 2 | 5 | 4 | 4 | 2 | 3 | 4 | 2 | 4 | 1 | 3 | 1 | 2 | 1 | 5 | 3 | 4 | 1 | 3 | 1 | 1 | 3 | 3 | 4 | 3 | 3 | 5 | 2 | 5 | 4
248 | 14 | 6 | 21 | 38 | 53 | 69 | 82 | 96 | 109 | 124 | 138 | 151 | 162 | 173 | 1 | 1 | 3 | 1 | 4 | 4 | 3 | 4 | 5 | 4 | 3 | 5 | 4 | 4 | 2 | 5 | 5 | 5 | 4 | 2 | 3 | 2 | 5 | 3 | 3 | 4 | 2 | 5 | 4 | 1 | 4 | 4 | 5 | 2 | 3 | 5 | 3 | 1 | 5 | 5 | 4 | 5 | 2 | 2 | 2 | 3 | 4 | 2 | 2 | 3 | 3 | 3
249 | 16 | 8 | 22 | 33 | 47 | 56 | 70 | 81 | 87 | 99 | 111 | 123 | 133 | 146 | 3 | 2 | 1 | 2 | 4 | 4 | 4 | 2 | 2 | 2 | 3 | 4 | 3 | 1 | 5 | 5 | 1 | 3 | 1 | 4 | 3 | 5 | 5 | 1 | 4 | 5 | 1 | 1 | 2 | 1 | 2 | 1 | 3 | 2 | 2 | 5 | 3 | 1 | 4 | 4 | 1 | 4 | 5 | 2 | 1 | 2 | 3 | 4 | 1 | 5 | 4 | 3
250 | 17 | 9 | 20 | 30 | 41 | 57 | 68 | 77 | 86 | 101 | 110 | 121 | 129 | 140 | 3 | 3 | 1 | 2 | 4 | 4 | 2 | 1 | 2 | 1 | 4 | 3 | 5 | 1 | 4 | 1 | 5 | 2 | 4 | 5 | 1 | 3 | 3 | 4 | 1 | 2 | 2 | 4 | 1 | 3 | 1 | 4 | 2 | 5 | 4 | 4 | 2 | 1 | 1 | 5 | 3 | 4 | 1 | 3 | 3 | 3 | 1 | 1 | 2 | 5 | 2 | 2
251 | 22 | 14 | 24 | 33 | 47 | 60 | 73 | 84 | 96 | 106 | 118 | 133 | 147 | 156 | 3 | 5 | 1 | 5 | 4 | 4 | 1 | 1 | 3 | 1 | 4 | 1 | 3 | 5 | 5 | 1 | 5 | 5 | 1 | 2 | 5 | 5 | 1 | 2 | 3 | 4 | 1 | 3 | 3 | 4 | 2 | 3 | 2 | 5 | 1 | 2 | 2 | 1 | 4 | 5 | 1 | 4 | 5 | 5 | 4 | 4 | 2 | 4 | 3 | 3 | 1 | 2
252 | 17 | 12 | 23 | 32 | 38 | 54 | 63 | 75 | 88 | 103 | 113 | 121 | 139 | 148 | 3 | 2 | 2 | 5 | 2 | 3 | 2 | 4 | 2 | 2 | 1 | 4 | 1 | 1 | 3 | 1 | 5 | 5 | 1 | 5 | 1 | 1 | 3 | 4 | 4 | 1 | 4 | 3 | 4 | 3 | 1 | 5 | 5 | 4 | 1 | 5 | 3 | 3 | 2 | 2 | 1 | 1 | 3 | 3 | 5 | 4 | 4 | 5 | 1 | 1 | 2 | 5
253 | 16 | 9 | 19 | 31 | 44 | 52 | 65 | 78 | 89 | 98 | 111 | 123 | 129 | 141 | 1 | 3 | 4 | 1 | 4 | 3 | 2 | 1 | 1 | 5 | 2 | 4 | 3 | 3 | 2 | 5 | 1 | 1 | 5 | 1 | 5 | 1 | 5 | 2 | 3 | 4 | 4 | 2 | 4 | 1 | 4 | 2 | 3 | 1 | 1 | 4 | 2 | 5 | 2 | 4 | 2 | 1 | 5 | 4 | 1 | 1 | 3 | 1 | 1 | 5 | 2 | 4
254 | 15 | 9 | 21 | 36 | 52 | 61 | 72 | 80 | 88 | 99 | 113 | 125 | 133 | 145 | 4 | 2 | 1 | 2 | 1 | 5 | 1 | 5 | 5 | 3 | 2 | 5 | 3 | 4 | 5 | 4 | 2 | 4 | 1 | 2 | 5 | 1 | 1 | 4 | 1 | 3 | 2 | 2 | 2 | 1 | 3 | 2 | 2 | 2 | 4 | 3 | 4 | 3 | 2 | 5 | 5 | 3 | 3 | 1 | 2 | 1 | 1 | 4 | 3 | 4 | 2 | 3
255 | 20 | 14 | 29 | 40 | 51 | 61 | 73 | 85 | 98 | 114 | 127 | 138 | 148 | 161 | 1 | 4 | 5 | 4 | 4 | 2 | 4 | 5 | 4 | 4 | 1 | 2 | 3 | 2 | 3 | 3 | 1 | 5 | 3 | 1 | 4 | 3 | 4 | 1 | 4 | 3 | 4 | 1 | 3 | 3 | 3 | 4 | 5 | 5 | 4 | 2 | 4 | 5 | 2 | 2 | 1 | 5 | 1 | 4 | 4 | 1 | 2 | 3 | 3 | 4 | 1 | 5
256 | 19 | 13 | 24 | 39 | 49 | 64 | 77 | 88 | 100 | 111 | 122 | 139 | 145 | 157 | 4 | 4 | 1 | 4 | 4 | 2 | 4 | 1 | 1 | 5 | 4 | 5 | 5 | 1 | 1 | 3 | 5 | 3 | 4 | 3 | 5 | 2 | 3 | 3 | 2 | 4 | 1 | 4 | 4 | 3 | 4 | 1 | 3 | 2 | 5 | 1 | 1 | 4 | 3 | 3 | 3 | 5 | 5 | 4 | 1 | 1 | 1 | 3 | 4 | 1 | 3 | 4
257 | 19 | 13 | 23 | 36 | 47 | 63 | 78 | 90 | 100 | 113 | 123 | 134 | 140 | 157 | 1 | 3 | 4 | 5 | 4 | 2 | 1 | 3 | 1 | 3 | 5 | 4 | 3 | 1 | 2 | 5 | 2 | 5 | 4 | 5 | 5 | 3 | 3 | 4 | 4 | 4 | 2 | 2 | 4 | 1 | 4 | 1 | 1 | 3 | 5 | 4 | 1 | 3 | 4 | 2 | 1 | 4 | 3 | 3 | 1 | 1 | 1 | 3 | 4 | 4 | 5 | 4
258 | 16 | 6 | 22 | 33 | 47 | 55 | 63 | 78 | 87 | 97 | 112 | 123 | 131 | 138 | 1 | 3 | 1 | 1 | 5 | 5 | 5 | 1 | 3 | 2 | 2 | 4 | 4 | 4 | 5 | 1 | 1 | 4 | 1 | 2 | 1 | 1 | 4 | 2 | 2 | 3 | 5 | 5 | 1 | 1 | 3 | 4 | 1 | 3 | 4 | 2 | 5 | 1 | 4 | 5 | 5 | 3 | 1 | 2 | 2 | 1 | 4 | 1 | 1 | 1 | 4 | 1
259 | 16 | 12 | 24 | 40 | 52 | 65 | 79 | 91 | 104 | 122 | 132 | 141 | 155 | 170 | 1 | 5 | 5 | 1 | 2 | 2 | 3 | 5 | 5 | 3 | 3 | 5 | 1 | 4 | 5 | 2 | 3 | 4 | 4 | 2 | 3 | 4 | 2 | 5 | 3 | 5 | 1 | 3 | 3 | 5 | 2 | 3 | 5 | 5 | 4 | 4 | 1 | 2 | 4 | 3 | 2 | 2 | 1 | 4 | 4 | 3 | 2 | 5 | 5 | 3 | 5 | 2
260 | 15 | 11 | 21 | 36 | 44 | 57 | 69 | 82 | 87 | 101 | 114 | 126 | 139 | 149 | 3 | 5 | 2 | 1 | 2 | 2 | 4 | 2 | 5 | 3 | 2 | 5 | 1 | 2 | 2 | 3 | 4 | 3 | 3 | 3 | 2 | 5 | 4 | 1 | 3 | 3 | 2 | 5 | 1 | 1 | 1 | 2 | 3 | 3 | 5 | 3 | 2 | 3 | 3 | 5 | 1 | 3 | 3 | 5 | 5 | 1 | 2 | 5 | 1 | 3 | 5 | 1
261 | 18 | 11 | 20 | 31 | 46 | 57 | 72 | 86 | 95 | 108 | 128 | 139 | 150 | 166 | 2 | 4 | 1 | 4 | 2 | 5 | 1 | 1 | 4 | 4 | 1 | 2 | 4 | 5 | 3 | 3 | 3 | 4 | 2 | 2 | 4 | 4 | 2 | 5 | 3 | 2 | 5 | 4 | 4 | 1 | 2 | 2 | 1 | 3 | 4 | 5 | 5 | 5 | 5 | 5 | 4 | 2 | 4 | 1 | 2 | 3 | 5 | 1 | 5 | 4 | 3 | 4
262 | 15 | 9 | 21 | 31 | 39 | 57 | 70 | 77 | 87 | 98 | 114 | 124 | 135 | 148 | 1 | 3 | 4 | 1 | 1 | 5 | 2 | 4 | 1 | 3 | 2 | 4 | 1 | 2 | 1 | 4 | 3 | 5 | 5 | 5 | 2 | 4 | 3 | 4 | 1 | 1 | 2 | 3 | 2 | 1 | 2 | 5 | 5 | 1 | 4 | 1 | 4 | 4 | 3 | 5 | 1 | 3 | 1 | 5 | 5 | 1 | 1 | 4 | 5 | 3 | 1 | 4
263 | 17 | 12 | 23 | 32 | 43 | 58 | 66 | 76 | 87 | 100 | 110 | 121 | 135 | 150 | 1 | 5 | 5 | 1 | 1 | 4 | 2 | 4 | 1 | 3 | 2 | 3 | 2 | 4 | 2 | 3 | 4 | 5 | 1 | 5 | 1 | 2 | 2 | 3 | 1 | 4 | 3 | 2 | 2 | 2 | 4 | 3 | 3 | 5 | 4 | 1 | 2 | 2 | 2 | 4 | 4 | 3 | 3 | 1 | 4 | 3 | 3 | 4 | 3 | 5 | 3 | 4
264 | 13 | 11 | 19 | 25 | 37 | 46 | 56 | 65 | 76 | 88 | 101 | 116 | 128 | 142 | 1 | 2 | 4 | 4 | 1 | 1 | 1 | 5 | 1 | 1 | 3 | 1 | 1 | 5 | 4 | 2 | 4 | 2 | 1 | 2 | 5 | 1 | 1 | 3 | 1 | 3 | 4 | 1 | 2 | 2 | 2 | 5 | 4 | 1 | 4 | 3 | 3 | 3 | 4 | 3 | 5 | 2 | 3 | 5 | 4 | 1 | 5 | 2 | 2 | 4 | 4 | 4
265 | 17 | 11 | 25 | 40 | 49 | 65 | 71 | 86 | 95 | 104 | 113 | 121 | 130 | 138 | 1 | 2 | 3 | 5 | 1 | 5 | 3 | 5 | 3 | 2 | 5 | 5 | 3 | 1 | 4 | 1 | 1 | 5 | 5 | 5 | 1 | 1 | 1 | 3 | 5 | 3 | 4 | 3 | 2 | 1 | 3 | 3 | 5 | 1 | 2 | 1 | 4 | 1 | 3 | 1 | 2 | 1 | 1 | 4 | 5 | 1 | 2 | 1 | 1 | 4 | 2 | 1
266 | 21 | 15 | 24 | 39 | 47 | 60 | 69 | 81 | 90 | 96 | 112 | 123 | 132 | 147 | 3 | 5 | 3 | 4 | 4 | 2 | 1 | 2 | 5 | 5 | 3 | 2 | 2 | 2 | 1 | 3 | 2 | 5 | 2 | 4 | 2 | 1 | 4 | 2 | 3 | 4 | 1 | 4 | 2 | 3 | 1 | 3 | 3 | 1 | 1 | 1 | 5 | 5 | 1 | 5 | 1 | 2 | 5 | 3 | 2 | 2 | 2 | 3 | 5 | 5 | 3 | 2
267 | 17 | 11 | 25 | 34 | 50 | 64 | 77 | 89 | 103 | 112 | 124 | 131 | 140 | 151 | 1 | 5 | 2 | 3 | 5 | 1 | 4 | 4 | 2 | 1 | 3 | 3 | 5 | 5 | 2 | 4 | 5 | 1 | 5 | 3 | 3 | 3 | 5 | 2 | 4 | 1 | 3 | 4 | 5 | 4 | 4 | 1 | 2 | 4 | 1 | 2 | 2 | 3 | 3 | 4 | 1 | 1 | 3 | 2 | 1 | 1 | 5 | 2 | 4 | 3 | 3 | 1
268 | 19 | 10 | 24 | 36 | 47 | 60 | 75 | 89 | 104 | 118 | 130 | 142 | 154 | 166 | 3 | 1 | 2 | 4 | 4 | 5 | 4 | 1 | 3 | 2 | 4 | 3 | 5 | 1 | 1 | 4 | 5 | 5 | 1 | 2 | 2 | 5 | 4 | 4 | 3 | 4 | 5 | 2 | 4 | 4 | 4 | 3 | 5 | 5 | 2 | 2 | 5 | 2 | 3 | 2 | 1 | 4 | 5 | 2 | 3 | 3 | 1 | 5 | 5 | 4 | 1 | 2
269 | 14 | 8 | 21 | 32 | 43 | 51 | 63 | 70 | 82 | 90 | 104 | 118 | 129 | 145 | 3 | 1 | 2 | 2 | 5 | 1 | 4 | 3 | 4 | 3 | 1 | 3 | 1 | 4 | 1 | 5 | 2 | 1 | 3 | 2 | 4 | 2 | 5 | 1 | 1 | 1 | 4 | 1 | 1 | 5 | 1 | 5 | 2 | 3 | 2 | 1 | 3 | 3 | 3 | 5 | 3 | 4 | 3 | 4 | 1 | 3 | 5 | 2 | 5 | 5 | 4 | 2
270 | 13 | 9 | 16 | 27 | 36 | 42 | 51 | 63 | 74 | 80 | 96 | 109 | 117 | 130 | 2 | 1 | 3 | 3 | 3 | 1 | 2 | 1 | 1 | 5 | 1 | 4 | 2 | 2 | 4 | 1 | 1 | 1 | 1 | 3 | 2 | 2 | 2 | 3 | 4 | 4 | 1 | 3 | 3 | 5 | 1 | 2 | 1 | 1 | 1 | 3 | 5 | 5 | 1 | 5 | 1 | 4 | 3 | 5 | 1 | 1 | 1 | 5 | 1 | 3 | 4 | 5
271 | 12 | 10 | 20 | 31 | 43 | 56 | 67 | 73 | 84 | 93 | 103 | 119 | 134 | 149 | 3 | 1 | 4 | 2 | 1 | 1 | 3 | 5 | 1 | 1 | 4 | 5 | 4 | 1 | 4 | 3 | 5 | 3 | 3 | 2 | 3 | 4 | 1 | 3 | 1 | 2 | 2 | 1 | 2 | 2 | 4 | 3 | 1 | 1 | 4 | 3 | 3 | 2 | 2 | 3 | 5 | 3 | 5 | 3 | 5 | 5 | 2 | 3 | 5 | 5 | 3 | 2
272 | 24 | 19 | 28 | 40 | 53 | 64 | 77 | 94 | 108 | 121 | 134 | 146 | 157 | 175 | 5 | 4 | 5 | 5 | 3 | 2 | 1 | 3 | 4 | 1 | 2 | 5 | 4 | 2 | 4 | 3 | 1 | 4 | 4 | 2 | 2 | 5 | 2 | 4 | 5 | 3 | 4 | 5 | 5 | 3 | 1 | 5 | 4 | 4 | 2 | 3 | 2 | 2 | 4 | 5 | 3 | 3 | 1 | 5 | 5 | 1 | 2 | 3 | 5 | 3 | 5 | 5
273 | 19 | 11 | 25 | 37 | 49 | 66 | 79 | 90 | 101 | 113 | 126 | 137 | 149 | 163 | 5 | 4 | 1 | 1 | 3 | 5 | 4 | 2 | 4 | 1 | 2 | 5 | 5 | 1 | 5 | 1 | 5 | 5 | 5 | 2 | 4 | 4 | 1 | 4 | 1 | 4 | 5 | 1 | 5 | 1 | 4 | 1 | 4 | 3 | 1 | 4 | 3 | 2 | 5 | 3 | 2 | 2 | 5 | 2 | 1 | 3 | 4 | 4 | 3 | 2 | 4 | 5
274 | 16 | 12 | 22 | 30 | 41 | 51 | 60 | 69 | 84 | 94 | 102 | 111 | 123 | 135 | 1 | 4 | 2 | 5 | 3 | 1 | 5 | 1 | 4 | 1 | 1 | 2 | 2 | 5 | 1 | 3 | 3 | 4 | 2 | 1 | 4 | 2 | 1 | 2 | 1 | 5 | 2 | 1 | 5 | 3 | 4 | 3 | 2 | 3 | 4 | 1 | 3 | 3 | 1 | 1 | 2 | 2 | 3 | 2 | 1 | 5 | 2 | 4 | 3 | 1 | 3 | 5
275 | 19 | 12 | 24 | 33 | 49 | 59 | 75 | 87 | 101 | 110 | 124 | 136 | 149 | 161 | 1 | 5 | 4 | 2 | 4 | 3 | 2 | 3 | 5 | 1 | 2 | 1 | 5 | 1 | 5 | 5 | 2 | 3 | 1 | 4 | 5 | 1 | 5 | 5 | 4 | 5 | 2 | 1 | 1 | 4 | 5 | 4 | 5 | 1 | 2 | 1 | 1 | 4 | 4 | 5 | 4 | 1 | 3 | 4 | 1 | 3 | 4 | 5 | 3 | 2 | 5 | 2
276 | 22 | 13 | 28 | 46 | 59 | 72 | 87 | 99 | 110 | 116 | 123 | 136 | 152 | 161 | 5 | 2 | 3 | 3 | 5 | 4 | 3 | 3 | 5 | 4 | 4 | 5 | 5 | 5 | 2 | 1 | 1 | 4 | 3 | 5 | 4 | 3 | 5 | 3 | 4 | 2 | 5 | 1 | 1 | 5 | 3 | 2 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 4 | 2 | 5 | 2 | 4 | 5 | 4 | 4 | 3 | 2 | 3 | 2 | 2
277 | 15 | 10 | 24 | 39 | 58 | 66 | 78 | 88 | 100 | 110 | 123 | 135 | 149 | 162 | 2 | 2 | 3 | 3 | 2 | 3 | 5 | 4 | 5 | 4 | 4 | 2 | 5 | 5 | 5 | 4 | 1 | 3 | 2 | 2 | 1 | 4 | 5 | 2 | 2 | 4 | 1 | 3 | 1 | 3 | 5 | 3 | 4 | 2 | 2 | 2 | 3 | 2 | 4 | 4 | 3 | 3 | 2 | 4 | 2 | 5 | 5 | 2 | 5 | 1 | 4 | 3
278 | 21 | 14 | 26 | 40 | 54 | 65 | 78 | 90 | 103 | 115 | 126 | 140 | 153 | 159 | 5 | 1 | 5 | 3 | 5 | 2 | 4 | 1 | 3 | 5 | 4 | 2 | 5 | 2 | 5 | 2 | 1 | 4 | 2 | 4 | 1 | 5 | 2 | 5 | 1 | 5 | 1 | 5 | 5 | 3 | 1 | 4 | 5 | 2 | 2 | 3 | 1 | 3 | 4 | 3 | 5 | 4 | 2 | 3 | 3 | 4 | 1 | 5 | 1 | 2 | 1 | 2
279 | 23 | 16 | 26 | 40 | 54 | 68 | 79 | 96 | 109 | 124 | 136 | 147 | 157 | 172 | 5 | 4 | 2 | 5 | 5 | 2 | 2 | 1 | 3 | 5 | 3 | 3 | 1 | 5 | 5 | 3 | 4 | 2 | 5 | 3 | 3 | 1 | 4 | 3 | 5 | 5 | 2 | 5 | 2 | 4 | 3 | 4 | 4 | 3 | 4 | 4 | 3 | 4 | 3 | 2 | 2 | 1 | 4 | 4 | 4 | 3 | 1 | 2 | 2 | 4 | 4 | 5
280 | 16 | 10 | 21 | 29 | 45 | 54 | 65 | 77 | 88 | 100 | 107 | 116 | 127 | 140 | 1 | 3 | 5 | 1 | 2 | 4 | 1 | 4 | 3 | 1 | 3 | 1 | 4 | 2 | 5 | 5 | 1 | 3 | 1 | 4 | 2 | 3 | 5 | 1 | 4 | 3 | 1 | 4 | 4 | 1 | 1 | 5 | 5 | 1 | 3 | 3 | 1 | 1 | 2 | 3 | 1 | 3 | 2 | 3 | 4 | 1 | 2 | 4 | 4 | 4 | 3 | 2
281 | 19 | 12 | 24 | 35 | 45 | 60 | 70 | 82 | 92 | 110 | 127 | 144 | 155 | 172 | 3 | 3 | 1 | 5 | 4 | 3 | 3 | 2 | 3 | 2 | 2 | 4 | 1 | 2 | 5 | 2 | 4 | 4 | 4 | 3 | 2 | 2 | 1 | 5 | 1 | 5 | 2 | 4 | 4 | 1 | 1 | 4 | 5 | 3 | 5 | 5 | 3 | 5 | 4 | 5 | 4 | 3 | 5 | 5 | 3 | 2 | 4 | 2 | 3 | 5 | 5 | 4
282 | 20 | 17 | 24 | 30 | 40 | 55 | 60 | 68 | 78 | 93 | 103 | 118 | 129 | 142 | 5 | 5 | 3 | 4 | 1 | 2 | 1 | 3 | 2 | 1 | 1 | 2 | 3 | 3 | 2 | 2 | 1 | 5 | 5 | 4 | 1 | 2 | 1 | 1 | 1 | 2 | 4 | 1 | 1 | 3 | 4 | 2 | 5 | 1 | 4 | 5 | 2 | 4 | 2 | 2 | 4 | 3 | 5 | 3 | 1 | 5 | 1 | 4 | 3 | 4 | 5 | 1
283 | 14 | 10 | 22 | 36 | 47 | 59 | 74 | 87 | 104 | 112 | 126 | 134 | 142 | 151 | 3 | 3 | 3 | 1 | 2 | 2 | 5 | 3 | 5 | 4 | 3 | 2 | 3 | 2 | 3 | 3 | 2 | 2 | 3 | 5 | 5 | 2 | 3 | 5 | 4 | 2 | 5 | 2 | 4 | 4 | 4 | 5 | 2 | 2 | 2 | 2 | 5 | 2 | 3 | 4 | 3 | 1 | 1 | 3 | 1 | 2 | 1 | 4 | 1 | 4 | 2 | 2
284 | 16 | 11 | 23 | 38 | 49 | 61 | 72 | 87 | 100 | 109 | 120 | 130 | 142 | 151 | 2 | 1 | 5 | 3 | 2 | 3 | 5 | 2 | 4 | 3 | 4 | 4 | 5 | 2 | 1 | 3 | 3 | 3 | 1 | 5 | 2 | 4 | 1 | 4 | 2 | 4 | 4 | 5 | 5 | 2 | 4 | 2 | 3 | 4 | 1 | 1 | 3 | 1 | 3 | 4 | 4 | 1 | 4 | 1 | 3 | 4 | 1 | 4 | 1 | 1 | 3 | 4
285 | 20 | 14 | 27 | 41 | 49 | 60 | 71 | 82 | 92 | 104 | 117 | 131 | 143 | 155 | 2 | 2 | 5 | 5 | 3 | 3 | 4 | 3 | 5 | 4 | 1 | 4 | 3 | 1 | 2 | 2 | 5 | 2 | 2 | 2 | 4 | 2 | 1 | 4 | 3 | 1 | 3 | 4 | 4 | 4 | 1 | 1 | 3 | 4 | 3 | 2 | 4 | 2 | 2 | 5 | 4 | 4 | 4 | 2 | 1 | 3 | 3 | 5 | 4 | 1 | 2 | 5
286 | 13 | 7 | 18 | 29 | 39 | 53 | 67 | 85 | 91 | 98 | 111 | 122 | 138 | 148 | 1 | 1 | 4 | 1 | 1 | 5 | 2 | 3 | 2 | 1 | 4 | 4 | 1 | 3 | 5 | 1 | 5 | 3 | 5 | 1 | 3 | 5 | 5 | 1 | 5 | 4 | 4 | 5 | 1 | 2 | 1 | 2 | 3 | 2 | 1 | 1 | 3 | 4 | 5 | 1 | 3 | 3 | 4 | 1 | 3 | 3 | 5 | 5 | 2 | 2 | 2 | 4
287 | 25 | 16 | 29 | 42 | 56 | 67 | 80 | 88 | 101 | 112 | 125 | 135 | 142 | 148 | 5 | 4 | 3 | 4 | 5 | 4 | 2 | 2 | 4 | 5 | 2 | 2 | 4 | 4 | 3 | 3 | 5 | 3 | 2 | 1 | 4 | 5 | 3 | 1 | 2 | 3 | 1 | 2 | 2 | 5 | 2 | 4 | 1 | 3 | 3 | 4 | 2 | 3 | 3 | 5 | 5 | 3 | 1 | 1 | 1 | 1 | 4 | 1 | 2 | 1 | 1 | 2
288 | 17 | 15 | 26 | 36 | 45 | 57 | 73 | 78 | 90 | 106 | 118 | 131 | 143 | 156 | 4 | 1 | 5 | 5 | 1 | 1 | 5 | 4 | 1 | 3 | 3 | 3 | 2 | 3 | 2 | 2 | 2 | 2 | 3 | 5 | 5 | 4 | 4 | 3 | 1 | 1 | 2 | 1 | 3 | 1 | 5 | 3 | 4 | 3 | 4 | 5 | 1 | 4 | 2 | 5 | 3 | 1 | 5 | 4 | 3 | 4 | 3 | 2 | 3 | 3 | 3 | 4
289 | 17 | 14 | 25 | 38 | 47 | 60 | 67 | 80 | 88 | 104 | 118 | 129 | 142 | 149 | 5 | 4 | 2 | 3 | 2 | 1 | 4 | 4 | 3 | 1 | 4 | 5 | 1 | 3 | 2 | 3 | 4 | 1 | 5 | 3 | 2 | 1 | 1 | 3 | 3 | 1 | 5 | 4 | 1 | 2 | 1 | 4 | 3 | 5 | 5 | 3 | 4 | 4 | 5 | 1 | 1 | 5 | 3 | 2 | 5 | 1 | 4 | 3 | 2 | 2 | 2 | 1
290 | 21 | 15 | 24 | 30 | 42 | 54 | 63 | 73 | 91 | 105 | 120 | 134 | 145 | 156 | 1 | 4 | 5 | 5 | 1 | 5 | 1 | 2 | 1 | 1 | 2 | 2 | 1 | 4 | 3 | 4 | 4 | 2 | 5 | 1 | 1 | 2 | 3 | 3 | 3 | 4 | 2 | 1 | 5 | 4 | 5 | 4 | 5 | 5 | 3 | 1 | 4 | 4 | 2 | 5 | 5 | 4 | 4 | 1 | 5 | 2 | 3 | 1 | 1 | 4 | 3 | 3
291 | 17 | 14 | 23 | 39 | 53 | 61 | 74 | 88 | 101 | 109 | 125 | 137 | 145 | 157 | 3 | 2 | 4 | 5 | 2 | 1 | 4 | 2 | 2 | 5 | 5 | 4 | 1 | 4 | 4 | 5 | 1 | 2 | 3 | 2 | 4 | 4 | 1 | 4 | 5 | 5 | 1 | 3 | 5 | 4 | 2 | 2 | 4 | 1 | 1 | 2 | 5 | 5 | 4 | 2 | 1 | 3 | 5 | 3 | 3 | 1 | 2 | 2 | 4 | 5 | 2 | 1
292 | 9 | 7 | 13 | 25 | 35 | 47 | 57 | 68 | 80 | 91 | 101 | 109 | 122 | 135 | 2 | 2 | 1 | 2 | 1 | 1 | 3 | 1 | 4 | 1 | 4 | 3 | 3 | 3 | 3 | 1 | 3 | 1 | 5 | 3 | 1 | 3 | 5 | 1 | 4 | 3 | 2 | 2 | 5 | 4 | 2 | 1 | 2 | 2 | 5 | 2 | 4 | 2 | 2 | 2 | 1 | 3 | 2 | 2 | 4 | 4 | 4 | 1 | 4 | 4 | 4 | 1
293 | 21 | 16 | 28 | 43 | 54 | 67 | 77 | 88 | 99 | 113 | 131 | 145 | 157 | 166 | 5 | 2 | 4 | 5 | 3 | 2 | 5 | 2 | 5 | 5 | 2 | 3 | 2 | 1 | 5 | 3 | 5 | 5 | 1 | 2 | 2 | 4 | 1 | 3 | 5 | 3 | 1 | 2 | 4 | 1 | 4 | 2 | 2 | 5 | 4 | 3 | 5 | 4 | 5 | 4 | 4 | 3 | 4 | 3 | 3 | 2 | 2 | 5 | 3 | 1 | 3 | 2
294 | 20 | 11 | 30 | 46 | 57 | 69 | 82 | 92 | 106 | 123 | 136 | 150 | 161 | 167 | 3 | 2 | 1 | 5 | 5 | 4 | 5 | 5 | 5 | 3 | 4 | 4 | 1 | 2 | 3 | 5 | 3 | 4 | 1 | 4 | 4 | 4 | 3 | 2 | 2 | 4 | 3 | 1 | 5 | 2 | 2 | 5 | 5 | 5 | 3 | 4 | 5 | 5 | 1 | 2 | 5 | 1 | 4 | 4 | 4 | 2 | 2 | 3 | 1 | 3 | 1 | 1
295 | 16 | 10 | 24 | 31 | 43 | 57 | 69 | 87 | 99 | 111 | 123 | 136 | 150 | 162 | 2 | 2 | 2 | 4 | 4 | 2 | 3 | 5 | 1 | 1 | 2 | 3 | 4 | 2 | 4 | 2 | 5 | 4 | 2 | 3 | 2 | 1 | 5 | 4 | 5 | 5 | 3 | 5 | 4 | 3 | 2 | 3 | 4 | 4 | 1 | 3 | 4 | 2 | 5 | 1 | 2 | 5 | 2 | 4 | 5 | 5 | 2 | 2 | 5 | 1 | 2 | 4
296 | 16 | 9 | 20 | 32 | 38 | 50 | 64 | 82 | 93 | 102 | 113 | 123 | 136 | 144 | 2 | 2 | 2 | 3 | 3 | 4 | 1 | 3 | 3 | 2 | 4 | 3 | 1 | 1 | 2 | 2 | 4 | 2 | 1 | 5 | 5 | 2 | 3 | 4 | 5 | 5 | 5 | 3 | 3 | 1 | 3 | 4 | 2 | 2 | 1 | 4 | 4 | 5 | 1 | 1 | 5 | 2 | 1 | 2 | 4 | 5 | 3 | 1 | 3 | 2 | 2 | 1
297 | 13 | 10 | 15 | 27 | 39 | 52 | 65 | 77 | 87 | 99 | 117 | 129 | 140 | 149 | 3 | 4 | 2 | 1 | 1 | 2 | 1 | 1 | 4 | 5 | 2 | 1 | 3 | 5 | 2 | 2 | 5 | 5 | 2 | 1 | 1 | 4 | 3 | 5 | 4 | 5 | 1 | 2 | 2 | 2 | 4 | 2 | 3 | 4 | 3 | 2 | 5 | 5 | 5 | 3 | 3 | 1 | 5 | 3 | 2 | 2 | 5 | 2 | 5 | 1 | 1 | 2
298 | 18 | 14 | 27 | 44 | 61 | 76 | 83 | 97 | 107 | 120 | 135 | 145 | 154 | 163 | 3 | 5 | 3 | 3 | 2 | 2 | 4 | 5 | 5 | 5 | 5 | 2 | 3 | 4 | 5 | 5 | 5 | 2 | 4 | 4 | 2 | 1 | 3 | 1 | 3 | 3 | 4 | 4 | 1 | 3 | 5 | 1 | 1 | 5 | 4 | 3 | 3 | 5 | 4 | 3 | 5 | 1 | 2 | 2 | 2 | 1 | 5 | 1 | 5 | 2 | 1 | 1
299 | 20 | 12 | 26 | 39 | 45 | 55 | 68 | 83 | 96 | 103 | 112 | 121 | 134 | 145 | 5 | 4 | 1 | 2 | 3 | 5 | 4 | 2 | 5 | 4 | 1 | 3 | 1 | 1 | 3 | 1 | 2 | 1 | 4 | 3 | 5 | 2 | 4 | 2 | 4 | 3 | 4 | 4 | 5 | 3 | 1 | 4 | 2 | 2 | 1 | 2 | 3 | 3 | 1 | 2 | 2 | 2 | 1 | 4 | 4 | 2 | 3 | 4 | 2 | 4 | 1 | 4
300 | 16 | 11 | 24 | 40 | 51 | 64 | 71 | 86 | 94 | 105 | 118 | 132 | 142 | 153 | 1 | 3 | 2 | 5 | 3 | 2 | 3 | 5 | 4 | 4 | 4 | 4 | 3 | 4 | 1 | 3 | 2 | 1 | 5 | 5 | 4 | 1 | 1 | 1 | 3 | 5 | 5 | 2 | 3 | 1 | 3 | 1 | 1 | 3 | 2 | 5 | 2 | 5 | 4 | 2 | 5 | 3 | 3 | 3 | 4 | 3 | 1 | 2 | 2 | 3 | 3 | 3
301 | 14 | 8 | 21 | 33 | 42 | 55 | 66 | 78 | 91 | 100 | 113 | 132 | 143 | 156 | 1 | 4 | 1 | 2 | 1 | 5 | 2 | 5 | 3 | 2 | 4 | 3 | 1 | 2 | 5 | 1 | 4 | 5 | 1 | 3 | 1 | 3 | 5 | 2 | 1 | 1 | 5 | 5 | 2 | 2 | 4 | 5 | 2 | 2 | 1 | 4 | 2 | 3 | 5 | 3 | 4 | 5 | 5 | 5 | 5 | 4 | 1 | 1 | 2 | 5 | 2 | 4
302 | 18 | 14 | 23 | 34 | 41 | 57 | 69 | 84 | 97 | 110 | 123 | 131 | 140 | 149 | 4 | 3 | 4 | 3 | 2 | 2 | 3 | 2 | 1 | 3 | 3 | 4 | 1 | 1 | 1 | 4 | 5 | 4 | 2 | 5 | 1 | 5 | 4 | 2 | 3 | 4 | 3 | 5 | 3 | 2 | 4 | 4 | 4 | 5 | 3 | 1 | 2 | 1 | 5 | 5 | 1 | 4 | 1 | 2 | 3 | 3 | 1 | 2 | 2 | 4 | 2 | 1
303 | 22 | 15 | 29 | 38 | 52 | 62 | 75 | 89 | 96 | 105 | 118 | 130 | 146 | 155 | 5 | 2 | 5 | 3 | 2 | 5 | 5 | 2 | 2 | 5 | 1 | 1 | 4 | 2 | 4 | 4 | 5 | 1 | 1 | 3 | 4 | 2 | 5 | 2 | 4 | 2 | 3 | 5 | 1 | 1 | 3 | 2 | 2 | 3 | 1 | 3 | 4 | 5 | 2 | 2 | 1 | 5 | 2 | 4 | 3 | 4 | 4 | 5 | 4 | 1 | 2 | 2
304 | 26 | 17 | 32 | 43 | 56 | 70 | 80 | 91 | 104 | 119 | 130 | 143 | 153 | 167 | 5 | 3 | 4 | 5 | 5 | 4 | 3 | 3 | 1 | 3 | 2 | 5 | 4 | 3 | 5 | 1 | 2 | 4 | 5 | 3 | 1 | 2 | 3 | 4 | 4 | 3 | 3 | 1 | 2 | 5 | 1 | 5 | 4 | 3 | 3 | 5 | 5 | 1 | 1 | 4 | 3 | 4 | 4 | 2 | 4 | 1 | 3 | 2 | 1 | 5 | 3 | 5
305 | 25 | 16 | 30 | 42 | 51 | 66 | 85 | 96 | 107 | 121 | 130 | 142 | 155 | 162 | 4 | 4 | 5 | 3 | 4 | 5 | 1 | 4 | 4 | 3 | 4 | 1 | 2 | 2 | 4 | 1 | 4 | 4 | 2 | 5 | 5 | 5 | 4 | 5 | 1 | 4 | 1 | 5 | 2 | 1 | 5 | 3 | 5 | 5 | 3 | 1 | 4 | 2 | 2 | 1 | 1 | 1 | 5 | 5 | 4 | 5 | 3 | 1 | 2 | 2 | 1 | 2
306 | 17 | 8 | 24 | 37 | 45 | 59 | 70 | 78 | 87 | 98 | 109 | 119 | 135 | 150 | 3 | 1 | 2 | 2 | 4 | 5 | 5 | 2 | 3 | 5 | 4 | 1 | 2 | 3 | 2 | 1 | 2 | 3 | 5 | 4 | 1 | 4 | 1 | 5 | 3 | 1 | 1 | 3 | 1 | 2 | 2 | 4 | 3 | 2 | 4 | 2 | 1 | 3 | 3 | 4 | 5 | 1 | 3 | 1 | 5 | 4 | 4 | 3 | 4 | 3 | 5 | 3
307 | 18 | 11 | 24 | 36 | 45 | 52 | 66 | 75 | 86 | 97 | 106 | 116 | 125 | 130 | 4 | 5 | 1 | 1 | 4 | 3 | 4 | 2 | 2 | 4 | 1 | 5 | 3 | 2 | 2 | 2 | 1 | 1 | 1 | 4 | 2 | 5 | 3 | 4 | 4 | 2 | 2 | 1 | 4 | 1 | 1 | 5 | 4 | 1 | 5 | 1 | 1 | 3 | 1 | 4 | 4 | 1 | 1 | 4 | 4 | 2 | 1 | 2 | 1 | 2 | 1 | 1
308 | 22 | 14 | 29 | 42 | 51 | 67 | 77 | 85 | 101 | 117 | 132 | 145 | 158 | 168 | 3 | 1 | 5 | 5 | 3 | 5 | 2 | 5 | 4 | 5 | 3 | 1 | 2 | 3 | 2 | 2 | 5 | 5 | 2 | 4 | 1 | 2 | 3 | 4 | 2 | 1 | 3 | 2 | 5 | 5 | 2 | 4 | 4 | 4 | 5 | 3 | 5 | 4 | 4 | 2 | 4 | 4 | 2 | 3 | 5 | 4 | 1 | 3 | 1 | 1 | 3 | 5
309 | 15 | 9 | 21 | 29 | 41 | 56 | 65 | 78 | 90 | 100 | 109 | 122 | 134 | 145 | 3 | 2 | 3 | 1 | 2 | 4 | 2 | 4 | 2 | 1 | 3 | 2 | 1 | 4 | 2 | 5 | 2 | 5 | 5 | 3 | 1 | 5 | 1 | 2 | 3 | 4 | 3 | 3 | 4 | 4 | 2 | 2 | 3 | 1 | 2 | 4 | 1 | 4 | 2 | 2 | 3 | 3 | 2 | 5 | 2 | 1 | 4 | 5 | 5 | 3 | 2 | 1
310 | 19 | 11 | 27 | 43 | 54 | 71 | 85 | 97 | 108 | 119 | 130 | 145 | 156 | 172 | 1 | 4 | 5 | 1 | 4 | 4 | 3 | 5 | 4 | 5 | 5 | 2 | 5 | 1 | 3 | 2 | 5 | 5 | 3 | 4 | 2 | 4 | 5 | 3 | 1 | 5 | 4 | 2 | 3 | 3 | 2 | 3 | 1 | 4 | 4 | 2 | 5 | 1 | 2 | 3 | 2 | 4 | 4 | 5 | 4 | 2 | 4 | 1 | 5 | 5 | 2 | 4
311 | 18 | 9 | 24 | 37 | 49 | 57 | 72 | 84 | 96 | 111 | 121 | 140 | 150 | 162 | 1 | 2 | 5 | 1 | 4 | 5 | 5 | 1 | 2 | 3 | 5 | 3 | 3 | 3 | 2 | 4 | 3 | 1 | 1 | 3 | 3 | 2 | 5 | 5 | 3 | 1 | 4 | 4 | 3 | 3 | 3 | 3 | 5 | 3 | 3 | 4 | 3 | 2 | 1 | 4 | 5 | 5 | 5 | 4 | 1 | 5 | 1 | 3 | 2 | 4 | 4 | 2
312 | 16 | 10 | 20 | 36 | 48 | 59 | 67 | 81 | 91 | 104 | 110 | 118 | 128 | 142 | 3 | 3 | 3 | 1 | 2 | 4 | 3 | 1 | 5 | 4 | 5 | 2 | 1 | 5 | 2 | 4 | 5 | 1 | 2 | 3 | 5 | 1 | 1 | 1 | 3 | 3 | 5 | 3 | 2 | 1 | 5 | 2 | 2 | 4 | 4 | 3 | 1 | 2 | 1 | 2 | 2 | 3 | 2 | 1 | 2 | 4 | 2 | 2 | 4 | 2 | 3 | 5
313 | 18 | 12 | 27 | 37 | 50 | 67 | 78 | 91 | 101 | 113 | 122 | 135 | 147 | 160 | 5 | 1 | 4 | 2 | 3 | 3 | 5 | 4 | 3 | 1 | 2 | 4 | 2 | 3 | 4 | 4 | 5 | 3 | 4 | 5 | 1 | 5 | 3 | 2 | 4 | 3 | 5 | 1 | 4 | 2 | 2 | 2 | 2 | 1 | 5 | 4 | 1 | 3 | 3 | 2 | 3 | 3 | 2 | 5 | 4 | 2 | 3 | 3 | 2 | 4 | 2 | 5
314 | 19 | 12 | 27 | 37 | 44 | 54 | 69 | 79 | 89 | 107 | 123 | 133 | 148 | 162 | 1 | 1 | 5 | 5 | 3 | 4 | 5 | 3 | 3 | 5 | 1 | 1 | 3 | 1 | 2 | 1 | 4 | 3 | 1 | 2 | 5 | 3 | 5 | 2 | 1 | 4 | 1 | 4 | 5 | 1 | 1 | 3 | 4 | 5 | 5 | 4 | 4 | 5 | 3 | 4 | 2 | 2 | 3 | 3 | 1 | 4 | 5 | 5 | 4 | 5 | 2 | 3
315 | 19 | 13 | 28 | 44 | 59 | 73 | 84 | 96 | 111 | 118 | 129 | 142 | 153 | 169 | 3 | 5 | 2 | 3 | 5 | 1 | 4 | 5 | 3 | 5 | 5 | 3 | 4 | 5 | 1 | 5 | 2 | 3 | 5 | 4 | 3 | 4 | 2 | 2 | 2 | 5 | 2 | 3 | 5 | 4 | 3 | 3 | 4 | 1 | 1 | 1 | 3 | 1 | 2 | 5 | 5 | 4 | 3 | 1 | 2 | 2 | 3 | 4 | 2 | 5 | 5 | 4
316 | 21 | 17 | 29 | 38 | 54 | 65 | 81 | 93 | 106 | 119 | 134 | 151 | 158 | 172 | 5 | 3 | 4 | 5 | 3 | 1 | 3 | 5 | 1 | 2 | 3 | 3 | 5 | 5 | 2 | 4 | 2 | 2 | 4 | 3 | 5 | 5 | 2 | 4 | 5 | 2 | 1 | 4 | 1 | 4 | 4 | 4 | 1 | 4 | 5 | 3 | 4 | 4 | 5 | 2 | 5 | 5 | 5 | 2 | 1 | 1 | 1 | 4 | 5 | 5 | 3 | 1
317 | 20 | 13 | 27 | 43 | 49 | 60 | 70 | 79 | 93 | 106 | 121 | 129 | 146 | 157 | 3 | 2 | 4 | 4 | 5 | 2 | 4 | 3 | 5 | 3 | 5 | 3 | 1 | 3 | 1 | 1 | 1 | 4 | 4 | 2 | 1 | 1 | 4 | 4 | 1 | 5 | 1 | 2 | 1 | 5 | 5 | 3 | 1 | 5 | 5 | 2 | 4 | 5 | 5 | 1 | 3 | 3 | 1 | 1 | 4 | 5 | 5 | 3 | 3 | 3 | 3 | 2
318 | 15 | 9 | 22 | 33 | 42 | 55 | 67 | 76 | 85 | 100 | 113 | 123 | 139 | 147 | 2 | 2 | 4 | 1 | 2 | 4 | 3 | 4 | 4 | 1 | 2 | 4 | 1 | 3 | 4 | 1 | 2 | 5 | 3 | 3 | 1 | 5 | 3 | 3 | 1 | 2 | 5 | 1 | 1 | 1 | 3 | 4 | 5 | 4 | 5 | 1 | 2 | 4 | 3 | 4 | 3 | 3 | 2 | 2 | 2 | 4 | 5 | 5 | 3 | 1 | 2 | 2
319 | 15 | 11 | 22 | 34 | 47 | 58 | 69 | 83 | 91 | 100 | 114 | 127 | 139 | 151 | 1 | 4 | 4 | 2 | 3 | 1 | 4 | 3 | 4 | 2 | 2 | 4 | 3 | 1 | 4 | 5 | 4 | 5 | 1 | 1 | 1 | 2 | 4 | 4 | 4 | 4 | 2 | 4 | 3 | 1 | 1 | 3 | 1 | 1 | 3 | 4 | 4 | 2 | 3 | 5 | 4 | 4 | 1 | 4 | 4 | 4 | 1 | 3 | 5 | 3 | 1 | 3
320 | 20 | 11 | 23 | 34 | 42 | 58 | 70 | 81 | 89 | 98 | 113 | 129 | 141 | 154 | 2 | 2 | 3 | 4 | 5 | 4 | 2 | 1 | 3 | 3 | 2 | 3 | 4 | 2 | 1 | 1 | 4 | 5 | 4 | 3 | 4 | 5 | 1 | 2 | 5 | 2 | 1 | 3 | 4 | 1 | 2 | 1 | 1 | 1 | 2 | 5 | 1 | 5 | 4 | 5 | 4 | 5 | 2 | 5 | 3 | 3 | 2 | 4 | 1 | 5 | 3 | 4
321 | 24 | 16 | 29 | 46 | 63 | 79 | 91 | 101 | 111 | 125 | 142 | 158 | 169 | 175 | 4 | 4 | 4 | 4 | 5 | 3 | 3 | 2 | 5 | 4 | 4 | 4 | 5 | 4 | 3 | 5 | 5 | 2 | 4 | 5 | 1 | 5 | 5 | 1 | 2 | 1 | 3 | 4 | 1 | 3 | 5 | 1 | 5 | 3 | 3 | 3 | 2 | 5 | 5 | 5 | 5 | 5 | 2 | 4 | 4 | 4 | 2 | 1 | 1 | 1 | 2 | 2
322 | 13 | 7 | 21 | 32 | 43 | 57 | 66 | 82 | 92 | 104 | 122 | 133 | 143 | 157 | 2 | 3 | 1 | 1 | 4 | 2 | 5 | 3 | 2 | 2 | 2 | 5 | 1 | 3 | 4 | 3 | 4 | 4 | 1 | 5 | 1 | 4 | 1 | 3 | 4 | 5 | 4 | 3 | 3 | 5 | 1 | 1 | 2 | 3 | 4 | 3 | 5 | 5 | 3 | 5 | 5 | 1 | 3 | 2 | 3 | 1 | 4 | 2 | 4 | 1 | 5 | 4
323 | 22 | 16 | 27 | 37 | 49 | 62 | 72 | 83 | 99 | 110 | 121 | 135 | 146 | 151 | 3 | 5 | 5 | 3 | 1 | 5 | 2 | 3 | 1 | 2 | 4 | 3 | 1 | 5 | 2 | 4 | 4 | 2 | 5 | 2 | 1 | 2 | 3 | 4 | 2 | 5 | 3 | 1 | 5 | 2 | 5 | 4 | 2 | 2 | 2 | 5 | 5 | 2 | 2 | 2 | 5 | 1 | 3 | 5 | 4 | 1 | 2 | 4 | 1 | 1 | 1 | 2
324 | 19 | 13 | 27 | 39 | 50 | 60 | 71 | 82 | 96 | 109 | 120 | 133 | 144 | 156 | 5 | 5 | 1 | 2 | 4 | 2 | 3 | 5 | 1 | 4 | 3 | 4 | 4 | 1 | 5 | 1 | 1 | 3 | 5 | 1 | 3 | 4 | 1 | 3 | 5 | 2 | 2 | 2 | 2 | 3 | 5 | 4 | 2 | 2 | 4 | 5 | 2 | 2 | 4 | 3 | 5 | 4 | 2 | 2 | 2 | 5 | 1 | 3 | 3 | 4 | 3 | 2
325 | 19 | 11 | 24 | 35 | 49 | 61 | 70 | 83 | 95 | 106 | 120 | 130 | 144 | 149 | 2 | 3 | 5 | 1 | 3 | 5 | 2 | 3 | 3 | 4 | 3 | 1 | 5 | 5 | 2 | 2 | 4 | 2 | 2 | 4 | 3 | 1 | 4 | 1 | 3 | 1 | 5 | 4 | 2 | 1 | 4 | 5 | 5 | 1 | 1 | 4 | 3 | 4 | 2 | 5 | 2 | 1 | 2 | 5 | 1 | 4 | 5 | 4 | 1 | 2 | 1 | 1
326 | 20 | 10 | 26 | 35 | 49 | 57 | 71 | 82 | 96 | 112 | 122 | 130 | 138 | 149 | 2 | 2 | 1 | 5 | 5 | 5 | 3 | 3 | 2 | 2 | 3 | 2 | 5 | 5 | 3 | 1 | 1 | 2 | 2 | 3 | 3 | 5 | 2 | 4 | 5 | 2 | 2 | 2 | 3 | 5 | 3 | 3 | 4 | 4 | 4 | 4 | 1 | 3 | 1 | 5 | 2 | 2 | 2 | 2 | 1 | 2 | 4 | 1 | 3 | 1 | 5 | 2
327 | 15 | 12 | 20 | 32 | 40 | 55 | 67 | 79 | 92 | 105 | 116 | 125 | 142 | 154 | 5 | 4 | 2 | 1 | 2 | 1 | 1 | 4 | 4 | 3 | 3 | 2 | 3 | 1 | 3 | 1 | 4 | 5 | 1 | 5 | 4 | 2 | 3 | 3 | 5 | 1 | 3 | 3 | 4 | 4 | 3 | 2 | 2 | 4 | 3 | 4 | 1 | 4 | 5 | 1 | 2 | 1 | 4 | 2 | 4 | 5 | 4 | 4 | 4 | 2 | 4 | 2
328 | 23 | 16 | 25 | 33 | 43 | 52 | 65 | 74 | 82 | 99 | 110 | 119 | 130 | 143 | 2 | 5 | 5 | 4 | 5 | 2 | 1 | 1 | 2 | 2 | 1 | 3 | 1 | 3 | 3 | 3 | 3 | 1 | 4 | 1 | 4 | 3 | 5 | 1 | 1 | 2 | 3 | 3 | 2 | 2 | 3 | 1 | 4 | 4 | 5 | 4 | 2 | 2 | 5 | 2 | 2 | 4 | 2 | 1 | 3 | 2 | 3 | 3 | 5 | 4 | 1 | 3
329 | 19 | 16 | 22 | 33 | 43 | 56 | 66 | 77 | 85 | 98 | 107 | 112 | 127 | 141 | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 2 | 3 | 4 | 3 | 1 | 4 | 3 | 2 | 1 | 3 | 5 | 2 | 3 | 2 | 5 | 2 | 1 | 3 | 4 | 2 | 2 | 1 | 2 | 1 | 4 | 4 | 3 | 5 | 1 | 4 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 3 | 5 | 4 | 3 | 2 | 5 | 3 | 4
330 | 17 | 11 | 24 | 34 | 45 | 56 | 68 | 80 | 92 | 102 | 115 | 129 | 140 | 154 | 2 | 3 | 5 | 1 | 4 | 2 | 3 | 4 | 1 | 1 | 3 | 5 | 4 | 1 | 3 | 3 | 2 | 2 | 3 | 4 | 4 | 1 | 4 | 3 | 4 | 1 | 2 | 5 | 2 | 3 | 3 | 4 | 1 | 2 | 5 | 2 | 5 | 3 | 1 | 4 | 1 | 3 | 5 | 5 | 4 | 5 | 1 | 1 | 4 | 5 | 3 | 2
331 | 24 | 16 | 32 | 43 | 56 | 65 | 78 | 96 | 107 | 119 | 127 | 142 | 158 | 170 | 5 | 5 | 3 | 3 | 3 | 5 | 3 | 5 | 5 | 2 | 2 | 2 | 2 | 4 | 4 | 3 | 1 | 3 | 2 | 3 | 3 | 4 | 5 | 1 | 5 | 5 | 4 | 4 | 4 | 5 | 1 | 1 | 3 | 3 | 1 | 5 | 2 | 4 | 1 | 1 | 4 | 4 | 3 | 4 | 4 | 5 | 5 | 2 | 2 | 5 | 1 | 4
332 | 21 | 13 | 30 | 43 | 54 | 68 | 79 | 94 | 105 | 117 | 125 | 138 | 148 | 162 | 1 | 4 | 3 | 5 | 4 | 4 | 5 | 4 | 3 | 3 | 4 | 3 | 4 | 1 | 2 | 4 | 4 | 5 | 2 | 3 | 2 | 3 | 4 | 2 | 3 | 4 | 3 | 5 | 3 | 2 | 1 | 5 | 2 | 3 | 2 | 5 | 4 | 1 | 2 | 1 | 1 | 3 | 4 | 5 | 3 | 1 | 3 | 3 | 3 | 4 | 2 | 5
333 | 21 | 13 | 29 | 46 | 57 | 75 | 82 | 92 | 100 | 111 | 119 | 129 | 139 | 149 | 3 | 4 | 4 | 2 | 4 | 4 | 3 | 5 | 5 | 4 | 5 | 3 | 2 | 5 | 1 | 3 | 5 | 3 | 5 | 5 | 3 | 1 | 2 | 1 | 4 | 1 | 3 | 2 | 1 | 5 | 1 | 1 | 5 | 3 | 2 | 1 | 2 | 1 | 2 | 3 | 4 | 4 | 1 | 1 | 1 | 5 | 3 | 1 | 3 | 5 | 1 | 1
334 | 19 | 15 | 23 | 37 | 46 | 59 | 74 | 81 | 94 | 109 | 120 | 134 | 148 | 162 | 2 | 5 | 3 | 5 | 2 | 2 | 3 | 1 | 4 | 2 | 5 | 3 | 2 | 3 | 3 | 1 | 4 | 3 | 1 | 5 | 5 | 3 | 2 | 5 | 1 | 4 | 1 | 1 | 3 | 3 | 5 | 2 | 4 | 3 | 3 | 5 | 3 | 5 | 1 | 2 | 4 | 4 | 4 | 2 | 3 | 3 | 3 | 5 | 3 | 4 | 5 | 2
335 | 19 | 12 | 22 | 37 | 51 | 61 | 73 | 85 | 100 | 111 | 126 | 144 | 152 | 164 | 4 | 5 | 1 | 2 | 2 | 5 | 1 | 2 | 3 | 5 | 3 | 4 | 4 | 3 | 2 | 5 | 1 | 3 | 5 | 1 | 3 | 2 | 5 | 2 | 2 | 4 | 4 | 2 | 4 | 4 | 5 | 2 | 4 | 1 | 3 | 3 | 4 | 2 | 4 | 5 | 5 | 5 | 4 | 4 | 2 | 1 | 4 | 1 | 1 | 2 | 5 | 4
336 | 16 | 10 | 22 | 36 | 51 | 59 | 71 | 85 | 100 | 115 | 125 | 136 | 149 | 159 | 2 | 1 | 4 | 3 | 3 | 3 | 4 | 2 | 2 | 2 | 5 | 5 | 4 | 3 | 4 | 4 | 1 | 4 | 1 | 2 | 4 | 2 | 2 | 4 | 5 | 3 | 1 | 5 | 5 | 1 | 5 | 4 | 4 | 1 | 5 | 5 | 1 | 5 | 2 | 2 | 4 | 1 | 3 | 3 | 4 | 4 | 3 | 2 | 2 | 2 | 5 | 1
337 | 21 | 12 | 28 | 36 | 50 | 62 | 76 | 84 | 95 | 110 | 118 | 129 | 142 | 156 | 5 | 5 | 1 | 1 | 5 | 4 | 5 | 2 | 2 | 3 | 1 | 2 | 5 | 4 | 3 | 2 | 3 | 3 | 5 | 1 | 5 | 4 | 1 | 4 | 1 | 1 | 2 | 4 | 4 | 4 | 1 | 2 | 5 | 2 | 3 | 5 | 2 | 1 | 4 | 1 | 1 | 5 | 4 | 1 | 2 | 5 | 3 | 3 | 5 | 4 | 1 | 4
338 | 12 | 10 | 15 | 32 | 42 | 55 | 65 | 83 | 94 | 103 | 117 | 130 | 144 | 151 | 1 | 1 | 4 | 4 | 1 | 1 | 2 | 1 | 4 | 5 | 4 | 4 | 1 | 4 | 3 | 2 | 4 | 3 | 3 | 3 | 3 | 2 | 1 | 4 | 5 | 3 | 5 | 5 | 3 | 3 | 2 | 3 | 1 | 4 | 1 | 3 | 3 | 4 | 5 | 2 | 3 | 5 | 4 | 1 | 2 | 5 | 4 | 3 | 3 | 2 | 1 | 1
339 | 19 | 13 | 27 | 37 | 50 | 61 | 70 | 85 | 99 | 115 | 124 | 137 | 151 | 167 | 3 | 5 | 3 | 2 | 1 | 5 | 5 | 3 | 5 | 2 | 1 | 2 | 2 | 2 | 4 | 5 | 3 | 2 | 1 | 5 | 3 | 1 | 4 | 1 | 5 | 2 | 3 | 5 | 3 | 5 | 2 | 4 | 5 | 3 | 3 | 5 | 1 | 2 | 4 | 2 | 3 | 4 | 3 | 3 | 3 | 5 | 3 | 3 | 1 | 5 | 5 | 5
340 | 17 | 10 | 21 | 37 | 48 | 60 | 74 | 87 | 99 | 111 | 125 | 135 | 147 | 156 | 2 | 5 | 2 | 1 | 3 | 4 | 2 | 2 | 5 | 5 | 2 | 4 | 2 | 5 | 2 | 2 | 4 | 1 | 2 | 5 | 4 | 2 | 4 | 4 | 3 | 3 | 2 | 5 | 5 | 1 | 2 | 4 | 4 | 1 | 3 | 4 | 3 | 3 | 5 | 3 | 5 | 2 | 1 | 2 | 3 | 1 | 3 | 5 | 2 | 1 | 2 | 4
341 | 14 | 8 | 20 | 32 | 44 | 55 | 62 | 71 | 80 | 96 | 109 | 118 | 127 | 132 | 1 | 1 | 5 | 1 | 5 | 1 | 3 | 3 | 3 | 4 | 2 | 3 | 4 | 2 | 1 | 5 | 1 | 5 | 3 | 2 | 2 | 3 | 1 | 1 | 4 | 1 | 2 | 2 | 2 | 4 | 1 | 2 | 2 | 5 | 4 | 5 | 2 | 3 | 4 | 4 | 2 | 1 | 1 | 5 | 2 | 4 | 2 | 1 | 2 | 1 | 1 | 1
342 | 19 | 15 | 26 | 32 | 43 | 56 | 64 | 80 | 93 | 106 | 119 | 135 | 144 | 159 | 4 | 4 | 4 | 3 | 3 | 1 | 5 | 2 | 1 | 2 | 1 | 2 | 1 | 3 | 3 | 4 | 1 | 2 | 5 | 5 | 2 | 2 | 1 | 3 | 3 | 5 | 3 | 5 | 2 | 3 | 5 | 3 | 4 | 5 | 1 | 3 | 3 | 5 | 1 | 4 | 3 | 4 | 4 | 5 | 3 | 4 | 1 | 1 | 2 | 5 | 3 | 5
343 | 15 | 11 | 23 | 38 | 52 | 63 | 78 | 91 | 105 | 117 | 128 | 138 | 146 | 161 | 2 | 5 | 2 | 2 | 2 | 2 | 3 | 5 | 3 | 5 | 4 | 3 | 4 | 5 | 2 | 3 | 3 | 3 | 1 | 4 | 4 | 5 | 5 | 1 | 5 | 2 | 2 | 4 | 5 | 2 | 4 | 3 | 5 | 4 | 1 | 2 | 5 | 1 | 3 | 2 | 3 | 3 | 3 | 1 | 5 | 1 | 1 | 1 | 1 | 5 | 5 | 4
344 | 22 | 16 | 25 | 39 | 57 | 67 | 78 | 90 | 99 | 112 | 125 | 137 | 152 | 164 | 4 | 3 | 5 | 4 | 5 | 1 | 2 | 1 | 1 | 5 | 4 | 4 | 5 | 3 | 5 | 5 | 4 | 1 | 4 | 1 | 2 | 3 | 5 | 1 | 1 | 5 | 4 | 2 | 4 | 1 | 2 | 2 | 4 | 1 | 4 | 4 | 2 | 3 | 5 | 3 | 4 | 1 | 4 | 3 | 4 | 1 | 5 | 5 | 4 | 5 | 1 | 2
345 | 18 | 11 | 23 | 33 | 42 | 54 | 66 | 84 | 96 | 108 | 122 | 136 | 153 | 167 | 2 | 5 | 3 | 1 | 3 | 4 | 3 | 2 | 1 | 3 | 4 | 2 | 3 | 1 | 3 | 2 | 1 | 1 | 5 | 5 | 4 | 3 | 2 | 3 | 5 | 4 | 4 | 5 | 4 | 4 | 2 | 2 | 1 | 3 | 3 | 5 | 2 | 2 | 5 | 5 | 5 | 2 | 5 | 2 | 4 | 5 | 5 | 3 | 3 | 5 | 1 | 5
346 | 16 | 11 | 24 | 32 | 48 | 60 | 74 | 80 | 93 | 106 | 115 | 130 | 146 | 157 | 2 | 1 | 4 | 4 | 1 | 4 | 5 | 3 | 1 | 3 | 2 | 2 | 2 | 4 | 5 | 5 | 4 | 4 | 1 | 3 | 3 | 1 | 5 | 5 | 3 | 1 | 1 | 1 | 5 | 1 | 3 | 4 | 3 | 4 | 5 | 1 | 1 | 1 | 3 | 4 | 5 | 2 | 3 | 5 | 5 | 5 | 4 | 2 | 2 | 4 | 1 | 4
347 | 17 | 10 | 23 | 35 | 44 | 57 | 67 | 81 | 93 | 107 | 119 | 128 | 145 | 162 | 3 | 1 | 2 | 4 | 5 | 2 | 2 | 4 | 2 | 4 | 5 | 1 | 1 | 5 | 1 | 2 | 1 | 5 | 5 | 2 | 3 | 1 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 1 | 2 | 5 | 4 | 5 | 3 | 2 | 2 | 3 | 4 | 3 | 1 | 5 | 1 | 2 | 4 | 4 | 5 | 4 | 3 | 5 | 4 | 5
348 | 15 | 9 | 20 | 28 | 39 | 48 | 55 | 69 | 80 | 90 | 102 | 112 | 121 | 135 | 4 | 1 | 3 | 1 | 3 | 3 | 4 | 1 | 2 | 2 | 1 | 3 | 3 | 3 | 1 | 4 | 3 | 3 | 1 | 2 | 1 | 1 | 1 | 4 | 3 | 5 | 5 | 1 | 2 | 4 | 3 | 2 | 1 | 2 | 4 | 3 | 3 | 1 | 4 | 4 | 3 | 3 | 1 | 3 | 3 | 2 | 2 | 2 | 3 | 2 | 5 | 4
349 | 20 | 11 | 25 | 40 | 53 | 68 | 85 | 98 | 114 | 129 | 139 | 156 | 169 | 179 | 3 | 4 | 3 | 1 | 4 | 5 | 3 | 2 | 5 | 4 | 5 | 1 | 1 | 4 | 5 | 3 | 5 | 4 | 3 | 3 | 5 | 5 | 4 | 3 | 4 | 4 | 2 | 3 | 5 | 3 | 4 | 4 | 2 | 4 | 5 | 4 | 4 | 3 | 1 | 2 | 5 | 5 | 2 | 5 | 2 | 4 | 3 | 4 | 3 | 1 | 3 | 3
350 | 20 | 13 | 22 | 36 | 51 | 62 | 74 | 83 | 93 | 104 | 111 | 116 | 128 | 140 | 4 | 1 | 4 | 4 | 3 | 4 | 1 | 1 | 5 | 2 | 3 | 4 | 1 | 5 | 5 | 4 | 3 | 1 | 4 | 3 | 4 | 5 | 1 | 2 | 1 | 4 | 1 | 3 | 4 | 2 | 3 | 1 | 4 | 2 | 3 | 2 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 2 | 5 | 1 | 4 | 2 | 3 | 3 | 3 | 3
351 | 19 | 13 | 22 | 41 | 54 | 66 | 75 | 83 | 90 | 99 | 114 | 122 | 134 | 142 | 5 | 5 | 2 | 1 | 1 | 5 | 2 | 1 | 5 | 4 | 5 | 5 | 1 | 4 | 5 | 3 | 5 | 1 | 2 | 4 | 1 | 4 | 1 | 3 | 2 | 3 | 1 | 2 | 2 | 1 | 2 | 2 | 1 | 3 | 4 | 1 | 3 | 3 | 5 | 4 | 3 | 2 | 2 | 1 | 4 | 2 | 2 | 4 | 1 | 2 | 3 | 2
352 | 15 | 11 | 18 | 31 | 41 | 55 | 70 | 77 | 87 | 103 | 115 | 131 | 147 | 163 | 3 | 3 | 2 | 3 | 1 | 3 | 2 | 1 | 4 | 5 | 3 | 1 | 2 | 1 | 5 | 2 | 4 | 1 | 4 | 5 | 5 | 1 | 4 | 5 | 1 | 2 | 1 | 3 | 1 | 2 | 2 | 5 | 4 | 4 | 5 | 3 | 4 | 4 | 3 | 1 | 4 | 2 | 5 | 5 | 5 | 2 | 4 | 5 | 5 | 5 | 1 | 5
353 | 15 | 10 | 23 | 38 | 53 | 67 | 82 | 92 | 106 | 117 | 133 | 142 | 159 | 168 | 1 | 5 | 1 | 3 | 4 | 1 | 3 | 5 | 4 | 5 | 1 | 5 | 5 | 4 | 4 | 2 | 4 | 4 | 4 | 2 | 5 | 5 | 4 | 1 | 2 | 1 | 4 | 3 | 3 | 3 | 5 | 3 | 2 | 3 | 2 | 4 | 5 | 3 | 3 | 5 | 3 | 3 | 2 | 1 | 5 | 5 | 4 | 3 | 2 | 4 | 1 | 2
354 | 19 | 15 | 25 | 36 | 48 | 56 | 71 | 86 | 99 | 106 | 118 | 128 | 143 | 151 | 4 | 5 | 4 | 2 | 1 | 3 | 3 | 3 | 5 | 3 | 2 | 1 | 2 | 5 | 1 | 4 | 4 | 1 | 1 | 2 | 4 | 2 | 5 | 4 | 2 | 5 | 5 | 3 | 5 | 4 | 2 | 2 | 1 | 1 | 3 | 2 | 4 | 1 | 4 | 3 | 2 | 2 | 3 | 3 | 2 | 4 | 4 | 5 | 2 | 2 | 2 | 2
355 | 24 | 19 | 27 | 40 | 49 | 63 | 79 | 86 | 103 | 110 | 127 | 137 | 144 | 161 | 5 | 5 | 5 | 4 | 1 | 4 | 1 | 2 | 2 | 5 | 4 | 2 | 3 | 1 | 1 | 4 | 5 | 4 | 2 | 3 | 4 | 5 | 3 | 4 | 3 | 1 | 1 | 2 | 5 | 4 | 4 | 4 | 1 | 1 | 2 | 3 | 4 | 5 | 5 | 3 | 1 | 3 | 3 | 3 | 2 | 1 | 1 | 3 | 4 | 5 | 5 | 3
356 | 15 | 7 | 25 | 38 | 46 | 56 | 67 | 80 | 90 | 102 | 113 | 128 | 139 | 154 | 1 | 1 | 2 | 3 | 4 | 4 | 5 | 5 | 1 | 5 | 5 | 2 | 3 | 1 | 2 | 2 | 2 | 2 | 1 | 5 | 1 | 5 | 3 | 2 | 3 | 3 | 2 | 5 | 1 | 4 | 1 | 4 | 3 | 1 | 3 | 5 | 4 | 2 | 3 | 2 | 3 | 3 | 4 | 5 | 4 | 2 | 4 | 1 | 5 | 3 | 5 | 2
357 | 21 | 17 | 26 | 40 | 54 | 69 | 76 | 92 | 103 | 113 | 126 | 138 | 145 | 160 | 5 | 4 | 5 | 3 | 3 | 1 | 3 | 2 | 2 | 3 | 5 | 4 | 3 | 5 | 5 | 1 | 5 | 5 | 1 | 4 | 1 | 1 | 3 | 2 | 5 | 2 | 5 | 4 | 2 | 3 | 2 | 4 | 3 | 5 | 1 | 1 | 5 | 2 | 4 | 2 | 2 | 4 | 5 | 1 | 1 | 3 | 2 | 1 | 3 | 3 | 4 | 5
358 | 19 | 13 | 25 | 38 | 51 | 63 | 73 | 86 | 92 | 103 | 111 | 122 | 130 | 141 | 4 | 3 | 1 | 5 | 1 | 5 | 3 | 3 | 4 | 5 | 2 | 2 | 1 | 5 | 4 | 3 | 1 | 3 | 5 | 3 | 2 | 4 | 1 | 3 | 1 | 5 | 4 | 3 | 2 | 2 | 1 | 1 | 1 | 2 | 5 | 3 | 1 | 2 | 4 | 1 | 4 | 4 | 2 | 1 | 4 | 2 | 1 | 1 | 2 | 2 | 5 | 2
359 | 22 | 15 | 27 | 35 | 54 | 70 | 85 | 100 | 109 | 121 | 129 | 137 | 151 | 169 | 4 | 5 | 5 | 1 | 4 | 3 | 1 | 4 | 2 | 2 | 1 | 3 | 5 | 5 | 4 | 5 | 5 | 2 | 5 | 4 | 4 | 5 | 4 | 2 | 5 | 4 | 4 | 2 | 2 | 1 | 3 | 3 | 4 | 1 | 4 | 3 | 1 | 1 | 3 | 3 | 1 | 3 | 2 | 2 | 2 | 5 | 4 | 3 | 4 | 5 | 4 | 5
360 | 20 | 12 | 26 | 37 | 50 | 61 | 73 | 84 | 94 | 105 | 119 | 135 | 146 | 159 | 1 | 3 | 3 | 5 | 4 | 4 | 3 | 3 | 3 | 4 | 2 | 2 | 5 | 4 | 1 | 3 | 2 | 4 | 3 | 2 | 3 | 2 | 2 | 5 | 3 | 1 | 3 | 4 | 3 | 1 | 3 | 3 | 3 | 1 | 4 | 3 | 5 | 4 | 3 | 2 | 4 | 4 | 5 | 3 | 1 | 4 | 2 | 4 | 1 | 5 | 2 | 5
361 | 18 | 10 | 23 | 32 | 45 | 58 | 72 | 84 | 95 | 106 | 116 | 129 | 139 | 148 | 2 | 1 | 3 | 4 | 5 | 3 | 2 | 3 | 1 | 2 | 4 | 2 | 2 | 5 | 5 | 1 | 5 | 4 | 2 | 2 | 1 | 4 | 4 | 5 | 3 | 3 | 3 | 3 | 4 | 1 | 5 | 1 | 1 | 3 | 3 | 4 | 3 | 2 | 4 | 1 | 3 | 5 | 2 | 3 | 2 | 2 | 1 | 5 | 1 | 5 | 2 | 1
362 | 14 | 7 | 21 | 30 | 40 | 52 | 62 | 73 | 83 | 93 | 103 | 118 | 129 | 140 | 1 | 1 | 2 | 3 | 2 | 5 | 2 | 5 | 1 | 4 | 3 | 1 | 3 | 2 | 3 | 2 | 5 | 1 | 4 | 2 | 2 | 2 | 3 | 3 | 1 | 4 | 1 | 5 | 3 | 1 | 1 | 5 | 3 | 1 | 4 | 2 | 4 | 2 | 2 | 2 | 2 | 5 | 4 | 4 | 2 | 4 | 1 | 4 | 3 | 1 | 4 | 3
363 | 21 | 14 | 27 | 41 | 51 | 61 | 71 | 81 | 95 | 102 | 118 | 129 | 137 | 151 | 4 | 5 | 4 | 1 | 5 | 2 | 3 | 3 | 4 | 3 | 4 | 3 | 2 | 3 | 2 | 3 | 5 | 2 | 2 | 1 | 1 | 1 | 3 | 5 | 2 | 3 | 2 | 3 | 3 | 2 | 4 | 5 | 2 | 1 | 1 | 3 | 4 | 5 | 5 | 2 | 1 | 4 | 4 | 2 | 1 | 2 | 2 | 3 | 3 | 5 | 2 | 4
364 | 17 | 7 | 23 | 32 | 42 | 51 | 64 | 76 | 84 | 93 | 103 | 114 | 123 | 132 | 4 | 1 | 1 | 1 | 5 | 5 | 5 | 1 | 4 | 1 | 1 | 3 | 4 | 4 | 1 | 1 | 1 | 2 | 2 | 4 | 1 | 5 | 4 | 3 | 4 | 2 | 4 | 2 | 1 | 4 | 2 | 1 | 4 | 2 | 1 | 2 | 1 | 3 | 3 | 3 | 4 | 2 | 3 | 2 | 1 | 1 | 2 | 5 | 1 | 4 | 3 | 1
365 | 18 | 12 | 25 | 34 | 46 | 61 | 73 | 86 | 99 | 107 | 113 | 127 | 143 | 154 | 5 | 3 | 1 | 3 | 3 | 3 | 4 | 3 | 3 | 2 | 3 | 1 | 3 | 3 | 3 | 3 | 3 | 5 | 4 | 3 | 3 | 1 | 4 | 4 | 4 | 5 | 3 | 1 | 3 | 3 | 2 | 5 | 2 | 1 | 3 | 2 | 1 | 1 | 3 | 1 | 5 | 4 | 1 | 4 | 5 | 3 | 4 | 4 | 3 | 5 | 1 | 2
366 | 21 | 13 | 29 | 39 | 50 | 63 | 77 | 92 | 105 | 115 | 129 | 141 | 152 | 163 | 1 | 5 | 3 | 4 | 4 | 4 | 4 | 4 | 1 | 2 | 4 | 3 | 2 | 4 | 2 | 3 | 2 | 4 | 4 | 3 | 5 | 2 | 3 | 4 | 3 | 5 | 2 | 5 | 3 | 4 | 4 | 2 | 2 | 2 | 1 | 5 | 5 | 4 | 2 | 3 | 3 | 5 | 2 | 2 | 4 | 2 | 1 | 4 | 4 | 3 | 2 | 2
367 | 19 | 13 | 29 | 39 | 47 | 55 | 67 | 79 | 95 | 107 | 120 | 134 | 143 | 152 | 5 | 3 | 4 | 1 | 3 | 3 | 5 | 5 | 1 | 3 | 3 | 3 | 1 | 1 | 3 | 3 | 1 | 2 | 2 | 3 | 2 | 4 | 3 | 3 | 4 | 4 | 3 | 1 | 5 | 5 | 1 | 5 | 4 | 5 | 1 | 2 | 2 | 4 | 4 | 3 | 5 | 3 | 5 | 1 | 1 | 3 | 4 | 1 | 4 | 1 | 3 | 1
368 | 23 | 17 | 29 | 41 | 53 | 62 | 72 | 84 | 96 | 108 | 124 | 137 | 148 | 163 | 5 | 4 | 4 | 4 | 5 | 1 | 4 | 2 | 1 | 5 | 1 | 5 | 4 | 4 | 3 | 1 | 1 | 3 | 4 | 1 | 3 | 2 | 4 | 1 | 4 | 4 | 2 | 2 | 3 | 3 | 5 | 1 | 5 | 3 | 1 | 3 | 5 | 4 | 5 | 2 | 4 | 2 | 2 | 5 | 5 | 1 | 1 | 4 | 3 | 2 | 5 | 5
369 | 18 | 15 | 25 | 40 | 52 | 62 | 77 | 94 | 105 | 116 | 133 | 145 | 155 | 170 | 3 | 5 | 3 | 4 | 1 | 2 | 5 | 2 | 5 | 5 | 2 | 3 | 2 | 5 | 3 | 2 | 1 | 2 | 2 | 5 | 5 | 1 | 5 | 4 | 5 | 5 | 2 | 5 | 3 | 5 | 2 | 1 | 2 | 3 | 4 | 2 | 5 | 3 | 5 | 4 | 2 | 3 | 3 | 4 | 2 | 2 | 2 | 4 | 4 | 4 | 3 | 4
370 | 14 | 11 | 22 | 35 | 45 | 55 | 66 | 76 | 88 | 99 | 107 | 122 | 139 | 153 | 4 | 3 | 1 | 3 | 1 | 2 | 5 | 3 | 1 | 5 | 5 | 2 | 5 | 1 | 2 | 2 | 1 | 3 | 3 | 3 | 4 | 1 | 5 | 1 | 3 | 1 | 4 | 2 | 2 | 4 | 1 | 5 | 1 | 5 | 1 | 4 | 1 | 3 | 1 | 3 | 4 | 5 | 5 | 1 | 4 | 4 | 4 | 5 | 4 | 2 | 5 | 3
371 | 15 | 8 | 19 | 26 | 36 | 50 | 61 | 68 | 80 | 99 | 108 | 120 | 129 | 144 | 1 | 1 | 1 | 5 | 3 | 4 | 1 | 3 | 1 | 1 | 4 | 1 | 1 | 4 | 4 | 1 | 3 | 5 | 3 | 3 | 2 | 1 | 3 | 5 | 1 | 2 | 2 | 2 | 4 | 2 | 5 | 1 | 5 | 4 | 5 | 5 | 3 | 1 | 1 | 4 | 4 | 5 | 1 | 2 | 4 | 1 | 3 | 1 | 4 | 4 | 5 | 2
372 | 20 | 13 | 25 | 43 | 59 | 72 | 83 | 95 | 102 | 114 | 123 | 132 | 145 | 157 | 4 | 4 | 4 | 1 | 5 | 2 | 3 | 2 | 4 | 4 | 5 | 5 | 1 | 5 | 5 | 5 | 1 | 2 | 5 | 5 | 2 | 1 | 5 | 3 | 4 | 4 | 1 | 3 | 3 | 1 | 1 | 2 | 4 | 2 | 1 | 5 | 4 | 3 | 1 | 1 | 1 | 1 | 5 | 2 | 2 | 5 | 5 | 1 | 2 | 2 | 3 | 5
373 | 17 | 12 | 25 | 34 | 45 | 57 | 72 | 86 | 104 | 116 | 124 | 132 | 144 | 153 | 2 | 3 | 5 | 2 | 3 | 2 | 3 | 5 | 3 | 1 | 1 | 4 | 3 | 4 | 2 | 2 | 5 | 1 | 4 | 2 | 5 | 4 | 2 | 4 | 3 | 5 | 5 | 1 | 5 | 5 | 4 | 4 | 4 | 1 | 2 | 5 | 2 | 2 | 2 | 2 | 2 | 1 | 3 | 2 | 4 | 2 | 1 | 5 | 3 | 2 | 1 | 3
374 | 15 | 11 | 19 | 34 | 45 | 54 | 66 | 83 | 92 | 103 | 113 | 125 | 140 | 149 | 4 | 2 | 4 | 1 | 1 | 3 | 1 | 3 | 2 | 5 | 5 | 3 | 3 | 2 | 4 | 2 | 2 | 1 | 5 | 1 | 3 | 4 | 2 | 3 | 4 | 4 | 5 | 4 | 3 | 4 | 1 | 1 | 2 | 4 | 1 | 4 | 1 | 4 | 2 | 3 | 5 | 2 | 4 | 1 | 4 | 3 | 4 | 4 | 4 | 3 | 1 | 1
375 | 19 | 11 | 21 | 32 | 46 | 60 | 78 | 92 | 108 | 120 | 133 | 147 | 157 | 168 | 3 | 4 | 3 | 1 | 3 | 5 | 1 | 1 | 3 | 3 | 4 | 1 | 1 | 4 | 4 | 5 | 2 | 5 | 2 | 5 | 4 | 5 | 5 | 4 | 3 | 1 | 5 | 5 | 4 | 4 | 4 | 4 | 2 | 5 | 3 | 2 | 2 | 3 | 5 | 3 | 2 | 5 | 4 | 3 | 5 | 3 | 1 | 1 | 1 | 5 | 3 | 2
376 | 14 | 12 | 19 | 33 | 40 | 50 | 60 | 73 | 91 | 99 | 105 | 114 | 127 | 141 | 3 | 2 | 3 | 4 | 1 | 1 | 3 | 2 | 3 | 3 | 5 | 3 | 1 | 2 | 2 | 2 | 3 | 2 | 4 | 1 | 3 | 5 | 1 | 1 | 2 | 5 | 2 | 4 | 4 | 5 | 5 | 4 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | 2 | 4 | 1 | 3 | 4 | 5 | 1 | 5 | 3 | 4 | 2
377 | 16 | 12 | 22 | 31 | 39 | 53 | 64 | 76 | 92 | 107 | 116 | 127 | 141 | 150 | 4 | 4 | 3 | 1 | 2 | 2 | 1 | 5 | 1 | 1 | 4 | 3 | 1 | 3 | 2 | 2 | 5 | 5 | 2 | 2 | 3 | 5 | 1 | 2 | 2 | 3 | 2 | 5 | 5 | 4 | 5 | 2 | 2 | 5 | 5 | 3 | 2 | 2 | 1 | 4 | 5 | 1 | 3 | 2 | 4 | 3 | 3 | 4 | 2 | 2 | 3 | 2
378 | 22 | 14 | 26 | 36 | 47 | 55 | 66 | 73 | 84 | 94 | 111 | 123 | 133 | 140 | 1 | 5 | 3 | 5 | 3 | 5 | 1 | 3 | 1 | 4 | 2 | 3 | 3 | 2 | 3 | 3 | 2 | 4 | 1 | 1 | 2 | 3 | 4 | 2 | 1 | 3 | 1 | 2 | 4 | 5 | 1 | 1 | 3 | 5 | 1 | 1 | 5 | 2 | 5 | 5 | 5 | 4 | 2 | 1 | 5 | 3 | 1 | 1 | 1 | 3 | 2 | 1
379 | 18 | 11 | 28 | 39 | 54 | 67 | 79 | 91 | 108 | 115 | 134 | 144 | 152 | 162 | 4 | 3 | 1 | 3 | 2 | 5 | 5 | 5 | 2 | 4 | 4 | 1 | 4 | 5 | 5 | 1 | 4 | 4 | 2 | 3 | 4 | 3 | 3 | 2 | 4 | 4 | 2 | 2 | 4 | 3 | 5 | 5 | 1 | 2 | 1 | 3 | 5 | 4 | 5 | 5 | 2 | 2 | 2 | 4 | 1 | 3 | 1 | 3 | 4 | 3 | 2 | 1
380 | 14 | 11 | 18 | 36 | 47 | 60 | 71 | 82 | 92 | 103 | 115 | 127 | 138 | 154 | 4 | 1 | 2 | 4 | 1 | 2 | 2 | 2 | 5 | 5 | 4 | 4 | 4 | 1 | 1 | 5 | 4 | 4 | 2 | 3 | 3 | 1 | 2 | 5 | 5 | 3 | 1 | 2 | 1 | 5 | 1 | 3 | 3 | 2 | 4 | 2 | 1 | 3 | 5 | 3 | 3 | 4 | 1 | 4 | 4 | 1 | 1 | 5 | 2 | 4 | 5 | 5
381 | 15 | 11 | 19 | 32 | 47 | 56 | 72 | 84 | 89 | 100 | 110 | 130 | 140 | 149 | 3 | 1 | 3 | 4 | 3 | 1 | 3 | 1 | 1 | 5 | 5 | 2 | 3 | 4 | 5 | 3 | 5 | 1 | 1 | 2 | 4 | 3 | 4 | 5 | 5 | 1 | 5 | 1 | 1 | 1 | 1 | 2 | 4 | 3 | 1 | 3 | 1 | 5 | 1 | 3 | 5 | 5 | 5 | 5 | 1 | 1 | 3 | 5 | 2 | 1 | 1 | 5
382 | 25 | 15 | 31 | 50 | 61 | 72 | 82 | 91 | 110 | 125 | 136 | 149 | 162 | 178 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 1 | 5 | 5 | 5 | 4 | 1 | 3 | 2 | 5 | 5 | 1 | 2 | 3 | 1 | 3 | 3 | 3 | 2 | 1 | 5 | 1 | 4 | 5 | 5 | 5 | 1 | 4 | 5 | 5 | 4 | 1 | 1 | 5 | 2 | 4 | 3 | 4 | 5 | 2 | 3 | 3 | 5 | 3 | 5 | 3
383 | 25 | 17 | 29 | 38 | 53 | 63 | 73 | 85 | 96 | 114 | 126 | 139 | 149 | 163 | 5 | 5 | 4 | 3 | 4 | 4 | 1 | 3 | 4 | 3 | 1 | 1 | 4 | 2 | 5 | 4 | 1 | 5 | 1 | 3 | 4 | 1 | 2 | 3 | 2 | 5 | 3 | 2 | 3 | 1 | 5 | 2 | 4 | 5 | 5 | 4 | 1 | 3 | 5 | 3 | 5 | 2 | 3 | 3 | 2 | 1 | 3 | 4 | 1 | 4 | 5 | 4
384 | 24 | 14 | 28 | 43 | 63 | 76 | 89 | 100 | 114 | 126 | 138 | 142 | 154 | 167 | 3 | 4 | 5 | 2 | 5 | 5 | 3 | 1 | 4 | 3 | 4 | 4 | 5 | 5 | 5 | 5 | 2 | 5 | 5 | 1 | 4 | 3 | 2 | 4 | 3 | 3 | 1 | 4 | 5 | 3 | 5 | 1 | 3 | 4 | 4 | 1 | 4 | 1 | 3 | 4 | 1 | 1 | 1 | 1 | 5 | 2 | 4 | 1 | 2 | 1 | 5 | 5
385 | 18 | 13 | 22 | 37 | 49 | 59 | 70 | 80 | 89 | 100 | 113 | 126 | 136 | 148 | 5 | 4 | 2 | 2 | 2 | 3 | 3 | 1 | 5 | 3 | 5 | 2 | 4 | 3 | 1 | 4 | 1 | 5 | 3 | 1 | 2 | 5 | 1 | 3 | 1 | 4 | 1 | 4 | 1 | 2 | 1 | 5 | 1 | 2 | 4 | 4 | 5 | 1 | 3 | 4 | 4 | 1 | 4 | 4 | 1 | 3 | 3 | 3 | 2 | 1 | 5 | 4
386 | 16 | 14 | 24 | 36 | 49 | 62 | 73 | 88 | 97 | 113 | 125 | 138 | 152 | 167 | 5 | 5 | 3 | 1 | 1 | 1 | 5 | 3 | 2 | 3 | 2 | 5 | 3 | 4 | 5 | 1 | 4 | 3 | 2 | 4 | 3 | 2 | 5 | 1 | 5 | 3 | 4 | 3 | 2 | 5 | 1 | 1 | 5 | 5 | 2 | 4 | 4 | 5 | 1 | 2 | 2 | 5 | 4 | 2 | 4 | 2 | 4 | 4 | 3 | 5 | 2 | 5
387 | 19 | 10 | 26 | 39 | 58 | 68 | 80 | 92 | 101 | 114 | 130 | 144 | 158 | 167 | 1 | 2 | 2 | 5 | 4 | 5 | 5 | 2 | 4 | 3 | 5 | 1 | 4 | 5 | 5 | 5 | 3 | 4 | 1 | 2 | 4 | 2 | 5 | 1 | 1 | 4 | 5 | 2 | 3 | 3 | 1 | 2 | 3 | 4 | 3 | 3 | 5 | 1 | 5 | 5 | 5 | 2 | 3 | 4 | 3 | 3 | 5 | 3 | 1 | 5 | 2 | 1
388 | 19 | 12 | 25 | 35 | 50 | 64 | 74 | 82 | 94 | 101 | 111 | 121 | 138 | 150 | 4 | 3 | 1 | 4 | 2 | 5 | 2 | 4 | 3 | 1 | 2 | 4 | 4 | 2 | 4 | 5 | 4 | 1 | 5 | 4 | 2 | 2 | 5 | 1 | 1 | 2 | 1 | 4 | 3 | 5 | 1 | 3 | 1 | 4 | 1 | 1 | 4 | 1 | 2 | 3 | 3 | 1 | 1 | 5 | 4 | 4 | 5 | 4 | 4 | 4 | 2 | 2
389 | 14 | 9 | 20 | 29 | 44 | 56 | 68 | 79 | 88 | 96 | 112 | 127 | 137 | 147 | 3 | 2 | 1 | 3 | 3 | 2 | 2 | 4 | 2 | 3 | 1 | 3 | 4 | 3 | 3 | 5 | 1 | 3 | 5 | 3 | 3 | 3 | 5 | 1 | 1 | 5 | 1 | 4 | 2 | 2 | 3 | 2 | 2 | 4 | 1 | 1 | 5 | 4 | 5 | 2 | 4 | 5 | 1 | 5 | 4 | 1 | 2 | 3 | 2 | 3 | 1 | 4
390 | 19 | 14 | 21 | 31 | 47 | 59 | 75 | 89 | 102 | 109 | 121 | 131 | 140 | 150 | 4 | 3 | 2 | 5 | 4 | 1 | 1 | 1 | 1 | 1 | 4 | 4 | 5 | 3 | 5 | 3 | 5 | 5 | 1 | 1 | 5 | 2 | 4 | 5 | 4 | 5 | 2 | 3 | 5 | 4 | 3 | 1 | 2 | 1 | 1 | 3 | 5 | 3 | 3 | 1 | 2 | 3 | 3 | 2 | 4 | 2 | 2 | 1 | 3 | 1 | 4 | 2
391 | 26 | 17 | 34 | 49 | 63 | 76 | 86 | 96 | 109 | 128 | 137 | 150 | 161 | 176 | 5 | 4 | 4 | 4 | 4 | 5 | 3 | 5 | 4 | 5 | 3 | 3 | 2 | 3 | 5 | 4 | 4 | 5 | 2 | 2 | 2 | 5 | 2 | 1 | 4 | 2 | 3 | 1 | 1 | 2 | 5 | 5 | 4 | 5 | 5 | 5 | 2 | 5 | 1 | 1 | 5 | 3 | 4 | 1 | 3 | 3 | 4 | 1 | 4 | 5 | 2 | 4
392 | 16 | 12 | 19 | 30 | 40 | 53 | 65 | 74 | 85 | 98 | 109 | 119 | 128 | 142 | 5 | 2 | 4 | 1 | 2 | 2 | 1 | 2 | 5 | 2 | 3 | 1 | 3 | 3 | 2 | 2 | 5 | 2 | 4 | 2 | 2 | 3 | 5 | 2 | 2 | 2 | 2 | 3 | 3 | 1 | 3 | 4 | 2 | 2 | 4 | 5 | 4 | 3 | 2 | 2 | 2 | 4 | 1 | 3 | 1 | 1 | 2 | 5 | 4 | 5 | 2 | 3
393 | 17 | 13 | 25 | 35 | 48 | 62 | 72 | 90 | 97 | 114 | 126 | 140 | 153 | 165 | 2 | 5 | 3 | 3 | 1 | 3 | 5 | 3 | 1 | 3 | 4 | 2 | 5 | 2 | 4 | 2 | 5 | 4 | 2 | 3 | 1 | 3 | 5 | 1 | 5 | 5 | 4 | 4 | 1 | 1 | 1 | 4 | 5 | 2 | 5 | 5 | 3 | 2 | 2 | 5 | 4 | 5 | 1 | 4 | 5 | 4 | 3 | 1 | 4 | 3 | 4 | 1
394 | 20 | 12 | 26 | 33 | 48 | 55 | 64 | 77 | 85 | 97 | 111 | 123 | 133 | 144 | 1 | 3 | 5 | 3 | 5 | 3 | 2 | 4 | 1 | 2 | 1 | 3 | 5 | 5 | 2 | 3 | 1 | 3 | 2 | 1 | 1 | 3 | 2 | 3 | 5 | 4 | 1 | 3 | 2 | 1 | 2 | 3 | 1 | 4 | 5 | 2 | 3 | 3 | 4 | 4 | 4 | 1 | 4 | 3 | 1 | 3 | 3 | 3 | 4 | 3 | 2 | 2
395 | 21 | 12 | 24 | 38 | 53 | 66 | 77 | 95 | 106 | 117 | 126 | 140 | 150 | 160 | 3 | 1 | 4 | 4 | 4 | 5 | 1 | 2 | 3 | 5 | 1 | 5 | 4 | 3 | 5 | 3 | 4 | 4 | 4 | 1 | 1 | 2 | 4 | 4 | 5 | 5 | 5 | 3 | 3 | 1 | 2 | 5 | 4 | 5 | 1 | 1 | 4 | 1 | 1 | 3 | 4 | 4 | 5 | 1 | 4 | 1 | 3 | 2 | 5 | 1 | 2 | 2
396 | 14 | 6 | 24 | 35 | 48 | 53 | 61 | 68 | 80 | 89 | 102 | 112 | 128 | 138 | 1 | 1 | 1 | 3 | 5 | 3 | 5 | 5 | 2 | 4 | 1 | 4 | 4 | 4 | 3 | 2 | 1 | 1 | 1 | 2 | 5 | 1 | 1 | 1 | 2 | 1 | 2 | 2 | 2 | 2 | 3 | 5 | 1 | 1 | 4 | 3 | 4 | 5 | 2 | 2 | 1 | 4 | 4 | 1 | 4 | 4 | 3 | 5 | 5 | 1 | 1 | 3
397 | 15 | 8 | 25 | 37 | 49 | 62 | 74 | 85 | 98 | 107 | 115 | 126 | 138 | 146 | 1 | 5 | 1 | 1 | 4 | 3 | 5 | 5 | 2 | 5 | 1 | 4 | 1 | 5 | 1 | 5 | 5 | 3 | 3 | 2 | 4 | 2 | 2 | 4 | 1 | 3 | 3 | 4 | 3 | 3 | 3 | 4 | 3 | 1 | 2 | 3 | 1 | 1 | 1 | 5 | 3 | 4 | 3 | 1 | 3 | 4 | 4 | 1 | 1 | 3 | 2 | 2
398 | 22 | 17 | 26 | 42 | 53 | 62 | 77 | 94 | 103 | 113 | 126 | 140 | 152 | 164 | 2 | 5 | 5 | 5 | 2 | 3 | 2 | 2 | 2 | 5 | 5 | 4 | 1 | 1 | 4 | 5 | 4 | 2 | 1 | 2 | 4 | 3 | 5 | 3 | 5 | 5 | 4 | 3 | 1 | 1 | 2 | 5 | 1 | 2 | 4 | 3 | 3 | 4 | 3 | 3 | 4 | 1 | 4 | 5 | 5 | 3 | 1 | 3 | 2 | 3 | 3 | 4
399 | 17 | 10 | 23 | 37 | 47 | 59 | 72 | 80 | 94 | 108 | 117 | 129 | 141 | 154 | 2 | 4 | 3 | 1 | 3 | 4 | 2 | 4 | 2 | 4 | 4 | 4 | 1 | 4 | 4 | 1 | 5 | 3 | 2 | 2 | 3 | 4 | 3 | 3 | 2 | 3 | 1 | 2 | 5 | 3 | 4 | 2 | 3 | 4 | 3 | 4 | 4 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 5 | 1 | 3 | 3 | 3 | 2 | 5 | 3
400 | 21 | 11 | 26 | 38 | 53 | 67 | 73 | 86 | 93 | 102 | 111 | 130 | 141 | 155 | 1 | 4 | 1 | 5 | 5 | 5 | 1 | 4 | 5 | 4 | 1 | 2 | 2 | 5 | 3 | 5 | 3 | 4 | 3 | 4 | 2 | 1 | 1 | 2 | 1 | 3 | 5 | 4 | 2 | 1 | 2 | 2 | 1 | 1 | 2 | 5 | 4 | 1 | 1 | 3 | 5 | 4 | 5 | 5 | 4 | 1 | 4 | 2 | 5 | 3 | 1 | 5
401 | 18 | 12 | 24 | 37 | 50 | 59 | 74 | 86 | 99 | 111 | 121 | 133 | 148 | 160 | 1 | 5 | 5 | 1 | 2 | 4 | 2 | 4 | 5 | 1 | 3 | 4 | 3 | 3 | 5 | 2 | 2 | 2 | 1 | 4 | 5 | 2 | 5 | 3 | 1 | 4 | 2 | 5 | 4 | 4 | 1 | 4 | 4 | 1 | 3 | 4 | 2 | 4 | 2 | 2 | 3 | 2 | 5 | 2 | 5 | 3 | 5 | 2 | 3 | 5 | 2 | 2
402 | 18 | 10 | 23 | 36 | 49 | 62 | 71 | 85 | 90 | 103 | 111 | 123 | 139 | 150 | 1 | 4 | 1 | 4 | 3 | 5 | 1 | 4 | 5 | 4 | 1 | 3 | 5 | 2 | 1 | 5 | 3 | 4 | 3 | 3 | 1 | 2 | 3 | 3 | 2 | 4 | 5 | 3 | 2 | 1 | 1 | 1 | 5 | 1 | 3 | 4 | 3 | 1 | 2 | 2 | 2 | 3 | 5 | 2 | 3 | 4 | 4 | 5 | 5 | 4 | 1 | 1
403 | 19 | 11 | 27 | 41 | 55 | 70 | 84 | 99 | 113 | 127 | 135 | 149 | 167 | 181 | 3 | 1 | 3 | 4 | 5 | 3 | 3 | 5 | 4 | 4 | 5 | 1 | 1 | 5 | 5 | 3 | 5 | 3 | 3 | 4 | 3 | 2 | 4 | 5 | 4 | 4 | 5 | 2 | 3 | 5 | 5 | 1 | 5 | 1 | 5 | 3 | 1 | 1 | 4 | 2 | 5 | 4 | 4 | 1 | 5 | 3 | 5 | 5 | 3 | 3 | 4 | 4
404 | 19 | 13 | 25 | 35 | 48 | 64 | 78 | 90 | 107 | 119 | 133 | 147 | 154 | 161 | 3 | 2 | 5 | 3 | 2 | 4 | 3 | 3 | 3 | 3 | 1 | 3 | 3 | 5 | 2 | 3 | 4 | 4 | 5 | 3 | 2 | 4 | 5 | 3 | 3 | 1 | 3 | 5 | 4 | 5 | 3 | 5 | 2 | 2 | 4 | 4 | 4 | 2 | 4 | 4 | 4 | 5 | 3 | 2 | 1 | 1 | 4 | 1 | 1 | 2 | 2 | 2
405 | 20 | 12 | 28 | 41 | 51 | 66 | 82 | 90 | 105 | 118 | 126 | 136 | 150 | 162 | 2 | 4 | 3 | 3 | 3 | 5 | 5 | 3 | 3 | 5 | 3 | 2 | 3 | 1 | 1 | 5 | 4 | 3 | 5 | 3 | 5 | 1 | 5 | 5 | 1 | 1 | 2 | 4 | 5 | 5 | 3 | 2 | 2 | 4 | 3 | 4 | 2 | 3 | 1 | 2 | 4 | 2 | 2 | 2 | 2 | 3 | 4 | 5 | 3 | 3 | 1 | 5
406 | 19 | 13 | 24 | 39 | 54 | 60 | 70 | 80 | 91 | 103 | 113 | 129 | 144 | 154 | 2 | 5 | 3 | 3 | 5 | 1 | 4 | 1 | 5 | 5 | 4 | 1 | 3 | 5 | 3 | 4 | 3 | 1 | 1 | 1 | 3 | 5 | 1 | 1 | 4 | 4 | 1 | 1 | 4 | 4 | 1 | 2 | 5 | 2 | 4 | 1 | 4 | 2 | 1 | 3 | 5 | 5 | 5 | 1 | 3 | 4 | 3 | 5 | 1 | 3 | 5 | 1
407 | 20 | 13 | 24 | 31 | 40 | 54 | 70 | 85 | 96 | 108 | 123 | 133 | 142 | 154 | 4 | 2 | 5 | 2 | 5 | 2 | 2 | 2 | 1 | 1 | 3 | 2 | 2 | 1 | 2 | 4 | 4 | 5 | 3 | 2 | 4 | 3 | 5 | 4 | 4 | 3 | 5 | 3 | 5 | 3 | 1 | 2 | 5 | 2 | 2 | 3 | 5 | 3 | 3 | 4 | 4 | 3 | 2 | 1 | 3 | 3 | 2 | 1 | 3 | 3 | 5 | 1
408 | 13 | 10 | 19 | 29 | 38 | 49 | 64 | 75 | 85 | 96 | 107 | 119 | 136 | 142 | 1 | 2 | 4 | 3 | 2 | 1 | 2 | 4 | 2 | 4 | 3 | 1 | 3 | 3 | 1 | 2 | 3 | 3 | 1 | 4 | 3 | 3 | 4 | 5 | 2 | 1 | 5 | 3 | 1 | 4 | 3 | 2 | 1 | 5 | 2 | 3 | 2 | 5 | 3 | 1 | 2 | 4 | 1 | 5 | 5 | 3 | 4 | 5 | 1 | 3 | 1 | 1
409 | 15 | 10 | 24 | 39 | 51 | 64 | 76 | 94 | 102 | 114 | 125 | 140 | 152 | 162 | 2 | 2 | 1 | 5 | 2 | 3 | 5 | 4 | 4 | 4 | 3 | 4 | 2 | 4 | 3 | 3 | 4 | 1 | 3 | 5 | 2 | 3 | 3 | 4 | 5 | 5 | 3 | 5 | 2 | 2 | 1 | 3 | 2 | 5 | 3 | 2 | 2 | 1 | 5 | 3 | 2 | 4 | 5 | 4 | 5 | 3 | 3 | 1 | 2 | 2 | 1 | 5
410 | 10 | 6 | 19 | 33 | 40 | 55 | 72 | 82 | 94 | 103 | 115 | 130 | 140 | 156 | 2 | 1 | 1 | 2 | 2 | 2 | 5 | 4 | 5 | 2 | 2 | 5 | 2 | 1 | 1 | 3 | 2 | 5 | 4 | 4 | 5 | 2 | 5 | 5 | 2 | 1 | 2 | 5 | 1 | 3 | 5 | 3 | 1 | 2 | 4 | 2 | 3 | 2 | 5 | 2 | 5 | 1 | 4 | 5 | 3 | 3 | 3 | 1 | 3 | 3 | 5 | 5
411 | 20 | 15 | 30 | 43 | 58 | 70 | 84 | 93 | 105 | 120 | 134 | 145 | 156 | 166 | 2 | 5 | 4 | 4 | 1 | 4 | 5 | 5 | 2 | 4 | 5 | 2 | 3 | 4 | 4 | 4 | 3 | 4 | 2 | 3 | 5 | 3 | 4 | 2 | 1 | 3 | 2 | 3 | 4 | 4 | 2 | 2 | 4 | 5 | 2 | 4 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 5 | 5 | 2 | 2 | 2 | 3 | 1 | 4 | 2
412 | 20 | 12 | 26 | 39 | 53 | 66 | 80 | 91 | 99 | 113 | 124 | 137 | 148 | 156 | 3 | 1 | 5 | 3 | 4 | 4 | 5 | 1 | 4 | 2 | 4 | 3 | 5 | 3 | 2 | 4 | 4 | 1 | 4 | 4 | 5 | 2 | 5 | 2 | 4 | 1 | 3 | 3 | 1 | 1 | 2 | 4 | 5 | 2 | 2 | 5 | 3 | 5 | 1 | 2 | 5 | 3 | 1 | 4 | 4 | 4 | 1 | 2 | 1 | 2 | 2 | 3
413 | 16 | 9 | 22 | 34 | 50 | 65 | 77 | 87 | 105 | 121 | 135 | 143 | 151 | 165 | 1 | 2 | 1 | 5 | 3 | 4 | 3 | 3 | 1 | 5 | 4 | 2 | 5 | 5 | 5 | 1 | 5 | 5 | 2 | 3 | 4 | 3 | 1 | 4 | 2 | 2 | 4 | 2 | 5 | 5 | 5 | 3 | 5 | 5 | 4 | 2 | 4 | 5 | 3 | 2 | 1 | 5 | 1 | 1 | 1 | 1 | 1 | 5 | 3 | 5 | 1 | 5
414 | 20 | 14 | 22 | 35 | 44 | 55 | 66 | 78 | 89 | 100 | 113 | 129 | 145 | 154 | 5 | 4 | 3 | 2 | 4 | 2 | 1 | 1 | 5 | 4 | 2 | 2 | 2 | 3 | 2 | 2 | 4 | 2 | 3 | 2 | 3 | 3 | 1 | 4 | 4 | 4 | 3 | 1 | 1 | 5 | 1 | 4 | 3 | 2 | 4 | 2 | 2 | 1 | 5 | 5 | 5 | 5 | 1 | 5 | 2 | 5 | 4 | 5 | 1 | 1 | 5 | 2
415 | 12 | 9 | 14 | 27 | 44 | 61 | 70 | 86 | 97 | 111 | 125 | 137 | 148 | 156 | 2 | 4 | 2 | 1 | 1 | 2 | 1 | 1 | 4 | 1 | 3 | 5 | 4 | 5 | 4 | 4 | 4 | 5 | 4 | 4 | 1 | 1 | 5 | 2 | 3 | 5 | 3 | 5 | 2 | 5 | 3 | 1 | 3 | 4 | 3 | 4 | 5 | 2 | 4 | 3 | 1 | 2 | 5 | 4 | 3 | 5 | 2 | 1 | 3 | 1 | 1 | 3
416 | 10 | 7 | 16 | 29 | 42 | 55 | 65 | 79 | 89 | 104 | 116 | 126 | 139 | 149 | 1 | 2 | 1 | 3 | 1 | 2 | 4 | 2 | 5 | 3 | 2 | 3 | 2 | 2 | 4 | 5 | 2 | 5 | 2 | 4 | 4 | 4 | 1 | 1 | 3 | 2 | 5 | 4 | 3 | 4 | 2 | 1 | 5 | 2 | 5 | 3 | 2 | 3 | 5 | 2 | 1 | 5 | 2 | 2 | 4 | 3 | 2 | 4 | 2 | 1 | 5 | 2
417 | 17 | 13 | 25 | 37 | 48 | 65 | 75 | 87 | 98 | 110 | 119 | 133 | 149 | 161 | 2 | 1 | 5 | 5 | 3 | 1 | 4 | 4 | 2 | 3 | 3 | 4 | 1 | 2 | 3 | 5 | 5 | 4 | 3 | 5 | 2 | 1 | 5 | 2 | 4 | 1 | 2 | 5 | 1 | 4 | 1 | 5 | 5 | 3 | 2 | 2 | 2 | 1 | 5 | 1 | 5 | 1 | 5 | 3 | 4 | 5 | 4 | 3 | 2 | 4 | 1 | 5
418 | 22 | 16 | 25 | 38 | 49 | 64 | 75 | 87 | 105 | 115 | 128 | 138 | 155 | 166 | 3 | 3 | 5 | 5 | 2 | 4 | 2 | 1 | 4 | 4 | 3 | 2 | 2 | 2 | 5 | 2 | 2 | 5 | 4 | 4 | 2 | 2 | 3 | 4 | 5 | 1 | 4 | 2 | 5 | 5 | 4 | 4 | 2 | 1 | 3 | 4 | 1 | 3 | 4 | 5 | 1 | 4 | 1 | 4 | 5 | 5 | 5 | 2 | 1 | 5 | 4 | 1
419 | 16 | 10 | 26 | 43 | 50 | 62 | 77 | 92 | 109 | 123 | 129 | 141 | 154 | 167 | 3 | 1 | 4 | 2 | 4 | 2 | 5 | 5 | 5 | 5 | 2 | 5 | 4 | 1 | 1 | 1 | 1 | 1 | 5 | 5 | 5 | 3 | 4 | 3 | 3 | 5 | 3 | 4 | 3 | 5 | 5 | 4 | 5 | 4 | 1 | 4 | 1 | 1 | 3 | 1 | 3 | 4 | 4 | 1 | 3 | 3 | 5 | 2 | 4 | 1 | 3 | 5
420 | 18 | 10 | 23 | 35 | 43 | 54 | 63 | 74 | 85 | 102 | 115 | 133 | 149 | 161 | 3 | 2 | 2 | 3 | 4 | 4 | 4 | 1 | 2 | 5 | 4 | 1 | 1 | 2 | 3 | 2 | 3 | 2 | 2 | 4 | 5 | 1 | 2 | 1 | 2 | 3 | 3 | 3 | 1 | 4 | 4 | 2 | 5 | 4 | 5 | 3 | 3 | 5 | 3 | 2 | 5 | 5 | 4 | 4 | 1 | 5 | 5 | 5 | 5 | 2 | 4 | 1
421 | 17 | 13 | 20 | 30 | 43 | 54 | 67 | 75 | 87 | 101 | 111 | 127 | 135 | 147 | 2 | 5 | 4 | 2 | 1 | 3 | 1 | 2 | 3 | 2 | 3 | 2 | 5 | 2 | 5 | 1 | 5 | 1 | 3 | 2 | 2 | 5 | 5 | 1 | 2 | 3 | 2 | 1 | 5 | 1 | 5 | 1 | 4 | 2 | 4 | 4 | 2 | 1 | 2 | 5 | 5 | 5 | 1 | 5 | 4 | 1 | 1 | 2 | 4 | 5 | 1 | 2
422 | 19 | 12 | 25 | 40 | 54 | 66 | 77 | 93 | 107 | 119 | 131 | 143 | 156 | 166 | 3 | 2 | 5 | 2 | 2 | 5 | 2 | 4 | 5 | 4 | 1 | 5 | 5 | 3 | 4 | 2 | 5 | 3 | 1 | 3 | 5 | 1 | 4 | 1 | 4 | 3 | 4 | 5 | 2 | 4 | 3 | 5 | 5 | 2 | 2 | 3 | 5 | 1 | 1 | 5 | 5 | 3 | 1 | 3 | 4 | 1 | 5 | 3 | 3 | 3 | 1 | 3
423 | 18 | 13 | 20 | 35 | 42 | 53 | 64 | 79 | 95 | 108 | 120 | 134 | 142 | 161 | 1 | 3 | 5 | 4 | 2 | 3 | 1 | 1 | 2 | 4 | 5 | 4 | 1 | 3 | 1 | 2 | 2 | 4 | 3 | 2 | 3 | 1 | 2 | 5 | 5 | 2 | 3 | 5 | 5 | 4 | 3 | 4 | 1 | 4 | 5 | 3 | 5 | 2 | 4 | 1 | 5 | 5 | 3 | 1 | 4 | 2 | 1 | 1 | 5 | 4 | 5 | 5
424 | 17 | 8 | 27 | 41 | 51 | 67 | 74 | 86 | 102 | 118 | 134 | 142 | 157 | 166 | 2 | 1 | 3 | 2 | 5 | 4 | 5 | 5 | 2 | 5 | 2 | 5 | 1 | 5 | 2 | 2 | 5 | 4 | 3 | 4 | 1 | 4 | 1 | 1 | 5 | 1 | 2 | 4 | 4 | 2 | 5 | 5 | 2 | 4 | 5 | 5 | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 4 | 5 | 5 | 3 | 2 | 1 | 1 | 5 | 2
425 | 17 | 9 | 23 | 36 | 47 | 56 | 71 | 85 | 93 | 106 | 123 | 135 | 148 | 155 | 1 | 2 | 2 | 4 | 3 | 5 | 3 | 3 | 4 | 1 | 5 | 3 | 4 | 3 | 1 | 3 | 4 | 2 | 1 | 2 | 4 | 4 | 2 | 5 | 3 | 3 | 3 | 5 | 3 | 1 | 2 | 2 | 3 | 3 | 4 | 3 | 5 | 3 | 5 | 4 | 2 | 3 | 2 | 5 | 5 | 2 | 3 | 3 | 1 | 4 | 1 | 1
426 | 25 | 17 | 30 | 42 | 56 | 71 | 83 | 100 | 108 | 124 | 134 | 144 | 158 | 168 | 3 | 5 | 4 | 5 | 5 | 3 | 2 | 3 | 3 | 2 | 2 | 5 | 1 | 5 | 5 | 3 | 4 | 4 | 3 | 4 | 4 | 2 | 5 | 1 | 5 | 2 | 5 | 5 | 3 | 3 | 1 | 1 | 4 | 5 | 3 | 4 | 1 | 5 | 2 | 2 | 5 | 3 | 1 | 1 | 2 | 5 | 4 | 3 | 5 | 1 | 2 | 2
427 | 16 | 14 | 25 | 33 | 39 | 52 | 66 | 80 | 93 | 103 | 117 | 130 | 146 | 155 | 5 | 3 | 4 | 2 | 1 | 1 | 5 | 4 | 4 | 2 | 1 | 1 | 2 | 2 | 1 | 1 | 5 | 3 | 2 | 3 | 5 | 3 | 3 | 3 | 4 | 2 | 3 | 5 | 2 | 4 | 3 | 4 | 2 | 1 | 4 | 3 | 1 | 3 | 5 | 5 | 5 | 3 | 3 | 2 | 4 | 5 | 2 | 5 | 4 | 1 | 2 | 2
428 | 17 | 11 | 25 | 33 | 44 | 53 | 62 | 80 | 94 | 105 | 116 | 127 | 138 | 148 | 1 | 4 | 2 | 4 | 5 | 1 | 5 | 3 | 2 | 2 | 3 | 1 | 1 | 1 | 4 | 5 | 3 | 2 | 2 | 2 | 5 | 2 | 1 | 1 | 4 | 5 | 4 | 5 | 3 | 4 | 4 | 3 | 3 | 5 | 2 | 1 | 5 | 1 | 2 | 3 | 3 | 2 | 3 | 3 | 3 | 1 | 2 | 5 | 5 | 2 | 1 | 2
429 | 18 | 10 | 26 | 41 | 54 | 70 | 83 | 93 | 105 | 116 | 124 | 136 | 143 | 155 | 2 | 3 | 1 | 4 | 4 | 4 | 5 | 3 | 2 | 5 | 5 | 3 | 4 | 2 | 2 | 5 | 3 | 5 | 5 | 3 | 5 | 4 | 2 | 2 | 3 | 1 | 1 | 5 | 1 | 5 | 3 | 3 | 4 | 2 | 4 | 1 | 1 | 4 | 2 | 1 | 2 | 3 | 5 | 2 | 2 | 2 | 2 | 1 | 3 | 4 | 3 | 2
430 | 13 | 9 | 17 | 29 | 44 | 50 | 61 | 73 | 90 | 105 | 119 | 134 | 145 | 157 | 2 | 5 | 1 | 1 | 2 | 2 | 1 | 3 | 4 | 3 | 1 | 4 | 2 | 5 | 5 | 3 | 2 | 2 | 1 | 1 | 4 | 4 | 2 | 1 | 2 | 1 | 4 | 5 | 5 | 5 | 3 | 4 | 4 | 5 | 2 | 4 | 1 | 5 | 5 | 3 | 5 | 4 | 1 | 5 | 4 | 2 | 3 | 2 | 3 | 4 | 1 | 4
431 | 18 | 14 | 26 | 36 | 51 | 62 | 80 | 97 | 109 | 120 | 132 | 143 | 161 | 176 | 3 | 1 | 5 | 5 | 3 | 1 | 5 | 3 | 5 | 1 | 2 | 2 | 4 | 5 | 4 | 2 | 5 | 3 | 1 | 2 | 5 | 5 | 4 | 4 | 4 | 3 | 5 | 5 | 2 | 4 | 4 | 2 | 1 | 4 | 3 | 3 | 5 | 2 | 2 | 3 | 4 | 2 | 1 | 4 | 4 | 5 | 5 | 4 | 5 | 4 | 2 | 4
432 | 17 | 10 | 22 | 35 | 49 | 65 | 73 | 88 | 96 | 106 | 122 | 136 | 145 | 156 | 2 | 5 | 2 | 1 | 4 | 3 | 1 | 4 | 4 | 3 | 3 | 3 | 5 | 4 | 2 | 3 | 5 | 3 | 3 | 5 | 2 | 2 | 3 | 1 | 2 | 4 | 4 | 5 | 1 | 3 | 3 | 1 | 4 | 1 | 2 | 3 | 5 | 3 | 3 | 5 | 1 | 3 | 5 | 5 | 2 | 4 | 1 | 2 | 5 | 3 | 2 | 1
433 | 15 | 9 | 22 | 36 | 44 | 58 | 70 | 81 | 96 | 108 | 125 | 136 | 151 | 159 | 1 | 3 | 3 | 2 | 1 | 5 | 5 | 2 | 4 | 3 | 5 | 2 | 1 | 3 | 1 | 3 | 4 | 2 | 3 | 5 | 2 | 2 | 5 | 3 | 3 | 1 | 2 | 5 | 5 | 5 | 1 | 4 | 2 | 3 | 5 | 2 | 5 | 5 | 3 | 4 | 4 | 2 | 1 | 4 | 5 | 3 | 3 | 4 | 1 | 3 | 1 | 3
434 | 23 | 16 | 25 | 37 | 53 | 67 | 81 | 101 | 115 | 125 | 131 | 142 | 153 | 163 | 1 | 5 | 5 | 5 | 2 | 5 | 1 | 1 | 5 | 3 | 2 | 2 | 3 | 4 | 5 | 4 | 5 | 3 | 2 | 4 | 4 | 2 | 3 | 5 | 5 | 5 | 5 | 5 | 1 | 4 | 4 | 5 | 5 | 1 | 2 | 2 | 1 | 1 | 2 | 2 | 3 | 1 | 5 | 2 | 1 | 3 | 5 | 2 | 1 | 3 | 3 | 3
435 | 21 | 16 | 26 | 42 | 49 | 62 | 76 | 89 | 97 | 108 | 115 | 125 | 134 | 152 | 5 | 2 | 5 | 4 | 1 | 4 | 2 | 3 | 3 | 5 | 3 | 5 | 1 | 2 | 3 | 1 | 4 | 2 | 5 | 2 | 2 | 3 | 4 | 5 | 1 | 3 | 4 | 5 | 1 | 5 | 1 | 1 | 2 | 3 | 1 | 5 | 2 | 3 | 1 | 1 | 3 | 1 | 2 | 4 | 1 | 5 | 2 | 1 | 4 | 5 | 4 | 5
436 | 25 | 16 | 31 | 42 | 57 | 69 | 84 | 95 | 109 | 123 | 132 | 139 | 146 | 160 | 4 | 4 | 5 | 3 | 4 | 5 | 5 | 1 | 1 | 3 | 4 | 3 | 5 | 5 | 3 | 2 | 2 | 2 | 3 | 5 | 5 | 3 | 5 | 2 | 2 | 2 | 5 | 2 | 1 | 4 | 4 | 5 | 5 | 2 | 5 | 2 | 1 | 5 | 2 | 1 | 3 | 2 | 1 | 1 | 1 | 3 | 2 | 1 | 5 | 3 | 2 | 4
437 | 23 | 16 | 33 | 45 | 59 | 67 | 74 | 84 | 100 | 111 | 120 | 135 | 142 | 155 | 4 | 3 | 5 | 4 | 4 | 3 | 5 | 5 | 3 | 4 | 3 | 2 | 5 | 1 | 5 | 3 | 1 | 1 | 4 | 2 | 3 | 1 | 2 | 1 | 4 | 3 | 2 | 1 | 2 | 5 | 5 | 4 | 2 | 1 | 3 | 5 | 3 | 1 | 1 | 4 | 5 | 1 | 5 | 4 | 2 | 1 | 1 | 3 | 4 | 3 | 1 | 5
438 | 15 | 11 | 23 | 36 | 48 | 64 | 80 | 92 | 107 | 121 | 131 | 143 | 154 | 165 | 3 | 1 | 3 | 4 | 2 | 2 | 3 | 5 | 3 | 4 | 2 | 4 | 3 | 3 | 5 | 1 | 4 | 4 | 3 | 5 | 5 | 5 | 4 | 2 | 1 | 3 | 3 | 5 | 4 | 2 | 4 | 5 | 5 | 2 | 4 | 3 | 3 | 2 | 1 | 4 | 3 | 2 | 3 | 4 | 1 | 2 | 4 | 4 | 3 | 2 | 1 | 5
439 | 14 | 9 | 21 | 30 | 39 | 50 | 67 | 78 | 89 | 102 | 119 | 128 | 136 | 153 | 1 | 2 | 2 | 4 | 2 | 3 | 5 | 2 | 5 | 1 | 2 | 1 | 2 | 1 | 5 | 1 | 5 | 1 | 1 | 4 | 4 | 4 | 5 | 4 | 3 | 5 | 1 | 2 | 1 | 5 | 3 | 2 | 5 | 4 | 1 | 3 | 5 | 5 | 5 | 2 | 1 | 3 | 1 | 4 | 2 | 4 | 1 | 1 | 5 | 3 | 5 | 4
440 | 14 | 10 | 17 | 31 | 45 | 59 | 72 | 84 | 94 | 107 | 118 | 127 | 139 | 147 | 2 | 4 | 3 | 1 | 1 | 3 | 1 | 2 | 3 | 4 | 5 | 2 | 5 | 4 | 3 | 2 | 5 | 3 | 5 | 1 | 2 | 5 | 2 | 4 | 3 | 2 | 3 | 4 | 5 | 2 | 2 | 1 | 5 | 2 | 2 | 4 | 1 | 4 | 1 | 5 | 3 | 4 | 1 | 1 | 1 | 2 | 4 | 5 | 4 | 1 | 1 | 2
441 | 20 | 11 | 26 | 38 | 50 | 56 | 70 | 81 | 92 | 106 | 114 | 127 | 137 | 147 | 1 | 5 | 2 | 3 | 5 | 4 | 2 | 4 | 3 | 1 | 5 | 3 | 3 | 1 | 5 | 3 | 1 | 1 | 2 | 2 | 2 | 5 | 3 | 4 | 2 | 3 | 2 | 4 | 4 | 2 | 3 | 2 | 1 | 4 | 4 | 5 | 2 | 3 | 1 | 2 | 2 | 2 | 4 | 5 | 1 | 4 | 3 | 2 | 1 | 2 | 2 | 5
442 | 16 | 9 | 20 | 31 | 46 | 61 | 72 | 87 | 103 | 120 | 132 | 149 | 162 | 175 | 1 | 1 | 3 | 4 | 3 | 4 | 2 | 2 | 5 | 1 | 1 | 4 | 4 | 5 | 4 | 2 | 4 | 5 | 2 | 4 | 1 | 4 | 5 | 1 | 4 | 4 | 2 | 5 | 5 | 5 | 1 | 5 | 5 | 4 | 4 | 4 | 5 | 1 | 3 | 3 | 5 | 5 | 4 | 3 | 4 | 1 | 5 | 3 | 5 | 5 | 1 | 2
443 | 15 | 11 | 20 | 35 | 44 | 55 | 65 | 76 | 87 | 102 | 112 | 122 | 133 | 147 | 2 | 3 | 5 | 1 | 2 | 2 | 4 | 1 | 3 | 4 | 4 | 4 | 2 | 1 | 3 | 3 | 4 | 3 | 1 | 3 | 1 | 1 | 5 | 3 | 3 | 1 | 4 | 3 | 4 | 3 | 2 | 2 | 4 | 5 | 4 | 2 | 2 | 5 | 1 | 2 | 3 | 3 | 3 | 1 | 2 | 1 | 4 | 4 | 5 | 5 | 1 | 3
444 | 15 | 10 | 25 | 34 | 45 | 56 | 63 | 76 | 86 | 94 | 107 | 120 | 129 | 140 | 2 | 1 | 2 | 5 | 4 | 1 | 5 | 5 | 1 | 5 | 1 | 2 | 3 | 1 | 2 | 5 | 3 | 2 | 1 | 5 | 1 | 1 | 2 | 3 | 3 | 3 | 2 | 5 | 1 | 3 | 3 | 3 | 2 | 2 | 1 | 3 | 3 | 3 | 2 | 5 | 3 | 5 | 3 | 2 | 1 | 1 | 2 | 5 | 3 | 2 | 1 | 5
445 | 21 | 14 | 25 | 37 | 51 | 68 | 81 | 89 | 100 | 112 | 124 | 132 | 142 | 153 | 4 | 1 | 4 | 5 | 4 | 3 | 1 | 3 | 2 | 4 | 2 | 4 | 2 | 3 | 5 | 4 | 3 | 5 | 5 | 4 | 2 | 4 | 3 | 4 | 5 | 1 | 1 | 1 | 4 | 1 | 2 | 4 | 2 | 2 | 5 | 3 | 3 | 5 | 2 | 2 | 1 | 4 | 2 | 1 | 3 | 1 | 5 | 1 | 3 | 3 | 1 | 4
446 | 18 | 13 | 23 | 39 | 52 | 63 | 70 | 85 | 99 | 111 | 126 | 137 | 149 | 162 | 3 | 3 | 4 | 3 | 1 | 4 | 3 | 2 | 5 | 3 | 5 | 3 | 2 | 4 | 4 | 3 | 4 | 1 | 5 | 1 | 1 | 1 | 1 | 4 | 2 | 4 | 5 | 4 | 1 | 5 | 3 | 5 | 2 | 3 | 2 | 5 | 5 | 4 | 2 | 4 | 4 | 1 | 3 | 3 | 2 | 1 | 4 | 5 | 4 | 4 | 1 | 4
447 | 20 | 12 | 23 | 35 | 46 | 61 | 79 | 88 | 100 | 108 | 120 | 136 | 146 | 157 | 5 | 5 | 1 | 1 | 5 | 3 | 1 | 2 | 2 | 2 | 4 | 4 | 3 | 1 | 3 | 4 | 4 | 4 | 2 | 5 | 3 | 5 | 5 | 5 | 2 | 5 | 1 | 1 | 2 | 3 | 2 | 5 | 1 | 1 | 3 | 3 | 1 | 5 | 4 | 2 | 5 | 4 | 4 | 3 | 2 | 3 | 3 | 2 | 1 | 2 | 5 | 3
448 | 19 | 14 | 28 | 38 | 49 | 56 | 64 | 76 | 85 | 92 | 108 | 117 | 129 | 140 | 3 | 3 | 5 | 3 | 3 | 2 | 4 | 5 | 3 | 4 | 1 | 2 | 5 | 3 | 1 | 2 | 3 | 1 | 1 | 2 | 1 | 1 | 4 | 2 | 4 | 4 | 3 | 1 | 3 | 1 | 4 | 1 | 1 | 2 | 1 | 3 | 4 | 4 | 3 | 5 | 2 | 2 | 2 | 3 | 2 | 1 | 5 | 4 | 2 | 3 | 3 | 3
449 | 16 | 12 | 26 | 38 | 48 | 63 | 74 | 81 | 95 | 107 | 120 | 129 | 134 | 147 | 4 | 2 | 2 | 4 | 1 | 3 | 5 | 5 | 5 | 4 | 2 | 1 | 4 | 1 | 4 | 1 | 1 | 5 | 5 | 4 | 1 | 2 | 4 | 4 | 2 | 1 | 2 | 2 | 5 | 3 | 5 | 1 | 5 | 3 | 2 | 2 | 3 | 3 | 2 | 5 | 2 | 3 | 1 | 3 | 1 | 2 | 1 | 1 | 5 | 4 | 3 | 1
450 | 17 | 14 | 22 | 34 | 49 | 57 | 70 | 82 | 95 | 109 | 124 | 139 | 154 | 173 | 5 | 2 | 3 | 4 | 1 | 2 | 4 | 1 | 3 | 3 | 4 | 2 | 5 | 1 | 5 | 4 | 2 | 2 | 3 | 1 | 4 | 3 | 1 | 5 | 2 | 5 | 1 | 4 | 4 | 2 | 4 | 3 | 4 | 5 | 2 | 3 | 1 | 5 | 5 | 4 | 5 | 5 | 1 | 4 | 4 | 5 | 4 | 2 | 5 | 4 | 5 | 5
451 | 17 | 7 | 22 | 35 | 47 | 63 | 75 | 88 | 104 | 117 | 130 | 142 | 157 | 172 | 4 | 1 | 1 | 1 | 5 | 5 | 4 | 1 | 2 | 5 | 5 | 1 | 4 | 4 | 1 | 3 | 5 | 5 | 1 | 5 | 2 | 4 | 4 | 2 | 3 | 4 | 4 | 2 | 4 | 5 | 5 | 2 | 1 | 5 | 4 | 3 | 5 | 3 | 4 | 1 | 5 | 2 | 1 | 4 | 3 | 5 | 3 | 4 | 2 | 4 | 4 | 5
452 | 17 | 12 | 22 | 37 | 51 | 67 | 82 | 94 | 105 | 115 | 125 | 139 | 148 | 167 | 4 | 2 | 2 | 4 | 2 | 3 | 1 | 4 | 5 | 4 | 3 | 3 | 4 | 4 | 2 | 4 | 5 | 5 | 5 | 1 | 4 | 5 | 3 | 3 | 5 | 3 | 2 | 2 | 5 | 4 | 1 | 1 | 1 | 3 | 1 | 5 | 1 | 4 | 4 | 1 | 3 | 5 | 2 | 4 | 5 | 1 | 2 | 1 | 5 | 5 | 4 | 5
453 | 15 | 11 | 22 | 28 | 40 | 54 | 62 | 78 | 93 | 103 | 116 | 126 | 133 | 142 | 2 | 4 | 4 | 1 | 3 | 1 | 4 | 3 | 1 | 1 | 1 | 3 | 1 | 4 | 2 | 5 | 3 | 4 | 4 | 3 | 1 | 2 | 4 | 1 | 3 | 3 | 5 | 5 | 5 | 4 | 2 | 4 | 2 | 2 | 2 | 4 | 5 | 3 | 1 | 4 | 1 | 1 | 4 | 4 | 1 | 2 | 2 | 2 | 3 | 1 | 3 | 2
454 | 19 | 13 | 29 | 42 | 56 | 70 | 78 | 91 | 105 | 111 | 123 | 130 | 142 | 150 | 2 | 4 | 2 | 5 | 4 | 2 | 5 | 5 | 5 | 1 | 2 | 5 | 4 | 5 | 4 | 1 | 3 | 5 | 3 | 3 | 3 | 1 | 3 | 1 | 5 | 2 | 5 | 1 | 5 | 3 | 4 | 2 | 2 | 1 | 2 | 1 | 4 | 2 | 5 | 1 | 1 | 3 | 1 | 2 | 1 | 5 | 2 | 4 | 2 | 1 | 2 | 3
455 | 14 | 9 | 21 | 29 | 40 | 49 | 58 | 75 | 84 | 98 | 107 | 120 | 132 | 144 | 2 | 2 | 3 | 2 | 4 | 1 | 3 | 4 | 4 | 1 | 1 | 2 | 2 | 3 | 1 | 5 | 1 | 5 | 2 | 1 | 3 | 2 | 3 | 1 | 5 | 5 | 5 | 2 | 1 | 3 | 1 | 4 | 3 | 5 | 2 | 4 | 1 | 2 | 3 | 3 | 4 | 5 | 3 | 1 | 3 | 4 | 4 | 1 | 5 | 2 | 3 | 2
456 | 18 | 14 | 25 | 34 | 49 | 61 | 68 | 83 | 90 | 103 | 117 | 126 | 138 | 148 | 1 | 5 | 5 | 3 | 2 | 2 | 2 | 5 | 2 | 3 | 2 | 2 | 3 | 5 | 4 | 3 | 4 | 1 | 5 | 2 | 1 | 4 | 1 | 1 | 1 | 5 | 5 | 4 | 1 | 1 | 4 | 1 | 5 | 3 | 2 | 3 | 4 | 4 | 5 | 1 | 4 | 2 | 1 | 2 | 1 | 3 | 5 | 3 | 3 | 4 | 2 | 1
457 | 12 | 9 | 17 | 27 | 35 | 52 | 61 | 76 | 83 | 97 | 110 | 125 | 138 | 146 | 2 | 2 | 4 | 1 | 1 | 2 | 2 | 3 | 5 | 2 | 1 | 2 | 3 | 2 | 2 | 1 | 3 | 5 | 4 | 5 | 2 | 3 | 2 | 2 | 4 | 4 | 4 | 3 | 3 | 1 | 2 | 1 | 4 | 5 | 3 | 2 | 3 | 4 | 5 | 1 | 5 | 4 | 4 | 2 | 2 | 2 | 4 | 5 | 4 | 1 | 1 | 2
458 | 16 | 11 | 22 | 35 | 45 | 57 | 69 | 84 | 102 | 113 | 127 | 141 | 155 | 166 | 2 | 5 | 2 | 2 | 2 | 3 | 2 | 4 | 3 | 3 | 2 | 5 | 3 | 1 | 3 | 3 | 3 | 2 | 5 | 2 | 3 | 4 | 4 | 1 | 5 | 3 | 4 | 3 | 4 | 5 | 4 | 5 | 5 | 1 | 1 | 4 | 2 | 3 | 4 | 5 | 5 | 5 | 3 | 1 | 2 | 4 | 4 | 4 | 3 | 4 | 2 | 2
459 | 14 | 12 | 17 | 29 | 42 | 49 | 64 | 82 | 88 | 97 | 109 | 116 | 130 | 147 | 1 | 5 | 3 | 3 | 1 | 1 | 2 | 1 | 3 | 3 | 5 | 1 | 5 | 5 | 2 | 1 | 1 | 4 | 1 | 1 | 4 | 3 | 5 | 3 | 5 | 3 | 5 | 5 | 2 | 2 | 1 | 1 | 2 | 3 | 3 | 1 | 3 | 3 | 3 | 3 | 1 | 1 | 4 | 1 | 5 | 1 | 5 | 3 | 5 | 2 | 5 | 5
460 | 16 | 13 | 24 | 37 | 49 | 63 | 76 | 88 | 99 | 108 | 118 | 128 | 144 | 154 | 1 | 5 | 2 | 5 | 2 | 1 | 4 | 4 | 5 | 2 | 5 | 1 | 1 | 2 | 4 | 5 | 2 | 3 | 4 | 5 | 4 | 3 | 5 | 1 | 4 | 3 | 4 | 1 | 3 | 4 | 1 | 3 | 5 | 2 | 1 | 1 | 2 | 2 | 1 | 5 | 2 | 5 | 2 | 1 | 4 | 5 | 4 | 3 | 2 | 3 | 4 | 1
461 | 21 | 12 | 30 | 38 | 45 | 56 | 72 | 85 | 96 | 111 | 124 | 134 | 146 | 156 | 1 | 2 | 4 | 5 | 4 | 5 | 4 | 5 | 1 | 3 | 1 | 3 | 1 | 1 | 1 | 4 | 4 | 5 | 1 | 1 | 3 | 4 | 4 | 5 | 3 | 3 | 2 | 5 | 5 | 1 | 2 | 3 | 5 | 5 | 3 | 2 | 4 | 2 | 2 | 5 | 1 | 4 | 1 | 4 | 2 | 3 | 4 | 3 | 2 | 2 | 1 | 5
462 | 20 | 16 | 24 | 39 | 48 | 60 | 75 | 88 | 97 | 106 | 121 | 131 | 143 | 156 | 3 | 4 | 4 | 5 | 3 | 1 | 1 | 3 | 5 | 3 | 3 | 4 | 2 | 2 | 2 | 3 | 2 | 4 | 3 | 3 | 3 | 4 | 3 | 5 | 3 | 1 | 5 | 4 | 1 | 2 | 4 | 2 | 2 | 1 | 4 | 2 | 3 | 3 | 4 | 5 | 2 | 1 | 5 | 2 | 3 | 3 | 5 | 1 | 3 | 2 | 3 | 5
463 | 21 | 14 | 27 | 42 | 55 | 63 | 73 | 83 | 96 | 110 | 121 | 135 | 146 | 158 | 2 | 5 | 4 | 3 | 4 | 3 | 3 | 3 | 5 | 1 | 4 | 5 | 2 | 1 | 5 | 5 | 1 | 3 | 3 | 1 | 3 | 3 | 2 | 2 | 2 | 5 | 2 | 1 | 4 | 3 | 2 | 4 | 4 | 4 | 2 | 4 | 1 | 4 | 1 | 5 | 5 | 5 | 1 | 3 | 5 | 1 | 3 | 2 | 2 | 5 | 2 | 3
464 | 23 | 17 | 30 | 47 | 62 | 76 | 89 | 106 | 120 | 133 | 149 | 163 | 177 | 193 | 3 | 5 | 4 | 5 | 4 | 2 | 3 | 4 | 4 | 5 | 4 | 4 | 5 | 1 | 5 | 4 | 3 | 3 | 3 | 5 | 2 | 5 | 4 | 2 | 5 | 5 | 3 | 4 | 3 | 5 | 3 | 3 | 3 | 2 | 3 | 5 | 1 | 5 | 5 | 5 | 4 | 2 | 3 | 5 | 2 | 2 | 5 | 5 | 5 | 3 | 4 | 4
465 | 14 | 8 | 23 | 35 | 50 | 63 | 72 | 88 | 97 | 114 | 126 | 137 | 148 | 161 | 3 | 3 | 1 | 1 | 4 | 2 | 5 | 4 | 4 | 3 | 3 | 2 | 2 | 5 | 4 | 4 | 4 | 3 | 3 | 3 | 2 | 1 | 4 | 2 | 5 | 1 | 5 | 5 | 3 | 1 | 1 | 4 | 3 | 5 | 4 | 5 | 4 | 2 | 3 | 3 | 3 | 2 | 4 | 2 | 5 | 4 | 1 | 1 | 5 | 2 | 2 | 4
466 | 22 | 13 | 29 | 42 | 51 | 63 | 73 | 86 | 94 | 108 | 124 | 134 | 144 | 156 | 3 | 4 | 3 | 3 | 5 | 4 | 4 | 3 | 3 | 3 | 5 | 2 | 2 | 1 | 2 | 4 | 5 | 2 | 4 | 1 | 2 | 3 | 1 | 4 | 2 | 2 | 4 | 5 | 1 | 1 | 4 | 2 | 4 | 2 | 4 | 4 | 4 | 5 | 4 | 3 | 1 | 4 | 3 | 2 | 4 | 4 | 1 | 1 | 5 | 1 | 1 | 5
467 | 15 | 8 | 21 | 34 | 44 | 54 | 69 | 79 | 89 | 98 | 107 | 114 | 128 | 139 | 2 | 1 | 1 | 4 | 2 | 5 | 3 | 3 | 5 | 4 | 2 | 2 | 4 | 3 | 1 | 2 | 4 | 1 | 4 | 1 | 5 | 1 | 5 | 4 | 4 | 1 | 3 | 2 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 3 | 1 | 3 | 1 | 4 | 1 | 1 | 2 | 3 | 4 | 2 | 3 | 5 | 2 | 1 | 3 | 5
468 | 25 | 17 | 32 | 46 | 52 | 63 | 74 | 84 | 94 | 109 | 121 | 135 | 145 | 153 | 5 | 3 | 5 | 4 | 5 | 3 | 3 | 4 | 4 | 4 | 5 | 1 | 1 | 1 | 1 | 3 | 2 | 3 | 2 | 4 | 5 | 4 | 1 | 1 | 3 | 4 | 1 | 2 | 4 | 3 | 1 | 2 | 2 | 5 | 4 | 4 | 4 | 2 | 1 | 5 | 3 | 2 | 5 | 4 | 3 | 4 | 1 | 2 | 1 | 2 | 3 | 2
469 | 16 | 10 | 22 | 36 | 46 | 60 | 73 | 86 | 101 | 112 | 126 | 136 | 148 | 156 | 5 | 1 | 3 | 1 | 4 | 2 | 3 | 3 | 1 | 4 | 4 | 5 | 2 | 1 | 3 | 4 | 5 | 4 | 3 | 2 | 5 | 1 | 4 | 3 | 5 | 2 | 1 | 5 | 2 | 3 | 5 | 5 | 5 | 2 | 3 | 1 | 4 | 3 | 4 | 3 | 3 | 2 | 4 | 1 | 1 | 5 | 3 | 3 | 3 | 1 | 2 | 2
470 | 21 | 13 | 29 | 43 | 58 | 67 | 75 | 87 | 96 | 105 | 117 | 126 | 137 | 145 | 4 | 1 | 5 | 3 | 5 | 3 | 3 | 5 | 5 | 1 | 3 | 5 | 5 | 4 | 2 | 4 | 1 | 1 | 3 | 4 | 2 | 2 | 3 | 1 | 2 | 3 | 3 | 4 | 3 | 4 | 1 | 1 | 2 | 3 | 2 | 2 | 2 | 2 | 5 | 3 | 2 | 3 | 3 | 1 | 1 | 1 | 5 | 4 | 4 | 1 | 2 | 1
471 | 17 | 10 | 21 | 33 | 50 | 64 | 70 | 85 | 101 | 117 | 131 | 138 | 143 | 161 | 4 | 4 | 1 | 1 | 4 | 3 | 1 | 3 | 2 | 2 | 5 | 3 | 5 | 5 | 4 | 3 | 5 | 3 | 3 | 3 | 1 | 3 | 1 | 1 | 5 | 4 | 2 | 4 | 3 | 3 | 5 | 5 | 4 | 2 | 5 | 5 | 2 | 2 | 5 | 5 | 1 | 4 | 1 | 1 | 2 | 1 | 1 | 1 | 5 | 5 | 3 | 5
472 | 23 | 16 | 28 | 43 | 51 | 61 | 73 | 86 | 102 | 114 | 123 | 135 | 144 | 158 | 3 | 4 | 4 | 5 | 2 | 5 | 3 | 2 | 2 | 4 | 5 | 4 | 1 | 2 | 4 | 1 | 3 | 3 | 1 | 3 | 5 | 2 | 4 | 1 | 5 | 2 | 1 | 5 | 5 | 5 | 2 | 4 | 5 | 4 | 2 | 1 | 1 | 1 | 3 | 4 | 2 | 1 | 4 | 5 | 3 | 2 | 3 | 1 | 5 | 2 | 4 | 3
473 | 22 | 18 | 25 | 39 | 48 | 63 | 78 | 90 | 101 | 112 | 125 | 133 | 145 | 160 | 5 | 5 | 4 | 4 | 1 | 3 | 2 | 1 | 5 | 3 | 2 | 4 | 1 | 1 | 2 | 5 | 3 | 3 | 4 | 5 | 3 | 2 | 5 | 5 | 5 | 4 | 2 | 1 | 5 | 1 | 3 | 2 | 5 | 3 | 1 | 2 | 4 | 1 | 4 | 4 | 2 | 1 | 1 | 4 | 5 | 1 | 5 | 1 | 1 | 5 | 4 | 5
474 | 15 | 9 | 20 | 29 | 36 | 42 | 54 | 64 | 79 | 89 | 105 | 124 | 137 | 150 | 2 | 1 | 5 | 1 | 5 | 1 | 3 | 2 | 1 | 2 | 5 | 1 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 3 | 4 | 4 | 2 | 2 | 3 | 1 | 2 | 4 | 5 | 4 | 1 | 5 | 4 | 2 | 1 | 3 | 5 | 5 | 4 | 2 | 5 | 5 | 4 | 5 | 3 | 4 | 2 | 4 | 1 | 5 | 3 | 4
475 | 15 | 9 | 21 | 32 | 41 | 53 | 64 | 78 | 88 | 98 | 113 | 126 | 136 | 149 | 4 | 3 | 1 | 1 | 3 | 3 | 5 | 1 | 2 | 5 | 1 | 3 | 1 | 5 | 1 | 2 | 2 | 2 | 3 | 5 | 3 | 1 | 3 | 4 | 5 | 1 | 5 | 3 | 2 | 2 | 4 | 2 | 2 | 3 | 4 | 1 | 4 | 4 | 3 | 4 | 4 | 4 | 1 | 4 | 2 | 1 | 4 | 3 | 5 | 4 | 2 | 2
476 | 17 | 14 | 23 | 32 | 42 | 54 | 72 | 88 | 103 | 113 | 128 | 143 | 160 | 170 | 1 | 5 | 5 | 3 | 1 | 2 | 3 | 3 | 3 | 2 | 2 | 2 | 1 | 5 | 3 | 1 | 3 | 5 | 2 | 2 | 5 | 5 | 3 | 5 | 4 | 5 | 3 | 4 | 5 | 4 | 2 | 4 | 5 | 1 | 3 | 1 | 5 | 3 | 4 | 3 | 4 | 2 | 4 | 5 | 5 | 4 | 5 | 3 | 1 | 2 | 3 | 4
477 | 16 | 11 | 24 | 34 | 46 | 58 | 73 | 84 | 99 | 103 | 117 | 128 | 141 | 151 | 4 | 4 | 2 | 1 | 2 | 3 | 3 | 5 | 2 | 1 | 4 | 3 | 3 | 3 | 4 | 2 | 4 | 2 | 4 | 2 | 2 | 5 | 3 | 5 | 4 | 1 | 4 | 2 | 5 | 4 | 5 | 1 | 1 | 1 | 1 | 1 | 1 | 5 | 4 | 4 | 4 | 1 | 4 | 2 | 3 | 5 | 2 | 3 | 4 | 1 | 1 | 4
478 | 16 | 9 | 21 | 30 | 45 | 56 | 66 | 82 | 92 | 105 | 116 | 126 | 137 | 149 | 5 | 1 | 2 | 1 | 2 | 5 | 3 | 2 | 4 | 2 | 1 | 2 | 4 | 5 | 5 | 1 | 3 | 2 | 3 | 3 | 2 | 3 | 2 | 3 | 5 | 4 | 5 | 2 | 4 | 3 | 2 | 1 | 3 | 4 | 5 | 1 | 5 | 2 | 2 | 2 | 3 | 2 | 2 | 3 | 3 | 3 | 1 | 4 | 5 | 5 | 1 | 1
479 | 19 | 14 | 26 | 37 | 47 | 56 | 70 | 85 | 96 | 108 | 116 | 127 | 144 | 158 | 4 | 4 | 3 | 3 | 1 | 4 | 4 | 3 | 3 | 2 | 5 | 1 | 4 | 3 | 2 | 1 | 1 | 1 | 4 | 3 | 5 | 5 | 2 | 2 | 5 | 3 | 2 | 5 | 1 | 3 | 2 | 5 | 4 | 3 | 3 | 2 | 1 | 2 | 3 | 2 | 1 | 4 | 4 | 2 | 4 | 5 | 3 | 5 | 2 | 5 | 4 | 3
480 | 20 | 13 | 25 | 34 | 42 | 52 | 65 | 76 | 89 | 102 | 114 | 128 | 139 | 147 | 5 | 2 | 2 | 4 | 3 | 4 | 1 | 4 | 4 | 1 | 1 | 3 | 4 | 2 | 1 | 1 | 3 | 1 | 2 | 4 | 3 | 3 | 3 | 4 | 2 | 5 | 3 | 1 | 5 | 2 | 3 | 3 | 4 | 2 | 5 | 2 | 3 | 3 | 3 | 3 | 5 | 5 | 3 | 1 | 5 | 2 | 3 | 1 | 2 | 3 | 1 | 2
481 | 18 | 13 | 26 | 36 | 43 | 61 | 70 | 77 | 91 | 103 | 115 | 125 | 135 | 146 | 3 | 3 | 3 | 4 | 1 | 4 | 5 | 3 | 3 | 3 | 2 | 2 | 1 | 3 | 2 | 1 | 5 | 4 | 5 | 4 | 2 | 5 | 1 | 1 | 1 | 1 | 4 | 1 | 2 | 3 | 5 | 4 | 4 | 2 | 1 | 5 | 5 | 2 | 4 | 1 | 2 | 3 | 1 | 4 | 2 | 3 | 3 | 2 | 4 | 3 | 1 | 3
482 | 18 | 13 | 23 | 37 | 48 | 61 | 76 | 83 | 97 | 109 | 122 | 138 | 155 | 164 | 4 | 3 | 4 | 2 | 4 | 1 | 4 | 1 | 4 | 4 | 3 | 3 | 5 | 1 | 4 | 1 | 1 | 5 | 5 | 2 | 3 | 3 | 4 | 5 | 3 | 2 | 1 | 1 | 5 | 1 | 3 | 5 | 2 | 1 | 5 | 4 | 1 | 2 | 5 | 5 | 5 | 5 | 3 | 3 | 5 | 4 | 5 | 3 | 2 | 2 | 2 | 3
483 | 20 | 11 | 25 | 33 | 45 | 59 | 73 | 87 | 97 | 107 | 125 | 137 | 145 | 160 | 1 | 4 | 2 | 4 | 5 | 4 | 2 | 3 | 2 | 3 | 1 | 2 | 3 | 2 | 3 | 4 | 5 | 2 | 5 | 2 | 2 | 4 | 5 | 3 | 4 | 1 | 4 | 5 | 3 | 2 | 2 | 3 | 1 | 3 | 1 | 5 | 5 | 5 | 3 | 5 | 4 | 3 | 3 | 2 | 3 | 2 | 2 | 1 | 4 | 1 | 5 | 5
484 | 18 | 12 | 26 | 39 | 52 | 62 | 72 | 88 | 99 | 110 | 124 | 142 | 155 | 164 | 5 | 2 | 1 | 4 | 2 | 4 | 3 | 5 | 2 | 5 | 3 | 3 | 4 | 4 | 4 | 1 | 4 | 4 | 1 | 1 | 5 | 1 | 3 | 1 | 5 | 2 | 5 | 4 | 2 | 5 | 3 | 1 | 4 | 2 | 2 | 3 | 5 | 2 | 2 | 5 | 5 | 4 | 4 | 5 | 2 | 3 | 3 | 5 | 2 | 1 | 3 | 3
485 | 16 | 11 | 21 | 31 | 48 | 59 | 67 | 82 | 99 | 109 | 120 | 132 | 146 | 156 | 2 | 2 | 3 | 4 | 2 | 3 | 4 | 1 | 2 | 2 | 2 | 4 | 3 | 5 | 4 | 5 | 2 | 3 | 2 | 4 | 1 | 1 | 3 | 3 | 5 | 3 | 4 | 3 | 5 | 5 | 2 | 5 | 2 | 1 | 5 | 2 | 4 | 2 | 3 | 2 | 5 | 3 | 3 | 1 | 5 | 3 | 4 | 2 | 1 | 5 | 2 | 2
486 | 14 | 8 | 18 | 28 | 40 | 56 | 64 | 74 | 93 | 99 | 105 | 116 | 129 | 143 | 3 | 1 | 1 | 3 | 2 | 4 | 2 | 2 | 1 | 3 | 5 | 1 | 4 | 5 | 1 | 2 | 5 | 5 | 2 | 4 | 3 | 2 | 2 | 1 | 2 | 2 | 2 | 4 | 5 | 5 | 5 | 4 | 1 | 1 | 1 | 3 | 1 | 2 | 1 | 2 | 4 | 3 | 1 | 3 | 4 | 4 | 4 | 1 | 5 | 3 | 3 | 3
487 | 16 | 9 | 22 | 34 | 45 | 59 | 68 | 83 | 92 | 108 | 125 | 134 | 142 | 155 | 3 | 1 | 2 | 3 | 3 | 4 | 4 | 2 | 5 | 1 | 4 | 2 | 1 | 4 | 3 | 3 | 4 | 5 | 2 | 3 | 1 | 4 | 3 | 1 | 5 | 3 | 4 | 3 | 1 | 1 | 3 | 4 | 5 | 2 | 5 | 4 | 3 | 5 | 4 | 5 | 1 | 1 | 3 | 4 | 1 | 1 | 3 | 3 | 4 | 2 | 3 | 4
488 | 16 | 12 | 20 | 33 | 47 | 60 | 70 | 80 | 93 | 107 | 118 | 130 | 143 | 155 | 4 | 1 | 3 | 4 | 3 | 1 | 1 | 3 | 4 | 3 | 1 | 5 | 3 | 4 | 2 | 5 | 5 | 3 | 4 | 1 | 3 | 3 | 1 | 3 | 2 | 3 | 4 | 1 | 4 | 4 | 4 | 1 | 5 | 4 | 2 | 3 | 2 | 5 | 2 | 2 | 2 | 3 | 3 | 4 | 3 | 5 | 3 | 2 | 4 | 3 | 3 | 2
489 | 18 | 11 | 26 | 38 | 48 | 58 | 69 | 82 | 90 | 100 | 117 | 130 | 147 | 161 | 2 | 3 | 3 | 3 | 5 | 2 | 3 | 5 | 4 | 3 | 3 | 2 | 1 | 4 | 1 | 4 | 1 | 3 | 1 | 5 | 2 | 1 | 3 | 5 | 4 | 2 | 4 | 3 | 3 | 2 | 2 | 1 | 5 | 3 | 1 | 1 | 3 | 4 | 5 | 5 | 3 | 5 | 4 | 1 | 3 | 5 | 4 | 5 | 5 | 3 | 1 | 5
490 | 20 | 11 | 26 | 42 | 60 | 76 | 91 | 104 | 117 | 129 | 141 | 154 | 166 | 183 | 2 | 3 | 1 | 5 | 5 | 4 | 4 | 2 | 4 | 4 | 4 | 4 | 5 | 4 | 5 | 4 | 2 | 5 | 5 | 4 | 4 | 5 | 2 | 4 | 2 | 5 | 1 | 5 | 5 | 5 | 1 | 2 | 3 | 5 | 2 | 2 | 2 | 1 | 4 | 5 | 1 | 4 | 5 | 3 | 1 | 2 | 5 | 4 | 5 | 4 | 3 | 5
491 | 19 | 12 | 24 | 33 | 45 | 57 | 75 | 89 | 103 | 118 | 130 | 143 | 155 | 167 | 3 | 5 | 2 | 2 | 4 | 3 | 3 | 2 | 4 | 3 | 1 | 1 | 2 | 4 | 2 | 4 | 5 | 2 | 3 | 2 | 4 | 5 | 5 | 4 | 4 | 3 | 5 | 2 | 5 | 2 | 4 | 3 | 5 | 2 | 4 | 4 | 3 | 4 | 2 | 3 | 4 | 4 | 1 | 4 | 5 | 5 | 1 | 1 | 5 | 4 | 1 | 2
492 | 22 | 14 | 25 | 34 | 47 | 61 | 74 | 85 | 96 | 108 | 116 | 126 | 135 | 147 | 3 | 4 | 2 | 5 | 3 | 5 | 2 | 1 | 1 | 1 | 4 | 3 | 2 | 5 | 2 | 4 | 3 | 3 | 3 | 5 | 4 | 1 | 3 | 5 | 3 | 1 | 5 | 2 | 4 | 4 | 1 | 2 | 1 | 5 | 2 | 4 | 4 | 1 | 2 | 1 | 3 | 3 | 1 | 3 | 2 | 3 | 2 | 2 | 4 | 2 | 1 | 5
493 | 14 | 9 | 21 | 30 | 43 | 59 | 69 | 81 | 97 | 106 | 116 | 125 | 140 | 148 | 4 | 2 | 1 | 2 | 4 | 1 | 3 | 4 | 5 | 1 | 1 | 2 | 3 | 1 | 5 | 4 | 2 | 5 | 5 | 4 | 1 | 2 | 4 | 3 | 1 | 5 | 1 | 5 | 5 | 5 | 2 | 4 | 5 | 1 | 1 | 2 | 2 | 2 | 5 | 1 | 1 | 4 | 2 | 2 | 4 | 4 | 2 | 5 | 2 | 1 | 3 | 2
494 | 9 | 7 | 19 | 30 | 41 | 50 | 62 | 76 | 84 | 95 | 108 | 117 | 126 | 140 | 1 | 1 | 2 | 3 | 1 | 1 | 5 | 5 | 2 | 1 | 3 | 5 | 2 | 2 | 4 | 3 | 1 | 4 | 3 | 1 | 1 | 5 | 4 | 2 | 2 | 4 | 3 | 5 | 1 | 3 | 3 | 1 | 2 | 3 | 5 | 1 | 2 | 4 | 5 | 2 | 2 | 1 | 4 | 2 | 1 | 2 | 2 | 4 | 5 | 5 | 2 | 2
495 | 18 | 14 | 24 | 32 | 43 | 58 | 70 | 75 | 86 | 99 | 111 | 125 | 137 | 152 | 3 | 5 | 3 | 3 | 3 | 1 | 1 | 5 | 2 | 3 | 1 | 2 | 2 | 2 | 5 | 2 | 5 | 1 | 4 | 5 | 3 | 2 | 4 | 3 | 1 | 2 | 1 | 1 | 4 | 1 | 1 | 5 | 2 | 5 | 2 | 4 | 5 | 3 | 3 | 1 | 4 | 1 | 4 | 5 | 5 | 5 | 1 | 1 | 5 | 2 | 4 | 4
496 | 16 | 12 | 22 | 36 | 51 | 68 | 82 | 97 | 105 | 116 | 130 | 144 | 152 | 166 | 5 | 3 | 2 | 2 | 1 | 3 | 2 | 4 | 5 | 3 | 2 | 4 | 5 | 2 | 5 | 3 | 3 | 5 | 4 | 5 | 4 | 4 | 1 | 5 | 5 | 2 | 3 | 5 | 5 | 1 | 1 | 1 | 5 | 2 | 3 | 1 | 4 | 5 | 4 | 1 | 5 | 3 | 3 | 3 | 1 | 4 | 2 | 1 | 4 | 3 | 5 | 2
497 | 15 | 10 | 19 | 31 | 46 | 58 | 68 | 82 | 92 | 107 | 121 | 134 | 146 | 159 | 2 | 2 | 2 | 4 | 3 | 2 | 2 | 2 | 5 | 1 | 2 | 4 | 2 | 5 | 3 | 5 | 3 | 4 | 3 | 2 | 2 | 5 | 2 | 1 | 3 | 5 | 1 | 5 | 1 | 4 | 1 | 4 | 4 | 5 | 3 | 3 | 4 | 5 | 2 | 3 | 2 | 5 | 5 | 1 | 4 | 1 | 3 | 4 | 4 | 5 | 1 | 3
498 | 15 | 11 | 20 | 27 | 32 | 39 | 53 | 62 | 75 | 88 | 98 | 109 | 118 | 131 | 2 | 3 | 2 | 4 | 1 | 3 | 1 | 4 | 2 | 2 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 4 | 4 | 1 | 5 | 4 | 4 | 1 | 2 | 2 | 5 | 3 | 4 | 1 | 1 | 2 | 5 | 5 | 1 | 2 | 5 | 2 | 2 | 2 | 4 | 3 | 1 | 1 | 3 | 4 | 5 | 3 | 4 | 1
499 | 21 | 15 | 25 | 37 | 50 | 61 | 76 | 87 | 95 | 102 | 115 | 126 | 137 | 146 | 3 | 3 | 4 | 5 | 1 | 5 | 3 | 1 | 1 | 4 | 4 | 3 | 5 | 4 | 2 | 2 | 5 | 3 | 2 | 1 | 4 | 2 | 4 | 5 | 4 | 5 | 1 | 1 | 3 | 2 | 1 | 2 | 3 | 1 | 2 | 1 | 3 | 5 | 3 | 2 | 4 | 1 | 5 | 1 | 3 | 3 | 1 | 4 | 2 | 1 | 2 | 4
500 | 23 | 20 | 28 | 39 | 47 | 60 | 74 | 86 | 98 | 105 | 114 | 125 | 137 | 146 | 5 | 5 | 5 | 5 | 1 | 2 | 3 | 2 | 4 | 3 | 1 | 3 | 4 | 1 | 2 | 1 | 1 | 5 | 5 | 2 | 3 | 5 | 5 | 1 | 5 | 3 | 1 | 3 | 2 | 1 | 5 | 4 | 1 | 3 | 1 | 2 | 1 | 3 | 4 | 1 | 2 | 3 | 3 | 3 | 4 | 3 | 1 | 4 | 1 | 1 | 3 | 4
| 6 | Sum4: 4; Sum8: 8; Sum12: 12; Sum16: 16; Sum20: 20; Sum24: 24; Sum28: 28; Sum32: 32; Sum36: 36; Sum40: 40; Sum44: 44; Sum48: 48; Sum52: 52
1% | 10 | Sum4: 6; Sum8: 15; Sum12: 25; Sum16: 35; Sum20: 45; Sum24: 54.99; Sum28: 64.99; Sum32: 76.99; Sum36: 87; Sum40: 100; Sum44: 109; Sum48: 121; Sum52: 131.99
2% | 11 | Sum4: 7; Sum8: 16; Sum12: 26; Sum16: 36; Sum20: 46.98; Sum24: 57; Sum28: 68; Sum32: 80; Sum36: 89; Sum40: 101; Sum44: 112; Sum48: 124.96; Sum52: 135
3% | 12 | Sum4: 7; Sum8: 17; Sum12: 27; Sum16: 36; Sum20: 48; Sum24: 59; Sum28: 69; Sum32: 80; Sum36: 90; Sum40: 102; Sum44: 114; Sum48: 126; Sum52: 137.94
4% | 13 | Sum4: 7; Sum8: 17; Sum12: 27.96; Sum16: 37; Sum20: 49; Sum24: 60; Sum28: 71; Sum32: 81.96; Sum36: 93; Sum40: 103; Sum44: 115.96; Sum48: 127; Sum52: 138
5% | 13 | Sum4: 7; Sum8: 18; Sum12: 28; Sum16: 38; Sum20: 49; Sum24: 60; Sum28: 71.95; Sum32: 82; Sum36: 93; Sum40: 105; Sum44: 116; Sum48: 127; Sum52: 139
6% | 13 | Sum4: 8; Sum8: 18; Sum12: 29; Sum16: 39; Sum20: 50; Sum24: 61; Sum28: 73; Sum32: 83; Sum36: 94; Sum40: 106; Sum44: 117; Sum48: 128; Sum52: 140
7% | 13 | Sum4: 8; Sum8: 18; Sum12: 29; Sum16: 39; Sum20: 51; Sum24: 62; Sum28: 73; Sum32: 84; Sum36: 96; Sum40: 107; Sum44: 118; Sum48: 129; Sum52: 140
8% | 14 | Sum4: 8; Sum8: 19; Sum12: 29; Sum16: 40; Sum20: 51; Sum24: 62; Sum28: 73; Sum32: 84; Sum36: 96; Sum40: 107; Sum44: 118; Sum48: 129; Sum52: 141
9% | 14 | Sum4: 8; Sum8: 19; Sum12: 30; Sum16: 40; Sum20: 52; Sum24: 62.91; Sum28: 74; Sum32: 85; Sum36: 97; Sum40: 108; Sum44: 119; Sum48: 130; Sum52: 141
10% | 14 | Sum4: 8; Sum8: 19; Sum12: 30; Sum16: 40; Sum20: 52; Sum24: 63; Sum28: 74; Sum32: 85; Sum36: 97; Sum40: 108; Sum44: 119; Sum48: 130; Sum52: 141
11% | 14 | Sum4: 9; Sum8: 19; Sum12: 30; Sum16: 41; Sum20: 53; Sum24: 63; Sum28: 75; Sum32: 85.89; Sum36: 97; Sum40: 108.89; Sum44: 120; Sum48: 130.89; Sum52: 142
12% | 14 | Sum4: 9; Sum8: 20; Sum12: 30; Sum16: 41; Sum20: 53; Sum24: 64; Sum28: 75; Sum32: 86; Sum36: 98; Sum40: 109; Sum44: 120; Sum48: 131; Sum52: 142
13% | 14 | Sum4: 9; Sum8: 20; Sum12: 30.87; Sum16: 41.87; Sum20: 53; Sum24: 64; Sum28: 76; Sum32: 86; Sum36: 98; Sum40: 110; Sum44: 120.87; Sum48: 131.87; Sum52: 142.87
14% | 14.86 | Sum4: 9; Sum8: 20; Sum12: 31; Sum16: 42; Sum20: 53; Sum24: 64; Sum28: 76; Sum32: 87; Sum36: 98; Sum40: 110; Sum44: 121; Sum48: 132; Sum52: 143.86
15% | 15 | Sum4: 9; Sum8: 20; Sum12: 31; Sum16: 42; Sum20: 54; Sum24: 64; Sum28: 76; Sum32: 87; Sum36: 99; Sum40: 110; Sum44: 121; Sum48: 132; Sum52: 144
16% | 15 | Sum4: 9; Sum8: 20; Sum12: 31; Sum16: 42; Sum20: 54; Sum24: 65; Sum28: 76; Sum32: 87; Sum36: 99; Sum40: 110; Sum44: 122; Sum48: 133; Sum52: 144.84
17% | 15 | Sum4: 9; Sum8: 20; Sum12: 31; Sum16: 42; Sum20: 54; Sum24: 65; Sum28: 76.83; Sum32: 87; Sum36: 99; Sum40: 111; Sum44: 122; Sum48: 133.83; Sum52: 145
18% | 15 | Sum4: 9; Sum8: 21; Sum12: 31; Sum16: 43; Sum20: 54; Sum24: 65; Sum28: 77; Sum32: 88; Sum36: 99.82; Sum40: 111; Sum44: 123; Sum48: 134; Sum52: 145
19% | 15 | Sum4: 10; Sum8: 21; Sum12: 31.81; Sum16: 43; Sum20: 55; Sum24: 65; Sum28: 77; Sum32: 88; Sum36: 100; Sum40: 111; Sum44: 123; Sum48: 134; Sum52: 146
20% | 15 | Sum4: 10; Sum8: 21; Sum12: 32; Sum16: 43; Sum20: 55; Sum24: 66; Sum28: 77; Sum32: 89; Sum36: 100; Sum40: 111; Sum44: 123; Sum48: 135; Sum52: 146
21% | 15 | Sum4: 10; Sum8: 21; Sum12: 32; Sum16: 43; Sum20: 55; Sum24: 66; Sum28: 78; Sum32: 89; Sum36: 100; Sum40: 112; Sum44: 123; Sum48: 135; Sum52: 147
22% | 15 | Sum4: 10; Sum8: 21; Sum12: 32; Sum16: 44; Sum20: 55; Sum24: 66; Sum28: 78; Sum32: 89; Sum36: 101; Sum40: 112; Sum44: 124; Sum48: 135; Sum52: 147
23% | 15 | Sum4: 10; Sum8: 21; Sum12: 32; Sum16: 44; Sum20: 55; Sum24: 66; Sum28: 78; Sum32: 89; Sum36: 101; Sum40: 112.77; Sum44: 124; Sum48: 136; Sum52: 147
24% | 16 | Sum4: 10; Sum8: 21; Sum12: 32; Sum16: 44; Sum20: 55; Sum24: 67; Sum28: 78; Sum32: 90; Sum36: 101; Sum40: 113; Sum44: 125; Sum48: 136; Sum52: 147
25% | 16 | Sum4: 10; Sum8: 21; Sum12: 32; Sum16: 44; Sum20: 56; Sum24: 67; Sum28: 79; Sum32: 90; Sum36: 102; Sum40: 113; Sum44: 125; Sum48: 137; Sum52: 148
26% | 16 | Sum4: 10; Sum8: 21; Sum12: 33; Sum16: 44; Sum20: 56; Sum24: 67; Sum28: 79; Sum32: 90; Sum36: 102; Sum40: 113; Sum44: 125; Sum48: 137; Sum52: 148
27% | 16 | Sum4: 10; Sum8: 22; Sum12: 33; Sum16: 45; Sum20: 56; Sum24: 67; Sum28: 79; Sum32: 90; Sum36: 102; Sum40: 113; Sum44: 125.73; Sum48: 137; Sum52: 148
28% | 16 | Sum4: 10; Sum8: 22; Sum12: 33; Sum16: 45; Sum20: 56; Sum24: 68; Sum28: 79; Sum32: 91; Sum36: 102; Sum40: 114; Sum44: 126; Sum48: 138; Sum52: 149
29% | 16 | Sum4: 10; Sum8: 22; Sum12: 33; Sum16: 45; Sum20: 56; Sum24: 68; Sum28: 80; Sum32: 91; Sum36: 103; Sum40: 114; Sum44: 126; Sum48: 138; Sum52: 149
30% | 16 | Sum4: 10; Sum8: 22; Sum12: 33; Sum16: 45; Sum20: 56; Sum24: 68; Sum28: 80; Sum32: 91; Sum36: 103; Sum40: 114; Sum44: 126; Sum48: 138; Sum52: 149
31% | 16 | Sum4: 11; Sum8: 22; Sum12: 33; Sum16: 45; Sum20: 57; Sum24: 68.69; Sum28: 80; Sum32: 91; Sum36: 103; Sum40: 114; Sum44: 127; Sum48: 138.69; Sum52: 149
32% | 16 | Sum4: 11; Sum8: 22; Sum12: 33; Sum16: 45; Sum20: 57; Sum24: 69; Sum28: 80; Sum32: 92; Sum36: 103; Sum40: 115; Sum44: 127; Sum48: 139; Sum52: 150
33% | 16 | Sum4: 11; Sum8: 22; Sum12: 34; Sum16: 45; Sum20: 57; Sum24: 69; Sum28: 81; Sum32: 92; Sum36: 103; Sum40: 115; Sum44: 127; Sum48: 139; Sum52: 150
34% | 16 | Sum4: 11; Sum8: 22; Sum12: 34; Sum16: 46; Sum20: 57; Sum24: 69; Sum28: 81; Sum32: 92; Sum36: 104; Sum40: 115; Sum44: 127; Sum48: 139; Sum52: 151
35% | 17 | Sum4: 11; Sum8: 22.65; Sum12: 34; Sum16: 46; Sum20: 57; Sum24: 69; Sum28: 81; Sum32: 92; Sum36: 104; Sum40: 116; Sum44: 128; Sum48: 140; Sum52: 151
36% | 17 | Sum4: 11; Sum8: 23; Sum12: 34; Sum16: 46; Sum20: 57.64; Sum24: 70; Sum28: 81; Sum32: 93; Sum36: 104; Sum40: 116; Sum44: 128; Sum48: 140; Sum52: 151
37% | 17 | Sum4: 11; Sum8: 23; Sum12: 34; Sum16: 46; Sum20: 58; Sum24: 70; Sum28: 82; Sum32: 93; Sum36: 105; Sum40: 116; Sum44: 128.63; Sum48: 140; Sum52: 152
38% | 17 | Sum4: 11; Sum8: 23; Sum12: 35; Sum16: 46; Sum20: 58; Sum24: 70; Sum28: 82; Sum32: 93; Sum36: 105; Sum40: 116; Sum44: 129; Sum48: 141; Sum52: 152.62
39% | 17 | 11 | 23 | 35 | 46 | 58 | 70 | 82 | 93 | 105 | 117 | 129 | 141 | 153
40% | 17 | 11 | 23 | 35 | 47 | 58 | 70 | 82 | 93 | 105 | 117 | 129 | 141 | 153
41% | 17 | 11 | 23 | 35 | 47 | 59 | 70 | 82 | 94 | 106 | 117 | 129 | 142 | 153
42% | 17 | 11 | 23 | 35 | 47 | 59 | 70 | 83 | 94 | 106 | 117 | 129.58 | 142 | 154
43% | 17 | 11 | 23 | 35 | 47 | 59 | 70 | 83 | 94 | 106 | 118 | 130 | 142 | 154
44% | 17 | 11 | 23 | 35.56 | 47 | 59 | 71 | 83 | 94 | 106 | 118 | 130 | 142 | 154
45% | 17 | 11.55 | 24 | 36 | 47 | 59 | 71 | 83 | 95 | 107 | 118 | 130 | 143 | 154
46% | 18 | 12 | 24 | 36 | 47 | 59 | 71 | 83 | 95 | 107 | 118 | 130 | 143 | 155
47% | 18 | 12 | 24 | 36 | 48 | 59 | 71 | 83.53 | 95 | 107 | 118.53 | 131 | 143 | 155
48% | 18 | 12 | 24 | 36 | 48 | 59 | 71 | 84 | 95 | 107 | 119 | 131 | 143 | 155
49% | 18 | 12 | 24 | 36 | 48 | 60 | 72 | 84 | 96 | 108 | 119 | 131 | 143 | 155
50% | 18 | 12 | 24 | 36 | 48 | 60 | 72 | 84 | 96 | 108 | 119 | 131 | 144 | 155
51% | 18 | 12 | 24 | 36 | 48 | 60 | 72 | 84 | 96 | 108 | 120 | 132 | 144 | 156
52% | 18 | 12 | 24 | 37 | 48 | 60 | 72 | 84 | 96 | 108 | 120 | 132 | 144 | 156
53% | 18 | 12 | 24 | 37 | 48.47 | 60 | 72 | 84 | 96 | 108 | 120 | 132.47 | 144 | 156
54% | 18 | 12 | 25 | 37 | 49 | 61 | 72 | 85 | 96 | 108 | 121 | 133 | 145 | 156
55% | 18 | 12 | 25 | 37 | 49 | 61 | 73 | 85 | 96 | 109 | 121 | 133 | 145 | 156
56% | 18 | 12 | 25 | 37 | 49 | 61 | 73 | 85 | 97 | 109 | 121 | 133 | 145 | 157
57% | 19 | 12 | 25 | 37 | 49 | 61 | 73 | 85 | 97 | 109 | 121 | 133.43 | 145 | 157
58% | 19 | 12 | 25 | 37 | 49 | 61 | 73 | 85 | 97 | 109 | 121 | 134 | 146 | 157
59% | 19 | 12.41 | 25 | 37 | 49 | 61 | 73 | 85.41 | 97 | 109.41 | 122 | 134 | 146 | 158
60% | 19 | 13 | 25 | 37 | 49 | 62 | 73 | 86 | 98 | 110 | 122 | 134 | 146 | 158
61% | 19 | 13 | 25 | 37 | 50 | 62 | 74 | 86 | 98 | 110 | 122 | 134 | 146 | 159
62% | 19 | 13 | 25 | 38 | 50 | 62 | 74 | 86 | 98 | 110 | 123 | 135 | 147 | 159
63% | 19 | 13 | 25 | 38 | 50 | 62 | 74 | 86 | 99 | 110 | 123 | 135 | 147 | 159.37
64% | 19 | 13 | 25 | 38 | 50 | 62 | 74 | 86 | 99 | 110.36 | 123 | 135 | 147 | 160
65% | 19 | 13 | 25 | 38 | 50 | 62 | 74 | 87 | 99 | 111 | 123 | 135 | 147 | 160
66% | 19 | 13 | 26 | 38 | 50 | 62 | 74 | 87 | 99 | 111 | 124 | 136 | 148 | 160
67% | 19 | 13 | 26 | 38 | 50 | 62.33 | 75 | 87 | 100 | 111 | 124 | 136 | 148 | 161
68% | 20 | 13 | 26 | 38 | 50 | 63 | 75 | 88 | 100 | 112 | 124 | 136 | 148 | 161
69% | 20 | 13 | 26 | 39 | 51 | 63 | 75 | 88 | 100 | 112 | 124 | 136 | 148 | 161
70% | 20 | 13 | 26 | 39 | 51 | 63 | 75.3 | 88 | 101 | 112 | 125 | 137 | 149 | 161
71% | 20 | 13 | 26 | 39 | 51 | 63 | 76 | 88 | 101 | 113 | 125 | 137 | 149 | 162
72% | 20 | 13 | 26 | 39 | 51 | 63 | 76 | 88 | 101 | 113 | 125 | 137 | 150 | 162
73% | 20 | 14 | 26 | 39 | 51 | 64 | 76 | 88 | 101 | 113 | 125 | 137 | 150 | 162
74% | 20 | 14 | 27 | 39 | 51 | 64 | 77 | 89 | 102 | 113 | 126 | 138 | 150 | 162.26
75% | 20 | 14 | 27 | 39 | 52 | 64 | 77 | 89 | 102 | 114 | 126 | 138 | 151 | 163
76% | 21 | 14 | 27 | 40 | 52 | 64.24 | 77 | 89 | 102 | 114 | 126 | 139 | 151 | 163
77% | 21 | 14 | 27 | 40 | 52 | 65 | 77 | 90 | 103 | 114 | 126.23 | 139 | 152 | 164
78% | 21 | 14 | 27 | 40 | 52 | 65 | 78 | 90 | 103 | 115 | 127 | 140 | 152 | 165
79% | 21 | 14 | 27 | 40 | 52.21 | 65 | 78 | 90 | 103 | 115 | 127 | 140 | 152 | 165
80% | 21 | 14 | 27 | 40 | 53 | 66 | 78 | 91 | 103 | 115 | 128 | 140.2 | 153 | 166
81% | 21 | 14 | 27 | 41 | 53 | 66 | 78 | 91 | 104 | 116 | 128 | 141 | 153 | 166
82% | 21 | 15 | 28 | 41 | 53 | 66 | 78 | 92 | 104 | 116 | 129 | 142 | 154 | 166
83% | 21 | 15 | 28 | 41 | 53 | 66 | 79 | 92 | 104 | 117 | 129 | 142 | 154 | 166
84% | 22 | 15 | 28 | 41 | 54 | 67 | 79 | 92 | 105 | 117 | 130 | 142 | 155 | 167
85% | 22 | 15 | 28 | 42 | 54 | 67 | 79.15 | 92 | 105 | 118 | 130 | 143 | 155 | 167
86% | 22 | 15 | 28 | 42 | 54 | 67 | 80 | 92 | 105 | 118 | 131 | 143 | 155 | 167
87% | 22 | 15 | 28 | 42 | 54 | 67 | 80 | 93 | 106 | 119 | 131 | 143 | 155 | 168
88% | 22 | 15 | 29 | 42 | 54 | 67 | 81 | 93.12 | 106 | 119 | 131.12 | 143.12 | 156 | 169
89% | 23 | 16 | 29 | 42 | 55 | 68 | 81 | 94 | 107 | 120 | 132 | 144 | 156 | 169
90% | 23 | 16 | 29 | 42 | 55.1 | 68 | 82 | 94 | 107 | 120 | 133 | 144 | 157 | 170
91% | 23 | 16 | 29 | 43 | 56 | 69 | 82 | 95 | 107 | 120 | 133 | 145 | 157.09 | 170
92% | 23 | 16 | 29 | 43 | 56 | 69 | 82 | 96 | 108 | 121 | 133 | 145.08 | 158 | 171
93% | 23 | 16 | 30 | 43 | 57 | 70 | 83 | 96 | 108 | 121 | 134 | 147 | 159 | 172
94% | 24 | 16 | 30 | 44 | 58 | 70 | 83 | 96 | 109 | 122.06 | 134 | 147.06 | 160.06 | 172.06
95% | 24 | 17 | 31 | 44 | 58 | 70.05 | 83 | 97 | 109 | 124 | 135 | 148 | 161 | 174
96% | 24 | 17 | 31 | 45 | 58.04 | 71 | 84 | 97 | 110 | 124 | 136 | 149.04 | 162 | 175
97% | 25 | 17 | 32 | 45.03 | 59 | 72 | 84.03 | 99 | 111 | 125 | 137 | 151 | 162.03 | 176
98% | 25 | 17 | 32 | 46 | 61 | 74 | 85 | 99 | 113 | 126 | 138.02 | 153 | 166 | 179
99% | 26 | 17.01 | 33 | 47 | 62 | 76 | 88.01 | 100.01 | 114 | 129 | 139.02 | 156.01 | 167.02 | 180.01
100% | 28 | 20 | 34 | 50 | 63 | 80 | 91 | 106 | 120 | 133 | 149 | 164 | 177 | 193